## Scheduling
ITEM_TYPE | DELIVERY_TYPE | WORKSTREAM | YEAR_OF_COMPETENCE | START_DATE | END_DATE | SOW_ID | JIRA_KEY | PROJECT_STREAM | PROJECT_DESCR | CLIENT | PM_SM | USER | AREA_CC | JOB | PLANNED_FTE | ACTUAL_FTE | STATUS | PROGRESS_% | YEAR | Tot_sched_next | gen | feb | mar | apr | mag | giu | lug | ago | set | ott | nov | dic | gen1 | feb1 | mar1 | apr1 | mag1 | giu1 | lug1 | ago1 | set1 | ott1 | nov1 | dic1
CONTRACT | PRJ |  | 2023-2024 | 2024-11-01 | 2025-02-28 | ABS23459 | AEACUGIW | EPM | Essilor Adj Conso Upstream group Integration_Wave1 | EssilorLuxottica | A. Albanese | A. Di Pietro | Operations | BackEnd | 60 | 60 | CLOSED | 100% | 2024 | 0 | 8 | 8 | [10 empty] | 44.44% | 40% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2023-2024 | 2024-11-01 | 2025-02-28 | ABS23459 | AEACUGIW | EPM | Essilor Adj Conso Upstream group Integration_Wave1 | EssilorLuxottica | A. Albanese | E. Storti | Delivery Projects | BackEnd | 60 | 60 | CLOSED | 100% | 2024 | 0 | 8 | 8 | [10 empty] | 44.44% | 40% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione Apex | Abstract | A. Albanese | L. Mangili | Operations | BackEnd | 0 | 0 |  | 0% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione FCCS | Abstract | A. Albanese | C. Esposito | Consolidated & Tax | BackEnd | 0 | 0 |  | 0% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione FCCS | Abstract | A. Albanese | M. Sorrentino | Consolidated & Tax | Analysis | 0 | 0 |  | 0% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione HFM | Abstract | A. Albanese | L. Pigazzini | Consolidated & Tax | BackEnd | 0 | 0 |  | 40% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione nuovo assunto |  | A. Albanese | L. Pigazzini | Consolidated & Tax | BackEnd | 0 | 0 |  | 50% | 2024 | 27 | 12.6 | 21 | 21 | 19 | 2 | 2 | 23 | [5 empty] | 70% | 105% | 100% | 86.36% | 10% | 10% | 100% | 0% | 0% | 0% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione Talentia | Abstract | A. Albanese | C. Tiberti | Operations | BackEnd | 0 | 0 |  | 100% | 2024 | 0 | 1.8 | 3.15 | 4.2 | 2.85 | [8 empty] | 10% | 15.75% | 20% | 12.95% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione Tax | Abstract | A. Albanese | C. Tiberti | Operations | BackEnd | 0 | 0 |  | 100% | 2024 | 0 | 5.4 | 6.3 | 5.25 | 3.8 | [8 empty] | 30% | 31.5% | 25% | 17.27% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - NRT | FERRERO | A. Albanese | F. Atanasio | Operations | BackEnd | 52 | 0 | PROPOSAL | 0% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - NRT | FERRERO | A. Albanese | F. Lombardini | Consolidated & Tax | Analysis | 52 | 0 | PROPOSAL | 0% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - NRT | FERRERO | A. Albanese | I. Bressan | Operations | Tech Lead | 52 | 0 | PROPOSAL | 0% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - NRT | FERRERO | A. Albanese | P. Galvagni | Consolidated & Tax | Analysis | 52 | 0 | PROPOSAL | 0% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato FCCS | Vision Group | A. Albanese | A. Albanese | Delivery Projects | PM - Project Governance | 210 | 220 | ON GOING | 95% | 2024 | 10 | [6 empty] | 2 |  | 3 | 3 | 2 |  | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 0% | 14.29% | 13.04% | 9.524% | 0%
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato FCCS | Vision Group | A. Albanese | Esterno | #N/A | Analysis | 210 | 220 | ON GOING | 95% | 2024 | 10 | [8 empty] | 4 | 6 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 19.05% | 26.09% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato FCCS | Vision Group | A. Albanese | F. Atanasio | Operations | BackEnd - Junior | 210 | 220 | ON GOING | 95% | 2024 | 32 | [8 empty] | 3 | 12 | 12 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 52.17% | 57.14% | 22.73%
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato FCCS | Vision Group | A. Albanese | F. De Pedis | Operations | BackEnd | 210 | 220 | ON GOING | 95% | 2024 | 23 | [8 empty] | 4 | 7 | 7 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 19.05% | 30.43% | 33.33% | 22.73%
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato FCCS | Vision Group | A. Albanese | M. Salcini | Consolidated & Tax | Analysis | 210 | 220 | ON GOING | 95% | 2024 | 15 | [8 empty] | 1 | 7 | 7 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762% | 30.43% | 33.33% | 0%
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato FCCS | Vision Group | A. Albanese | M. Sorrentino | Consolidated & Tax | Analysis | 210 | 220 | ON GOING | 95% | 2024 | 14 | [6 empty] | 1 |  | 1 | 7 | 5 |  | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 0% | 4.762% | 30.43% | 23.81% | 0%
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato FCCS | Vision Group | A. Albanese | P. Galvagni | Consolidated & Tax | Tech Lead | 210 | 220 | ON GOING | 95% | 2024 | 19 | [6 empty] | 1 |  | 1 | 7 | 5 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 0% | 4.762% | 30.43% | 23.81% | 22.73%
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato Managerial / Store P&L | Vision Group | A. Albanese | C. DI LORENZO | Delivery Projects | Analysis | 210 | 220 | ON GOING | 95% | 2024 | 4 | [6 empty] | 1 |  | 1 | 1 | 1 |  | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 0% | 4.762% | 4.348% | 4.762% | 0%
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato Managerial / Store P&L | Vision Group | A. Albanese | L. Franco | Operations | Tech Lead | 210 | 220 | ON GOING | 95% | 2024 | 37 | [6 empty] | 3 | 2 | 13 | 9 | 5 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 16.67% | 61.9% | 39.13% | 23.81% | 22.73%
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato Managerial / Store P&L | Vision Group | A. Albanese | L. Mangili | Operations | BackEnd | 210 | 220 | ON GOING | 95% | 2024 | 12 | [7 empty] | 3 | 1 | 1 | 7 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 4.762% | 4.348% | 33.33% | 0%
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato Managerial / Store P&L | Vision Group | A. Albanese | M. Favalli | Operations | BackEnd - Junior | 210 | 220 | ON GOING | 95% | 2024 | 35 | [7 empty] | 3 | 12 | 1 | 14 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 57.14% | 4.348% | 66.67% | 22.73%
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato Managerial / Store P&L | Vision Group | A. Albanese | P. Galvagni | Consolidated & Tax | Analysis | 210 | 220 | ON GOING | 95% | 2024 | 28 | [6 empty] | 3 | 5 | 5 | 5 | 5 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 41.67% | 23.81% | 21.74% | 23.81% | 22.73%
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato Managerial / Store P&L | Vision Group | A. Albanese | S. Preziosa | Delivery Projects | Analysis | 210 | 220 | ON GOING | 95% | 2024 | 23 | [6 empty] | 3 | 5 | 5 | 5 | 5 |  | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 41.67% | 23.81% | 21.74% | 23.81% | 0%
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-05-31 | ABS24494 | ABS24494 | EPM | Lux - Job Type - Wave1 | EssilorLuxottica | A. Albanese | A. Albanese | Delivery Projects | BackEnd | 35 | 15 | CLOSED | 100% | 2024 | 2 | [9 empty] | 1 | 1 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 4.762% | 0%
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-05-31 | ABS24494 | ABS24494 | EPM | Lux - Job Type - Wave1 | EssilorLuxottica | A. Albanese | T. Baldi | Operations | BackEnd | 35 | 15 | CLOSED | 100% | 2024 | 1 | [9 empty] | 1 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-01-01 | 2024-06-30 | ABS23458 | APLTENCR | EPM | Push Lux to ESSTECH + New CMFA Region | EssilorLuxottica | A. Albanese | F. Atanasio | Operations | BackEnd | 50 | 66 | CLOSED | 100% | 2024 | 0 | 9 | 5.4 | 2.7 | [9 empty] | 50% | 27% | 12.86% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-01-01 | 2024-06-30 | ABS23458 | APLTENCR | EPM | Push Lux to ESSTECH + New CMFA Region | EssilorLuxottica | A. Albanese | M. Favalli | Operations | BackEnd | 50 | 66 | CLOSED | 100% | 2024 | 0 | 9 | 5.4 | 2.7 | [9 empty] | 50% | 27% | 12.86% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-01-01 | 2024-06-30 | ABS23458 | APLTENCR | EPM | Push Lux to ESSTECH + New CMFA Region | EssilorLuxottica | A. Albanese | P. Buonasorte | Operations | BackEnd | 50 | 66 | CLOSED | 100% | 2024 | 0 | 9 | 5.4 | 2.7 | [9 empty] | 50% | 27% | 12.86% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-06-30 | ABS23496 | AERSSDVF | EPM | Reply Supporto specialistico DM vs FCCS | Reply | A. Albanese | F. Atanasio | Operations | BackEnd | 160 | 123 | CLOSED | 100% | 2024 | 0 | 9 | 1.5 | 11.55 | [9 empty] | 50% | 7.5% | 55% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-06-30 | ABS23496 | AERSSDVF | EPM | Reply Supporto specialistico DM vs FCCS | Reply | A. Albanese | F. De Pedis | Operations | BackEnd | 160 | 123 | CLOSED | 100% | 2024 | 16 |  |  |  |  | 1 | 15 | [6 empty] | 0% | 0% | 0% | 0% | 5% | 75% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Time&Materials | 2024 | 2024-07-01 | 2024-12-31 | ABS24230 | ABS24230 | EPM | Reply Supporto specialistico DM vs FCCS | Reply | A. Albanese | F. De Pedis | Operations | BackEnd | 160 | 130 | ON GOING | 90% | 2024 | 16 | [6 empty] | 5 |  | 6 | 5 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 0% | 28.57% | 21.74% | 0% | 0%
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-06-30 | ABS23496 | AERSSDVF | EPM | Reply Supporto specialistico DM vs FCCS | Reply | A. Albanese | M. Favalli | Operations | BackEnd | 160 | 123 | CLOSED | 100% | 2024 | 1 |  |  |  | 19 | 1 | [7 empty] | 0% | 0% | 0% | 86.36% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Time&Materials | 2024 | 2024-07-01 | 2024-12-31 | ABS24230 | ABS24230 | EPM | Reply Supporto specialistico DM vs FCCS | Reply | A. Albanese | M. Favalli | Operations | BackEnd | 160 | 130 | ON GOING | 90% | 2024 | 9 |  |  |  |  | 1 | 2 | 5 |  | 1 |  |  |  | 0% | 0% | 0% | 0% | 5% | 10% | 21.74% | 0% | 4.762% | 0% | 0% | 0%
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-06-30 | ABS23496 | AERSSDVF | EPM | Reply Supporto specialistico DM vs FCCS | Reply | A. Albanese | P. Buonasorte | Operations | BackEnd | 160 | 123 | CLOSED | 100% | 2024 | 27 |  |  |  | 19 | 22 | 5 | [6 empty] | 0% | 0% | 0% | 86.36% | 110% | 25% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-09-01 | 2024-11-30 | ABS24384 | ABS24384 | EPM | Tax Normalization | EssilorLuxottica | A. Albanese | A. Albanese | Delivery Projects | PM - Project Governance | 46 | 25 | ON GOING | 50% | 2024 | 4 | [8 empty] | 2 | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.524% | 8.696% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-09-01 | 2024-11-30 | ABS24384 | ABS24384 | EPM | Tax Normalization | EssilorLuxottica | A. Albanese | F. Atanasio | Operations | BackEnd | 46 | 25 | ON GOING | 50% | 2024 | 13 | [9 empty] | 8 |  | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 34.78% | 0% | 22.73%
CONTRACT | PRJ |  | 2024 | 2024-09-01 | 2024-11-30 | ABS24384 | ABS24384 | EPM | Tax Normalization | EssilorLuxottica | A. Albanese | F. Lombardini | Consolidated & Tax | Analysis | 46 | 25 | ON GOING | 50% | 2024 | 8 | [8 empty] | 3 | 3 | 2 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 13.04% | 9.524% | 0%
CONTRACT | PRJ |  | 2024 | 2024-09-01 | 2024-11-30 | ABS24384 | ABS24384 | EPM | Tax Normalization | EssilorLuxottica | A. Albanese | L. Mangili | Operations | BackEnd | 46 | 25 | ON GOING | 50% | 2024 | 6 | [11 empty] | 6 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 27.27%
CONTRACT | PRJ |  | 2024 | 2024-09-01 | 2024-11-30 | ABS24384 | ABS24384 | EPM | Tax Normalization | EssilorLuxottica | A. Albanese | M. Salcini | Consolidated & Tax | Analysis | 46 | 25 | ON GOING | 50% | 2024 | 4 | [9 empty] | 2 | 2 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 9.524% | 0%
CONTRACT | PRJ |  | 2024 | 2024-09-01 | 2024-11-30 | ABS24384 | ABS24384 | EPM | Tax Normalization | EssilorLuxottica | A. Albanese | P. Galvagni | Consolidated & Tax | Analysis | 46 | 25 | ON GOING | 50% | 2024 | 8 | [8 empty] | 3 | 3 | 2 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 13.04% | 9.524% | 0%
CONTRACT | PRJ |  | 2024 | 2024-09-01 | 2024-11-30 | ABS24384 | ABS24384 | EPM | Tax Normalization | EssilorLuxottica | A. Albanese | P. Pieroni | Operations | Solution Architect | 46 | 25 | ON GOING | 50% | 2024 | 3 | [9 empty] | 2 | 1 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 4.762% | 0%
CONTRACT | PRJ | WATERFALL | 2024 | 2024-09-01 | 2025-12-31 | ABS24401 | ABS24401 | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - EVOLUTIVA DI 2024 | AO FERRARA | A. Coletti | L. Lazzari | SAP ECC | Account Manager | 100 | 258 | ON GOING | 90% | 2024 | 5 | [9 empty] | 2 | 2 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 9.524% | 4.545%
CONTRACT | PRJ | WATERFALL | 2024 | 2024-09-01 | 2025-12-31 | ABS24401 | ABS24401 | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - EVOLUTIVA DI 2024 | AO FERRARA | A. Coletti | M. Calabrese | Delivery Projects | PM - Project Governance | 100 | 258 | ON GOING | 90% | 2024 | 45 | [9 empty] | 15 | 15 | 15 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 65.22% | 71.43% | 68.18%
CONTRACT | PRJ | WATERFALL | 2024 | 2024-09-01 | 2025-12-31 | ABS24401 | ABS24401 | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - EVOLUTIVA DI 2024 | AO FERRARA | A. Coletti | P. Singh | AREA TECH | BackEnd | 100 | 258 | ON GOING | 90% | 2024 | 2 | [9 empty] | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 0% | 0%
CONTRACT | PRJ | WATERFALL | 2024 | 2024-09-01 | 2025-12-31 | ABS24401 | ABS24401 | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - EVOLUTIVA DI 2024 | AO FERRARA | A. Coletti | R. Bondi | Operations | FrontEnd | 100 | 258 | ON GOING | 90% | 2024 | 4 | [10 empty] | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.524% | 9.091%
CONTRACT | PRJ | WATERFALL | 2024 | 2024-09-01 | 2025-12-31 | ABS24401 | ABS24401 | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - EVOLUTIVA DI 2024 | AO FERRARA | A. Coletti | R. Tortora | Operations | FrontEnd | 100 | 258 | ON GOING | 90% | 2024 | 25 | [9 empty] | 8 | 2 | 15 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 34.78% | 9.524% | 68.18%
CONTRACT | PRJ |  | 2022-2023 | 2023-01-01 | 2023-12-31 | ABS24305 | CT | LOGISTIC | CONTROL TOWER | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | Data Management | 1376 | 911 | CLOSED | 100% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-12-01 | 2024-12-24 | ABS24565 | ABS24565 | LOGISTIC | CONTROL TOWER - Grand Vision Italy and Poland plant integration | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | Data Engineering | 30 | 29 | CLOSED | 100% | 2024 | 8 | [11 empty] | 8 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 36.36%
CONTRACT | PRJ |  | 2024-2025 | 2024-12-01 | 2024-12-24 | ABS24565 | ABS24565 | LOGISTIC | CONTROL TOWER - Grand Vision Italy and Poland plant integration | EssilorLuxottica | A. Cuomo | J. Daci | Operations | BackEnd | 30 | 29 | CLOSED | 100% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-12-01 | 2024-12-24 | ABS24565 | ABS24565 | LOGISTIC | CONTROL TOWER - Grand Vision Italy and Poland plant integration | EssilorLuxottica | A. Cuomo | T. Lazzari | SAP ECC | ECC Developer | 30 | 29 | CLOSED | 100% | 2024 | 2 | [11 empty] | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.091%
CONTRACT | PRJ |  | 2024 | 2024-10-01 | 2024-11-30 | ABS24471 | ABS24471 | LOGISTIC | CONTROL TOWER - CONTACT LENSES ENHANCEMENT & NEW BRANDsINTEGRATION | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | Data Engineering | 125 | 120 | CLOSED | 100% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-10-01 | 2024-11-30 | ABS24471 | ABS24471 | LOGISTIC | CONTROL TOWER - CONTACT LENSES ENHANCEMENT & NEW BRANDsINTEGRATION | EssilorLuxottica | A. Cuomo | J. Daci | Operations | BackEnd | 125 | 120 | CLOSED | 100% | 2024 | 8 | [11 empty] | 8 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 36.36%
CONTRACT | PRJ |  | 2024 | 2024-10-01 | 2024-11-30 | ABS24471 | ABS24471 | LOGISTIC | CONTROL TOWER - CONTACT LENSES ENHANCEMENT & NEW BRANDsINTEGRATION | EssilorLuxottica | A. Cuomo | S. Ben Younes | Operations | DataManagement | 125 | 120 | CLOSED | 100% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-10-01 | 2024-11-30 | ABS24471 | ABS24471 | LOGISTIC | CONTROL TOWER - CONTACT LENSES ENHANCEMENT & NEW BRANDsINTEGRATION | EssilorLuxottica | A. Cuomo | T. Lazzari | SAP ECC | ECC Developer | 125 | 120 | CLOSED | 100% | 2024 | 2 | [11 empty] | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.091%
CONTRACT | PRJ |  | 2024 | 2024-05-01 | 2024-09-30 | ABS24348 | ABS24348 | LOGISTIC | CONTROL TOWER - ROLLOUT- NEW BRANDsINTEGRATION-CRs | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | Data Engineering | 310 | 271 | CLOSED | 100% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-05-01 | 2024-09-30 | ABS24348 | ABS24348 | LOGISTIC | CONTROL TOWER - ROLLOUT- NEW BRANDsINTEGRATION-CRs | EssilorLuxottica | A. Cuomo | F. Ianni | SAP FIORI | FrontEnd | 310 | 271 | CLOSED | 100% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-05-01 | 2024-09-30 | ABS24348 | ABS24348 | LOGISTIC | CONTROL TOWER - ROLLOUT- NEW BRANDsINTEGRATION-CRs | EssilorLuxottica | A. Cuomo | F. Tarquini | SAP ECC | ECC Analyst | 310 | 271 | CLOSED | 100% | 2024 | 3 | [11 empty] | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.64%
CONTRACT | PRJ |  | 2024 | 2024-05-01 | 2024-09-30 | ABS24348 | ABS24348 | LOGISTIC | CONTROL TOWER - ROLLOUT- NEW BRANDsINTEGRATION-CRs | EssilorLuxottica | A. Cuomo | J. Daci | Operations | BackEnd | 310 | 271 | CLOSED | 100% | 2024 | 3 | [11 empty] | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.64%
CONTRACT | PRJ |  | 2024 | 2024-05-01 | 2024-09-30 | ABS24348 | ABS24348 | LOGISTIC | CONTROL TOWER - ROLLOUT- NEW BRANDsINTEGRATION-CRs | EssilorLuxottica | A. Cuomo | L. Cariglia | Operations | DataManagement | 310 | 271 | CLOSED | 100% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-05-01 | 2024-09-30 | ABS24348 | ABS24348 | LOGISTIC | CONTROL TOWER - ROLLOUT- NEW BRANDsINTEGRATION-CRs | EssilorLuxottica | A. Cuomo | M. Sabarese | SAP FIORI | FrontEnd | 310 | 271 | CLOSED | 100% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-05-01 | 2024-09-30 | ABS24348 | ABS24348 | LOGISTIC | CONTROL TOWER - ROLLOUT- NEW BRANDsINTEGRATION-CRs | EssilorLuxottica | A. Cuomo | T. Lazzari | SAP ECC | ECC Developer | 310 | 271 | CLOSED | 100% | 2024 | 3 | [11 empty] | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.64%
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-04-30 | ABS24204 | ACTW567 | LOGISTIC | Control Tower Wave 5-6-7 | EssilorLuxottica | A. Cuomo | A. Camara | SAP ECC | ECC Analyst | 553 | 519 | CLOSED | 100% | 2024 | 0 | 17 | 21 | 2 | 11 | [8 empty] | 94.44% | 105% | 9.524% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-04-30 | ABS24204 | ACTW567 | LOGISTIC | Control Tower Wave 5-6-7 | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | Data Engineering | 553 | 519 | CLOSED | 100% | 2024 | 0 | 18 | 2 | 2 | 19 | [8 empty] | 100% | 10% | 9.524% | 86.36% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-04-30 | ABS24204 | ACTW567 | LOGISTIC | Control Tower Wave 5-6-7 | EssilorLuxottica | A. Cuomo | A. Germinario | SAP ECC | ECC Developer | 553 | 519 | CLOSED | 100% | 2024 | 0 |  | 2.5 | 1 | 1 | [8 empty] | 0% | 12.5% | 4.762% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-04-30 | ABS24204 | ACTW567 | LOGISTIC | Control Tower Wave 5-6-7 | EssilorLuxottica | A. Cuomo | F. Ianni | SAP FIORI | FrontEnd | 553 | 519 | CLOSED | 100% | 2024 | 0 | 2 | 5 | 2 | 1 | [8 empty] | 11.11% | 25% | 9.524% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-04-30 | ABS24204 | ACTW567 | LOGISTIC | Control Tower Wave 5-6-7 | EssilorLuxottica | A. Cuomo | F. Tarquini | SAP ECC | ECC Analyst | 553 | 519 | CLOSED | 100% | 2024 | 0 | 17 | 19 | 2 | 12 | [8 empty] | 94.44% | 95% | 9.524% | 54.55% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-04-30 | ABS24204 | ACTW567 | LOGISTIC | Control Tower Wave 5-6-7 | EssilorLuxottica | A. Cuomo | J. Daci | Operations | DataManagement | 553 | 519 | CLOSED | 100% | 2024 | 0 | 6.5 | 13 | 2 | 16 | [8 empty] | 36.11% | 65% | 9.524% | 72.73% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-04-30 | ABS24204 | ACTW567 | LOGISTIC | Control Tower Wave 5-6-7 | EssilorLuxottica | A. Cuomo | L. Cariglia | Operations | DataManagement | 553 | 519 | CLOSED | 100% | 2024 | 0 | 15 | 16 | 11 | 12 | [8 empty] | 83.33% | 80% | 52.38% | 54.55% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-04-30 | ABS24204 | ACTW567 | LOGISTIC | Control Tower Wave 5-6-7 | EssilorLuxottica | A. Cuomo | M. Sabarese | SAP FIORI | FrontEnd | 553 | 519 | CLOSED | 100% | 2024 | 0 |  | 3 | 2 | 3 | [8 empty] | 0% | 15% | 9.524% | 13.64% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-04-30 | ABS24204 | ACTW567 | LOGISTIC | Control Tower Wave 5-6-7 | EssilorLuxottica | A. Cuomo | P. Dolzani | SAP ECC | ECC Developer | 553 | 519 | CLOSED | 100% | 2024 | 0 | 18 | 2 | 11 | 11 | [8 empty] | 100% | 10% | 52.38% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-04-30 | ABS24204 | ACTW567 | LOGISTIC | Control Tower Wave 5-6-7 | EssilorLuxottica | A. Cuomo | S. Boriashov | Operations | DataManagement | 553 | 519 | CLOSED | 100% | 2024 | 0 | 18 | 21 | [10 empty] | 100% | 105% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-04-30 | ABS24204 | ACTW567 | LOGISTIC | Control Tower Wave 5-6-7 | EssilorLuxottica | A. Cuomo | T. Lazzari | SAP ECC | ECC Developer | 553 | 519 | CLOSED | 100% | 2024 | 0 | 9 | 21 | 16 | 14 | [8 empty] | 50% | 105% | 76.19% | 63.64% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-12-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | A. Cerrato | Operations | BackEnd | 190 | 177 | CLOSED | 100% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-12-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | Data Engineering | 190 | 177 | CLOSED | 100% | 2024 | 3 | [11 empty] | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.64%
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-12-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | BackEnd | 190 | 177 | CLOSED | 100% | 2024 | 4 | [11 empty] | 4 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 18.18%
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-12-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | A. Strada | Operations | BackEnd | 190 | 177 | CLOSED | 100% | 2024 | 1 | [11 empty] | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.545%
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-12-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | A. Torone | Delivery AMS | Data Management | 190 | 177 | CLOSED | 100% | 2024 | 3 | [11 empty] | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.64%
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-12-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | C. Paz | Delivery Projects | PMO - Project Management Officer | 190 | 177 | CLOSED | 100% | 2024 | 1 | [11 empty] | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.545%
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-12-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | F. Reale | Operations | FrontEnd | 190 | 177 | CLOSED | 100% | 2024 | 17 | [11 empty] | 17 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 77.27%
CONTRACT | PRJ |  | 2024 |  |  | ABS24403 | LUCY | Lucy | Lucy PTP AI: Invoices Classification Suggestion | EssilorLuxottica | A. Graziani | A. Imbimbo | Operations | Data Scientist | 150 | 70 | ON GOING | 50% | 2024 | 73 | [5 empty] | 6 | 5 |  | 14 | 17 | 17 | 14 | 0% | 0% | 0% | 0% | 0% | 30% | 21.74% | 0% | 66.67% | 73.91% | 80.95% | 63.64%
CONTRACT | PRJ |  | 2024 |  |  | ABS24403 | LUCY | Lucy | Lucy PTP AI: Invoices Classification Suggestion | EssilorLuxottica | A. Graziani | F. Malvezzi | Operations | Data Scientist | 150 | 70 | ON GOING | 50% | 2024 | 13 | [8 empty] | 4 | 4 | 4 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 19.05% | 17.39% | 19.05% | 4.545%
CONTRACT | PRJ |  | 2024 |  |  | ABS24403 | LUCY | Lucy | Lucy PTP AI: Invoices Classification Suggestion | EssilorLuxottica | A. Graziani | G. Sabbatini | Operations | Data Engineering | 150 | 70 | ON GOING | 50% | 2024 | 5 | [6 empty] | 1 |  | 3 | 1 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 0% | 14.29% | 4.348% | 0% | 0%
CONTRACT | PRJ |  | 2024 |  |  | ABS24403 | LUCY | Lucy | Lucy PTP AI: Invoices Classification Suggestion | EssilorLuxottica | A. Graziani | G. Sironi | Operations | Team Leadership | 150 | 70 | ON GOING | 50% | 2024 | 22 | [5 empty] | 3 | 4 |  | 4 | 5 | 3 | 3 | 0% | 0% | 0% | 0% | 0% | 15% | 17.39% | 0% | 19.05% | 21.74% | 14.29% | 13.64%
CONTRACT | PRJ |  | 2024 |  |  | ABS24403 | LUCY | Lucy | Lucy PTP AI: Invoices Classification Suggestion | EssilorLuxottica | A. Graziani | M. Gomitoni | Operations | Tech Lead | 150 | 70 | ON GOING | 50% | 2024 | 14 | [5 empty] | 5 | 5 |  | 1 | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 25% | 21.74% | 0% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | PRJ |  | 2024 |  |  | ABS24403 | LUCY | Lucy | Lucy PTP AI: Invoices Classification Suggestion | EssilorLuxottica | A. Graziani | V. Echarry | Operations | Data Scientist | 150 | 70 | ON GOING | 50% | 2024 | 23 | [8 empty] | 4 | 7 | 7 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 19.05% | 30.43% | 33.33% | 22.73%
CONTRACT | PRJ |  | 2024 |  |  | N/A | N/A | Lucy | Lucy Vendor Matching ML | EssilorLuxottica | A. Graziani | A. Imbimbo | Operations | Data Scientist | 0 | 0 | PROPOSAL | 0% | 2024 | 9 | [9 empty] | 3 | 3 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 14.29% | 13.64%
CONTRACT | PRJ |  | 2024 |  |  | N/A | N/A | Lucy | Lucy Vendor Matching ML | EssilorLuxottica | A. Graziani | F. Malvezzi | Operations | Data Scientist | 0 | 0 | PROPOSAL | 0% | 2024 | 15 | [9 empty] | 5 | 5 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 23.81% | 22.73%
CONTRACT | PRJ |  | 2024 |  |  | N/A | N/A | Lucy | Lucy Vendor Matching ML | EssilorLuxottica | A. Graziani | G. Sironi | Operations | Team Leadership | 0 | 0 | PROPOSAL | 0% | 2024 | 6 | [9 empty] | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 9.524% | 9.091%
CONTRACT | PRJ |  | 2024 |  |  | N/A | N/A | Lucy | Lucy Vendor Matching ML | EssilorLuxottica | A. Graziani | M. Gomitoni | Operations | Tech Lead | 0 | 0 | PROPOSAL | 0% | 2024 | 9 | [9 empty] | 3 | 3 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 14.29% | 13.64%
CONTRACT | PRJ |  | 2024 |  |  | N/A | N/A | Lucy | Lucy Vendor Matching ML | EssilorLuxottica | A. Graziani | V. Echarry | Operations | Data Scientist | 0 | 0 | PROPOSAL | 0% | 2024 | 15 | [9 empty] | 5 | 5 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 23.81% | 22.73%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24049 | ALAFDP2 | FINANCE | AMS FRAUD Detection Platform 2024 | EssilorLuxottica | A. Morterra | A. Crescimone | Operations | BackEnd | 0 | 0 | CLOSED | 0% | 2024 | 24 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5.556% | 5% | 4.762% | 4.545% | 15% | 15% | 13.04% | 25% | 14.29% | 13.04% | 14.29% | 13.64%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24049 | ALAFDP2 | FINANCE | AMS FRAUD Detection Platform 2024 | EssilorLuxottica | A. Morterra | A. SAIJA | Operations | BackEnd | 0 | 0 | CLOSED | 0% | 2024 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24049 | ALAFDP2 | FINANCE | AMS FRAUD Detection Platform 2024 | EssilorLuxottica | A. Morterra | G. D'Amanti | Operations | BackEnd | 0 | 0 | ON GOING | 0% | 2024 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 |  | 2.778% | 2.5% | 2.381% | 2.273% | 2.5% | 2.5% | 2.174% | 4.167% | 2.381% | 2.174% | 4.762% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24049 | ALAFDP2 | FINANCE | AMS FRAUD Detection Platform 2024 | EssilorLuxottica | A. Morterra | G. Luongo | Delivery AMS | PM - Project Governance | 0 | 0 | CLOSED | 0% | 2024 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24049 | ALAFDP2 | FINANCE | AMS FRAUD Detection Platform 2024 | EssilorLuxottica | A. Morterra | L. Gullotto | Operations | BackEnd | 0 | 0 | CLOSED | 0% | 2024 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.778% | 2.5% | 2.381% | 2.273% | 2.5% | 2.5% | 2.174% | 4.167% | 2.381% | 2.174% | 2.381% | 2.273%
CONTRACT | AMS |  | 2024 |  |  | ABS24089 | ABS24089 | FINANCE | FDP - Fraud Detection Plathform 2024 | EssilorLuxottica | A. Morterra | A. Imbimbo | Operations | Data Scientist | 110 | 0 | ON GOING | 75% | 2024 | 19 |  |  | 4 | 4 | 4 | 4 | 2 | 1 | 3 | 1 | 1 | 3 | 0% | 0% | 19.05% | 18.18% | 20% | 20% | 8.696% | 8.333% | 14.29% | 4.348% | 4.762% | 13.64%
CONTRACT | AMS |  | 2024 |  |  | ABS24089 | ABS24089 | FINANCE | FDP - Fraud Detection Plathform 2024 | EssilorLuxottica | A. Morterra | G. Sabbatini | Operations | Data Engineering | 110 | 0 | ON GOING | 75% | 2024 | 21 |  |  | 2 | 2 | 2 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 0% | 0% | 9.524% | 9.091% | 10% | 15% | 8.696% | 16.67% | 14.29% | 13.04% | 14.29% | 13.64%
CONTRACT | AMS |  | 2024 |  |  | ABS24089 | ABS24089 | FINANCE | FDP - Fraud Detection Plathform 2024 | EssilorLuxottica | A. Morterra | G. Sironi | Operations | PM - Project Governance Support | 110 | 0 | ON GOING | 75% | 2024 | 20 |  |  | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 0% | 0% | 4.762% | 4.545% | 10% | 10% | 8.696% | 16.67% | 14.29% | 13.04% | 14.29% | 13.64%
CONTRACT | AMS |  | 2024 |  |  | ABS24089 | ABS24089 | FINANCE | FDP - Fraud Detection Plathform 2024 | EssilorLuxottica | A. Morterra | L. Cariglia | Operations | DataManagement | 110 | 0 | ON GOING | 75% | 2024 | 29 |  |  | 4 | 4 | 5 | 8 | 9 | 3 | 1 | 1 | 1 | 1 | 0% | 0% | 19.05% | 18.18% | 25% | 40% | 39.13% | 25% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS |  | 2024 |  |  | ABS24089 | ABS24089 | FINANCE | FDP - Fraud Detection Plathform 2024 | EssilorLuxottica | A. Morterra | M. Gomitoni | Operations | Tech Lead | 110 | 0 | ON GOING | 75% | 2024 | 6 | [5 empty] | 1 | 1 |  | 1 | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 5% | 4.348% | 0% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS |  | 2024 |  |  | ABS24089 | ABS24089 | FINANCE | FDP - Fraud Detection Plathform 2024 | EssilorLuxottica | A. Morterra | V. Echarry | Operations | Data Scientist | 110 | 0 | ON GOING | 75% | 2024 | 19 |  |  | 4 | 4 | 4 | 4 | 2 | 3 | 2 | 1 | 1 | 2 | 0% | 0% | 19.05% | 18.18% | 20% | 20% | 8.696% | 25% | 9.524% | 4.348% | 4.762% | 9.091%
PROSPECT | PRESALES - DELIVERY |  | 2024 |  |  | N/A | N/A | FINANCE/DS | Outlier Detection - PO & I | EssilorLuxottica | A. Morterra | A. Imbimbo | Operations | Data Scientist | 0 | 0 | PROPOSAL | 0% | 2024 | 7 |  |  |  |  | 2 | 3 | 2 | [5 empty] | 0% | 0% | 0% | 0% | 10% | 15% | 8.696% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRESALES - DELIVERY |  | 2024 |  |  | N/A | N/A | FINANCE/DS | Outlier Detection - PO & I | EssilorLuxottica | A. Morterra | G. Sabbatini | Operations | Data Engineering | 0 | 0 | PROPOSAL | 0% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRESALES - DELIVERY |  | 2024 |  |  | N/A | N/A | FINANCE/DS | Outlier Detection - PO & I | EssilorLuxottica | A. Morterra | G. Sironi | Operations | PM - Project Governance | 0 | 0 | PROPOSAL | 0% | 2024 | 3 |  |  |  |  | 1 | 1 | 1 | [5 empty] | 0% | 0% | 0% | 0% | 5% | 5% | 4.348% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRESALES - DELIVERY |  | 2024 |  |  | N/A | N/A | FINANCE/DS | Outlier Detection - PO & I | EssilorLuxottica | A. Morterra | L. Cariglia | Operations | DataManagement | 0 | 0 | PROPOSAL | 0% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRESALES - DELIVERY |  | 2024 |  |  | N/A | N/A | FINANCE/DS | Outlier Detection - PO & I | EssilorLuxottica | A. Morterra | M. Gomitoni | Operations | Tech Lead | 0 | 0 | PROPOSAL | 0% | 2024 | 2 | [5 empty] | 1 | 1 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 5% | 4.348% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRESALES - DELIVERY |  | 2024 |  |  | N/A | N/A | FINANCE/DS | Outlier Detection - PO & I | EssilorLuxottica | A. Morterra | V. Echarry | Operations | Data Scientist | 0 | 0 | PROPOSAL | 0% | 2024 | 7 |  |  |  |  | 4 | 2 | 1 | [5 empty] | 0% | 0% | 0% | 0% | 20% | 10% | 4.348% | 0% | 0% | 0% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  | N/A | ATD | OTHER | Formazione | Abstract | A. Strada | A. Crescimone | Operations | PM - Project Governance | 0 | 0 |  | 0% | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 10% | 8.696% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  | N/A | ATD | OTHER | Formazione | Abstract | A. Strada | A. Cuomo | Operations | PM - Project Governance | 0 | 0 |  | 0% | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 10% | 8.696% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  | N/A | ATD | OTHER | Formazione | Abstract | A. Strada | A. Saija | Operations | PM - Project Governance | 0 | 0 |  | 0% | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 10% | 8.696% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  | N/A | ATD | OTHER | Formazione | Abstract | A. Strada | A. Strada | Operations | PM - Project Governance | 0 | 0 |  | 0% | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 10% | 8.696% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  | N/A | ATD | OTHER | Formazione | Abstract | A. Strada | F. Reale | Operations | PM - Project Governance | 0 | 0 |  | 0% | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 10% | 8.696% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  | N/A | ATD | OTHER | Formazione | Abstract | A. Strada | F. Reale | Operations | backEnd | 0 | 0 |  | 0% | 2024 | 4 | [5 empty] | 2 | 2 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 10% | 8.696% | 0% | 0% | 0% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  | N/A | ATD | OTHER | Formazione | Abstract | A. Strada | G. D'Amanti | Operations | PM - Project Governance | 0 | 0 |  | 0% | 2024 | 8 | [5 empty] | 2 | 2 |  | 2 | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 10% | 8.696% | 0% | 9.524% | 8.696% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  | N/A | ATD | OTHER | Formazione | Abstract | A. Strada | J. Daci | Operations | PM - Project Governance | 0 | 0 |  | 0% | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 10% | 8.696% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  | N/A | ATD | OTHER | Formazione | Abstract | A. Strada | L. Cariglia | Operations | PM - Project Governance | 0 | 0 |  | 0% | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 10% | 8.696% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  | N/A | ATD | OTHER | Formazione | Abstract | A. Strada | L. Gullotto | Operations | PM - Project Governance | 0 | 0 |  | 0% | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 10% | 8.696% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  | N/A | ATD | OTHER | Formazione | Abstract | A. Strada | M. Migliorati | Operations | PM - Project Governance | 0 | 0 |  | 0% | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 10% | 8.696% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  | N/A | ATD | OTHER | Formazione | Abstract | A. Strada | M. Vimercati | Operations | PM - Project Governance | 0 | 0 |  | 0% | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 10% | 8.696% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  | N/A | ATD | OTHER | Formazione | Abstract | A. Strada | R. Alves | Operations | PM - Project Governance | 0 | 0 |  | 0% | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 10% | 8.696% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  | N/A | ATD | OTHER | Formazione | Abstract | A. Strada | R. Bondi | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0% | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 10% | 8.696% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  | N/A | ATD | OTHER | Formazione | Abstract | A. Strada | R. Grandi | Operations | Data Management | 0 | 0 |  | 0% | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 10% | 8.696% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  | N/A | ATD | OTHER | Formazione | Abstract | A. Strada | S. Ben Younes | Operations | PM - Project Governance | 0 | 0 |  | 0% | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 10% | 8.696% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | PRJ |  | 2024 | 2024-02-01 | 2024-02-29 | ABS24110 | AGCBSUB | CRM/CS | Global CS - BI Streaming-UK Brands | EssilorLuxottica | A. Torone | A. Strada | Operations | DataManagement | 35 | 30 | CLOSED | 100% | 2024 | 0 |  | 12 |  | 5 | [8 empty] | 0% | 60% | 0% | 22.73% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-02-01 | 2024-02-29 | ABS24110 | AGCBSUB | CRM/CS | Global CS - BI Streaming-UK Brands | EssilorLuxottica | A. Torone | A. Torone | Delivery AMS | PM - Project Governance | 35 | 30 | CLOSED | 100% | 2024 | 0 |  | 0.25 | 0.25 | 0.25 | [8 empty] | 0% | 1.25% | 1.19% | 1.136% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-02-01 | 2024-02-29 | ABS24110 | AGCBSUB | CRM/CS | Global CS - BI Streaming-UK Brands | EssilorLuxottica | A. Torone | M. Porcu | Operations | BackEnd | 35 | 30 | CLOSED | 100% | 2024 | 0 |  | 1.5 | 8 | [9 empty] | 0% | 7.5% | 38.1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-02-01 | 2024-02-29 | ABS24110 | AGCBSUB | CRM/CS | Global CS - BI Streaming-UK Brands | EssilorLuxottica | A. Torone | P. Anzellotti | Operations | BackEnd | 35 | 30 | CLOSED | 100% | 2024 | 0 |  |  | 2.75 | [9 empty] | 0% | 0% | 13.1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-12-31 | ABS24347 | BS24163 | CRM/CS | Global CS Enhancements 2024 | EssilorLuxottica | A. Torone | A. Strada | Operations | BackEnd | 48 | 38 | CLOSED | 100% | 2024 | 0 | 1 | [11 empty] | 5.556% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-04-30 | ABS24347 | BS24163 | CRM/CS | Global CS Enhancements 2024 | EssilorLuxottica | A. Torone | A. Torone | Delivery AMS | PM - Project Governance | 48 | 38 | CLOSED | 100% | 2024 | 0 | 1 | 1.5 | 1.5 | 0.5 | [8 empty] | 5.556% | 7.5% | 7.143% | 2.273% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-12-31 | ABS24347 | BS24163 | CRM/CS | Global CS Enhancements 2024 | EssilorLuxottica | A. Torone | D. Scalia | Operations | BackEnd | 48 | 38 | CLOSED | 100% | 2024 | 0 | 5.5 | 4.625 | 3.25 | [9 empty] | 30.56% | 23.12% | 15.48% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-12-31 | ABS24347 | BS24163 | CRM/CS | Global CS Enhancements 2024 | EssilorLuxottica | A. Torone | G. Esposito | AREA TECH | BackEnd | 48 | 38 | CLOSED | 100% | 2024 | 0 |  |  | 2.875 | [9 empty] | 0% | 0% | 13.69% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-12-31 | ABS24347 | BS24163 | CRM/CS | Global CS Enhancements 2024 | EssilorLuxottica | A. Torone | M. Porcu | Operations | BackEnd | 48 | 38 | CLOSED | 100% | 2024 | 0 | 0.5 |  |  | 1.3125 | [8 empty] | 2.778% | 0% | 0% | 5.966% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-12-31 | ABS24347 | BS24163 | CRM/CS | Global CS Enhancements 2024 | EssilorLuxottica | A. Torone | M. Toci | Operations | BackEnd | 48 | 38 | CLOSED | 100% | 2024 | 0 |  |  | 9.625 | 3.5 | [8 empty] | 0% | 0% | 45.83% | 15.91% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-12-31 | ABS24347 | BS24163 | CRM/CS | Global CS Enhancements 2024 | EssilorLuxottica | A. Torone | P. Anzellotti | Operations | BackEnd | 48 | 38 | CLOSED | 100% | 2024 | 0 |  |  |  | 1.25 | [8 empty] | 0% | 0% | 0% | 5.682% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-01-31 | 2024-03-31 | ABS24104 | ABS24104 | CRM/CS | Global CS-B2B | EssilorLuxottica | A. Torone | A. Torone | Delivery AMS | PM - Project Governance | 24 | 46 | CLOSED | 100% | 2024 | 0 | 0.25 | 0.25 | 0.25 | 0.25 | [8 empty] | 1.389% | 1.25% | 1.19% | 1.136% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-01-31 | 2024-03-31 | ABS24104 | ABS24104 | CRM/CS | Global CS-B2B | EssilorLuxottica | A. Torone | D. Scalia | Operations | BackEnd | 24 | 46 | CLOSED | 100% | 2024 | 0 | 0.875 | 8.75 | 4.375 | [9 empty] | 4.861% | 43.75% | 20.83% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-01-31 | 2024-03-31 | ABS24104 | ABS24104 | CRM/CS | Global CS-B2B | EssilorLuxottica | A. Torone | M. Porcu | Operations | BackEnd | 24 | 46 | CLOSED | 100% | 2024 | 0 | 1.8125 | 1.5625 | 4.9375 | 0.9375 | [8 empty] | 10.07% | 7.812% | 23.51% | 4.261% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-01-31 | 2024-03-31 | ABS24104 | ABS24104 | CRM/CS | Global CS-B2B | EssilorLuxottica | A. Torone | M. Toci | Operations | BackEnd | 24 | 46 | CLOSED | 100% | 2024 | 0 |  |  | 3.5 | 11.125 | [8 empty] | 0% | 0% | 16.67% | 50.57% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-01-31 | 2024-03-31 | ABS24104 | ABS24104 | CRM/CS | Global CS-B2B | EssilorLuxottica | A. Torone | P. Anzellotti | Operations | Technical Leader | 24 | 46 | CLOSED | 100% | 2024 | 0 |  |  |  | 3.5 | [8 empty] | 0% | 0% | 0% | 15.91% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2023-11-27 | 2024-03-31 | ABS23340 | LMD2 | OTHER | LUX_Marginality_Discounts_CMD_WF_2023 | EssilorLuxottica | A. Torone | A. Torone | Delivery AMS | PM - Project Governance | 45 | 65 | CLOSED | 100% | 2024 | 1.25 | 0.3125 | 1.4375 | 1 | 0.25 | 0.25 | 0.5 | 0.5 | [5 empty] | 1.736% | 7.187% | 4.762% | 1.136% | 1.25% | 2.5% | 2.174% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2023-11-27 | 2024-03-31 | ABS23340 | LMD2 | OTHER | LUX_Marginality_Discounts_CMD_WF_2023 | EssilorLuxottica | A. Torone | P. Singh | AREA TECH | DataManagement | 45 | 65 | CLOSED | 100% | 2024 | 0 | 13.875 | 14.125 | 8 | 7 | [8 empty] | 77.08% | 70.62% | 38.1% | 31.82% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2023-11-27 | 2024-03-31 | ABS23340 | LMD2 | OTHER | LUX_Marginality_Discounts_CMD_WF_2023 | EssilorLuxottica | A. Torone | R. Alves | Operations | FrontEnd | 45 | 65 | CLOSED | 100% | 2024 | 2.125 | 0.625 | 3.6875 | 3.5938 | 3.3963 | 1.625 |  | 0.5 | [5 empty] | 3.472% | 18.44% | 17.11% | 15.44% | 8.125% | 0% | 2.174% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2023-11-27 | 2024-03-31 | ABS23340 | LMD2 | OTHER | LUX_Marginality_Discounts_CMD_WF_2023 | EssilorLuxottica | A. Torone | S. Guastavigna | SAP ECC | Analysis | 45 | 65 | CLOSED | 100% | 2024 | 0 | 2.7 | 3.15 | [10 empty] | 15% | 15.75% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Out per Permesso MBA |  | C. Paz | C. Paz | Delivery Projects |  | 50 | 0 |  | 0% | 2024 | 31 | 3.6 | 4.2 | 4.2 | 3.8 | 4 | 6 | 5 |  | 4 | 4 | 4 | 4 | 20% | 21% | 20% | 17.27% | 20% | 30% | 21.74% | 0% | 19.05% | 17.39% | 19.05% | 18.18%
CONTRACT | PRJ |  |  |  |  | ABS23334 | ALESCP | BIP | Eliot Short Trip | EssilorLuxottica | C. Piraccini | C. Piraccini | Operations | BackEnd | 0 | 0 | CLOSED | 100% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  |  |  |  | ABS23334 | ALESCP | BIP | Eliot Short Trip | EssilorLuxottica | C. Piraccini | M. Regini | Operations | BackEnd | 0 | 0 | CLOSED | 100% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRESALES - DELIVERY |  | 2024 | 2024-07-01 | 2024-11-01 | N/A | N/A | CRM/DS | CRM-User Scoring Model | EDISON | F. Ferri | G. Sironi | Operations | PM - Project Governance | 8 | 8 | PROPOSAL | 0% | 2024 | 5 | [6 empty] | 1 | 1 | 2 | 1 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 8.333% | 9.524% | 4.348% | 0% | 0%
PROSPECT | PRESALES - DELIVERY |  | 2024 | 2024-07-01 | 2024-11-01 | N/A | N/A | CRM/DS | CRM-User Scoring Model | EDISON | F. Ferri | M. Gomitoni | Operations | Tech Lead | 8 | 8 | PROPOSAL | 0% | 2024 | 5 | [6 empty] | 1 | 1 | 2 | 1 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 8.333% | 9.524% | 4.348% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2024-07-01 | 2024-12-31 | ABS24060 | ABS24060 | EPM | RDM - AMS Talentia | RDM | F. Lombardini | F. Lombardini | Consolidated & Tax | PM - Project Governance | 40 | 8 | ON GOING | 20% | 2024 | 11 | [6 empty] | 2 | 1 | 1 | 4 | 1 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 8.333% | 4.762% | 17.39% | 4.762% | 9.091%
CONTRACT | AMS |  | 2024 | 2024-07-01 | 2024-12-31 | ABS24060 | ABS24060 | EPM | RDM - AMS Talentia | RDM | F. Lombardini | G. Picerno | Consolidated & Tax | BackEnd | 40 | 8 | ON GOING | 20% | 2024 | 11 | [6 empty] | 2 | 1 | 1 | 4 | 1 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 8.333% | 4.762% | 17.39% | 4.762% | 9.091%
CONTRACT | AMS |  | 2024 | 2023-07-01 | 2024-06-30 | ABS24334 | ABS24334 | EPM | Thom Browne | Thom Browne | F. Lombardini | F. Lombardini | Consolidated & Tax | Analysis | 16 | 0 | ON GOING | 0% | 2024 | 4 | 1 | 1 | 1 | 1 | 2 | 2 | [6 empty] | 5.556% | 5% | 4.762% | 4.545% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024-2025 | 2024-07-01 | 2025-06-30 | ABS24334 | ABS24334 | EPM | Thom Browne | Thom Browne | F. Lombardini | F. Lombardini | Consolidated & Tax | Analysis | 20 | 0 | ON GOING | 0% | 2024 | 5 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 0% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS |  | 2024 | 2023-07-01 | 2024-06-30 | ABS24334 | ABS24334 | EPM | Thom Browne | Thom Browne | F. Lombardini | G. Picerno | Consolidated & Tax | Analysis | 16 | 0 | ON GOING | 0% | 2024 | 4 | 1 | 1 | 1 | 1 | 2 | 2 | [6 empty] | 5.556% | 5% | 4.762% | 4.545% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024-2025 | 2024-07-01 | 2025-06-30 | ABS24334 | ABS24334 | EPM | Thom Browne | Thom Browne | F. Lombardini | G. Picerno | Consolidated & Tax | Analysis | 20 | 0 | ON GOING | 0% | 2024 | 5 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 0% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24325 | BS24108 | Retail | DMV AMS 2024 | EssilorLuxottica | F. Pinnelli | A. Torone | Delivery AMS | Project Governance | 164 | 0 | ON GOING | 0% | 2024 | 24.5 | [8 empty] | 0.5 | 8 | 8 | 8 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.381% | 34.78% | 38.1% | 36.36%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24325 | BS24108 | Retail | DMV AMS 2024 | EssilorLuxottica | F. Pinnelli | S. Calvi | Operations | Data Management | 164 | 0 | ON GOING | 0% | 2024 | 9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 1 |  |  |  | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 41.67% | 4.762% | 0% | 0% | 0%
INTERNAL PRJ | AMS | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | N/A | IAA | QA | Quality Assurance | EssilorLuxottica | F. Pinnelli | G. Picerno | Consolidated & Tax | Analysis | 220 | 0 | ON GOING | 0 | 2024 | 38 | [8 empty] | 4 | 4 | 15 | 15 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 19.05% | 17.39% | 71.43% | 68.18%
INTERNAL PRJ | AMS | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | N/A | IAA | QA | Quality Assurance | EssilorLuxottica | F. Pinnelli | L. Stefanelli | Delivery Maintenance | Tester | 220 | 0 | ON GOING | 0 | 2024 | 19 | [10 empty] | 2 | 17 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.524% | 77.27%
INTERNAL PRJ | AMS | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | N/A | IAA | QA | Quality Assurance | EssilorLuxottica | F. Pinnelli | M. Strada | Delivery Maintenance | Tester | 220 | 0 | ON GOING | 0 | 2024 | 19 | [10 empty] | 2 | 17 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.524% | 77.27%
INTERNAL PRJ | AMS | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | N/A | IAA | QA | Quality Assurance | EssilorLuxottica | F. Pinnelli | M. Vianelli | Delivery Projects | Analysis | 220 | 0 | ON GOING | 0 | 2024 | 16 | [8 empty] | 4 | 4 | 4 | 4 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 19.05% | 17.39% | 19.05% | 18.18%
PROSPECT | AMS |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | BIP | BIP Projects 2025 | EssilorLuxottica | F. Taita | A. Seira | Operations | Backend | 620 | 0 | PROPOSAL | 0% | 2024 | 7 | [11 empty] | 7 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 31.82%
PROSPECT | AMS |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | BIP | BIP Projects 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | DataManagement | 620 | 0 | PROPOSAL | 0% | 2024 | 4 | [11 empty] | 4 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 18.18%
PROSPECT | AMS |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | BIP | BIP Projects 2025 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | Backend | 620 | 0 | PROPOSAL | 0% | 2024 | 9 | [11 empty] | 9 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40.91%
PROSPECT | AMS |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | BIP | BIP Projects 2025 | EssilorLuxottica | F. Taita | T. Baldi | Operations | Backend | 620 | 0 | PROPOSAL | 0% | 2024 | 6 | [11 empty] | 6 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 27.27%
CONTRACT | AMS |  | 2024 | 2024-05-01 | 2024-12-31 | ABS24219 | ABS24219 | BIP | Ecommerce Rollout support 2 quater 2024 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | DataManagement | 70 | 36.25 | CLOSED | 100% | 2024 | 16 |  |  |  |  | 8 | 8 | [6 empty] | 0% | 0% | 0% | 0% | 40% | 40% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2024-05-01 | 2024-12-31 | ABS24219 | ABS24219 | BIP | Ecommerce Rollout support 2 quater 2024 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | DataManagement | 70 | 36.25 | CLOSED | 100% | 2024 | 19 |  |  |  |  | 18 | 1 | [6 empty] | 0% | 0% | 0% | 0% | 90% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2024-05-01 | 2024-12-31 | ABS24219 | ABS24219 | BIP | Ecommerce Rollout support 2 quater 2024 | EssilorLuxottica | F. Taita | R. Grienti | Operations | DataManagement | 70 | 36.25 | CLOSED | 100% | 2024 | 3 |  |  |  |  | 1 | 2 | [6 empty] | 0% | 0% | 0% | 0% | 5% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2024-05-01 | 2024-12-31 | ABS24219 | ABS24219 | BIP | Ecommerce Rollout support 2 quater 2024 | EssilorLuxottica | F. Taita | T. Baldi | Operations | DataManagement | 70 | 36.25 | CLOSED | 100% | 2024 | 17 |  |  |  |  | 9 | 8 | [6 empty] | 0% | 0% | 0% | 0% | 45% | 40% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2024-06-17 | 2024-08-31 | ABS24323 | ABS24323 | BIP | Ecommerce Rollout support 3rd quarter 2024 | EssilorLuxottica | F. Taita | A. Cerrato | Operations | DataManagement | 55 | 55 | CLOSED | 100% | 2024 | 5 | [5 empty] | 3 | 2 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 15% | 8.696% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2024-06-17 | 2024-08-31 | ABS24323 | ABS24323 | BIP | Ecommerce Rollout support 3rd quarter 2024 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | DataManagement | 55 | 55 | CLOSED | 100% | 2024 | 5 | [5 empty] | 4 | 1 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 20% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2024-06-17 | 2024-08-31 | ABS24323 | ABS24323 | BIP | Ecommerce Rollout support 3rd quarter 2024 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | DataManagement | 55 | 55 | CLOSED | 100% | 2024 | 23 | [5 empty] | 8 | 15 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 40% | 65.22% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2024-06-17 | 2024-08-31 | ABS24323 | ABS24323 | BIP | Ecommerce Rollout support 3rd quarter 2024 | EssilorLuxottica | F. Taita | R. Grienti | Operations | DataManagement | 55 | 55 | CLOSED | 100% | 2024 | 5 | [5 empty] | 3 | 2 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 15% | 8.696% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2024-06-17 | 2024-08-31 | ABS24323 | ABS24323 | BIP | Ecommerce Rollout support 3rd quarter 2024 | EssilorLuxottica | F. Taita | T. Baldi | Operations | DataManagement | 55 | 55 | CLOSED | 100% | 2024 | 24 | [5 empty] | 8 | 16 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 40% | 69.57% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2024-09-01 | 2024-12-31 | ABS24371 | ABS24371 | BIP | Ecommerce Rollout support 4Q 2024 | EssilorLuxottica | F. Taita | A. Seira | Operations | Backend | 56 | 47 | CLOSED | 100% | 2024 | 19 | [7 empty] | 1 | 18 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.333% | 85.71% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2024-09-01 | 2024-12-31 | ABS24371 | ABS24371 | BIP | Ecommerce Rollout support 4Q 2024 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | DataManagement | 56 | 47 | CLOSED | 100% | 2024 | 2 | [7 empty] | 1 | 1 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.333% | 4.762% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2024-09-01 | 2024-12-31 | ABS24371 | ABS24371 | BIP | Ecommerce Rollout support 4Q 2024 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | Backend | 56 | 47 | CLOSED | 100% | 2024 | 18 | [7 empty] | 3 | 15 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 71.43% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2024-09-01 | 2024-12-31 | ABS24371 | ABS24371 | BIP | Ecommerce Rollout support 4Q 2024 | EssilorLuxottica | F. Taita | T. Baldi | Operations | Backend | 56 | 47 | CLOSED | 100% | 2024 | 18 | [7 empty] | 1 | 17 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.333% | 80.95% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2023-12-01 | 2024-12-31 | ABS24053 | ALDDRES2 | BIP | Ecommerce Rollout Supporto 2024 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | DataManagement | 200 | 200 | CLOSED | 100% | 2024 | 0 | 2 | 2 | 2 | 16.15 | [8 empty] | 11.11% | 10% | 9.524% | 73.41% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2023-12-01 | 2024-12-31 | ABS24053 | ALDDRES2 | BIP | Ecommerce Rollout Supporto 2024 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | DataManagement | 200 | 200 | CLOSED | 100% | 2024 | 0 | 19 | 19 | 19 | 17 | [8 empty] | 105.6% | 95% | 90.48% | 77.27% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2023-12-01 | 2024-12-31 | ABS24053 | ALDDRES2 | BIP | Ecommerce Rollout Supporto 2024 | EssilorLuxottica | F. Taita | R. Grienti | Operations | DataManagement | 200 | 200 | CLOSED | 100% | 2024 | 5 |  |  |  | 5 | 5 | [7 empty] | 0% | 0% | 0% | 22.73% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2023-12-01 | 2024-12-31 | ABS24053 | ALDDRES2 | BIP | Ecommerce Rollout Supporto 2024 | EssilorLuxottica | F. Taita | T. Baldi | Operations | DataManagement | 200 | 200 | CLOSED | 100% | 2024 | 9 | 5 |  | 17 | 17 | 9 | [7 empty] | 27.78% | 0% | 80.95% | 77.27% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2022-01-01 | 2024-05-31 | ABS24292 | ALB | LOGISTIC | LMS BRASILE - LIGHT | EssilorLuxottica | F. Taita | C. Piraccini | Operations | Data Engineering | 188 | 180 | CLOSED | 96% | 2024 | 56.5 | 1.8 | 8.5 | 16 | 14.3 | 17 | 9 | 8 | 3.5 | 5 | 6 | 4 | 4 | 10% | 42.5% | 76.19% | 65% | 85% | 45% | 34.78% | 29.17% | 23.81% | 26.09% | 19.05% | 18.18%
CONTRACT | PRJ | Waterfall | 2024 | 2022-01-01 | 2024-05-31 | ABS24292 | ALB | LOGISTIC | LMS BRASILE - LIGHT | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | DataManagement | 188 | 180 | CLOSED | 96% | 2024 | 9 | [8 empty] | 2 | 3 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.524% | 13.04% | 9.524% | 9.091%
CONTRACT | PRJ | Waterfall | 2024 | 2022-01-01 | 2024-05-31 | ABS24292 | ALB | LOGISTIC | LMS BRASILE - LIGHT | EssilorLuxottica | F. Taita | M. Regini | Operations | BackEnd | 188 | 180 | CLOSED | 96% | 2024 | 49.5 |  | 6.4 | 17 | 11 | 13.5 | 15 | 6 |  | 4 | 4 | 3 | 4 | 0% | 32% | 80.95% | 50% | 67.5% | 75% | 26.09% | 0% | 19.05% | 17.39% | 14.29% | 18.18%
CONTRACT | PRJ | Waterfall | 2024 | 2022-01-01 | 2024-05-31 | ABS24292 | ALB | LOGISTIC | LMS BRASILE - LIGHT | EssilorLuxottica | F. Taita | R. Bondi | Operations | Data Engineering | 188 | 180 | CLOSED | 96% | 2024 | 10 | [5 empty] | 7 | 3 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 35% | 13.04% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2024 | 2024-10-15 | 2024-12-31 | N/A | N/A | LOGISTIC | LMS GIRONA- LIGHT | EssilorLuxottica | F. Taita | C. Piraccini | Operations | Data Engineering | 20 | 12 | CLOSED | 60% | 2024 | 8 | [9 empty] | 4 | 4 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 17.39% | 19.05% | 0%
PROSPECT | PRJ | Waterfall | 2024 | 2024-10-15 | 2024-12-31 | N/A | N/A | LOGISTIC | LMS GIRONA- LIGHT | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | DataManagement | 20 | 12 | CLOSED | 60% | 2024 | 2 | [9 empty] | 1 | 1 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 4.762% | 0%
PROSPECT | PRJ | Waterfall | 2024 | 2024-10-15 | 2024-12-31 | N/A | N/A | LOGISTIC | LMS GIRONA- LIGHT | EssilorLuxottica | F. Taita | M. Regini | Operations | BackEnd | 20 | 12 | CLOSED | 60% | 2024 | 9 | [9 empty] | 5 | 4 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 19.05% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-04-01 | 2024-12-31 | ABS24164 | ALT | LOGISTIC | LMS TIJUANA | EssilorLuxottica | F. Taita | C. Piraccini | Operations | Data Engineering | 133 | 88 | ON GOING | 66% | 2024 | 50.45 |  |  | 1.125 |  | 1.4 | 3 | 11 | 1.3 | 12.75 | 7 | 7 | 7 | 0% | 0% | 5.357% | 0% | 7% | 15% | 47.83% | 10.83% | 60.71% | 30.43% | 33.33% | 31.82%
CONTRACT | PRJ | Waterfall | 2024 | 2024-04-01 | 2024-12-31 | ABS24164 | ALT | LOGISTIC | LMS TIJUANA | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Engineering | 133 | 88 | ON GOING | 66% | 2024 | 8 | [8 empty] | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | PRJ | Waterfall | 2024 | 2024-04-01 | 2024-12-31 | ABS24164 | ALT | LOGISTIC | LMS TIJUANA | EssilorLuxottica | F. Taita | M. Regini | Operations | BackEnd | 133 | 88 | ON GOING | 66% | 2024 | 31.6 | [6 empty] | 7 | 1.3 | 7.3 | 6 | 5 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 30.43% | 10.83% | 34.76% | 26.09% | 23.81% | 22.73%
CONTRACT | PRJ | Waterfall | 2024 | 2022-01-01 | 2024-05-31 | ABS24208 | ALDSE2ER | LOGISTIC | LUX DM Supporto ELECTRA 2024 - anhancement & Rollout | EssilorLuxottica | F. Taita | C. Piraccini | Operations | Data Engineering | 50 | 43.5 | ON GOING | 87% | 2024 | 13.8 |  |  |  | 1 | 0.25 | 0.5 | 2 | 0.25 | 1.8 | 3 | 3 | 3 | 0% | 0% | 0% | 4.545% | 1.25% | 2.5% | 8.696% | 2.083% | 8.571% | 13.04% | 14.29% | 13.64%
CONTRACT | PRJ | Waterfall | 2024 | 2022-01-01 | 2024-05-31 | ABS24208 | ALDSE2ER | LOGISTIC | LUX DM Supporto ELECTRA 2024 - anhancement & Rollout | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | DataManagement | 50 | 43.5 | ON GOING | 87% | 2024 | 3 | [9 empty] | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 4.762% | 4.545%
CONTRACT | PRJ | Waterfall | 2024 | 2022-01-01 | 2024-05-31 | ABS24208 | ALDSE2ER | LOGISTIC | LUX DM Supporto ELECTRA 2024 - anhancement & Rollout | EssilorLuxottica | F. Taita | M. Regini | Operations | BackEnd | 50 | 43.5 | ON GOING | 87% | 2024 | 29 |  |  |  | 3 | 3 | 2.5 | 5 | 1.5 | 5 | 6 | 3 | 3 | 0% | 0% | 0% | 13.64% | 15% | 12.5% | 21.74% | 12.5% | 23.81% | 26.09% | 14.29% | 13.64%
CONTRACT | AMS | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS24450 | ABS24450 | BIP | LUX-DI-DM – fifth ecommerce support- rollout 2024 | EssilorLuxottica | F. Taita | A. Seira | Operations | BackEnd | 55 | 50 | ON GOING | 91% | 2024 | 21 | [9 empty] | 21 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 91.3% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS24450 | ABS24450 | BIP | LUX-DI-DM – fifth ecommerce support- rollout 2024 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | PM - Project Governance | 55 | 53 | CLOSED | 96% | 2024 | 4 | [9 empty] | 4 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 17.39% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS24450 | ABS24450 | BIP | LUX-DI-DM – fifth ecommerce support- rollout 2024 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | BackEnd | 55 | 53 | CLOSED | 96% | 2024 | 1 | [9 empty] | 1 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS24450 | ABS24450 | BIP | LUX-DI-DM – fifth ecommerce support- rollout 2024 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | BackEnd | 55 | 53 | CLOSED | 96% | 2024 | 16 | [9 empty] | 16 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 69.57% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS24450 | ABS24450 | BIP | LUX-DI-DM – fifth ecommerce support- rollout 2024 | EssilorLuxottica | F. Taita | T. Baldi | Operations | BackEnd | 55 | 53 | CLOSED | 96% | 2024 | 1 | [9 empty] | 1 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-11-01 | 2024-12-31 | ABS24526 | ABS24526 | BIP | LUX-DI-DM – Sixth ecommerce support- rollout 2024 | EssilorLuxottica | F. Taita | A. Seira | Operations | BackEnd | 60 | 44 | ON GOING | 73% | 2024 | 3 | [10 empty] | 2 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.524% | 4.545%
CONTRACT | AMS | Waterfall | 2024 | 2024-11-01 | 2024-12-31 | ABS24526 | ABS24526 | BIP | LUX-DI-DM – Sixth ecommerce support- rollout 2024 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | PM - Project Governance | 60 | 44 | ON GOING | 73% | 2024 | 6 | [10 empty] | 4 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 19.05% | 9.091%
CONTRACT | AMS | Waterfall | 2024 | 2024-11-01 | 2024-12-31 | ABS24526 | ABS24526 | BIP | LUX-DI-DM – Sixth ecommerce support- rollout 2024 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | BackEnd | 60 | 44 | ON GOING | 73% | 2024 | 4 | [10 empty] | 1 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762% | 13.64%
CONTRACT | AMS | Waterfall | 2024 | 2024-11-01 | 2024-12-31 | ABS24526 | ABS24526 | BIP | LUX-DI-DM – Sixth ecommerce support- rollout 2024 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | BackEnd | 60 | 44 | ON GOING | 73% | 2024 | 20 | [10 empty] | 14 | 6 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 66.67% | 27.27%
CONTRACT | AMS | Waterfall | 2024 | 2024-11-01 | 2024-12-31 | ABS24526 | ABS24526 | BIP | LUX-DI-DM – Sixth ecommerce support- rollout 2024 | EssilorLuxottica | F. Taita | T. Baldi | Operations | BackEnd | 60 | 44 | ON GOING | 73% | 2024 | 20 | [10 empty] | 14 | 6 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 66.67% | 27.27%
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-12-31 | ABS24163 | BS24163 | LOGISTIC | RTTF support 2024 | EssilorLuxottica | F. Taita | A. Cerrato | Operations | BackEnd | 100 | 100 | CLOSED | 100% | 2024 | 22 |  |  |  |  | 8 | 1 | 13 | [5 empty] | 0% | 0% | 0% | 0% | 40% | 5% | 56.52% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-12-31 | ABS24163 | BS24163 | LOGISTIC | RTTF support 2024 | EssilorLuxottica | F. Taita | A. Strada | Operations | DataManagement | 100 | 100 | CLOSED | 100% | 2024 | 4 |  |  |  |  | 2 | 1 | 1 | [5 empty] | 0% | 0% | 0% | 0% | 10% | 5% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-12-31 | ABS24163 | BS24163 | LOGISTIC | RTTF support 2024 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | PM - Project Governance | 100 | 100 | CLOSED | 100% | 2024 | 16 |  |  |  | 4 | 5 | 4 | 4 |  | 3 |  |  |  | 0% | 0% | 0% | 18.18% | 25% | 20% | 17.39% | 0% | 14.29% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-12-31 | ABS24163 | BS24163 | LOGISTIC | RTTF support 2024 | EssilorLuxottica | F. Taita | M. Calabrese | Delivery Projects | Analysis | 100 | 100 | CLOSED | 100% | 2024 | 1 |  |  |  |  | 1 | [7 empty] | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-12-31 | ABS24163 | BS24163 | LOGISTIC | RTTF support 2024 | EssilorLuxottica | F. Taita | M. Vimercati | Operations | FrontEnd | 100 | 100 | CLOSED | 100% | 2024 | 1 |  |  |  |  | 1 | [7 empty] | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-12-31 | ABS24163 | BS24163 | LOGISTIC | RTTF support 2024 | EssilorLuxottica | F. Taita | R. Bondi | Operations | FrontEnd | 100 | 100 | CLOSED | 100% | 2024 | 12.5 |  |  |  | 0.5 | 4.5 | 2 | 5 |  | 1 |  |  |  | 0% | 0% | 0% | 2.273% | 22.5% | 10% | 21.74% | 0% | 4.762% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-12-31 | ABS24163 | BS24163 | LOGISTIC | RTTF support 2024 | EssilorLuxottica | F. Taita | R. Grienti | Operations | BackEnd | 100 | 100 | CLOSED | 100% | 2024 | 11 |  |  |  |  | 7 | 1 | 1 |  | 2 |  |  |  | 0% | 0% | 0% | 0% | 35% | 5% | 4.348% | 0% | 9.524% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24593 | ABS24593 | RETAIL | LUX-DI-VAPP GRA Wave1 + Wave2 | EssilorLuxottica | F. Vassallo | F. Vassallo | Delivery AMS | PM - Project Governance | 75 | 10 | ON GOING | 13% | 2024 | 15 | [8 empty] | 5 | 5 | 5 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 23.81% | 21.74% | 23.81% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24593 | ABS24593 | RETAIL | LUX-DI-VAPP GRA Wave1 + Wave2 | EssilorLuxottica | F. Vassallo | I. OSTYMCHUCK | Operations | BackEnd | 75 | 10 | ON GOING | 13% | 2024 | 15 | [8 empty] | 5 | 5 | 5 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 23.81% | 21.74% | 23.81% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24593 | ABS24593 | RETAIL | LUX-DI-VAPP GRA Wave1 + Wave2 | EssilorLuxottica | F. Vassallo | M. Porcu | Operations | Technical Leader | 75 | 10 | ON GOING | 13% | 2024 | 2 | [8 empty] | 1 | 1 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762% | 4.348% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24593 | ABS24593 | RETAIL | LUX-DI-VAPP GRA Wave1 + Wave2 | EssilorLuxottica | F. Vassallo | S. Beltrami | Operations | FrontEnd | 75 | 10 | ON GOING | 13% | 2024 | 15 | [8 empty] | 5 | 5 | 5 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 23.81% | 21.74% | 23.81% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24592 | ABS24592 | RETAIL | LUX-DI-VAPP GRSD Top Brand Wave 1 | EssilorLuxottica | F. Vassallo | A. Pirola | Operations | BackEnd | 60 | 50.7 | ON GOING | 85% | 2024 | 1 | [6 empty] | 0.5 | 0.5 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 2.174% | 4.167% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24592 | ABS24592 | RETAIL | LUX-DI-VAPP GRSD Top Brand Wave 1 | EssilorLuxottica | F. Vassallo | D. Heba | Operations | BackEnd | 60 | 50.7 | ON GOING | 85% | 2024 | 21 | [7 empty] | 6 | 15 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 71.43% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24592 | ABS24592 | RETAIL | LUX-DI-VAPP GRSD Top Brand Wave 1 | EssilorLuxottica | F. Vassallo | F. Vassallo | Delivery AMS | PM - Project Governance | 60 | 50.7 | ON GOING | 85% | 2024 | 1 | [6 empty] | 1 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24592 | ABS24592 | RETAIL | LUX-DI-VAPP GRSD Top Brand Wave 1 | EssilorLuxottica | F. Vassallo | M. Mannarino | Operations | BackEnd | 60 | 50.7 | ON GOING | 85% | 2024 | 18 | [6 empty] | 1 | 5 | 12 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 41.67% | 57.14% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24592 | ABS24592 | RETAIL | LUX-DI-VAPP GRSD Top Brand Wave 1 | EssilorLuxottica | F. Vassallo | M. Vianelli | Delivery Projects | Analysis | 60 | 50.7 | ON GOING | 85% | 2024 | 3 | [6 empty] | 3 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24592 | ABS24592 | RETAIL | LUX-DI-VAPP GRSD Top Brand Wave 1 | EssilorLuxottica | F. Vassallo | R. Grandi | Operations | Data Management | 60 | 50.7 | ON GOING | 85% | 2024 | 2.5 | [6 empty] | 2 | 0.5 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 4.167% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24592 | ABS24592 | RETAIL | LUX-DI-VAPP GRSD Top Brand Wave 1 | EssilorLuxottica | F. Vassallo | R. Tortora | Operations | Data Management | 60 | 50.7 | ON GOING | 85% | 2024 | 2 | [7 empty] | 2 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 16.67% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24592 | ABS24592 | RETAIL | LUX-DI-VAPP GRSD Top Brand Wave 1 | EssilorLuxottica | F. Vassallo | S. Delle Fave | Operations | BackEnd | 60 | 50.7 | ON GOING | 85% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2023 | 2024-09-01 | 2024-12-31 | ABS24592 | ABS24592 | RETAIL | LUX-DI-VAPP GRSD Top Brand Wave 1 | EssilorLuxottica | F. Vassallo | T. Porzio | Delivery AMS | PM - Project Governance | 60 | 50.7 | ON GOING | 85% | 2024 | 4 | [6 empty] | 1 | 3 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 25% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | A. Ferrari | Operations | Monitoraggio WE | 1210 | 755 | ON GOING | 62% | 2024 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 8.696% | 16.67% | 9.524% | 8.696% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | A. Pirola | Operations | FrontEnd | 1210 | 755 | ON GOING | 62% | 2024 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | A. Pirola | Operations | FrontEnd | 1210 | 755 | ON GOING | 62% | 2024 | 6 |  |  |  | 1 | 1 | 5 | [6 empty] | 0% | 0% | 0% | 4.545% | 5% | 25% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | A. Vladi | Operations | Reperibilità | 1210 | 755 | ON GOING | 62% | 2024 | 15 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 2 | 2 |  |  | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 8.696% | 41.67% | 9.524% | 8.696% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | C. Piraccini | Operations | Data Management | 1210 | 755 | ON GOING | 62% | 2024 | 10 | [10 empty] | 5 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 23.81% | 22.73%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | D. Heba | Operations | BackEnd | 1210 | 755 | ON GOING | 62% | 2024 | 37 | [8 empty] | 5 | 15 | 2 | 15 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 23.81% | 65.22% | 9.524% | 68.18%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | D. HEBA | Operations | Reperibilità | 1210 | 755 | ON GOING | 62% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | F. D'ALBERTO | Operations | BackEnd | 1210 | 755 | ON GOING | 62% | 2024 | 2 | [11 empty] | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.091%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | F. Malvezzi | Operations | Data Engineer | 1210 | 755 | ON GOING | 62% | 2024 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | F. Origlia | Operations | Technical Leader | 1210 | 755 | ON GOING | 62% | 2024 | 3 |  |  |  | 2 | 3 | [7 empty] | 0% | 0% | 0% | 9.091% | 15% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | F. Vassallo | Delivery AMS | PM - Project Governance | 1210 | 755 | ON GOING | 62% | 2024 | 200 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 138.9% | 125% | 119% | 113.6% | 125% | 125% | 108.7% | 208.3% | 119% | 108.7% | 119% | 113.6%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | F. Vassallo | Delivery AMS | Reperibilità | 1210 | 755 | ON GOING | 62% | 2024 | 32 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 4 | 4 | 4 |  |  | 44.44% | 40% | 38.1% | 36.36% | 40% | 40% | 17.39% | 33.33% | 19.05% | 17.39% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | G. Mordà | Operations | Data Management | 1210 | 755 | ON GOING | 62% | 2024 | 2 | [8 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.381% | 2.174% | 2.381% | 2.273%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | G. Sabbatini | Operations | Synapse | 1210 | 755 | ON GOING | 62% | 2024 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [5 empty] | 2.778% | 2.5% | 2.381% | 2.273% | 2.5% | 2.5% | 2.174% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | G. Tartaglia | Operations | Monitoraggio WE | 1210 | 755 | ON GOING | 62% | 2024 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 8.696% | 16.67% | 9.524% | 8.696% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | M. Mannarino | Operations | BackEnd | 1210 | 755 | ON GOING | 62% | 2024 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | M. Mannarino | Operations | BackEnd | 1210 | 755 | ON GOING | 62% | 2024 | 60 | 12 | 12 | 12 | 5 | 5 | 5 | 5 | 5 | 1 | 15 | 12 | 12 | 66.67% | 60% | 57.14% | 22.73% | 25% | 25% | 21.74% | 41.67% | 4.762% | 65.22% | 57.14% | 54.55%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | M. Mannarino | Operations | Reperibilità | 1210 | 755 | ON GOING | 62% | 2024 | 15 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 2 | 2 |  |  | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 8.696% | 41.67% | 9.524% | 8.696% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | M. Vianelli | Delivery Projects | Analysis | 1210 | 755 | ON GOING | 62% | 2024 | 41 | 5 | 6 | 6 | 5 | 6 | 6 | 6 | 5 | 3 | 5 | 5 | 5 | 27.78% | 30% | 28.57% | 22.73% | 30% | 30% | 26.09% | 41.67% | 14.29% | 21.74% | 23.81% | 22.73%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | N. GUERRERO | Delivery AMS | PM - Project Governance | 1210 | 755 | ON GOING | 62% | 2024 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.778% | 2.5% | 2.381% | 2.273% | 2.5% | 2.5% | 2.174% | 4.167% | 2.381% | 2.174% | 2.381% | 2.273%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | N. GUERRERO | Delivery AMS | Monitoraggio WE | 1210 | 755 | ON GOING | 62% | 2024 | 11 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 |  |  | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 8.696% | 8.333% | 9.524% | 8.696% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | N. Pescione | Operations | Monitoraggio WE | 1210 | 755 | ON GOING | 62% | 2024 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 8.696% | 16.67% | 9.524% | 8.696% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | P. Anzellotti | Operations | Technical Leader | 1210 | 755 | ON GOING | 62% | 2024 | 4.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 2.778% | 2.5% | 2.381% | 2.273% | 2.5% | 2.5% | 2.174% | 4.167% | 2.381% | 2.174% | 2.381% | 4.545%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | P. Anzellotti | Operations | Monitoraggio WE | 1210 | 755 | ON GOING | 62% | 2024 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 8.696% | 16.67% | 9.524% | 8.696% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | P. SINGH | AREA TECH | Data Management | 1210 | 755 | ON GOING | 62% | 2024 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [7 empty] | 2.778% | 2.5% | 2.381% | 2.273% | 2.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | R. Grandi | Operations | Data Management | 1210 | 755 | ON GOING | 62% | 2024 | 42 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 15 | 15 | 2 | 2 | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 41.67% | 71.43% | 65.22% | 9.524% | 9.091%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | R. Marasca | Delivery Projects | Analysis | 1210 | 755 | ON GOING | 62% | 2024 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [7 empty] | 2.778% | 2.5% | 2.381% | 2.273% | 2.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | R. Tortora | Operations | Data Management | 1210 | 755 | ON GOING | 62% | 2024 | 71 | [5 empty] | 5 | 1 | 5 | 15 | 15 | 15 | 15 | 0% | 0% | 0% | 0% | 0% | 25% | 4.348% | 41.67% | 71.43% | 65.22% | 71.43% | 68.18%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | T. Porzio | Delivery AMS | Data Management | 1210 | 755 | ON GOING | 62% | 2024 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 4 |  |  | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 25% | 9.524% | 17.39% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24377 | ABS24377 | RETAIL | VAPP CR Plus Q3Q4 2024 | EssilorLuxottica | F. Vassallo | D. Heba | Operations | BackEnd | 50 | 0 | ON GOING | 0% | 2024 | 25 | [6 empty] | 5 |  | 15 | 5 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 0% | 71.43% | 21.74% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24377 | ABS24377 | RETAIL | VAPP CR Plus Q3Q4 2024 | EssilorLuxottica | F. Vassallo | F. Vassallo | Delivery AMS | PM - Project Governance | 50 | 0 | ON GOING | 0% | 2024 | 15 | [6 empty] | 5 |  | 5 | 5 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 0% | 23.81% | 21.74% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24377 | ABS24377 | RETAIL | VAPP CR Plus Q3Q4 2024 | EssilorLuxottica | F. Vassallo | M. Mannarino | Operations | Data Engineer | 50 | 0 | ON GOING | 0% | 2024 | 20 | [6 empty] | 5 |  | 15 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 0% | 71.43% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24377 | ABS24377 | RETAIL | VAPP CR Plus Q3Q4 2024 | EssilorLuxottica | F. Vassallo | M. Vianelli | Delivery Projects | Analysis | 50 | 0 | ON GOING | 0% | 2024 | 19 | [8 empty] | 5 | 5 | 5 | 4 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 23.81% | 21.74% | 23.81% | 18.18%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24377 | ABS24377 | RETAIL | VAPP CR Plus Q3Q4 2024 | EssilorLuxottica | F. Vassallo | R. Grandi | Operations | Data Management | 50 | 0 | ON GOING | 0% | 2024 | 11 | [6 empty] | 5 |  | 1 | 5 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 0% | 4.762% | 21.74% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24377 | ABS24377 | RETAIL | VAPP CR Plus Q3Q4 2024 | EssilorLuxottica | F. Vassallo | R. Tortora | Operations | Data Management | 50 | 0 | ON GOING | 0% | 2024 | 11 | [6 empty] | 5 |  | 1 | 5 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 0% | 4.762% | 21.74% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24377 | ABS24377 | RETAIL | VAPP CR Plus Q3Q4 2024 | EssilorLuxottica | F. Vassallo | S. Beltrami | Operations | FrontEnd | 50 | 0 | ON GOING | 0% | 2024 | 40 | [6 empty] | 5 |  | 21 | 14 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 0% | 100% | 60.87% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24377 | ABS24377 | RETAIL | VAPP CR Plus Q3Q4 2024 | EssilorLuxottica | F. Vassallo | S. Delle Fave | Operations | FrontEnd | 50 | 0 | ON GOING | 0% | 2024 | 6 | [6 empty] | 5 |  | 1 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 0% | 4.762% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24377 | ABS24377 | RETAIL | VAPP CR Plus Q3Q4 2024 | EssilorLuxottica | F. Vassallo | T. Porzio | Delivery AMS | Data Management | 50 | 0 | ON GOING | 0% | 2024 | 9 | [6 empty] | 2 |  | 5 | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 0% | 23.81% | 8.696% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | A. PIROLA | Operations | FrontEnd | 75 | 14 | ON GOING | 19% | 2024 | 8 | [10 empty] | 3 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 22.73%
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | C. Piraccini | Operations | Data Management | 75 | 14 | ON GOING | 19% | 2024 | 6 | [10 empty] | 3 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 13.64%
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | D. Heba | Operations | BackEnd | 75 | 14 | ON GOING | 19% | 2024 | 4 | [10 empty] | 3 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 4.545%
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | F. Vassallo | Delivery AMS | PM - Project Governance | 75 | 14 | ON GOING | 19% | 2024 | 7 | [10 empty] | 2 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.524% | 22.73%
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | M. Mannarino | Operations | Data Engineer | 75 | 14 | ON GOING | 19% | 2024 | 4 | [10 empty] | 3 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 4.545%
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | M. Vianelli | Consulting | Analysis | 75 | 14 | ON GOING | 19% | 2024 | 5 | [10 empty] | 3 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 9.091%
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | R. Grandi | Operations | Data Management | 75 | 14 | ON GOING | 19% | 2024 | 6 | [10 empty] | 3 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 13.64%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | A. Caldana | Operations | BackEnd | 188 | 170 | CLOSED | 90% | 2024 | 7 | 5 | 4 | 5 | 5 | 5 | 2 | [6 empty] | 27.78% | 20% | 23.81% | 22.73% | 25% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | A. Pirola | Operations | FrontEnd | 188 | 170 | CLOSED | 99% | 2024 | 19 |  |  |  | 5 | 5 | 6 | 1 | 2 | 5 |  |  |  | 0% | 0% | 0% | 22.73% | 25% | 30% | 4.348% | 16.67% | 23.81% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | B. Capotorto | Operations | BackEnd | 188 | 170 | CLOSED | 90% | 2024 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | [6 empty] | 27.78% | 25% | 23.81% | 22.73% | 25% | 25% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | D. Heba | Operations | BackEnd | 188 | 170 | CLOSED | 99% | 2024 | 0 |  | 2 | 1 | [9 empty] | 0% | 10% | 4.762% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | F. Origlia | Operations | Architecture Analysis | 188 | 170 | CLOSED | 99% | 2024 | 1 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [6 empty] | 0% | 2.5% | 2.381% | 2.273% | 2.5% | 2.5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | F. Vassallo | Delivery AMS | PM - Project Governance | 188 | 170 | CLOSED | 99% | 2024 | 3 |  | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 0% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | G. Fiorentini | Operations | BackEnd | 188 | 170 | CLOSED | 90% | 2024 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | G. Luongo | Delivery AMS | PM - Project Governance | 188 | 170 | CLOSED | 90% | 2024 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | M. Mannarino | Operations | BackEnd | 188 | 170 | CLOSED | 99% | 2024 | 3 |  | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 0% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | M. Vianelli | Delivery Projects | Analysis | 188 | 170 | CLOSED | 99% | 2024 | 0 |  | 5 | 5 | 5 | [8 empty] | 0% | 25% | 23.81% | 22.73% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | P. Anzellotti | Operations | Technical Leader | 188 | 170 | CLOSED | 99% | 2024 | 0.6 |  |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | [5 empty] | 0% | 0% | 0.9524% | 0.9091% | 1% | 1% | 0.8696% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | P. Assirelli | Operations | Technical Leader | 188 | 170 | CLOSED | 90% | 2024 | 12 | 6 | 6 | 6 | 6 | 6 | 6 | [6 empty] | 33.33% | 30% | 28.57% | 27.27% | 30% | 30% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | R. Grandi | Operations | Data Management | 188 | 170 | CLOSED | 99% | 2024 | 3 |  | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 0% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | S. Delle Fave | Operations | FrontEnd | 188 | 170 | CLOSED | 99% | 2024 | 2 |  | 2 | 2 |  | 2 | [7 empty] | 0% | 10% | 9.524% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | T. Porzio | Delivery AMS | Data Management | 188 | 170 | CLOSED | 99% | 2024 | 11 |  | 3 | 3 | 3 | 3 | 3 | 3 |  | 1 | 1 |  |  | 0% | 15% | 14.29% | 13.64% | 15% | 15% | 13.04% | 0% | 4.762% | 4.348% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | N/A | ECC | ECC LOGISTIC PROJECTS GOVERNANCE | EssilorLuxottica | G. D'alesio | A. Torone | Delivery AMS | PM - Project Governance | 154 | 143 | ON GOING | 75% | 2024 | 83.5 | 12 | 14 | 15 | 13.5 | 15 | 14 | 16 | 8 | 15 | 11.5 | 2 | 2 | 66.67% | 70% | 71.43% | 61.36% | 75% | 70% | 69.57% | 66.67% | 71.43% | 50% | 9.524% | 9.091%
CONTRACT | AMS | Watefall | 2024 | 2024-05-01 | 2024-08-31 | ABS24216 | ABS24216 | CRM | Global CS B2C AMS 2024 | EssilorLuxottica | G. Galati | A. De Sanctis | Operations | Data Management | 21 | 6.5 | CLOSED | 31% | 2024 | 13 |  |  | 2 | 2 | 4 | 5 | 4 | [5 empty] | 0% | 0% | 9.524% | 9.091% | 20% | 25% | 17.39% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Watefall | 2024 | 2024-05-01 | 2024-08-31 | ABS24216 | ABS24216 | CRM | Global CS B2C AMS 2024 | EssilorLuxottica | G. Galati | G. Galati | Delivery AMS | PM - Project Governance | 21 | 6.5 | CLOSED | 31% | 2024 | 4 |  |  |  |  | 1.5 | 1.5 | 1 | [5 empty] | 0% | 0% | 0% | 0% | 7.5% | 7.5% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2023-11-01 | 2024-12-31 | ABS24087 | ACTAA | Logistic | CTRL-Tower Atlanta AMS 2024 | EssilorLuxottica | G. Luongo | A. Crescimone | Operations | BackEnd | 212 | 56 | ON GOING | 26% | 2024 | 16 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2.778% | 2.5% | 2.381% | 2.273% | 10% | 10% | 8.696% | 16.67% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | AMS | Waterfall | 2024 | 2023-11-01 | 2024-12-31 | ABS24087 | ACTAA | Logistic | CTRL-Tower Atlanta AMS 2024 | EssilorLuxottica | G. Luongo | A. Saija | Operations | BackEnd | 212 | 56 | ON GOING | 26% | 2024 | 16 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 8.696% | 16.67% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | AMS | Waterfall | 2024 | 2023-11-01 | 2024-12-31 | ABS24087 | ACTAA | Logistic | CTRL-Tower Atlanta AMS 2024 | EssilorLuxottica | G. Luongo | G. D'Amanti | Operations | BackEnd | 212 | 56 | ON GOING | 26% | 2024 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 |  | 2.778% | 2.5% | 2.381% | 2.273% | 2.5% | 2.5% | 2.174% | 4.167% | 2.381% | 2.174% | 4.762% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2023-11-01 | 2024-12-31 | ABS24087 | ACTAA | Logistic | CTRL-Tower Atlanta AMS 2024 | EssilorLuxottica | G. Luongo | G. Luongo | Delivery AMS | PM - Project Governance | 212 | 56 | ON GOING | 26% | 2024 | 8 | 1 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5.556% | 2.5% | 2.381% | 2.273% | 5% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS | Waterfall | 2024 | 2023-11-01 | 2024-12-31 | ABS24087 | ACTAA | Logistic | CTRL-Tower Atlanta AMS 2024 | EssilorLuxottica | G. Luongo | L. Gullotto | Operations | BackEnd | 212 | 56 | ON GOING | 26% | 2024 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.778% | 2.5% | 2.381% | 2.273% | 2.5% | 2.5% | 2.174% | 4.167% | 2.381% | 2.174% | 2.381% | 2.273%
CONTRACT | AMS | Waterfall | 2024 | 2023-11-01 | 2024-12-31 | ABS24087 | ACTAA | Logistic | CTRL-Tower Atlanta AMS 2024 | EssilorLuxottica | G. Luongo | P. Assirelli | Operations | Technical Leader | 212 | 56 | ON GOING | 26% | 2024 | 16 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 8.696% | 16.67% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-01 | ABS24318 | ADATLS | RETAIL | Digital Platform LENS Transition Simulator | EssilorLuxottica | G. Luongo | G. D'Amanti | Operations | BackEnd | 9 | 1 | ON GOING | 11% | 2024 | 8 | [9 empty] | 6 | 2 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 26.09% | 9.524% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-01 | ABS24318 | ADATLS | RETAIL | Digital Platform LENS Transition Simulator | EssilorLuxottica | G. Luongo | P. Assirelli | Operations | Technical Leader | 9 | 1 | ON GOING | 11% | 2024 | 1 | [6 empty] | 1 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | A. Caldana | Operations | BackEnd | 1610 | 1067 | ON GOING | 66% | 2024 | 63 | 13 | 16 | 16 | 14 | 17 | 12 | 18 |  | 16 |  |  |  | 72.22% | 80% | 76.19% | 63.64% | 85% | 60% | 78.26% | 0% | 76.19% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | A. Crescimone | Operations | BackEnd | 1610 | 1067 | ON GOING | 66% | 2024 | 113 | 19 | 21 | 21 | 19 | 19 | 15 | 18 |  | 16 | 18 | 15 | 12 | 105.6% | 105% | 100% | 86.36% | 95% | 75% | 78.26% | 0% | 76.19% | 78.26% | 71.43% | 54.55%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | A. Saija | Operations | BackEnd | 1610 | 1067 | ON GOING | 66% | 2024 | 110 | 16 | 18 | 19 | 17 | 2 | 16 | 19 |  | 19 | 21 | 18 | 15 | 88.89% | 90% | 90.48% | 77.27% | 10% | 80% | 82.61% | 0% | 90.48% | 91.3% | 85.71% | 68.18%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | B. Capotorto | Operations | Analysis | 1610 | 1067 | ON GOING | 66% | 2024 | 102 | 13 | 15 | 16 | 14 | 17 | 15 | 18 |  | 7 | 18 | 15 | 12 | 72.22% | 75% | 76.19% | 63.64% | 85% | 75% | 78.26% | 0% | 33.33% | 78.26% | 71.43% | 54.55%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | C. Piraccini | Operations | Backend | 1610 | 1067 | ON GOING | 66% | 2024 | 15 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | [5 empty] | 27.78% | 25% | 23.81% | 22.73% | 25% | 25% | 21.74% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | G. D'Amanti | Operations | BackEnd | 1610 | 1067 | ON GOING | 66% | 2024 | 83 | 17 | 19 | 21 | 19 | 21 | 17 | 2 |  | 21 | 14 | 8 |  | 94.44% | 95% | 100% | 86.36% | 105% | 85% | 8.696% | 0% | 100% | 60.87% | 38.1% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | G. Fiorentini | Operations | BackEnd | 1610 | 1067 | ON GOING | 66% | 2024 | 32 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  | 8 |  |  |  | 44.44% | 40% | 38.1% | 36.36% | 40% | 40% | 34.78% | 0% | 38.1% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | G. Luongo | Delivery AMS | PM - Project Governance | 1610 | 1067 | ON GOING | 66% | 2024 | 202 | 17 | 2 | 2 | 18 | 19 | 19 | 19 |  | 19 | 48 | 42 | 36 | 94.44% | 10% | 9.524% | 81.82% | 95% | 95% | 82.61% | 0% | 90.48% | 208.7% | 200% | 163.6%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | L. Gullotto | Operations | BackEnd | 1610 | 1067 | ON GOING | 66% | 2024 | 101 | 17 | 19 | 21 | 19 | 21 | 17 | 2 |  | 19 | 23 | 2 | 17 | 94.44% | 95% | 100% | 86.36% | 105% | 85% | 8.696% | 0% | 90.48% | 100% | 9.524% | 77.27%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | M. Regini | Operations | Backend | 1610 | 1067 | ON GOING | 66% | 2024 | 23 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  | 2 | 2 | 2 | 2 | 27.78% | 25% | 23.81% | 22.73% | 25% | 25% | 21.74% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | P. Assirelli | Operations | Technical Leader/Analista | 1610 | 1067 | ON GOING | 66% | 2024 | 82 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 1 | 15 | 15 | 15 | 66.67% | 60% | 57.14% | 54.55% | 60% | 60% | 52.17% | 0% | 4.762% | 65.22% | 71.43% | 68.18%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | T. Baldi | Operations | Backend | 1610 | 1067 | ON GOING | 66% | 2024 | 7 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 1 |  |  |  | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 8.696% | 0% | 4.762% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24568 | N/A | RETAIL | OneLRA CR Plus Q3Q4 2024 | EssilorLuxottica | G. Luongo | A. Caldana | Operations | BackEnd | 250 | 79 | ON GOING | 32% | 2024 | 17 | 5 | 4 | 5 | 5 | 5 | 2 | 5 |  | 5 |  |  |  | 27.78% | 20% | 23.81% | 22.73% | 25% | 10% | 21.74% | 0% | 23.81% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24568 | N/A | RETAIL | OneLRA CR Plus Q3Q4 2024 | EssilorLuxottica | G. Luongo | B. Capotorto | Operations | BackEnd | 250 | 79 | ON GOING | 32% | 2024 | 19 | [6 empty] | 5 |  | 5 | 1 | 7 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 0% | 23.81% | 4.348% | 33.33% | 4.545%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24568 | N/A | RETAIL | OneLRA CR Plus Q3Q4 2024 | EssilorLuxottica | G. Luongo | G. Fiorentini | Operations | BackEnd | 250 | 79 | ON GOING | 32% | 2024 | 4 | [6 empty] | 2 |  | 2 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 0% | 9.524% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24568 | N/A | RETAIL | OneLRA CR Plus Q3Q4 2024 | EssilorLuxottica | G. Luongo | G. Luongo | Delivery AMS | PM - Project Governance | 250 | 79 | ON GOING | 32% | 2024 | 5 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 0% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24568 | N/A | RETAIL | OneLRA CR Plus Q3Q4 2024 | EssilorLuxottica | G. Luongo | P. Assirelli | Operations | Technical Leader | 250 | 79 | ON GOING | 32% | 2024 | 31 | [6 empty] | 5 |  | 5 | 7 | 7 | 7 | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 0% | 23.81% | 30.43% | 33.33% | 31.82%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-01 | ABS24115 | ALDDDC | RETAIL | S&V Dashboard Changes | EssilorLuxottica | G. Luongo | A. Caldana | Operations | BackEnd | 31 | 30 | CLOSED | 97% | 2024 | 0 |  |  | 1 | 5 | [8 empty] | 0% | 0% | 4.762% | 22.73% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-01 | ABS24115 | ALDDDC | RETAIL | S&V Dashboard Changes | EssilorLuxottica | G. Luongo | P. Assirelli | Operations | Technical Leader | 31 | 30 | CLOSED | 97% | 2024 | 0 |  |  | 1 | 5 | [8 empty] | 0% | 0% | 4.762% | 22.73% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2023-09-01 | 2024-11-30 | N/A | N/A | OTHER | EyeMed | Abstract | G. Maffini | M. Simeone | Operations | FrontEnd | 0 | 0 | ON GOING | 0% | 2024 | 3 | [6 empty] | 3 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ |  | 2024 | 2024-07-01 | 2024-12-31 | N/A | N/A | HR | AI for HR Recruiting and Absenteeism | EssilorLuxottica | G. Sironi | G. Sironi | Operations | PM - Project Governance | 0 | 0 | ON HOLD | 0% | 2024 | 1 | [5 empty] | 1 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ |  | 2024 | 2024-07-01 | 2024-12-31 | N/A | N/A | HR | AI for HR Recruiting and Absenteeism | EssilorLuxottica | G. Sironi | M. Gomitoni | Operations | Tech Lead | 0 | 0 | ON HOLD | 0% | 2024 | 1 | [5 empty] | 1 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS0019 | RETAIL | Edison Targeting & Churn - Presale | Edison | G. Sironi | G. Sironi | Operations | Tech Lead Support | 110 | 0 | PROPOSAL | 0% | 2024 | 4 | [6 empty] | 1 | 1 | 2 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 8.333% | 9.524% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS0019 | RETAIL | Edison Targeting & Churn - Presale | Edison | G. Sironi | M. Gomitoni | Operations | Tech Lead | 110 | 0 | PROPOSAL | 0% | 2024 | 4 | [6 empty] | 1 | 1 | 2 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 8.333% | 9.524% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | A. Imbimbo | Operations | Data Scientist | 105 | 177 | ON GOING | 70% | 2024 | 5 | [6 empty] | 1 | 1 | 1 | 1 | 1 |  | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 0%
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | A. Pirola | Operations | FrontEnd | 105 | 177 | ON GOING | 70% | 2024 | 45 | [5 empty] | 7 | 1 | 7 | 8 | 8 | 9 | 5 | 0% | 0% | 0% | 0% | 0% | 35% | 4.348% | 58.33% | 38.1% | 34.78% | 42.86% | 22.73%
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | F. Origlia | Operations | Architecture Analysis | 105 | 177 | ON GOING | 70% | 2024 | 2 | [5 empty] | 2 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | G. Lopez | Operations | FrontEnd | 105 | 177 | ON GOING | 70% | 2024 | 38 | [5 empty] | 1 | 15 | 5 | 13 | 2 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 5% | 65.22% | 41.67% | 61.9% | 8.696% | 4.762% | 4.545%
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | G. Mordà | Operations | DataManagement | 105 | 177 | ON GOING | 70% | 2024 | 20 | [7 empty] | 5 | 5 | 5 | 5 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 41.67% | 23.81% | 21.74% | 23.81% | 0%
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | G. Sabbatini | Operations | Data Engineering | 105 | 177 | ON GOING | 70% | 2024 | 28 | [5 empty] | 5 | 5 | 5 | 5 | 6 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 25% | 21.74% | 41.67% | 23.81% | 26.09% | 4.762% | 4.545%
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | G. Sironi | Operations | PM - Project Governance | 105 | 177 | ON GOING | 70% | 2024 | 17 | [5 empty] | 3 | 3 | 3 | 3 | 3 | 2 |  | 0% | 0% | 0% | 0% | 0% | 15% | 13.04% | 25% | 14.29% | 13.04% | 9.524% | 0%
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | M. MANNARINO | Operations | BackEnd | 105 | 177 | ON GOING | 70% | 2024 | 12 | [5 empty] | 1 | 3 | 2 | 1 | 3 | 2 |  | 0% | 0% | 0% | 0% | 0% | 5% | 13.04% | 16.67% | 4.762% | 13.04% | 9.524% | 0%
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | M. Vianelli | Delivery Projects | Analysis | 105 | 177 | ON GOING | 70% | 2024 | 24 | [5 empty] | 5 | 8 | 2 | 3 | 3 | 3 |  | 0% | 0% | 0% | 0% | 0% | 25% | 34.78% | 16.67% | 14.29% | 13.04% | 14.29% | 0%
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | N. Pescione | Operations | BackEnd | 105 | 177 | ON GOING | 70% | 2024 | 57 | [5 empty] | 1 | 15 | 8 | 13 | 16 | 4 |  | 0% | 0% | 0% | 0% | 0% | 5% | 65.22% | 66.67% | 61.9% | 69.57% | 19.05% | 0%
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | P. Anzellotti | Operations | Solution Architect | 105 | 177 | ON GOING | 70% | 2024 | 40 | [5 empty] | 4 | 8 | 3 | 4 | 8 | 8 | 5 | 0% | 0% | 0% | 0% | 0% | 20% | 34.78% | 25% | 19.05% | 34.78% | 38.1% | 22.73%
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | P. Singh | AREA TECH | DataManagement | 105 | 177 | ON GOING | 70% | 2024 | 4 | [5 empty] | 3 | 1 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 15% | 4.348% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-03-31 | N/A | DSL | FINANCE | Laboratorio AI per Lux | EssilorLuxottica | G. Sironi | I. Bressan | Operations | Data Engineering | 0 | 0 | CLOSED | 0% | 2024 | 0 | 9 | 1.5 | 1.5 | [9 empty] | 50% | 7.5% | 7.143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-05-01 | 2024-10-30 | ABS24329 | ABS24329 | RETAIL | Red Carpet & Recommendations 2024 | EssilorLuxottica | G. SIRONI | A. Imbimbo | Operations | Data Scientist | 94 | 96 | ON GOING | 95% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-05-01 | 2024-10-30 | ABS24329 | ABS24329 | RETAIL | Red Carpet & Recommendations 2024 | EssilorLuxottica | G. SIRONI | F. Malvezzi | Operations | Data Scientist | 94 | 96 | ON GOING | 95% | 2024 | 43 | [5 empty] | 5 | 5 | 3 | 8 | 8 | 8 | 6 | 0% | 0% | 0% | 0% | 0% | 25% | 21.74% | 25% | 38.1% | 34.78% | 38.1% | 27.27%
CONTRACT | PRJ |  | 2024 | 2024-05-01 | 2024-10-30 | ABS24329 | ABS24329 | RETAIL | Red Carpet & Recommendations 2024 | EssilorLuxottica | G. SIRONI | G. Sabbatini | Operations | Data Engineering | 94 | 96 | ON GOING | 95% | 2024 | 13 | [5 empty] | 3 | 3 |  | 3 | 4 |  |  | 0% | 0% | 0% | 0% | 0% | 15% | 13.04% | 0% | 14.29% | 17.39% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-05-01 | 2024-10-30 | ABS24329 | ABS24329 | RETAIL | Red Carpet & Recommendations 2024 | EssilorLuxottica | G. SIRONI | G. Sironi | Operations | PM - Project Governance | 94 | 96 | ON GOING | 95% | 2024 | 7 |  |  |  |  | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 5% | 5% | 4.348% | 0% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | PRJ |  | 2024 | 2024-05-01 | 2024-10-30 | ABS24329 | ABS24329 | RETAIL | Red Carpet & Recommendations 2024 | EssilorLuxottica | G. SIRONI | M. Gomitoni | Operations | Tech Lead | 94 | 96 | ON GOING | 95% | 2024 | 14 | [6 empty] | 3 |  | 2 | 2 | 4 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 0% | 9.524% | 8.696% | 19.05% | 13.64%
CONTRACT | PRJ |  | 2024 | 2024-05-01 | 2024-10-30 | ABS24329 | ABS24329 | RETAIL | Red Carpet & Recommendations 2024 | EssilorLuxottica | G. SIRONI | V. Echarry | Operations | Data Scientist | 94 | 96 | ON GOING | 95% | 2024 | 39 |  |  |  |  | 3 | 5 | 5 | 3 | 8 | 8 | 1 | 6 | 0% | 0% | 0% | 0% | 15% | 25% | 21.74% | 25% | 38.1% | 34.78% | 4.762% | 27.27%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | A. BRANDIZZI | Operations | FRONT END | 220 | 190 | CLOSED | 0 | 2024 | 24 | [9 empty] | 5 | 2 | 17 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 9.524% | 77.27%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | A. SANTORO | Delivery Projects | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 13.4375 | [8 empty] | 8.4375 | 5 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40.18% | 21.74% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | A. STRADA | Operations | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 2 | [9 empty] | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | A. TORONE | Delivery AMS | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 16.5 | [8 empty] | 1 | 5 | 5.5 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762% | 21.74% | 26.19% | 22.73%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | C. DI LORENZO | Delivery Projects | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 15 | [9 empty] | 5 | 5 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 23.81% | 22.73%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | C. TIBERTI | Operations | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 42 | [9 empty] | 23 | 2 | 17 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 9.524% | 77.27%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | F. SCOGNAMIGLIO | Operations | BACK END | 220 | 190 | CLOSED | 0 | 2024 | 42 | [9 empty] | 23 | 2 | 17 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 9.524% | 77.27%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | F. SPACAGNA | Operations | BACK END | 220 | 190 | CLOSED | 0 | 2024 | 14.25 | [9 empty] | 5 | 5 | 4.25 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 23.81% | 19.32%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | F. VASSALLO | Delivery AMS | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 1 | [8 empty] | 1 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762% | 0% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | G. DE FEO | Delivery Projects | PM - Project Governance | 220 | 190 | CLOSED | 0 | 2024 | 8.375 | [8 empty] | 2.375 | 3 | 3 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.31% | 13.04% | 14.29% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | G. TARTAGLIA | Operations | BACK END | 220 | 190 | CLOSED | 0 | 2024 | 24 | [9 empty] | 5 | 2 | 17 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 9.524% | 77.27%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | I. OSTYMCHUCK | Operations | BACK END | 220 | 190 | CLOSED | 0 | 2024 | 20 | [9 empty] | 1 | 2 | 17 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 9.524% | 77.27%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | J. SORGATO | #N/A | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 15 | [8 empty] | 6 | 1 | 1 | 7 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 28.57% | 4.348% | 4.762% | 31.82%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | L. BARIANI | Delivery Projects | PM - Project Governance | 220 | 190 | CLOSED | 0 | 2024 | 7 | [8 empty] | 1 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762% | 8.696% | 9.524% | 9.091%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | L. BARIANI | Delivery Projects | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 54 | [9 empty] | 21 | 18 | 15 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 91.3% | 85.71% | 68.18%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | L. CATTANEO | #N/A | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 10 | [8 empty] | 1 | 1 | 1 | 7 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762% | 4.348% | 4.762% | 31.82%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | M. Porcu | Operations | BACK END | 220 | 190 | CLOSED | 0 | 2024 | 48 | [8 empty] | 2 | 18 | 16 | 12 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.524% | 78.26% | 76.19% | 54.55%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | M. TOCI | Operations | BACK END | 220 | 190 | CLOSED | 0 | 2024 | 20 | [9 empty] | 1 | 2 | 17 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 9.524% | 77.27%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | M. VIANELLI | Delivery Projects | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 1 | [8 empty] | 1 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762% | 0% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | M. VIMERCATI | Operations | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 1 | [8 empty] | 1 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762% | 0% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | O. SAGAZIO | Operations | BACK END | 220 | 190 | CLOSED | 0 | 2024 | 17 | [9 empty] | 6 | 6 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 26.09% | 28.57% | 22.73%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | P. ANZELLOTTI | Operations | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 1 | [8 empty] | 1 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762% | 0% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | S. Beltrami | Operations | BACK END | 220 | 190 | CLOSED | 0 | 2024 | 27 | [9 empty] | 8 | 2 | 17 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 34.78% | 9.524% | 77.27%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | S. BEN YOUNES | Operations | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 3 | [9 empty] | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 4.762% | 4.545%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | S. DELLE FAVE | Operations | FRONT END | 220 | 190 | CLOSED | 0 | 2024 | 49.6 | [8 empty] | 1 | 19 | 16 | 13.6 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762% | 82.61% | 76.19% | 61.82%
LEAD | PRESALES - DELIVERY |  | 2024-2025 | 2024-09-01 | 2025-01-31 | ABS24523 | ABS24523 | EPM | Tax Cube | EssilorLuxottica | L. Bariani | A. Di Pietro | Operations | BackEnd | 180 | 0 | ON HOLD | 0% | 2024 | 2 | [9 empty] | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 0% | 0%
LEAD | PRESALES - DELIVERY |  | 2024-2025 | 2024-09-01 | 2025-01-31 | ABS24523 | ABS24523 | EPM | Tax Cube | EssilorLuxottica | L. Bariani | E. Storti | Delivery Projects | Analisys | 180 | 0 | ON HOLD | 0% | 2024 | 3 | [8 empty] | 1 | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762% | 8.696% | 0% | 0%
LEAD | PRESALES - DELIVERY |  | 2024-2025 | 2024-09-01 | 2025-01-31 | ABS24523 | ABS24523 | EPM | Tax Cube | EssilorLuxottica | L. Bariani | F. Atanasio | Operations | BackEnd | 180 | 0 | ON HOLD | 0% | 2024 | 2 | [9 empty] | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 0% | 0%
LEAD | PRESALES - DELIVERY |  | 2024-2025 | 2024-09-01 | 2025-01-31 | ABS24523 | ABS24523 | EPM | Tax Cube | EssilorLuxottica | L. Bariani | I. Bressan | Operations | Architecture Analysis | 180 | 0 | ON HOLD | 0% | 2024 | 3 | [8 empty] | 1 | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762% | 8.696% | 0% | 0%
LEAD | PRESALES - DELIVERY |  | 2024-2025 | 2024-09-01 | 2025-01-31 | ABS24523 | ABS24523 | EPM | Tax Cube | EssilorLuxottica | L. Bariani | L. BARIANI | Delivery Projects | PM - Project Governance | 180 | 0 | ON HOLD | 0% | 2024 | 4 | [8 empty] | 2 | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.524% | 8.696% | 0% | 0%
LEAD | PRESALES - DELIVERY |  | 2024-2025 | 2024-09-01 | 2025-01-31 | ABS24523 | ABS24523 | EPM | Tax Cube | EssilorLuxottica | L. Bariani | S. Preziosa | Delivery Projects | Analisys | 180 | 0 | ON HOLD | 0% | 2024 | 6 | [8 empty] | 4 | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 19.05% | 8.696% | 0% | 0%
PROSPECT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-03-15 | 2024-12-31 | N/A | ABS0015 | RETAIL | BullsEye POC Data Science | EssilorLuxottica | L. Franceschini | A. Imbimbo | Operations | Data Scientist | 35 | 14 | ON GOING | 0% | 2024 | 1 |  |  |  | 1 | 1 | [7 empty] | 0% | 0% | 0% | 4.545% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-03-15 | 2024-12-31 | N/A | ABS0015 | RETAIL | BullsEye POC Data Science | EssilorLuxottica | L. Franceschini | F. Malvezzi | Operations | Data Scientist | 35 | 14 | ON GOING | 0% | 2024 | 2 |  |  |  | 1 | 1 | 1 | [6 empty] | 0% | 0% | 0% | 4.545% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-03-15 | 2024-12-31 | N/A | ABS0015 | RETAIL | BullsEye POC Data Science | EssilorLuxottica | L. Franceschini | G. Sabbatini | Operations | Data Engineering | 35 | 14 | ON GOING | 0% | 2024 | 2 |  |  |  | 1 | 1 | 1 | [6 empty] | 0% | 0% | 0% | 4.545% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-03-15 | 2024-12-31 | N/A | ABS0015 | RETAIL | BullsEye POC Data Science | EssilorLuxottica | L. Franceschini | G. Sironi | Operations | Team Leadership | 35 | 14 | ON GOING | 0% | 2024 | 2 |  |  |  | 1 | 1 | 1 | [6 empty] | 0% | 0% | 0% | 4.545% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-03-15 | 2024-12-31 | N/A | ABS0015 | RETAIL | BullsEye POC Data Science | EssilorLuxottica | L. Franceschini | M. Gomitoni | Operations | Tech Lead | 35 | 14 | ON GOING | 0% | 2024 | 3 |  |  |  | 1 | 2 | 1 | [6 empty] | 0% | 0% | 0% | 4.545% | 10% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-03-15 | 2024-12-31 | N/A | ABS0015 | RETAIL | BullsEye POC Data Science | EssilorLuxottica | L. Franceschini | V. Echarry | Operations | Data Scientist | 35 | 14 | ON GOING | 0% | 2024 | 2 |  |  |  | 1 | 1 | 1 | [6 empty] | 0% | 0% | 0% | 4.545% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | A. Ferrari | Operations | DataManagement | 780 | 735 | ON HOLD | 0% | 2024 | 31 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 8 | 1 | 1 | 1 | 5 | 11.11% | 25% | 23.81% | 22.73% | 25% | 25% | 21.74% | 66.67% | 4.762% | 4.348% | 4.762% | 22.73%
CONTRACT | PRJ | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | A. Lorena | Operations | FrontEnd | 780 | 735 | ON HOLD | 0% | 2024 | 41 |  | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 15 |  |  | 0% | 10% | 23.81% | 22.73% | 25% | 25% | 21.74% | 41.67% | 28.57% | 65.22% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | A. Pirola | Operations | FrontEnd | 780 | 735 | ON HOLD | 0% | 2024 | 18 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 4 | 4 | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 4.348% | 8.333% | 9.524% | 8.696% | 19.05% | 18.18%
CONTRACT | PRJ | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | A. Vladi | Operations | TL - DataManagement | 780 | 735 | ON HOLD | 0% | 2024 | 139 | 8 | 1 | 1 | 1 | 18 | 18 | 18 | 15 | 18 | 18 | 18 | 16 | 44.44% | 5% | 4.762% | 4.545% | 90% | 90% | 78.26% | 125% | 85.71% | 78.26% | 85.71% | 72.73%
CONTRACT | PRJ | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | C. Elia | Operations | DataManagement | 780 | 735 | ON HOLD | 0% | 2024 | 36 | [6 empty] | 5 | 5 | 5 | 7 | 7 | 7 | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 41.67% | 23.81% | 30.43% | 33.33% | 31.82%
CONTRACT | PRJ | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | F. D'Alberto | Operations | DataManagement | 780 | 735 | ON HOLD | 0% | 2024 | 72 | 4 | 4 | 4 | 4 | 5 | 1 | 2 | 1 | 21 | 23 | 2 | 17 | 22.22% | 20% | 19.05% | 18.18% | 25% | 5% | 8.696% | 8.333% | 100% | 100% | 9.524% | 77.27%
CONTRACT | PRJ | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | F. Origlia | Operations | Solution Architect | 780 | 735 | ON HOLD | 0% | 2024 | 17 | 8 | 8 | 8 | 9 | 9 | 8 | [6 empty] | 44.44% | 40% | 38.1% | 40.91% | 45% | 40% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | F. Spacagna | Operations | Solution Architect | 780 | 735 | ON HOLD | 0% | 2024 | 71 | [6 empty] | 8 | 7 | 13 | 15 | 15 | 13 | 0% | 0% | 0% | 0% | 0% | 0% | 34.78% | 58.33% | 61.9% | 65.22% | 71.43% | 59.09%
CONTRACT | PRJ | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | G. Franchi | Operations | BackEnd | 780 | 735 | ON HOLD | 0% | 2024 | 66 | [5 empty] | 1 | 15 | 1 | 15 | 15 | 2 | 17 | 0% | 0% | 0% | 0% | 0% | 5% | 65.22% | 8.333% | 71.43% | 65.22% | 9.524% | 77.27%
CONTRACT | PRJ | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | L. Franceschini | Delivery Projects | PM - Project Governance | 780 | 735 | ON HOLD | 0% | 2024 | 34 | 9 | 9 | 9 | 3 | 3 | 3 | 3 | 2 | 6 | 6 | 6 | 5 | 50% | 45% | 42.86% | 13.64% | 15% | 15% | 13.04% | 16.67% | 28.57% | 26.09% | 28.57% | 22.73%
CONTRACT | PRJ | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | M. Vianelli | Delivery Projects | Analysis | 780 | 735 | ON HOLD | 0% | 2024 | 31 | 4 | 5 | 5 | 5 | 5 | 5 | 5 |  |  | 6 | 5 | 5 | 22.22% | 25% | 23.81% | 22.73% | 25% | 25% | 21.74% | 0% | 0% | 26.09% | 23.81% | 22.73%
CONTRACT | PRJ | Waterfall | 2024 | 2023-12-01 | 2024-08-01 | ABS23409 | AE | FINANCE | EDEN ESSILOR FRANCIA | EssilorLuxottica | L. Franceschini | A. De Sanctis | Operations | FrontEnd | 125 | 66 | CLOSED | 0% | 2024 | 23 | 7 | 1 | 1 | 8 | 9 | 9 | 1 | 4 |  |  |  |  | 38.89% | 5% | 4.762% | 36.36% | 45% | 45% | 4.348% | 33.33% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2023-12-01 | 2024-08-01 | ABS23409 | AE | FINANCE | EDEN ESSILOR FRANCIA | EssilorLuxottica | L. Franceschini | A. Strada | Operations | DataManagement | 125 | 66 | CLOSED | 0% | 2024 | 20 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 27.78% | 25% | 23.81% | 22.73% | 25% | 25% | 21.74% | 41.67% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2023-12-01 | 2024-08-01 | ABS23409 | AE | FINANCE | EDEN ESSILOR FRANCIA | EssilorLuxottica | L. Franceschini | F. Taita | Delivery Projects | DataManagement | 125 | 66 | CLOSED | 0% | 2024 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | [6 empty] | 11.11% | 10% | 9.524% | 4.545% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2023-12-01 | 2024-08-01 | ABS23409 | AE | FINANCE | EDEN ESSILOR FRANCIA | EssilorLuxottica | L. Franceschini | L. Franceschini | Delivery Projects | PM - Project Governance | 125 | 66 | CLOSED | 0% | 2024 | 12 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 2 |  |  |  |  | 11.11% | 10% | 9.524% | 9.091% | 10% | 20% | 17.39% | 16.67% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2023-12-01 | 2024-08-01 | ABS23409 | AE | FINANCE | EDEN ESSILOR FRANCIA | EssilorLuxottica | L. Franceschini | R. Bondi | Operations | FrontEnd | 125 | 66 | CLOSED | 0% | 2024 | 17 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 2 |  |  |  |  | 22.22% | 25% | 23.81% | 22.73% | 25% | 25% | 21.74% | 16.67% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2023-12-01 | 2024-04-01 | ABS24369 | ABS24336 | FINANCE | EDEN W2 | EssilorLuxottica | L. Franceschini | A. De Sanctis | Operations | FrontEnd | 100 | 124 | CLOSED | 0% | 2024 | 8 | [8 empty] | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | PRJ | Waterfall | 2024 | 2023-12-01 | 2024-04-01 | ABS24369 | ABS24336 | FINANCE | EDEN W2 | EssilorLuxottica | L. Franceschini | A. Strada | Operations | DataManagement | 100 | 124 | CLOSED | 0% | 2024 | 8 | [8 empty] | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | PRJ | Waterfall | 2024 | 2023-12-01 | 2024-04-01 | ABS24369 | ABS24336 | FINANCE | EDEN W2 | EssilorLuxottica | L. Franceschini | L. Franceschini | Delivery Projects | PM - Project Governance | 100 | 124 | CLOSED | 0% | 2024 | 11 | [5 empty] | 2 | 1 |  | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 10% | 4.348% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | PRJ | Waterfall | 2024 | 2023-12-01 | 2024-04-01 | ABS24369 | ABS24336 | FINANCE | EDEN W2 | EssilorLuxottica | L. Franceschini | R. Bondi | Operations | FrontEnd | 100 | 124 | CLOSED | 0% | 2024 | 28 | [8 empty] | 7 | 7 | 7 | 7 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 33.33% | 30.43% | 33.33% | 31.82%
CONTRACT | PRJ | Waterfall | 2024 | 2023-12-01 | 2024-04-01 | ABS24369 | ABS24336 | FINANCE | EDEN W2 | EssilorLuxottica | L. Franceschini | S. Ben Younes | Operations | DataManagement | 100 | 124 | CLOSED | 0% | 2024 | 44 | [8 empty] | 7 | 7 | 13 | 17 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 33.33% | 30.43% | 61.9% | 77.27%
CONTRACT | PRJ | Waterfall | 2024 | 2023-01-01 | 2024-12-31 | N/A | LXT | FINANCE | EEFR | EssilorLuxottica | L. Franceschini | L. Franceschini | Delivery Projects | PM - Project Governance | 50 | 34 | ON GOING | 0% | 2024 | 9 |  |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 3 | 1 | 1 | 0% | 0% | 4.762% | 4.545% | 5% | 5% | 4.348% | 0% | 4.762% | 13.04% | 4.762% | 4.545%
CONTRACT | PRJ | Waterfall | 2024 | 2024-05-01 | 2024-12-31 | N/A | U20R | ERP | UNIEURO | UNIEURO | L. Franceschini | L. Franceschini | Delivery Projects | PM - Project Governance | 100 | 55 | ON GOING | 0% | 2024 | 47 |  |  |  | 7 | 7 | 7 | 7 |  | 7 | 7 | 7 | 5 | 0% | 0% | 0% | 31.82% | 35% | 35% | 30.43% | 0% | 33.33% | 30.43% | 33.33% | 22.73%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-06-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione | Abstract | L. Franco | G. Minervini | Operations | BackEnd | 0 | 0 |  | 0% | 2024 | 6 | [5 empty] | 3 | 3 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 15% | 13.04% | 0% | 0% | 0% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-06-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione | Abstract | L. Franco | L. Franco | Operations | PM - Project Governance | 0 | 0 |  | 0% | 2024 | 6 | [5 empty] | 3 | 3 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 15% | 13.04% | 0% | 0% | 0% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-06-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione | Abstract | L. Franco | O. BEN OTHMANE | Operations | BackEnd | 0 | 0 |  | 0% | 2024 | 6 | [5 empty] | 3 | 3 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 15% | 13.04% | 0% | 0% | 0% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-06-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione | Abstract | L. Franco | P. Buonasorte | Operations | BackEnd | 0 | 0 |  | 0% | 2024 | 6 | [5 empty] | 3 | 3 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 15% | 13.04% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ |  | 2024 |  |  | N/A | N/A | HR | Assessment Logiche DWH | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 0 | 0 | CLOSED | 0% | 2024 | 3 | [5 empty] | 3 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 15% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | ABS23148 | ABS0008-33 | HR | Attività progettuali Salary 2025 | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Management | 30 | 0 | CLOSED | 100% | 2024 | 5 | [9 empty] | 2 | 3 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 14.29% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | ABS23148 | ABS0008-33 | HR | Attività progettuali Salary 2025 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | Project Governance | 30 | 0 | CLOSED | 100% | 2024 | 0.5 | [10 empty] | 0.5 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.381% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | ABS23148 | ABS0008-33 | HR | Attività progettuali Salary 2025 | EssilorLuxottica | L. Roberto | M. VIMERCATI | Operations | Data Management | 30 | 0 | CLOSED | 100% | 2024 | 5 | [9 empty] | 2 | 3 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 14.29% | 0%
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | IAA | OTHER | CC - Attività |  | L. ROBERTO | C. Elia | Operations | BackEnd | 0 | 0 | CLOSED | 0% | 2024 | 8 | [5 empty] | 2 | 2 | 2 | 2 |  |  |  | 0% | 0% | 0% | 0% | 0% | 10% | 8.696% | 16.67% | 9.524% | 0% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  | N/A | ATD | OTHER | Formazione | Abstract | L. Roberto | A. Brandizzi | Operations | FrontEnd | 0 | 0 | CLOSED | 0% | 2024 | 19 |  |  |  |  | 2 | 3 | 3 |  | 3 | 3 | 3 | 2 | 0% | 0% | 0% | 0% | 10% | 15% | 13.04% | 0% | 14.29% | 13.04% | 14.29% | 9.091%
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  | N/A | ATD | OTHER | Formazione | Abstract | L. Roberto | C. Elia | Operations | BackEnd | 0 | 0 | CLOSED | 0% | 2024 | 21 |  |  |  |  | 3 | 3 | 3 |  | 3 | 3 | 3 | 3 | 0% | 0% | 0% | 0% | 15% | 15% | 13.04% | 0% | 14.29% | 13.04% | 14.29% | 13.64%
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  | N/A | ATD | OTHER | Formazione | Abstract | L. Roberto | F. Spacagna | Operations | BackEnd | 0 | 0 | CLOSED | 0% | 2024 | 21 |  |  |  |  | 3 | 3 | 3 |  | 3 | 3 | 3 | 3 | 0% | 0% | 0% | 0% | 15% | 15% | 13.04% | 0% | 14.29% | 13.04% | 14.29% | 13.64%
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  | N/A | ATD | OTHER | Formazione | Abstract | L. Roberto | L. Roberto | Operations | PM - Project Governance | 0 | 0 | CLOSED | 0% | 2024 | 17 |  |  |  | 2 | 3 | 3 | 3 |  | 3 | 3 | 2 |  | 0% | 0% | 0% | 9.091% | 15% | 15% | 13.04% | 0% | 14.29% | 13.04% | 9.524% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  | N/A | ATD | OTHER | Formazione | Abstract | L. Roberto | M. Simeone | Operations | FrontEnd | 0 | 0 | CLOSED | 0% | 2024 | 16 |  |  |  |  | 2 | 3 | 3 |  |  | 3 | 2 | 3 | 0% | 0% | 0% | 0% | 10% | 15% | 13.04% | 0% | 0% | 13.04% | 9.524% | 13.64%
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-05-31 | N/A | ATD |  | Formazione Scala | Abstract | L. Roberto | F. Spacagna | Operations | BackEnd | 0 | 0 | CLOSED | 100% | 2024 | 5 |  |  | 5 | 5 | 5 | [7 empty] | 0% | 0% | 23.81% | 22.73% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRESALES - GO TO MARKET |  | 2024 |  |  | N/A | ABS0007 | CRM/DS | Gara Mediamarket | MediaMarket | L. Roberto | G. Sabbatini | Operations | Data Engineering | 20 | 20 | CLOSED | 100% | 2024 | 3 | [5 empty] | 3 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 15% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRESALES - GO TO MARKET |  | 2024 |  |  | N/A | ABS0007 | CRM/DS | Gara Mediamarket | MediaMarket | L. Roberto | G. Sironi | Operations | Team Leadership | 20 | 20 | CLOSED | 100% | 2024 | 2 | [5 empty] | 2 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRESALES - GO TO MARKET |  | 2024 |  |  | N/A | ABS0007 | CRM/DS | Gara Mediamarket | MediaMarket | L. Roberto | L. Roberto | Operations | PM - Project Governance | 20 | 20 | CLOSED | 100% | 2024 | 4 | [5 empty] | 4 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRESALES - GO TO MARKET |  | 2024 |  |  | N/A | ABS0007 | CRM/DS | Gara Mediamarket | MediaMarket | L. Roberto | M. Gomitoni | Operations | Tech Lead | 20 | 20 | CLOSED | 100% | 2024 | 3 | [5 empty] | 3 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 15% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRESALES - GO TO MARKET |  | 2024 |  |  | N/A | ABS0007 | CRM/DS | Gara Mediamarket | MediaMarket | L. ROBERTO | V. Echarry | Operations | Data Scientist | 20 | 20 | CLOSED | 100% | 2024 | 3 |  |  |  |  | 2 | 1 | [6 empty] | 0% | 0% | 0% | 0% | 10% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-12-31 | N/A | ABS24299 | ABS24299 | HR - BPO CROSS ACTIVITIES | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 570 | 567 | CLOSED | 0% | 2024 | 18 |  |  |  |  | 2 | 5 | 6 |  | 5 |  |  |  | 0% | 0% | 0% | 0% | 10% | 25% | 26.09% | 0% | 23.81% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-01-30 | ABS23135 | AHW5 | HR | HR - Coni di Visibilità - Wave 5 | EssilorLuxottica | L. Roberto | A. Nastasi | Operations | DataManagement | 275 | 0 | CLOSED | 100% | 2024 | 2 |  |  |  |  | 1 | 1 | [6 empty] | 0% | 0% | 0% | 0% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-01-30 | ABS23135 | AHW5 | HR | HR - Coni di Visibilità - Wave 5 | EssilorLuxottica | L. Roberto | C. Elia | Operations | Architecture Analysis | 275 | 0 | CLOSED | 100% | 2024 | 13 |  |  |  |  | 8 | 1 | 4 | [5 empty] | 0% | 0% | 0% | 0% | 40% | 5% | 17.39% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-01-30 | ABS23135 | AHW5 | HR | HR - Coni di Visibilità - Wave 5 | EssilorLuxottica | L. Roberto | F. D'Alberto | Operations | DataManagement | 275 | 0 | CLOSED | 100% | 2024 | 2 |  |  |  |  | 1 | 1 | [6 empty] | 0% | 0% | 0% | 0% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-01-30 | ABS23135 | AHW5 | HR | HR - Coni di Visibilità - Wave 5 | EssilorLuxottica | L. Roberto | F. Plebani | Operations | Data Management | 275 | 0 | CLOSED | 100% | 2024 | 24 |  |  |  |  | 8 | 8 | 5 |  | 3 |  |  |  | 0% | 0% | 0% | 0% | 40% | 40% | 21.74% | 0% | 14.29% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-01-30 | ABS23135 | AHW5 | HR | HR - Coni di Visibilità - Wave 5 | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 275 | 0 | CLOSED | 100% | 2024 | 8 |  |  |  |  | 4 | 4 | [6 empty] | 0% | 0% | 0% | 0% | 20% | 20% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-01-30 | ABS23135 | AHW5 | HR | HR - Coni di Visibilità - Wave 5 | EssilorLuxottica | L. Roberto | M. Porcu | Operations | BackEnd | 275 | 0 | CLOSED | 100% | 2024 | 22 |  |  |  |  | 9 | 9 | 4 | [5 empty] | 0% | 0% | 0% | 0% | 45% | 45% | 17.39% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-01-30 | ABS23135 | AHW5 | HR | HR - Coni di Visibilità - Wave 5 | EssilorLuxottica | L. Roberto | M. Toci | Operations | BackEnd | 275 | 0 | CLOSED | 100% | 2024 | 28 |  |  |  |  | 9 | 14 | 5 | [5 empty] | 0% | 0% | 0% | 0% | 45% | 70% | 21.74% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-01-01 | 2024-12-31 | ABS23135 | AHW5 | HR | HR - Coni di Visibilità - Wave 5 | EssilorLuxottica | L. Roberto | P. Anzellotti | Operations | PM - Project Governance | 275 | 0 | CLOSED | 100% | 2024 | 3 |  |  |  |  | 1 | 1 | 1 | [5 empty] | 0% | 0% | 0% | 0% | 5% | 5% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-01-30 | ABS23135 | AHW5 | HR | HR - Coni di Visibilità - Wave 5 | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects |  | 275 | 0 | CLOSED | 100% | 2024 | 15 | [5 empty] | 5 | 5 |  | 3 | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 25% | 21.74% | 0% | 14.29% | 8.696% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-01-30 | ABS23135 | AHW5 | HR | HR - Coni di Visibilità - Wave 5 | EssilorLuxottica | L. Roberto | S. Beltrami | Operations | FrontEnd | 275 | 0 | CLOSED | 100% | 2024 | 12 | [5 empty] | 7 | 5 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 35% | 21.74% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2024 | 2024-08-01 | 2024-05-31 | ABS24107 | AABGCV | HR | HR - Coni visibilità BO | EssilorLuxottica | L. Roberto | F. Plebani | Operations | BackEnd | 61 | 10 | CLOSED | 0% | 2024 | 1 |  | 2.1 | 2.1 | 3.8 | [5 empty] | 1 |  |  | 0% | 10.5% | 10% | 17.27% | 0% | 0% | 0% | 0% | 0% | 4.348% | 0% | 0%
CONTRACT | PRJ | Agile | 2024 | 2024-08-01 | 2024-05-31 | ABS24107 | AABGCV | HR | HR - Coni visibilità BO | EssilorLuxottica | L. Roberto | M. Vimercati | Operations | PM - Project Governance | 61 | 10 | CLOSED | 0% | 2024 | 11 |  | 2.1 | 2.1 | 3.8 | 8 |  |  |  |  | 3 |  |  | 0% | 10.5% | 10% | 17.27% | 40% | 0% | 0% | 0% | 0% | 13.04% | 0% | 0%
CONTRACT | PRJ | Agile | 2024 | 2024-08-01 | 2024-05-31 | ABS24107 | AABGCV | HR | HR - Coni visibilità BO | EssilorLuxottica | L. Roberto | R. Alves | Operations | FrontEnd | 61 | 10 | CLOSED | 0% | 2024 | 1 |  |  |  | 9.5 | 1 | [7 empty] | 0% | 0% | 0% | 43.18% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-12-31 | ABS24048 | ABS24048 | HR | HR - DATAFLOW- ROLLOUT | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | BackEnd | 25 | 0 | CLOSED | 30% | 2024 | 14.4 | 1.8 | 2.1 | 2.1 | 1.9 | 2 | 2 | 2.3 |  | 2.1 | 2.3 | 2 | 1.7 | 10% | 10.5% | 10% | 8.636% | 10% | 10% | 10% | 0% | 10% | 10% | 9.524% | 7.727%
CONTRACT | PRJ | Agile | 2024 | 2024-02-01 | 2024-04-30 | N/A | N/A | HR | HR - ECP MD/TM/PY - ROLLOUT | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | BackEnd | 15 | 0 | ON GOING | 5% | 2024 | 0 |  | 2.5 | 2 | 8 | [8 empty] | 0% | 12.5% | 9.524% | 36.36% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2024 | 2024-02-01 | 2024-04-30 | N/A | N/A | HR | HR - ECP MD/TM/PY - ROLLOUT | EssilorLuxottica | L. Roberto | M. Vimercati | Operations | PM - Project Governance | 15 | 0 | ON GOING | 5% | 2024 | 0 |  | 2.5 | 1 | 4 | [8 empty] | 0% | 12.5% | 4.762% | 18.18% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-09-18 | 2024-10-03 | N/A | ABS0008-3 | HR | HR - Gestione permessi Talent V1 | EssilorLuxottica | L. Roberto | C. Elia | Operations | BackEnd | 16 | 14.5 | CLOSED | 95% | 2024 | 2 | [8 empty] | 2 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.524% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-09-18 | 2024-10-03 | N/A | ABS0008-3 | HR | HR - Gestione permessi Talent V1 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | BackEnd | 16 | 14.5 | CLOSED | 95% | 2024 | 2 | [8 empty] | 1 | 1 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762% | 4.348% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-09-18 | 2024-10-03 | N/A | ABS0008-3 | HR | HR - Gestione permessi Talent V1 | EssilorLuxottica | L. Roberto | M. PORCU | Operations | BackEnd | 16 | 14.5 | CLOSED | 95% | 2024 | 3 | [8 empty] | 2 | 1 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.524% | 4.348% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-09-18 | 2024-10-03 | N/A | ABS0008-3 | HR | HR - Gestione permessi Talent V1 | EssilorLuxottica | L. Roberto | M. Toci | Operations | BackEnd | 16 | 14.5 | CLOSED | 95% | 2024 | 5 | [8 empty] | 3 | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 8.696% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-09-18 | 2024-10-03 | N/A | ABS0008-3 | HR | HR - Gestione permessi Talent V1 | EssilorLuxottica | L. Roberto | S. Beltrami | Operations | BackEnd | 16 | 14.5 | CLOSED | 95% | 2024 | 5 | [8 empty] | 3 | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 8.696% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-09-18 | 2024-11-18 | N/A | ABS0008-9 | HR | HR - Gestione permessi Talent v2 | EssilorLuxottica | L. Roberto | A. De Sanctis | Operations | Data Management | 34 | 3 | ON GOING | 95% | 2024 | 4 | [9 empty] | 3 | 1 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 4.762% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-09-18 | 2024-11-18 | N/A | ABS0008-9 | HR | HR - Gestione permessi Talent v2 | EssilorLuxottica | L. Roberto | C. Elia | Operations | Data Engineer | 34 | 3 | ON GOING | 95% | 2024 | 3 | [9 empty] | 1 | 2 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 9.524% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-09-18 | 2024-11-18 | N/A | ABS0008-9 | HR | HR - Gestione permessi Talent v2 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 34 | 3 | ON GOING | 95% | 2024 | 3 | [9 empty] | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 4.762% | 4.545%
CONTRACT | PRJ | Waterfall | 2024 | 2024-09-18 | 2024-11-18 | N/A | ABS0008-9 | HR | HR - Gestione permessi Talent v2 | EssilorLuxottica | L. Roberto | M. Porcu | Operations | BackEnd | 34 | 3 | ON GOING | 95% | 2024 | 4 | [9 empty] | 1 | 2 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 9.524% | 4.545%
CONTRACT | PRJ | Waterfall | 2024 | 2024-09-18 | 2024-11-18 | N/A | ABS0008-9 | HR | HR - Gestione permessi Talent v2 | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 34 | 0 | ON GOING | 95% | 2024 | 4 | [9 empty] | 1 | 2 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 9.524% | 4.545%
CONTRACT | PRJ | Waterfall | 2024 | 2024-09-18 | 2024-11-18 | N/A | ABS0008-9 | HR | HR - Gestione permessi Talent v2 | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 34 | 3 | ON GOING | 95% | 2024 | 5 | [9 empty] | 3 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 4.762% | 4.545%
CONTRACT | PRJ | Time&Materials |  | 2024-01-01 | 2024-09-01 | ABS24027 | LGRAVISION | HR | HR - GV Light | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | BackEnd | 35 | 24 | CLOSED | 100% | 2024 | 4 |  | 6.3 | 1.5 | 1.9 |  |  | 2 |  | 2 |  |  |  | 0% | 31.5% | 7.143% | 8.636% | 0% | 0% | 8.696% | 0% | 9.524% | 0% | 0% | 0%
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-12-31 | N/A | N/A | HR | HR - INTEGRAZIONE INFOTYPE 9906 | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | BackEnd | 10 | 0 | CLOSED | 100% | 2024 | 0 |  |  | 5.25 | [9 empty] | 0% | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-12-31 | N/A | N/A | HR | HR - INTEGRAZIONE INFOTYPE 9906 | EssilorLuxottica | L. Roberto | M. Vimercati | Operations | FrontEnd | 10 | 0 | CLOSED | 100% | 2024 | 0 |  |  | 5.25 | [9 empty] | 0% | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | N/A | ABS0008-29 | HR | HR - Job Architecture | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Management | 0 | 0 | ON GOING | 0% | 2024 | 10 | [10 empty] | 5 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 23.81% | 22.73%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | N/A | ABS0008-29 | HR | HR - Job Architecture | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 0 | 0 | ON GOING | 0% | 2024 | 3 | [10 empty] | 1 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762% | 9.091%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | N/A | ABS0008-29 | HR | HR - Job Architecture | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 0 | 0 | ON GOING | 0% | 2024 | 6 | [10 empty] | 3 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 13.64%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | N/A | ABS0008-29 | HR | HR - Job Architecture | EssilorLuxottica | L. Roberto | L. Roberto | Operations | Project Governance | 0 | 0 | ON GOING | 0% | 2024 | 3 | [9 empty] | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 4.762% | 4.545%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | N/A | ABS0008-29 | HR | HR - Job Architecture | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 0 | 0 | ON GOING | 0% | 2024 | 5 | [9 empty] | 2 | 2 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 9.524% | 4.545%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | ABS25085 | ABS25085 | HR | HR - LandingPage wave1 | EssilorLuxottica | L. Roberto | C. Elia | Operations | BackEnd | 65 | 60 | ON HOLD | 90% | 2024 | 17 | [9 empty] | 6 | 6 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 26.09% | 28.57% | 22.73%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | ABS25085 | ABS25085 | HR | HR - LandingPage wave1 | EssilorLuxottica | L. Roberto | C. Paz | Delivery Projects | PMO - Project Management Officer | 65 | 60 | ON HOLD | 90% | 2024 | 3 | [9 empty] | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 4.762% | 4.545%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | ABS25085 | ABS25085 | HR | HR - LandingPage wave1 | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 65 | 60 | ON HOLD | 90% | 2024 | 5 | [9 empty] | 1 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 9.524% | 9.091%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | ABS25085 | ABS25085 | HR | HR - LandingPage wave1 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 65 | 60 | ON HOLD | 90% | 2024 | 5 | [9 empty] | 2 | 2 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 9.524% | 4.545%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | ABS25085 | ABS25085 | HR | HR - LandingPage wave1 | EssilorLuxottica | L. Roberto | M. Porcu | Operations | BackEnd | 65 | 60 | ON HOLD | 90% | 2024 | 12 | [9 empty] | 5 | 4 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 19.05% | 13.64%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | ABS25085 | ABS25085 | HR | HR - LandingPage wave1 | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 65 | 60 | ON HOLD | 90% | 2024 | 7 | [9 empty] | 2 | 2 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 9.524% | 13.64%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | ABS25085 | ABS25085 | HR | HR - LandingPage wave1 | EssilorLuxottica | L. Roberto | S. Delle Fave | Operations | FrontEnd | 65 | 60 | ON HOLD | 90% | 2024 | 6 | [9 empty] | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 9.524% | 9.091%
CONTRACT | PRJ | Scrum | 2024 | 2024-01-22 | 2024-05-31 | ABS24059 | DQAW1 | HR | HR - QLIK ASSESSMENT | EssilorLuxottica | L. ROBERTO | E. Storti | Delivery Projects | Analysis | 146 | 151.7 | CLOSED | 100% | 2024 | 11 |  |  |  |  | 11 | [7 empty] | 0% | 0% | 0% | 0% | 55% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-01-22 | 2024-05-31 | ABS24059 | DQAW1 | HR | HR - QLIK ASSESSMENT | EssilorLuxottica | L. ROBERTO | F. Reale | Operations | FrontEnd | 146 | 151.7 | CLOSED | 100% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-01-22 | 2024-05-31 | ABS24059 | DQAW1 | HR | HR - QLIK ASSESSMENT | EssilorLuxottica | L. ROBERTO | G. De Feo | Delivery Projects | PMO - Project Management Officer | 146 | 151.7 | CLOSED | 100% | 2024 | 14 | 2.7 | 14.7 | 14.7 | 13.3 | 14 | [7 empty] | 15% | 73.5% | 70% | 60.45% | 70% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-01-22 | 2024-05-31 | ABS24059 | DQAW1 | HR | HR - QLIK ASSESSMENT | EssilorLuxottica | L. ROBERTO | M. Porcu | Operations | PM - Project Governance | 146 | 151.7 | CLOSED | 100% | 2024 | 2 | 2.7 | 2.1 | 2.1 | 1.9 | 2 | [7 empty] | 15% | 10.5% | 10% | 8.636% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-01-22 | 2024-05-31 | ABS24059 | DQAW1 | HR | HR - QLIK ASSESSMENT | EssilorLuxottica | L. ROBERTO | M. Vimercati | Operations | FrontEnd | 146 | 151.7 | CLOSED | 100% | 2024 | 4 | 2.7 | 5.25 | 4.75 | 4.75 | 4 | [7 empty] | 15% | 26.25% | 22.62% | 21.59% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-01-22 | 2024-05-31 | ABS24059 | DQAW1 | HR | HR - QLIK ASSESSMENT | EssilorLuxottica | L. ROBERTO | R. Marasca | Delivery Projects | Analysis | 146 | 151.7 | CLOSED | 100% | 2024 | 11 | 9 | 9 | 9 | 9 | 11 | [7 empty] | 50% | 45% | 42.86% | 40.91% | 55% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile |  | 2024-01-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | HR - Reporting Projects management | EssilorLuxottica | L. Roberto | M. Vimercati | Operations | PM - Project Governance | 570 | 567 | CLOSED | 100% | 2024 | 25 | 14.4 | 12.6 | 5.25 | 3.8 | 5 | 8 | 3 |  | 3 | 2 | 2 | 2 | 80% | 63% | 25% | 17.27% | 25% | 40% | 13.04% | 0% | 14.29% | 8.696% | 9.524% | 9.091%
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-12-02 | 2025-03-18 | ABS25085 | ABS25085 | HR | HR - Revisione DMGLOBAL | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Management | 109 | 60 | ON GOING | 80% | 2024 | 5 | [11 empty] | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 22.73%
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-12-02 | 2025-03-18 | ABS25085 | ABS25085 | HR | HR - Revisione DMGLOBAL | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 109 | 60 | ON GOING | 80% | 2024 | 5 | [11 empty] | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 22.73%
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-12-02 | 2025-03-18 | ABS25085 | ABS25085 | HR | HR - Revisione DMGLOBAL | EssilorLuxottica | L. Roberto | L. Roberto | Operations | Project Governance | 109 | 60 | ON GOING | 80% | 2024 | 3 | [11 empty] | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.64%
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-12-02 | 2025-03-18 | ABS25085 | ABS25085 | HR | HR - Revisione DMGLOBAL | EssilorLuxottica | L. Roberto | M. VIMERCATI | Operations | Data Management | 109 | 60 | ON GOING | 80% | 2024 | 5 | [11 empty] | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 22.73%
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-12-02 | 2025-03-18 | ABS25085 | ABS25085 | HR | HR - Revisione DMGLOBAL | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 109 | 60 | ON GOING | 80% | 2024 | 2 | [11 empty] | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.091%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | N/A | ABS0008-16 | HR | HR - Revisione PA0002 | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Management | 29 | 12 | CLOSED | 90% | 2024 | 8 | [9 empty] | 3 | 3 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 14.29% | 9.091%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | N/A | ABS0008-16 | HR | HR - Revisione PA0002 | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 29 | 12 | CLOSED | 90% | 2024 | 7 | [9 empty] | 3 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 9.524% | 9.091%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | N/A | ABS0008-16 | HR | HR - Revisione PA0002 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | Project Governance | 29 | 12 | CLOSED | 90% | 2024 | 3 | [9 empty] | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 4.762% | 4.545%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | N/A | ABS0008-16 | HR | HR - Revisione PA0002 | EssilorLuxottica | L. Roberto | M. VIMERCATI | Operations | Data Management | 29 | 12 | CLOSED | 90% | 2024 | 8 | [9 empty] | 3 | 3 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 14.29% | 9.091%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | N/A | ABS0008-16 | HR | HR - Revisione PA0002 | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 29 | 12 | CLOSED | 90% | 2024 | 3 | [9 empty] | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 4.762% | 4.545%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | N/A | ABS0008-17 | HR | HR - Revisione PA0709 | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Management | 13 | 0 | CLOSED | 90% | 2024 | 4 | [9 empty] | 1 | 2 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 9.524% | 4.545%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | N/A | ABS0008-17 | HR | HR - Revisione PA0709 | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 13 | 0 | CLOSED | 90% | 2024 | 4 | [9 empty] | 2 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 4.762% | 4.545%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | N/A | ABS0008-17 | HR | HR - Revisione PA0709 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | Project Governance | 13 | 0 | CLOSED | 90% | 2024 | 2 | [9 empty] | 1 | 1 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 4.762% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | N/A | ABS0008-17 | HR | HR - Revisione PA0709 | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 13 | 0 | CLOSED | 90% | 2024 | 3 | [9 empty] | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 4.762% | 4.545%
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-01-30 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | A. Brandizzi | Operations | FrontEnd | 450 | 244 | ON GOING | 45% | 2024 | 64 |  |  |  |  | 4 | 12 | 14 |  | 16 | 18 |  |  | 0% | 0% | 0% | 0% | 20% | 60% | 60.87% | 0% | 76.19% | 78.26% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | A. Lorena | Operations | FrontEnd | 450 | 244 | ON GOING | 45% | 2024 | 3 | [10 empty] | 2 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.524% | 4.545%
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | A. Pirola | Operations | BackEnd | 450 | 244 | ON GOING | 45% | 2024 | 31 | [6 empty] | 1 |  | 15 | 15 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 0% | 71.43% | 65.22% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | C. Di Lorenzo | Delivery Projects | Analysis | 450 | 244 | ON GOING | 45% | 2024 | 24 | 5 | 5 | 5 | 4 | 4 | 5 | 5 |  | 3 | 3 | 1 | 3 | 27.78% | 25% | 23.81% | 18.18% | 20% | 25% | 21.74% | 0% | 14.29% | 13.04% | 4.762% | 13.64%
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | C. Elia | Operations | Architecture Analysis | 450 | 244 | ON GOING | 45% | 2024 | 19 | [5 empty] | 4 | 5 |  | 5 | 5 |  |  | 0% | 0% | 0% | 0% | 0% | 20% | 21.74% | 0% | 23.81% | 21.74% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | F. Delogu | Operations | BackEnd | 450 | 244 | ON GOING | 45% | 2024 | 45 | [6 empty] | 15 |  | 15 | 15 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 65.22% | 0% | 71.43% | 65.22% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | F. Spacagna | Operations | BackEnd | 450 | 244 | ON GOING | 45% | 2024 | 4 |  |  |  |  | 2 | 2 | [6 empty] | 0% | 0% | 0% | 0% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | G. De Feo | Delivery Projects | BackEnd | 450 | 244 | ON GOING | 45% | 2024 | 19 | [6 empty] | 5 |  | 4 | 4 | 3 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 0% | 19.05% | 17.39% | 14.29% | 13.64%
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | G. Lopez | Operations | FrontEnd | 450 | 244 | ON GOING | 45% | 2024 | 12 | [10 empty] | 4 | 8 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 19.05% | 36.36%
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | G. Tartaglia | Operations | BackEnd | 450 | 244 | ON GOING | 45% | 2024 | 46 | [6 empty] | 15 |  | 15 | 15 | 1 |  | 0% | 0% | 0% | 0% | 0% | 0% | 65.22% | 0% | 71.43% | 65.22% | 4.762% | 0%
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | L. Roberto | Operations | PM - Project Governance | 450 | 244 | ON GOING | 45% | 2024 | 21 | 1 | 1 | 1 | 3 | 4 | 4 | 5 |  | 3 | 3 | 1 | 1 | 5.556% | 5% | 4.762% | 13.64% | 20% | 20% | 21.74% | 0% | 14.29% | 13.04% | 4.762% | 4.545%
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | M. Porcu | Operations | BackEnd | 450 | 244 | ON GOING | 45% | 2024 | 14 | [6 empty] | 5 |  | 4 | 5 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 0% | 19.05% | 21.74% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | M. Toci | Operations | BackEnd | 450 | 244 | ON GOING | 45% | 2024 | 36 | [6 empty] | 1 |  | 17 | 18 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 0% | 80.95% | 78.26% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | N. Pescione | Operations | BackEnd | 450 | 244 | ON GOING | 45% | 2024 | 3 | [10 empty] | 2 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.524% | 4.545%
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | P. Anzellotti | Operations | BackEnd | 450 | 244 | ON GOING | 45% | 2024 | 11 | [5 empty] | 4 |  |  |  |  | 1 | 6 | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 4.762% | 27.27%
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | S. Beltrami | Operations | FrontEnd | 450 | 244 | ON GOING | 45% | 2024 | 46 | [6 empty] | 12 |  | 17 | 17 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 52.17% | 0% | 80.95% | 73.91% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | S. Delle Fave | Operations | FrontEnd | 450 | 244 | ON GOING | 45% | 2024 | 26 | [6 empty] | 6 |  | 9 | 9 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 26.09% | 0% | 42.86% | 39.13% | 4.762% | 4.545%
INTERNAL PRJ | PRJ |  |  | 2023-09-01 | 2024-05-31 | N/A | IAA | HR | MY PLACE | Abstract | L. Roberto | A. Brandizzi | Operations | FrontEnd | 0 | 0 | ON GOING | 0% | 2024 | 37 | 18 | 21 | 18 | 19 | 15 | 1 | 7 |  | 5 | 3 | 3 | 3 | 100% | 105% | 85.71% | 86.36% | 75% | 5% | 30.43% | 0% | 23.81% | 13.04% | 14.29% | 13.64%
INTERNAL PRJ | PRJ |  |  | 2023-09-01 | 2024-05-31 | N/A | IAA | HR | MY PLACE | Abstract | L. Roberto | A. Elia | UX/UI | Graphic Interface | 0 | 0 | ON GOING | 0% | 2024 | 0 |  |  |  | 4.75 | [8 empty] | 0% | 0% | 0% | 21.59% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 | 2023-09-01 | 2024-05-31 | N/A | IAA | HR | MY PLACE | Abstract | L. Roberto | C. Di Lorenzo | Delivery Projects | Analysis | 0 | 0 | ON GOING | 0% | 2024 | 23 |  |  | 5 | 4 | 4 | 4 | 5 |  | 3 | 3 | 2 | 2 | 0% | 0% | 23.81% | 18.18% | 20% | 20% | 21.74% | 0% | 14.29% | 13.04% | 9.524% | 9.091%
INTERNAL PRJ | PRJ |  |  | 2023-09-01 | 2024-05-31 | N/A | IAA | HR | MY PLACE | Abstract | L. Roberto | C. Elia | Operations | BackEnd | 0 | 0 | ON GOING | 0% | 2024 | 14 | 4 | 4 | 4 | 3 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 22.22% | 20% | 19.05% | 13.64% | 10% | 10% | 8.696% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
INTERNAL PRJ | PRJ |  |  | 2023-09-01 | 2024-05-31 | N/A | IAA | HR | MY PLACE | Abstract | L. Roberto | F. Spacagna | Operations | BackEnd | 0 | 0 | ON GOING | 0% | 2024 | 14 | 14.4 | 16.8 |  | 2 | 6 | 2 | 2 |  | 2 | 2 |  |  | 80% | 84% | 0% | 9.091% | 30% | 10% | 8.696% | 0% | 9.524% | 8.696% | 0% | 0%
INTERNAL PRJ | PRJ |  |  | 2023-09-01 | 2024-05-31 | N/A | IAA | HR | MY PLACE | Abstract | L. Roberto | G. Esposito | AREA TECH | FrontEnd | 0 | 0 | ON GOING | 0% | 2024 | 4 |  |  |  | 3 | 2 | 2 | [6 empty] | 0% | 0% | 0% | 13.64% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  |  | 2023-09-01 | 2024-05-31 | N/A | IAA | HR | MY PLACE | Abstract | L. Roberto | L. Roberto | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0% | 2024 | 25 | 4 | 4 | 4 | 5 | 5 | 4 | 4 |  | 4 | 4 | 2 | 2 | 22.22% | 20% | 19.05% | 22.73% | 25% | 20% | 17.39% | 0% | 19.05% | 17.39% | 9.524% | 9.091%
INTERNAL PRJ | PRJ |  |  | 2023-09-01 | 2024-05-31 | N/A | IAA | HR | MY PLACE | Abstract | L. Roberto | M. Attanasio | R&D | FrontEnd | 0 | 0 | ON GOING | 0% | 2024 | 1 | 18 | 21 | 18 | 19 | 1 | [7 empty] | 100% | 105% | 85.71% | 86.36% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  |  | 2023-09-01 | 2024-05-31 | N/A | IAA | HR | MY PLACE | Abstract | L. Roberto | M. Simeone | Operations | FrontEnd | 0 | 0 | ON GOING | 0% | 2024 | 119 | 18 | 21 | 13 | 15 | 19 | 19 | 18 |  | 18 | 15 | 15 | 15 | 100% | 105% | 61.9% | 68.18% | 95% | 95% | 78.26% | 0% | 85.71% | 65.22% | 71.43% | 68.18%
CONTRACT | PRJ |  | 2024 | 2024-03-15 | 2024-04-30 | ABS24176 | AEPP | OTHER | POC PODCAST | EssilorLuxottica | L. Roberto | A. Elia | UX/UI | Graphic Interface | 18 | 20 | CLOSED | 100% | 2024 | 0 |  |  |  | 1 | [8 empty] | 0% | 0% | 0% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-03-15 | 2024-04-30 | ABS24176 | AEPP | OTHER | POC PODCAST | EssilorLuxottica | L. Roberto | F. Spacagna | Operations | BackEnd | 18 | 20 | CLOSED | 100% | 2024 | 0 |  |  | 1 | 5 | [8 empty] | 0% | 0% | 4.762% | 22.73% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-03-15 | 2024-04-30 | ABS24176 | AEPP | OTHER | POC PODCAST | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 18 | 20 | CLOSED | 100% | 2024 | 0 |  |  | 1 | 1 | [8 empty] | 0% | 0% | 4.762% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-03-15 | 2024-04-30 | ABS24176 | AEPP | OTHER | POC PODCAST | EssilorLuxottica | L. Roberto | M. Simeone | Operations | FrontEnd | 18 | 20 | CLOSED | 100% | 2024 | 0 |  |  | 6 | [9 empty] | 0% | 0% | 28.57% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione | EssilorLuxottica | L. Roberto | C. Paz | Delivery Projects | PMO - Project Management Officer | 570 | 567 | CLOSED | 100% | 2024 | 29 | [5 empty] | 3 | 6 |  | 7 | 5 | 3 | 5 | 0% | 0% | 0% | 0% | 0% | 15% | 26.09% | 0% | 33.33% | 21.74% | 14.29% | 22.73%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 570 | 567 | CLOSED | 100% | 2024 | 36 | [5 empty] | 8 | 8 |  | 5 | 5 | 5 | 5 | 0% | 0% | 0% | 0% | 0% | 40% | 34.78% | 0% | 23.81% | 21.74% | 23.81% | 22.73%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Management | 570 | 567 | CLOSED | 100% | 2024 | 28 | [5 empty] | 3 | 9 |  | 6 | 6 | 3 | 1 | 0% | 0% | 0% | 0% | 0% | 15% | 39.13% | 0% | 28.57% | 26.09% | 14.29% | 4.545%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione | EssilorLuxottica | L. Roberto | M. Calabrese | Delivery Projects | Analysis | 570 | 567 | CLOSED | 100% | 2024 | 15 | [5 empty] | 3 | 3 |  | 3 | 3 | 2 | 1 | 0% | 0% | 0% | 0% | 0% | 15% | 13.04% | 0% | 14.29% | 13.04% | 9.524% | 4.545%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS25085 | ABS25085 | HR | Qlik - Project Dismissione - DE&I phase 1 | EssilorLuxottica | L. Roberto | C. Paz | Delivery Projects | Project Governance | 80 | 60 | CLOSED | 100% | 2024 | 7 | [9 empty] | 1 | 3 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 14.29% | 13.64%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS25085 | ABS25085 | HR | Qlik - Project Dismissione - DE&I phase 1 | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analysis | 80 | 60 | CLOSED | 100% | 2024 | 12 | [8 empty] | 3 | 3 | 2 | 4 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 13.04% | 9.524% | 18.18%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS25085 | ABS25085 | HR | Qlik - Project Dismissione - DE&I phase 1 | EssilorLuxottica | L. Roberto | F. Reale | Operations | FrontEnd | 80 | 60 | CLOSED | 100% | 2024 | 9 | [9 empty] | 5 | 4 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 19.05% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS25085 | ABS25085 | HR | Qlik - Project Dismissione - DE&I phase 1 | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | Project Governance | 80 | 60 | CLOSED | 100% | 2024 | 9 | [9 empty] | 3 | 3 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 14.29% | 13.64%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS25085 | ABS25085 | HR | Qlik - Project Dismissione - DE&I phase 1 | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 80 | 60 | CLOSED | 100% | 2024 | 10 | [9 empty] | 5 | 5 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 23.81% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS25085 | ABS25085 | HR | Qlik - Project Dismissione - DE&I phase 1 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | Project Governance | 80 | 60 | CLOSED | 100% | 2024 | 7 | [8 empty] | 2 | 2 | 2 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.524% | 8.696% | 9.524% | 4.545%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS25085 | ABS25085 | HR | Qlik - Project Dismissione - DE&I phase 1 | EssilorLuxottica | L. Roberto | R. Bondi | Operations | FrontEnd | 80 | 60 | CLOSED | 100% | 2024 | 12 | [9 empty] | 6 | 1 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 26.09% | 4.762% | 22.73%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS25085 | ABS25085 | HR | Qlik - Project Dismissione - DE&I phase 1 | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 80 | 60 | CLOSED | 100% | 2024 | 9 | [8 empty] | 3 | 3 | 2 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 13.04% | 9.524% | 4.545%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - Eye Resumè (Hana Cloud) | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 570 | 567 | CLOSED | 100% | 2024 | 22 | [5 empty] | 3 | 3 |  | 4 | 4 | 4 | 4 | 0% | 0% | 0% | 0% | 0% | 15% | 13.04% | 0% | 19.05% | 17.39% | 19.05% | 18.18%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - POC | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analysis | 570 | 567 | CLOSED | 100% | 2024 | 11 | [8 empty] | 3 | 4 | 4 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 17.39% | 19.05% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - POC | EssilorLuxottica | L. Roberto | R. Bondi | Operations | FrontEnd | 570 | 567 | CLOSED | 100% | 2024 | 3 | [6 empty] | 1 |  | 2 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 0% | 9.524% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - POC | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 570 | 567 | CLOSED | 100% | 2024 | 7 | [8 empty] | 3 | 1 | 1 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 4.348% | 4.762% | 9.091%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analysis | 570 | 567 | CLOSED | 100% | 2024 | 27 | [5 empty] | 3 | 1 |  | 6 | 6 | 5 | 6 | 0% | 0% | 0% | 0% | 0% | 15% | 4.348% | 0% | 28.57% | 26.09% | 23.81% | 27.27%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye | EssilorLuxottica | L. Roberto | F. Plebani | Operations | Data Management | 570 | 567 | CLOSED | 100% | 2024 | 11.5 | [6 empty] | 7.5 |  |  | 1 | 2 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 32.61% | 0% | 0% | 4.348% | 9.524% | 4.545%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye | EssilorLuxottica | L. Roberto | F. Reale | Operations | FrontEnd | 570 | 567 | CLOSED | 100% | 2024 | 13 | [8 empty] | 3 | 5 | 5 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 21.74% | 23.81% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Management | 570 | 567 | CLOSED | 100% | 2024 | 29.5 | [6 empty] | 2.5 |  | 2 | 15 | 6 | 4 | 0% | 0% | 0% | 0% | 0% | 0% | 10.87% | 0% | 9.524% | 65.22% | 28.57% | 18.18%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 570 | 567 | CLOSED | 100% | 2024 | 21 | [5 empty] | 3.5 | 3.5 |  | 3.5 | 3.5 | 3.5 | 3.5 | 0% | 0% | 0% | 0% | 0% | 17.5% | 15.22% | 0% | 16.67% | 15.22% | 16.67% | 15.91%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye | EssilorLuxottica | L. Roberto | L. Roberto | Operations | Project Governance | 570 | 567 | CLOSED | 100% | 2024 | 16 | [8 empty] | 4 | 4 | 4 | 4 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 19.05% | 17.39% | 19.05% | 18.18%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye | EssilorLuxottica | L. Roberto | M. Vimercati | Operations | Data Management | 570 | 567 | CLOSED | 100% | 2024 | 42 | [5 empty] | 4 | 4 |  | 8 | 14 | 7 | 5 | 0% | 0% | 0% | 0% | 0% | 20% | 17.39% | 0% | 38.1% | 60.87% | 33.33% | 22.73%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye | EssilorLuxottica | L. Roberto | R. Bondi | Operations | FrontEnd | 570 | 567 | CLOSED | 100% | 2024 | 24 | [5 empty] | 5 | 5 |  | 3 | 3 | 3 | 5 | 0% | 0% | 0% | 0% | 0% | 25% | 21.74% | 0% | 14.29% | 13.04% | 14.29% | 22.73%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 570 | 567 | CLOSED | 100% | 2024 | 16 | [5 empty] | 2 | 4 |  | 3 | 3 | 3 | 1 | 0% | 0% | 0% | 0% | 0% | 10% | 17.39% | 0% | 14.29% | 13.04% | 14.29% | 4.545%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | C. Di Lorenzo | Delivery Projects | Analysis | 570 | 567 | CLOSED | 100% | 2024 | 8 | [10 empty] | 1 | 7 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762% | 31.82%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | C. Elia | Operations | Data Engineering | 570 | 567 | CLOSED | 100% | 2024 | 17 | [6 empty] | 12 |  | 2 |  | 1 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 52.17% | 0% | 9.524% | 0% | 4.762% | 9.091%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analysis | 570 | 567 | CLOSED | 100% | 2024 | 16 | [5 empty] | 3 | 1 |  | 4 | 4 | 3 | 1 | 0% | 0% | 0% | 0% | 0% | 15% | 4.348% | 0% | 19.05% | 17.39% | 14.29% | 4.545%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | F. Plebani | Operations | Data Management | 570 | 567 | CLOSED | 100% | 2024 | 19.5 | [6 empty] | 7.5 |  | 8 | 2 | 2 |  | 0% | 0% | 0% | 0% | 0% | 0% | 32.61% | 0% | 38.1% | 8.696% | 9.524% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Management | 570 | 567 | CLOSED | 100% | 2024 | 31.5 | [6 empty] | 2.5 |  | 18 | 5 | 4 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 10.87% | 0% | 85.71% | 21.74% | 19.05% | 9.091%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 570 | 567 | CLOSED | 100% | 2024 | 4 | [10 empty] | 1 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762% | 13.64%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | G. Tuninetti | #N/A | UX/UI | 570 | 567 | CLOSED | 100% | 2024 | 12 | [6 empty] | 12 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 52.17% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 570 | 567 | CLOSED | 100% | 2024 | 21 | [5 empty] | 3.5 | 3.5 |  | 3.5 | 3.5 | 3.5 | 3.5 | 0% | 0% | 0% | 0% | 0% | 17.5% | 15.22% | 0% | 16.67% | 15.22% | 16.67% | 15.91%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 570 | 567 | CLOSED | 100% | 2024 | 13 | [8 empty] | 4 | 3 | 3 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 19.05% | 13.04% | 14.29% | 13.64%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | M. Porcu | Operations | BackEnd | 570 | 567 | CLOSED | 100% | 2024 | 24 | [5 empty] | 2 | 8 |  | 8 | 4 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 10% | 34.78% | 0% | 38.1% | 17.39% | 4.762% | 4.545%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | M. Toci | Operations | BackEnd | 570 | 567 | CLOSED | 100% | 2024 | 4 | [6 empty] | 1 |  | 3 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 0% | 14.29% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | M. Vimercati | Operations | Data Management | 570 | 567 | CLOSED | 100% | 2024 | 16 | [8 empty] | 7 | 4 | 3 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 33.33% | 17.39% | 14.29% | 9.091%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 570 | 567 | CLOSED | 100% | 2024 | 18 | [5 empty] | 2 | 4 |  | 4 | 4 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 10% | 17.39% | 0% | 19.05% | 17.39% | 9.524% | 9.091%
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | S. Beltrami | Operations | FrontEnd | 570 | 567 | CLOSED | 100% | 2024 | 14 | [6 empty] | 12 |  | 2 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 52.17% | 0% | 9.524% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2023-10-01 | 2024-03-31 | ABS23397 | AR | CRM/CS | REWARD HUB - AMS | EssilorLuxottica | L. Roberto | C. Di Lorenzo | Delivery Projects | Analysis | 51 | 47 | CLOSED | 100% | 2024 | 0 | 4 | 6 | 6 | [9 empty] | 22.22% | 30% | 28.57% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2023-10-01 | 2024-03-31 | ABS23397 | AR | CRM/CS | REWARD HUB - AMS | EssilorLuxottica | L. Roberto | C. Elia | Operations | BackEnd | 51 | 47 | CLOSED | 100% | 2024 | 0 | 5 | 5 | 5 | [9 empty] | 27.78% | 25% | 23.81% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2023-10-01 | 2024-03-31 | ABS23397 | AR | CRM/CS | REWARD HUB - AMS | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 51 | 47 | CLOSED | 100% | 2024 | 0 | 2.7 | 3.15 | 3 | [9 empty] | 15% | 15.75% | 14.29% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-03-15 | 2024-05-31 | ABS24158 | AER30E | CRM/CS | REWARD HUB w3 | EssilorLuxottica | L. Roberto | A. Elia | UX/UI | Graphic Interface | 192 | 155 | CLOSED | 100% | 2024 | 0 |  |  |  | 7.6 | [8 empty] | 0% | 0% | 0% | 34.55% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-03-15 | 2024-05-31 | ABS24158 | AER30E | CRM/CS | REWARD HUB w3 | EssilorLuxottica | L. Roberto | C. Di Lorenzo | Delivery Projects | Analysis | 192 | 155 | CLOSED | 100% | 2024 | 24 | 9 | 1 | 5 | 11 | 12 | 12 | [6 empty] | 50% | 5% | 23.81% | 50% | 60% | 60% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-03-15 | 2024-05-31 | ABS24158 | AER30E | CRM/CS | REWARD HUB w3 | EssilorLuxottica | L. Roberto | C. Elia | Operations | BackEnd | 192 | 155 | CLOSED | 100% | 2024 | 19 |  |  | 5 | 19 | 14 | 5 | [6 empty] | 0% | 0% | 23.81% | 86.36% | 70% | 25% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-03-15 | 2024-05-31 | ABS24158 | AER30E | CRM/CS | REWARD HUB w3 | EssilorLuxottica | L. Roberto | G. Esposito | AREA TECH | FrontEnd | 192 | 155 | CLOSED | 100% | 2024 | 9 |  |  | 1 | 19 | 2 | 7 | [6 empty] | 0% | 0% | 4.762% | 86.36% | 10% | 35% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-03-15 | 2024-05-31 | ABS24158 | AER30E | CRM/CS | REWARD HUB w3 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 192 | 155 | CLOSED | 100% | 2024 | 6 |  |  | 5 | 9.5 | 1 | 5 | [6 empty] | 0% | 0% | 23.81% | 43.18% | 5% | 25% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-03-15 | 2024-05-31 | ABS24158 | AER30E | CRM/CS | REWARD HUB w3 | EssilorLuxottica | L. Roberto | L. Tironese | Operations | FrontEnd | 192 | 155 | CLOSED | 100% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2024 | 2024-04-01 | 2024-07-31 | ABS23342 | ATAW2 | HR | Talent Acquisition W2 - SF fields through API to DWH | EssilorLuxottica | L. Roberto | F. Reale | Operations | FrontEnd | 0 | 0 | CLOSED | 0% | 2024 | 3 | [5 empty] | 3 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 15% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2024 | 2024-04-01 | 2024-07-31 | ABS23342 | ATAW2 | HR | Talent Acquisition W2 - SF fields through API to DWH | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Engineering | 0 | 0 | CLOSED | 0% | 2024 | 3 | [5 empty] | 3 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 15% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2024 | 2024-04-01 | 2024-07-31 | ABS23342 | ATAW2 | HR | Talent Acquisition W2 - SF fields through API to DWH | EssilorLuxottica | L. Roberto | M. Vimercati | Operations | PM - Project Governance | 0 | 0 | CLOSED | 0% | 2024 | 10 |  |  |  | 1 | 5 | 3 | 2 | [5 empty] | 0% | 0% | 0% | 4.545% | 25% | 15% | 8.696% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-11-02 | 2025-12-31 | ABS24539 | ABS24539 | CRM/CS | Trenord | Trenord | L. Roberto | L. Roberto | Operations | PM - Project Governance | 58 | 7 | ON GOING | 0% | 2024 | 7 | [10 empty] | 2 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.524% | 22.73%
PRE-SALES | PRJ |  | 2025 | 2025-02-01 | 2025-06-30 | N/A | N/A | LOGISTIC | Control tower AI - Preparazione proposta | EssilorLuxottica | M. Calabrese | F. Spacagna | Operations | Tech Lead | 15 | 11 | CLOSED | 100% | 2024 | 2 | [5 empty] | 2 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
PRE-SALES | PRJ |  | 2025 | 2025-02-01 | 2025-06-30 | N/A | N/A | LOGISTIC | Control tower AI - Preparazione proposta | EssilorLuxottica | M. Calabrese | G. Sironi | Operations | Team Leadership | 15 | 11 | CLOSED | 100% | 2024 | 3 |  |  |  |  | 1 | 2 | [6 empty] | 0% | 0% | 0% | 0% | 5% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
PRE-SALES | PRJ |  | 2025 | 2025-02-01 | 2025-06-30 | N/A | N/A | LOGISTIC | Control tower AI - Preparazione proposta | EssilorLuxottica | M. Calabrese | M. Calabrese | Delivery Projects | PM - Project Governance | 15 | 11 | CLOSED | 100% | 2024 | 10 |  |  |  |  | 5 | 5 | [6 empty] | 0% | 0% | 0% | 0% | 25% | 25% | 0% | 0% | 0% | 0% | 0% | 0%
PRE-SALES | PRJ |  | 2025 | 2025-02-01 | 2025-06-30 | N/A | N/A | LOGISTIC | Control tower AI - Preparazione proposta | EssilorLuxottica | M. Calabrese | M. Gomitoni | Operations | Backend | 15 | 11 | CLOSED | 100% | 2024 | 2 | [5 empty] | 2 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile |  | 2022-01-01 | 2024-06-01 | ABS23298 | ACTEF | LOGISTIC | ELECTRA FRANCE-AUGE CONTROL TOWER | EssilorLuxottica | M. Calabrese | A. Strada | Operations | DataManagement | 1326 | 1111 | CLOSED | 100% | 2024 | 8.25 | 0.9 | 1.5 | 1.5 | 0.95 | 1 | 4 | 1.15 | 0.6 | 1.5 |  |  |  | 5% | 7.5% | 7.143% | 4.318% | 5% | 20% | 5% | 5% | 7.143% | 0% | 0% | 0%
CONTRACT | PRJ | Agile |  | 2022-01-01 | 2024-06-01 | ABS23298 | ACTEF | LOGISTIC | ELECTRA FRANCE-AUGE CONTROL TOWER | EssilorLuxottica | M. Calabrese | M. Calabrese | Delivery Projects | PM - Project Governance | 1326 | 1111 | CLOSED | 100% | 2024 | 29 | 1 | 1 | 1 | 5 | 5 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 5.556% | 5% | 4.762% | 22.73% | 25% | 30% | 13.04% | 25% | 14.29% | 13.04% | 14.29% | 13.64%
CONTRACT | PRJ | Agile |  | 2022-01-01 | 2024-06-01 | ABS23298 | ACTEF | LOGISTIC | ELECTRA FRANCE-AUGE CONTROL TOWER | EssilorLuxottica | M. Calabrese | M. Sabarese | SAP FIORI | FrontEnd | 1326 | 1111 | CLOSED | 100% | 2024 | 4 | [5 empty] | 4 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile |  | 2022-01-01 | 2024-06-01 | ABS23298 | ACTEF | LOGISTIC | ELECTRA FRANCE-AUGE CONTROL TOWER | EssilorLuxottica | M. Calabrese | R. Nunziata | SAP ECC | Analysis | 1326 | 1111 | CLOSED | 100% | 2024 | 12 | 9 | 1.5 | 1.5 | 9.5 | 5 | 5 | 2 | [5 empty] | 50% | 7.5% | 7.143% | 43.18% | 25% | 25% | 8.696% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrumban | 2024 | 2024-01-01 | 2024-04-01 | ABS24103 | AESCARW | BIP | ELIOT SUPPLY CHAIN - ARS RXO W2 | EssilorLuxottica | M. Calabrese | A. Cerrato | Operations | Analysis | 43 | 43 | CLOSED | 100% | 2024 | 0 | 0.9 | 2.1 | 2.1 | [9 empty] | 5% | 10.5% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrumban | 2024 | 2024-01-01 | 2024-04-01 | ABS24103 | AESCARW | BIP | ELIOT SUPPLY CHAIN - ARS RXO W2 | EssilorLuxottica | M. Calabrese | M. Calabrese | Delivery Projects | PM - Project Governance | 43 | 43 | CLOSED | 100% | 2024 | 0 | 1.8 | 2.1 | 2.1 | [9 empty] | 10% | 10.5% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrumban | 2024 | 2024-01-01 | 2024-04-01 | ABS24103 | AESCARW | BIP | ELIOT SUPPLY CHAIN - ARS RXO W2 | EssilorLuxottica | M. Calabrese | M. Vimercati | Operations | FrontEnd | 43 | 43 | CLOSED | 100% | 2024 | 0 | 0.9 | 1.5 | 1.5 | [9 empty] | 5% | 7.5% | 7.143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrumban | 2024 | 2024-01-01 | 2024-04-01 | ABS24103 | AESCARW | BIP | ELIOT SUPPLY CHAIN - ARS RXO W2 | EssilorLuxottica | M. Calabrese | R. Alves | Operations | FrontEnd | 43 | 43 | CLOSED | 100% | 2024 | 0 |  | 1.5 | 1.5 | [9 empty] | 0% | 7.5% | 7.143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrumban | 2024 | 2024-01-01 | 2024-04-01 | ABS24103 | AESCARW | BIP | ELIOT SUPPLY CHAIN - ARS RXO W2 | EssilorLuxottica | M. Calabrese | R. Grienti | Operations | DataManagement | 43 | 43 | CLOSED | 100% | 2024 | 0 | 4.5 | 1.5 | 1.5 | [9 empty] | 25% | 7.5% | 7.143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRESALES - DELIVERY | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24293 | ACTU | LOGISTIC | POC - CONTROL TOWER UNIFICATA | EssilorLuxottica | M. Calabrese | M. Calabrese | Delivery Projects | PM - Project Governance | 10 | 8 | CLOSED | 100% | 2024 | 3 |  |  | 2 |  | 1 | 2 | [6 empty] | 0% | 0% | 9.524% | 0% | 5% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRESALES - DELIVERY | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24293 | ACTU | LOGISTIC | POC - CONTROL TOWER UNIFICATA | EssilorLuxottica | M. Calabrese | M. Piazza | SAP ECC | ECC Analyst | 10 | 8 | CLOSED | 100% | 2024 | 2 |  | 1 |  |  | 1 | 1 | [6 empty] | 0% | 5% | 0% | 0% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRESALES - DELIVERY | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24293 | ACTU | LOGISTIC | POC - CONTROL TOWER UNIFICATA | EssilorLuxottica | M. Calabrese | R. Nunziata | SAP ECC | ECC Analyst | 10 | 8 | CLOSED | 100% | 2024 | 1 |  | 1 |  |  |  | 1 | [6 empty] | 0% | 5% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
PRE-SALES | PRESALES - GO TO MARKET |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ABS0007 | EPM | Attività di Pre-Sales |  | M. COCCHI | A. Albanese | Delivery Projects | Analysis | 0 | 0 | ON GOING | 0% | 2024 | 10 |  | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 |  |  | 0% | 5% | 4.762% | 4.545% | 15% | 15% | 4.348% | 8.333% | 4.762% | 4.348% | 0% | 0%
PRE-SALES | PRESALES - GO TO MARKET |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ABS0007 | OTHER | Attività di Pre-Sales |  | M. COCCHI | F. Lombardini | Consolidated & Tax | Analysis | 0 | 0 | ON GOING | 0% | 2024 | 23 | 2 | 1 | 2 | 1 | 2 | 1 | 2 |  |  |  | 9 | 9 | 11.11% | 5% | 9.524% | 4.545% | 10% | 5% | 8.696% | 0% | 0% | 0% | 42.86% | 40.91%
PRE-SALES | PRESALES - GO TO MARKET |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ABS0007 | FINANCE | Attività di Pre-Sales |  | M. COCCHI | M. Cocchi | Consolidated & Tax | PM - Project Governance | 0 | 0 | ON GOING | 0% | 2024 | 46 | 9 | 11 | 11 | 1 | 1 | 9 | 11 | 5 | 1 | 11 | 1 | 7 | 50% | 55% | 52.38% | 4.545% | 5% | 45% | 47.83% | 41.67% | 4.762% | 47.83% | 4.762% | 31.82%
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Carrier Manager Activities | Abstract | M. COCCHI | F. Lombardini | Consolidated & Tax | PM - Project Governance | 0 | 0 | ON GOING | 0% | 2024 | 7 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Carrier Manager Activities | Abstract | M. COCCHI | M. Cocchi | Consolidated & Tax | PM - Project Governance | 0 | 0 | ON GOING | 0% | 2024 | 7 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Carrier Manager Activities | Abstract | M. COCCHI | S. Preziosa | Delivery Projects | PM - Project Governance | 0 | 0 | ON GOING | 0% | 2024 | 6 | [5 empty] | 1 | 1 |  | 1 | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 5% | 4.348% | 0% | 4.762% | 4.348% | 4.762% | 4.545%
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-03-31 | N/A | EPM | OTHER | Corporate Performance Platform | Abstract | M. COCCHI | C. Tiberti | Operations | Analysis | 0 | 0 | ON GOING | 0% | 2024 | 8 | 8 | 8 | 8 | 8 | 8 | [7 empty] | 44.44% | 40% | 38.1% | 36.36% | 40% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-03-31 | N/A | EPM | OTHER | Corporate Performance Platform | Abstract | M. COCCHI | F. Lombardini | Consolidated & Tax | Analysis | 0 | 0 | ON GOING | 0% | 2024 | 11 | 5 | 1 | 1 | 1 | 5 | 6 | [6 empty] | 27.78% | 5% | 4.762% | 4.545% | 25% | 30% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-06-05 | N/A | EPM | CPP | Corporate Performance Platform | Abstract | M. COCCHI | G. Picerno | Consolidated & Tax | Analysis | 0 | 0 | ON GOING | 0% | 2024 | 10 | 7 | 14 | 14 | 12 | 5 | 5 | [6 empty] | 38.89% | 70% | 66.67% | 54.55% | 25% | 25% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRESALES - GO TO MARKET |  | 2024 |  |  | N/A | N/A | CPP | CPP - ML forecasting | EssilorLuxottica | M. COCCHI | G. Sironi | Operations | Team Leadership | 0 | 0 | PROPOSAL | 0% | 2024 | 0 |  | 1 | 1 | 1 | [8 empty] | 0% | 5% | 4.762% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRESALES - GO TO MARKET |  | 2024 |  |  | N/A | N/A | CPP | CPP - ML forecasting | EssilorLuxottica | M. COCCHI | M. Gomitoni | Operations | Tech Lead | 0 | 0 | PROPOSAL | 0% | 2024 | 0 |  | 1 | 2 | 2 | [8 empty] | 0% | 5% | 9.524% | 9.091% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ |  | 2024 |  |  | N/A | N/A | EPM | EPM - Time series forecasting | EssilorLuxottica | M. COCCHI | A. Imbimbo | Operations | Data Scientist | 0 | 0 | CLOSED | 0% | 2024 | 0 | 2 | 4 | 2 | [9 empty] | 11.11% | 20% | 9.524% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ |  | 2024 |  |  | N/A | N/A | EPM | EPM - Time series forecasting | EssilorLuxottica | M. COCCHI | F. Malvezzi | Operations | Data Scientist | 0 | 0 | CLOSED | 0% | 2024 | 0 | 4 | 7 | 4 | [9 empty] | 22.22% | 35% | 19.05% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ |  | 2024 |  |  | N/A | N/A | EPM | EPM - Time series forecasting | EssilorLuxottica | M. COCCHI | G. Sabbatini | Operations | Data Engineering | 0 | 0 | CLOSED | 0% | 2024 | 0 | 2 | 3 | 2 | [9 empty] | 11.11% | 15% | 9.524% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ |  | 2024 |  |  | N/A | N/A | EPM | EPM - Time series forecasting | EssilorLuxottica | M. COCCHI | G. Sironi | Operations | Team Leadership | 0 | 0 | CLOSED | 0% | 2024 | 0 | 2 | 3 | 2 | [9 empty] | 11.11% | 15% | 9.524% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ |  | 2024 |  |  | N/A | N/A | EPM | EPM - Time series forecasting | EssilorLuxottica | M. COCCHI | M. Gomitoni | Operations | Tech Lead | 0 | 0 | CLOSED | 0% | 2024 | 0 | 5 | 1 | 5 | [9 empty] | 27.78% | 5% | 23.81% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ |  | 2024 |  |  | N/A | N/A | EPM | EPM - Time series forecasting | EssilorLuxottica | M. COCCHI | V. Echarry | Operations | Data Scientist | 0 | 0 | CLOSED | 0% | 2024 | 0 | 4 | 7 | 4 | [9 empty] | 22.22% | 35% | 19.05% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione | Abstract | M. COCCHI | C. Di Lorenzo | Delivery Projects | Training | 19 | 0 | ON GOING | 50% | 2024 | 18 | [5 empty] | 2 | 5 |  | 3 | 3 | 3 | 2 | 0% | 0% | 0% | 0% | 0% | 10% | 21.74% | 0% | 14.29% | 13.04% | 14.29% | 9.091%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione | Abstract | M. COCCHI | E. Storti | Delivery Projects | Training | 14 | 0 | ON GOING | 50% | 2024 | 13 | [5 empty] | 1 | 2 |  | 4 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 5% | 8.696% | 0% | 19.05% | 8.696% | 9.524% | 9.091%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione | Abstract | M. COCCHI | F. Lombardini | Consolidated & Tax | Training | 3 | 0 | ON GOING | 50% | 2024 | 3 | [5 empty] | 1 |  |  |  | 1 | 1 |  | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 4.348% | 4.762% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione | Abstract | M. COCCHI | M. Salcini | Consolidated & Tax | Training | 3 | 0 | ON GOING | 50% | 2024 | 3 | [9 empty] | 2 | 1 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 4.762% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione nuovo assunto | Abstract | M. COCCHI | P. Galvagni | Consolidated & Tax | Training | 1.5 | 0 | CLOSED | 20% | 2024 | 1.5 | [8 empty] | 0.5 | 1 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.381% | 4.348% | 0% | 0%
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | IAA | FINANCE | Gestione Consulting | ABSTRACT | M. COCCHI | M. Cocchi | Consolidated & Tax | PM - Project Governance | 0 | 0 | ON GOING | 100% | 2024 | 34 | 9 | 1 | 1 | 9 | 6 | 5 | 5 |  | 5 | 5 | 4 | 4 | 50% | 5% | 4.762% | 40.91% | 30% | 25% | 21.74% | 0% | 23.81% | 21.74% | 19.05% | 18.18%
CONTRACT | PRJ |  | 2024-2025 | 2024-11-01 | 2024-06-30 | ABS24604 | N/A | EPM | KPMG - Ferrero - Supporto + CR | FERRERO | M. COCCHI | A. Albanese | Delivery Projects | PM - Project Governance | 110 | 40 | ON GOING | 40% | 2024 | 1 | [9 empty] | 0.5 | 0.5 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.174% | 2.381% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-11-01 | 2024-06-30 | ABS24604 | N/A | EPM | KPMG - Ferrero - Supporto + CR | FERRERO | M. COCCHI | A. Albanese | Delivery Projects | PM - Project Governance | 110 | 40 | ON GOING | 40% | 2024 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | [7 empty] | 5 | 2.778% | 2.5% | 2.381% | 2.273% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 22.73%
CONTRACT | PRJ |  | 2024-2025 | 2024-11-01 | 2024-06-30 | ABS24604 | N/A | EPM | KPMG - Ferrero - Supporto + CR | FERRERO | M. COCCHI | A. Di Pietro | Operations | BackEnd | 110 | 40 | ON GOING | 40% | 2024 | 24 | [9 empty] | 13 | 11 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 56.52% | 52.38% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-11-01 | 2024-06-30 | ABS24604 | N/A | EPM | KPMG - Ferrero - Supporto + CR | FERRERO | M. COCCHI | I. Bressan | Operations | BackEnd | 110 | 40 | ON GOING | 40% | 2024 | 17 | [10 empty] | 17 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 80.95% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-11-01 | 2024-06-30 | ABS24604 | N/A | EPM | KPMG - Ferrero - Supporto + CR | FERRERO | M. COCCHI | M. Favalli | Operations | BackEnd | 110 | 40 | ON GOING | 40% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - Tax Control Framework | FERRERO | M. COCCHI | A. Albanese | Delivery Projects | PM - Project Governance | 305 | 300 | ON GOING | 98% | 2024 | 19 |  |  |  | 2 | 2 | 3 | 3 |  | 3 | 3 | 3 | 2 | 0% | 0% | 0% | 9.091% | 10% | 15% | 13.04% | 0% | 14.29% | 13.04% | 14.29% | 9.091%
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - Tax Control Framework | FERRERO | M. COCCHI | F. Atanasio | Operations | BackEnd | 305 | 300 | ON GOING | 95% | 2024 | 24 |  |  |  |  | 3 | 2 | 16 | 0.5 | 1.5 |  | 1 |  | 0% | 0% | 0% | 0% | 15% | 10% | 69.57% | 4.167% | 7.143% | 0% | 4.762% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - Tax Control Framework | FERRERO | M. COCCHI | F. Lombardini | Consolidated & Tax | Analysis | 305 | 300 | ON GOING | 95% | 2024 | 15 |  |  |  |  | 1 | 7 | 4 | 3 |  |  |  |  | 0% | 0% | 0% | 0% | 5% | 35% | 17.39% | 25% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - Tax Control Framework | FERRERO | M. COCCHI | I. Bressan | Operations | Tech Lead | 305 | 300 | ON GOING | 95% | 2024 | 27 |  |  |  |  | 1 | 16 | 7 |  | 1.5 | 1 | 0.5 |  | 0% | 0% | 0% | 0% | 5% | 80% | 30.43% | 0% | 7.143% | 4.348% | 2.381% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - Tax Control Framework | FERRERO | M. COCCHI | P. Galvagni | Consolidated & Tax | Analysis | 305 | 300 | ON GOING | 95% | 2024 | 68 |  |  |  |  | 22 | 2 | 23 |  | 21 |  |  |  | 0% | 0% | 0% | 0% | 110% | 10% | 100% | 0% | 100% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - Value Chain | FERRERO | M. COCCHI | A. Di Pietro | Operations | BackEnd | 305 | 300 | ON GOING | 40% | 2024 | 36 |  |  |  |  | 2 | 1 | 7 | 5.5 | 6 | 1.5 | 8 | 5 | 0% | 0% | 0% | 0% | 10% | 5% | 30.43% | 45.83% | 28.57% | 6.522% | 38.1% | 22.73%
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - Value Chain | FERRERO | M. COCCHI | L. Mangili | Operations | BackEnd | 305 | 300 | ON GOING | 40% | 2024 | 10 |  |  |  |  | 2 | 1 | 7 | [5 empty] | 0% | 0% | 0% | 0% | 10% | 5% | 30.43% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - VBA Support | FERRERO | M. COCCHI | F. De Pedis | Operations | BackEnd | 305 | 300 | CLOSED | 100% | 2024 | 0 |  |  | 3 | 2 | [8 empty] | 0% | 0% | 14.29% | 9.091% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - VBA Support | FERRERO | M. COCCHI | P. Pieroni | Operations | BackEnd | 305 | 300 | CLOSED | 100% | 2024 | 0 |  |  | 2 | 1.5 | [8 empty] | 0% | 0% | 9.524% | 6.818% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - Weekly Sales | FERRERO | M. COCCHI | F. Atanasio | Operations | BackEnd | 305 | 300 | ON GOING | 90% | 2024 | 19 |  |  |  | 16 | 19 | [7 empty] | 0% | 0% | 0% | 72.73% | 95% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - Weekly Sales | FERRERO | M. COCCHI | L. Mangili | Operations | BackEnd | 305 | 300 | ON GOING | 90% | 2024 | 41.5 |  |  |  | 14.5 | 18 | 1 | 11 | 2 | 8 | 1.5 |  |  | 0% | 0% | 0% | 65.91% | 90% | 5% | 47.83% | 16.67% | 38.1% | 6.522% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - Weekly Sales (CR Plus) | FERRERO | M. COCCHI | L. Mangili | Operations | BackEnd | 305 | 300 | ON GOING | 90% | 2024 | 35 | [9 empty] | 15 | 15 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 65.22% | 71.43% | 22.73%
INTERNAL PRJ | PRJ |  | 2024 |  |  | N/A | DSL | EPM | Laboratorio AI per Lux | EssilorLuxottica | M. COCCHI | L. Franco | Operations | Analysis | 0 | 0 | CLOSED | 100% | 2024 | 0 | 5 | 5 | [10 empty] | 27.78% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Skill Acceleration Ed. 2 | Abstract | M. COCCHI | G. Picerno | Consolidated & Tax | Training | 5 | 0 | ON GOING | 20% | 2024 | 5 | [5 empty] | 1 | 1 |  | 1 | 1 | 1 |  | 0% | 0% | 0% | 0% | 0% | 5% | 4.348% | 0% | 4.762% | 4.348% | 4.762% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-09-01 | 2024-11-30 | N/A | ATD | OTHER | Training on the Job FCCS - Pro Vision Group (xView) | Abstract | M. COCCHI | M. Salcini | Consolidated & Tax | BackEnd | 10 | 0 | ON GOING | 0% | 2024 | 10 | [8 empty] | 3 | 5 | 2 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 21.74% | 9.524% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-10-15 | 2024-05-30 | ABS24025 | ABS24025 | EPM | Webuild - Migrazione HFM | WeBuild | M. COCCHI | A. Albanese | Delivery Projects | PM - Project Governance | 115 | 15 | ON GOING | 0% | 2024 | 1.5 | [9 empty] | 0.5 | 0.5 | 0.5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.174% | 2.381% | 2.273%
CONTRACT | PRJ |  | 2024-2025 | 2024-10-15 | 2024-05-30 | ABS24025 | ABS24025 | EPM | Webuild - Migrazione HFM | WeBuild | M. COCCHI | Esterno Oracle | #N/A | PM - Project Governance | 115 | 15 | ON GOING | 0% | 2024 | 1 | [11 empty] | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.545%
CONTRACT | PRJ |  | 2024-2025 | 2024-10-15 | 2024-05-30 | ABS24025 | ABS24025 | EPM | Webuild - Migrazione HFM | WeBuild | M. COCCHI | F. De Pedis | Operations | BackEnd | 115 | 15 | ON GOING | 0% | 2024 | 2 | [11 empty] | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.091%
CONTRACT | PRJ |  | 2024-2025 | 2024-10-15 | 2024-05-30 | ABS24025 | ABS24025 | EPM | Webuild - Migrazione HFM | WeBuild | M. COCCHI | I. Bressan | Operations | Technical Leader | 115 | 15 | ON GOING | 0% | 2024 | 3 | [11 empty] | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.64%
CONTRACT | PRJ |  | 2024-2025 | 2024-10-15 | 2024-05-30 | ABS24025 | ABS24025 | EPM | Webuild - Migrazione HFM | WeBuild | M. COCCHI | M. Salcini | Consolidated & Tax | Analysis | 115 | 15 | ON GOING | 0% | 2024 | 2 | [10 empty] | 2 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.524% | 0%
INTERNAL PRJ | PRJ |  | 2024 | 2024-04-01 | 2024-12-31 | N/A | ABS0008 | ECC | ELETTRA JIRA |  | M. Pallotti | A. Torone | Delivery AMS | PM - Project Governance | 24 | 11 | ON GOING | 50% | 2024 | 17 |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 1 | 2 | 0% | 0% | 0% | 9.091% | 10% | 10% | 8.696% | 16.67% | 9.524% | 17.39% | 4.762% | 9.091%
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS0008 | ECC | ELETTRA JIRA |  | M. Pallotti | A. Torone | Delivery AMS | PM - Project Governance | 24 | 0 | ON GOING | 0% | 2024 | 8 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 11.11% | 10% | 9.524% | 4.545% | 5% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS0008 | ECC | ELETTRA JIRA |  | M. Pallotti | C. Paz | Delivery Projects | PMO | 24 | 0 | ON GOING | 0% | 2024 | 15 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 8.696% | 8.333% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | AMS |  | 2024 | 2024-01-01 | 2024-06-30 | ABS24009 | AEAA1 | EPM | HFM Ariston AMS 2024 1 Semestre | ARISTON | M. Salcini | G. Galati | Delivery AMS | BackEnd | 60 | 0 | CLOSED | 100% | 2024 | 8 | 3.6 | 4.2 | 4.2 | 3.8 | 4 | 4 | [6 empty] | 20% | 21% | 20% | 17.27% | 20% | 20% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2024-01-01 | 2024-06-30 | ABS24009 | AEAA1 | EPM | HFM Ariston AMS 2024 1 Semestre | ARISTON | M. Salcini | M. Salcini | Consolidated & Tax | PM - Project Governance | 60 | 0 | CLOSED | 100% | 2024 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | [6 empty] | 11.11% | 10% | 9.524% | 9.091% | 10% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2024-01-01 | 2024-06-30 | ABS24009 | AEAA1 | EPM | HFM Ariston AMS 2024 1 Semestre | ARISTON | M. Salcini | M. Sorrentino | Consolidated & Tax | Analysis | 60 | 0 | CLOSED | 100% | 2024 | 6 | 1.8 | 2.1 | 2.1 | 1.9 | 2 | 4 | [6 empty] | 10% | 10.5% | 10% | 8.636% | 10% | 20% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2024-01-01 | 2024-06-30 | ABS24009 | AEAA1 | EPM | HFM Ariston AMS 2024 1 Semestre | ARISTON | M. Salcini | R. Freddi | Operations | BackEnd | 60 | 0 | CLOSED | 100% | 2024 | 0 | 1.8 | 2.1 | 2.1 | 1.9 | [8 empty] | 10% | 10.5% | 10% | 8.636% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2024-01-01 | 2024-06-30 | ABS23317 | AETHA | EPM | Transmec AMS HFM 2023/2024 | Transmec | M. Salcini | G. Galati | Delivery AMS | BackEnd | 30 | 0 | CLOSED | 0% | 2024 | 14 | 1.8 | 2.1 | 2.1 | 1.9 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 10% | 10.5% | 10% | 8.636% | 10% | 10% | 8.696% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | AMS |  | 2024 | 2024-01-01 | 2024-06-30 | ABS23317 | AETHA | EPM | Transmec AMS HFM 2023/2024 | Transmec | M. Salcini | M. Salcini | Consolidated & Tax | PM - Project Governance | 30 | 0 | CLOSED | 0% | 2024 | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 0% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS |  | 2024 | 2024-01-01 | 2024-06-30 | ABS23317 | AETHA | EPM | Transmec AMS HFM 2023/2024 | Transmec | M. Salcini | M. Sorrentino | Consolidated & Tax | Analysis | 30 | 0 | CLOSED | 0% | 2024 | 6 | 1.8 | 2.1 | 2.1 | 1.9 | 3 | 3 | [6 empty] | 10% | 10.5% | 10% | 8.636% | 15% | 15% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-09-01 | 2024-11-30 | N/A | ATD | OTHER | Corsi OneStream - Essentials | Abstract | M. SORRENTINO | C. Tiberti | Operations | Solution Architect | 4 | 0 | ON GOING | 0% | 2024 | 10 | [9 empty] | 4 | 4 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 17.39% | 19.05% | 9.091%
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  | N/A | ATD | Formazione | Formazione HFM Consolidato | EssilorLuxottica | M. SORRENTINO | C. Tiberti | Operations | BackEnd | 0 | 0 | PROPOSAL | 0% | 2024 | 12 | [5 empty] | 9 | 3 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 45% | 13.04% | 0% | 0% | 0% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione Oracle FCCS | Abstract | M. SORRENTINO | C. Esposito | Consolidated & Tax | BackEnd | 3 | 0 | ON GOING | 0% | 2024 | 5 | [6 empty] | 3 |  |  | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 0% | 0% | 8.696% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione Oracle FCCS | Abstract | M. SORRENTINO | C. Tiberti | Operations | BackEnd | 3 | 0 | ON GOING | 0% | 2024 | 5 | [6 empty] | 3 |  |  | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 0% | 0% | 8.696% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione Oracle FCCS | Abstract | M. SORRENTINO | E. Tosetto | Consolidated & Tax | BackEnd | 3 | 0 | ON GOING | 0% | 2024 | 5 | [6 empty] | 3 |  |  | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 0% | 0% | 8.696% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione Oracle FCCS | Abstract | M. SORRENTINO | L. Pigazzini | Consolidated & Tax | BackEnd | 3 | 0 | ON GOING | 0% | 2024 | 5 | [6 empty] | 3 |  |  | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 0% | 0% | 8.696% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione Oracle FCCS | Abstract | M. SORRENTINO | M. Sorrentino | Consolidated & Tax | BackEnd | 3 | 0 | ON GOING | 0% | 2024 | 5 | [6 empty] | 3 |  |  | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 0% | 0% | 8.696% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-6 | HR | AMS - HR - Web App -2024 | EssilorLuxottica | N. GUERRERO | L. Carloni | Operations | Data Engineering | 112 | 59 | ON GOING | 0% | 2024 | 0 |  | 2 | 2 | [9 empty] | 0% | 10% | 9.524% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-6 | HR | AMS - HR - Web App -2024 | EssilorLuxottica | N. GUERRERO | M. Mannarino | Operations | Data Engineering | 112 | 59 | ON GOING | 0% | 2024 | 19 |  |  |  | 3 | 3 | 3 | 3 |  | 1 | 1 | 4 | 4 | 0% | 0% | 0% | 13.64% | 15% | 15% | 13.04% | 0% | 4.762% | 4.348% | 19.05% | 18.18%
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-6 | HR | AMS - HR - Web App -2024 | EssilorLuxottica | N. GUERRERO | M. Porcu | Operations | Technical Leader | 112 | 59 | ON GOING | 0% | 2024 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 2 | 5 | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 0% | 4.762% | 4.348% | 9.524% | 22.73%
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-6 | HR | AMS - HR - Web App -2024 | EssilorLuxottica | N. GUERRERO | M. Toci | Operations | BackEnd | 112 | 59 | ON GOING | 0% | 2024 | 14 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 8.696% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-6 | HR | AMS - HR - Web App -2024 | EssilorLuxottica | N. GUERRERO | N. GUERRERO | Delivery AMS | PM - Project Governance | 112 | 59 | ON GOING | 0% | 2024 | 7.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1 | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 4.167% | 4.762% | 4.348% | 4.762% | 4.545%
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-6 | HR | AMS - HR - Web App -2024 | EssilorLuxottica | N. GUERRERO | R. Marasca | Delivery Projects | Analysis | 112 | 59 | ON GOING | 0% | 2024 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 0% | 4.762% | 4.348% | 4.762% | 0%
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-6 | HR | AMS - HR - Web App -2024 | EssilorLuxottica | N. GUERRERO | S. Beltrami | Operations | FrontEnd | 112 | 59 | ON GOING | 0% | 2024 | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 0% | 4.762% | 4.348% | 4.762% | 4.545%
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-31 | HR | CR - HR - Web App - 2024 | EssilorLuxottica | N. GUERRERO | A. Nastasi | Operations | DataManagement | 35 | 59 | ON GOING | 169% | 2024 | 3 | [5 empty] | 0.5 | 0.5 |  | 1 | 0.5 | 0.5 |  | 0% | 0% | 0% | 0% | 0% | 2.5% | 2.174% | 0% | 4.762% | 2.174% | 2.381% | 0%
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-31 | HR | CR - HR - Web App - 2024 | EssilorLuxottica | N. GUERRERO | L. Carloni | Operations | Data Engineering | 35 | 59 | ON GOING | 169% | 2024 | 0 |  | 0.5 | 0.5 | [9 empty] | 0% | 2.5% | 2.381% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-31 | HR | CR - HR - Web App - 2024 | EssilorLuxottica | N. GUERRERO | M. Mannarino | Operations | Data Engineering | 35 | 59 | ON GOING | 169% | 2024 | 3 |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 |  | 0% | 0% | 0% | 2.273% | 2.5% | 2.5% | 2.174% | 0% | 2.381% | 2.174% | 2.381% | 0%
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-31 | HR | CR - HR - Web App - 2024 | EssilorLuxottica | N. GUERRERO | M. Porcu | Operations | Technical Leader | 35 | 59 | ON GOING | 169% | 2024 | 8.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 3 | 3 | 0% | 2.5% | 2.381% | 2.273% | 2.5% | 2.5% | 2.174% | 0% | 2.381% | 2.174% | 14.29% | 13.64%
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-31 | HR | CR - HR - Web App - 2024 | EssilorLuxottica | N. GUERRERO | M. Toci | Operations | BackEnd | 35 | 59 | ON GOING | 169% | 2024 | 14 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 8 | 2.778% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 0% | 4.762% | 4.348% | 4.762% | 36.36%
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-31 | HR | CR - HR - Web App - 2024 | EssilorLuxottica | N. GUERRERO | N. GUERRERO | Delivery AMS | PM - Project Governance | 35 | 59 | ON GOING | 169% | 2024 | 1.4 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 1.111% | 1% | 0.9524% | 0.9091% | 1% | 1% | 0.8696% | 0% | 0.9524% | 0.8696% | 0.9524% | 0.9091%
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-31 | HR | CR - HR - Web App - 2024 | EssilorLuxottica | N. GUERRERO | R. Marasca | Delivery Projects | Analysis | 35 | 59 | ON GOING | 169% | 2024 | 3.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 2.778% | 2.5% | 2.381% | 2.273% | 2.5% | 2.5% | 2.174% | 0% | 2.381% | 2.174% | 2.381% | 2.273%
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-31 | HR | CR - HR - Web App - 2024 | EssilorLuxottica | N. GUERRERO | S. Beltrami | Operations | FrontEnd | 35 | 59 | ON GOING | 169% | 2024 | 26.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 12 | 12 | 5.556% | 2.5% | 2.381% | 2.273% | 2.5% | 2.5% | 2.174% | 0% | 2.381% | 2.174% | 57.14% | 54.55%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | A. De Sanctis | Operations | DataManagement | 0 | 0 | CLOSED | 100% | 2024 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | A. Nastasi | Operations | DataManagement | 0 | 0 | CLOSED | 100% | 2024 | 34 |  |  | 5 | 16 | 17 | 17 | [6 empty] | 0% | 0% | 23.81% | 72.73% | 85% | 85% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | A. Torone | Delivery AMS | FrontEnd | 0 | 0 | CLOSED | 100% | 2024 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | F. D'Alberto | Operations | DataManagement | 0 | 0 | CLOSED | 100% | 2024 | 5 | 1 | 1 | 1 | 1 | 5 | [7 empty] | 5.556% | 5% | 4.762% | 4.545% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | F. Plebani | Operations | DataManagement | 0 | 0 | CLOSED | 100% | 2024 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | G. Cataldo | Operations | DataManagement | 0 | 0 | CLOSED | 100% | 2024 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | I. Bressan | Operations | BackEnd | 0 | 0 | CLOSED | 100% | 2024 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | [6 empty] | 27.78% | 25% | 23.81% | 22.73% | 25% | 25% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | M. Migliorati | Operations | FrontEnd | 0 | 0 | CLOSED | 100% | 2024 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | N. GUERRERO | Delivery AMS | PM - Project Governance | 0 | 0 | CLOSED | 100% | 2024 | 36 | 18 | 18 | 18 | 18 | 18 | 18 | [6 empty] | 100% | 90% | 85.71% | 81.82% | 90% | 90% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | R. Alves | Operations | BackEnd | 0 | 0 | CLOSED | 100% | 2024 | 2 |  | 1 | 1 | 1 | 1 | 1 | [6 empty] | 0% | 5% | 4.762% | 4.545% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | R. Marasca | Delivery Projects | Data Integrator | 0 | 0 | CLOSED | 100% | 2024 | 1 | [5 empty] | 1 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | W. Morandelli | Operations | FrontEnd | 0 | 0 | CLOSED | 100% | 2024 | 32 | 16 | 16 | 16 | 16 | 16 | 16 | [6 empty] | 88.89% | 80% | 76.19% | 72.73% | 80% | 80% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | A. De Sanctis | Operations | DataManagement | 0 | 0 | ON GOING | 80% | 2024 | 65 | [6 empty] | 1 |  | 21 | 23 | 2 | 18 | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 0% | 100% | 100% | 9.524% | 81.82%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | A. Nastasi | Operations | DataManagement | 0 | 0 | ON GOING | 80% | 2024 | 57 | [6 empty] | 2 |  | 14 | 15 | 14 | 12 | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 0% | 66.67% | 65.22% | 66.67% | 54.55%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | A. Torone | Delivery AMS | FrontEnd | 0 | 0 | ON GOING | 80% | 2024 | 2.5 | [6 empty] | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0% | 0% | 0% | 0% | 0% | 0% | 2.174% | 0% | 2.381% | 2.174% | 2.381% | 2.273%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | F. Plebani | Operations | DataManagement | 0 | 0 | ON GOING | 80% | 2024 | 8 | [6 empty] | 4 |  | 4 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 17.39% | 0% | 19.05% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | G. Cataldo | Operations | DataManagement | 0 | 0 | ON GOING | 80% | 2024 | 16 | [6 empty] | 5 |  | 5 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 0% | 23.81% | 8.696% | 9.524% | 9.091%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | G. Fiorentini | Operations | DataManagement | 0 | 0 | ON GOING | 80% | 2024 | 2 | [6 empty] | 1 |  | 1 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 0% | 4.762% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | G. Galati | Delivery AMS | DataManagement | 0 | 0 | ON GOING | 80% | 2024 | 20 | [8 empty] | 5 | 5 | 5 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 23.81% | 21.74% | 23.81% | 22.73%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | G. Mordà | Operations | Data Management | 0 | 0 | ON GOING | 80% | 2024 | 42 | [8 empty] | 6 | 6 | 14 | 16 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 28.57% | 26.09% | 66.67% | 72.73%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | I. Bressan | Operations | BackEnd | 0 | 0 | ON GOING | 80% | 2024 | 7 | [6 empty] | 5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 0% | 2.381% | 2.174% | 2.381% | 2.273%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | L. Cariglia | Operations | DataManagement | 0 | 0 | ON GOING | 80% | 2024 | 30 | [6 empty] | 6 |  | 6 | 6 | 6 | 6 | 0% | 0% | 0% | 0% | 0% | 0% | 26.09% | 0% | 28.57% | 26.09% | 28.57% | 27.27%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | M. Migliorati | Operations | FrontEnd | 0 | 0 | ON GOING | 80% | 2024 | 66 | [6 empty] | 2 |  | 21 | 23 | 2 | 18 | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 0% | 100% | 100% | 9.524% | 81.82%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | M. Vimercati | Operations | Data Management | 0 | 0 | ON GOING | 80% | 2024 | 6 | [9 empty] | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 9.524% | 9.091%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | N. GUERRERO | Delivery AMS | PM - Project Governance | 0 | 0 | ON GOING | 80% | 2024 | 90 | [6 empty] | 18 |  | 18 | 18 | 18 | 18 | 0% | 0% | 0% | 0% | 0% | 0% | 78.26% | 0% | 85.71% | 78.26% | 85.71% | 81.82%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | R. Marasca | Delivery Projects | Data Integrator | 0 | 0 | ON GOING | 80% | 2024 | 9 | [6 empty] | 1 |  | 1 | 1 | 1 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 0% | 4.762% | 4.348% | 4.762% | 22.73%
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | W. Morandelli | Operations | FrontEnd | 0 | 0 | ON GOING | 80% | 2024 | 37 | [6 empty] | 16 |  | 21 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 69.57% | 0% | 100% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | IAA | OTHER | CC - Attività |  | O. Sagazio | A. Strada | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0% | 2024 | 62.4 |  |  | 8.4 | 7.6 | 8 | 8 | 9.2 | 4.8 | 8.4 | 9.2 | 8 | 6.8 | 0% | 0% | 40% | 34.55% | 40% | 40% | 40% | 40% | 40% | 40% | 38.1% | 30.91%
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | IAA | OTHER | CC - Attività |  | O. Sagazio | G. Sironi | Operations | Team Management | 0 | 0 | ON GOING | 0% | 2024 | 34 |  |  |  |  | 8 | 6 | 3 | 2 | 4 | 4 | 4 | 3 | 0% | 0% | 0% | 0% | 40% | 30% | 13.04% | 16.67% | 19.05% | 17.39% | 19.05% | 13.64%
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | IAA | OTHER | CC - Attività |  | O. Sagazio | L. Roberto | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0% | 2024 | 51 |  |  | 5 | 2 | 2 | 4 | 7 | 7 | 7 | 8 | 8 | 8 | 0% | 0% | 23.81% | 9.091% | 10% | 20% | 30.43% | 58.33% | 33.33% | 34.78% | 38.1% | 36.36%
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | IAA | OTHER | CC - Attività |  | O. Sagazio | M. Porcu | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0% | 2024 | 62.4 |  |  | 8.4 | 7.6 | 8 | 8 | 9.2 | 4.8 | 8.4 | 9.2 | 8 | 6.8 | 0% | 0% | 40% | 34.55% | 40% | 40% | 40% | 40% | 40% | 40% | 38.1% | 30.91%
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | IAA | OTHER | CC - supporto CC Leader come Deputy |  | O. Sagazio | P. Anzellotti | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0% | 2024 | 37 |  |  | 5.25 | 4.75 | 5 | 5 | 5 | 3 | 5 | 5 | 5 | 4 | 0% | 0% | 25% | 21.59% | 25% | 25% | 21.74% | 25% | 23.81% | 21.74% | 23.81% | 18.18%
PROSPECT | PRJ |  | 2024 |  |  | N/A | N/A | OTHER | DASHBOARDING FOR SAPWIN | EssilorLuxottica | O. Sagazio | t.b.d. | t.b.d. | FrontEnd | 0 | 0 |  | 0% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-08-31 | N/A | ATD | OTHER | Formazione | Abstract | O. Sagazio | G. Tartaglia | Operations | BackEnd | 0 | 0 | ON GOING | 5% | 2024 | 27 |  |  | 21 | 19 | 2 | 2 | 23 | [5 empty] | 0% | 0% | 100% | 86.36% | 10% | 10% | 100% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-01-30 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | A. Nastasi | Operations | DataManagement | 110 | 0 | CLOSED | 100% | 2024 | 1 |  |  | 1.5 | 0.95 | 1 | [7 empty] | 0% | 0% | 7.143% | 4.318% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-04-01 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | D. Scalia | Operations | BackEnd | 110 | 0 | CLOSED | 100% | 2024 | 0 | 1.8 | 12.6 | 12.6 | [9 empty] | 10% | 63% | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-04-01 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | D. Scarci | Operations | FrontEnd | 110 | 0 | CLOSED | 100% | 2024 | 0 | 18 | 21 | 21 | [9 empty] | 100% | 105% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-04-01 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | E. Soldoni | Operations | Graphic Interface | 110 | 0 | CLOSED | 100% | 2024 | 0 | 9 | 1.5 | 1.5 | [9 empty] | 50% | 7.5% | 7.143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-04-01 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | E. Uliu | Operations | FrontEnd | 110 | 0 | CLOSED | 100% | 2024 | 0 | 9 | 1.5 | 1.5 | [9 empty] | 50% | 7.5% | 7.143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-01-30 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | F. D'Alberto | Operations | DataManagement | 110 | 0 | CLOSED | 100% | 2024 | 1 |  |  | 1.5 | 0.95 | 1 | [7 empty] | 0% | 0% | 7.143% | 4.318% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-04-01 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | G. De Feo | Delivery Projects | PMO - Project Management Officer | 110 | 0 | CLOSED | 100% | 2024 | 2 |  |  | 4.2 | 3.8 | 2 | [7 empty] | 0% | 0% | 20% | 17.27% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-04-01 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | L. Carloni | Operations | Data Engineering | 110 | 0 | CLOSED | 100% | 2024 | 0 | 18 | 21 | 1.5 | [9 empty] | 100% | 105% | 7.143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-04-01 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | L. Tironese | Operations | Architecture Analysis | 110 | 0 | CLOSED | 100% | 2024 | 0 | 18 | 21 | 21 | [9 empty] | 100% | 105% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-01-30 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | M. Porcu | Operations | Architecture Analysis | 110 | 0 | CLOSED | 100% | 2024 | 1 |  |  | 9.45 | 8.55 | 1 | [7 empty] | 0% | 0% | 45% | 38.86% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-01-30 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | M. Toci | Operations | BackEnd | 110 | 0 | CLOSED | 100% | 2024 | 2 |  |  | 4.2 | 3.8 | 2 | [7 empty] | 0% | 0% | 20% | 17.27% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-04-01 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | O. Sagazio | Operations | PM - Project Governance | 110 | 0 | CLOSED | 100% | 2024 | 0 | 7.2 | 8.4 | 8.4 | [9 empty] | 40% | 42% | 40% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-04-01 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | P. Anzellotti | Operations | PM - Project Governance | 110 | 0 | CLOSED | 100% | 2024 | 1 |  |  | 1.5 | 0.95 | 1 | [7 empty] | 0% | 0% | 7.143% | 4.318% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-04-01 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | R. Marasca | Delivery Projects | Analysis | 110 | 0 | CLOSED | 100% | 2024 | 3 |  | 4 | 4 | 3 | 3 | [7 empty] | 0% | 20% | 19.05% | 13.64% | 15% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-01-30 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | S. Beltrami | Operations | FrontEnd | 110 | 0 | CLOSED | 100% | 2024 | 4 |  |  | 8.4 | 7.6 | 4 | [7 empty] | 0% | 0% | 40% | 34.55% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ | Scrum | 2024 | 2024-11-15 | 2025-01-14 | N/A | N/A | RETAIL | HR - BUONI SCONTO - LSA | EssilorLuxottica | P. Anzellotti | A. Lorena | Operations | FrontEnd | 22 | 0 | ON GOING | 0% | 2024 | 5 | [10 empty] | 3 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 9.091%
LEAD | PRJ | Scrum | 2024 | 2024-11-15 | 2025-01-14 | N/A | N/A | RETAIL | HR - BUONI SCONTO - LSA | EssilorLuxottica | P. Anzellotti | G. TARTAGLIA | Operations | BackEnd | 22 | 0 | ON GOING | 0% | 2024 | 5 | [10 empty] | 3 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 9.091%
LEAD | PRJ | Scrum | 2024 | 2024-11-15 | 2025-01-14 | N/A | N/A | RETAIL | HR - BUONI SCONTO - LSA | EssilorLuxottica | P. Anzellotti | P. Anzellotti | Operations | Techincal Leader | 22 | 0 | ON GOING | 0% | 2024 | 7 | [10 empty] | 4 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 19.05% | 13.64%
CONTRACT | PRJ | Scrum | 2024 | 2024-02-15 | 2024-07-01 | ABS24138 | AHBSDW | HR | HR - BUONI SCONTO - W2 | EssilorLuxottica | P. Anzellotti | N. Pescione | Operations | BackEnd | 156 | 0 | CLOSED | 100% | 2024 | 4 |  |  | 1.5 | 9.5 | 1 | 3 | [6 empty] | 0% | 0% | 7.143% | 43.18% | 5% | 15% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-02-15 | 2024-07-01 | ABS24138 | AHBSDW | HR | HR - BUONI SCONTO - W2 | EssilorLuxottica | P. Anzellotti | P. Anzellotti | Operations | PM - Project Governance | 156 | 0 | CLOSED | 100% | 2024 | 18 |  |  | 12.6 | 11.4 | 12 | 6 | [6 empty] | 0% | 0% | 60% | 51.82% | 60% | 30% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-02-15 | 2024-07-01 | ABS24138 | AHBSDW | HR | HR - BUONI SCONTO - W2 | EssilorLuxottica | P. Anzellotti | R. Marasca | Delivery Projects | Analysis | 156 | 0 | CLOSED | 100% | 2024 | 0 | 5 | 4 | 4 | 4 | [8 empty] | 27.78% | 20% | 19.05% | 18.18% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-02-15 | 2024-07-01 | ABS24138 | AHBSDW | HR | HR - BUONI SCONTO - W2 | EssilorLuxottica | P. Anzellotti | S. Delle Fave | Operations | FrontEnd | 156 | 0 | CLOSED | 100% | 2024 | 9 |  |  | 7.35 | 6.65 | 7 | 2 | [6 empty] | 0% | 0% | 35% | 30.23% | 35% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-01-01 | 2024-12-01 | ABS24138 | AHBSDW | HR | HR - BUONI SCONTO - W2 - CR | EssilorLuxottica | P. Anzellotti | M. Toci | Operations | BackEnd | 17 | 0 | CLOSED | 100% | 2024 | 2 | [6 empty] | 2 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-01-01 | 2024-12-01 | ABS24138 | AHBSDW | HR | HR - BUONI SCONTO - W2 - CR | EssilorLuxottica | P. Anzellotti | P. Anzellotti | Operations | Techincal Leader | 17 | 0 | CLOSED | 100% | 2024 | 4 | [6 empty] | 4 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 17.39% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2024 | 2024-01-01 | 2024-12-01 | ABS24138 | AHBSDW | HR | HR - BUONI SCONTO - W2 - CR | EssilorLuxottica | P. Anzellotti | S. Delle Fave | Operations | BackEnd | 17 | 0 | CLOSED | 100% | 2024 | 2 | [6 empty] | 2 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ | Scrum | 2024 | 2024-01-01 | 2024-12-01 | ABS24344 | ABS0008 | RETAIL | HR - BUONI SCONTO - W3 | EssilorLuxottica | P. Anzellotti | N. Pescione | Operations | BackEnd | 42 | 0 | CLOSED | 0% | 2024 | 4 | [8 empty] | 1 | 2 | 1 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762% | 8.696% | 4.762% | 0%
LEAD | PRJ | Scrum | 2024 | 2024-01-01 | 2024-12-01 | ABS24344 | ABS0008 | RETAIL | HR - BUONI SCONTO - W3 | EssilorLuxottica | P. Anzellotti | P. Anzellotti | Operations | Techincal Leader | 42 | 0 | CLOSED | 0% | 2024 | 14 | [8 empty] | 3 | 8 | 3 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 34.78% | 14.29% | 0%
LEAD | PRJ | Scrum | 2024 | 2024-01-01 | 2024-12-01 | ABS24344 | ABS0008 | RETAIL | HR - BUONI SCONTO - W3 | EssilorLuxottica | P. Anzellotti | S. Delle Fave | Operations | BackEnd | 42 | 0 | CLOSED | 0% | 2024 | 10 | [8 empty] | 2 | 6 | 2 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.524% | 26.09% | 9.524% | 0%
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Carrier Manager Activities | Abstract | P. Pieroni | A. Di Pietro | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0% | 2024 | 7 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Carrier Manager Activities | Abstract | P. Pieroni | I. Bressan | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0% | 2024 | 7 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Carrier Manager Activities | Abstract | P. Pieroni | N. Fragale | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0% | 2024 | 7 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | EPM | Carrier Manager Activities | Abstract | P. Pieroni | P. Pieroni | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0% | 2024 | 6 | [5 empty] | 1 | 1 |  | 1 | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 5% | 4.348% | 0% | 4.762% | 4.348% | 4.762% | 4.545%
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ABS0007 | PRACTICE DI | CDC/AREA MANAGEMENT | ABSTRACT | P. Pieroni | P. Pieroni | Operations | PM - Project Governance | 30 | 20 | ON GOING | 100% | 2024 | 30 | [5 empty] | 5 | 5 |  | 5 | 5 | 5 | 5 | 0% | 0% | 0% | 0% | 0% | 25% | 21.74% | 0% | 23.81% | 21.74% | 23.81% | 22.73%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-09-01 | 2024-12-31 | N/A | ATD | OTHER | Coaching | Abstract | P. Pieroni | F. De Pedis | Operations | BackEnd | 15 | 0 | ON GOING | 0% | 2024 | 15 | [8 empty] | 4 | 4 | 4 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 19.05% | 17.39% | 19.05% | 13.64%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-09-01 | 2024-12-31 | N/A | ATD | OTHER | Coaching | Abstract | P. Pieroni | I. Bressan | Operations | BackEnd | 15 | 0 | ON GOING | 0% | 2024 | 15 | [8 empty] | 4 | 4 | 4 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 19.05% | 17.39% | 19.05% | 13.64%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-09-01 | 2024-12-31 | N/A | ATD | OTHER | Coaching | Abstract | P. Pieroni | L. Franco | Operations | BackEnd | 15 | 0 | ON GOING | 0% | 2024 | 15 | [8 empty] | 4 | 4 | 4 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 19.05% | 17.39% | 19.05% | 13.64%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-09-01 | 2024-11-30 | N/A | ATD | OTHER | Corsi OneStream - Essentials | Abstract | P. Pieroni | I. Bressan | Operations | Solution Architect | 4 | 0 | ON GOING | 0% | 2024 | 10 | [9 empty] | 4 | 4 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 17.39% | 19.05% | 9.091%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-09-01 | 2024-11-30 | N/A | ATD | OTHER | Corsi OneStream - Essentials | Abstract | P. Pieroni | P. Pieroni | Operations | BackEnd | 4 | 0 | ON GOING | 0% | 2024 | 11 | [8 empty] | 1 | 5 | 3 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762% | 21.74% | 14.29% | 9.091%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione Oracle FCCS | Abstract | P. Pieroni | F. Atanasio | Operations | BackEnd | 3 | 0 | ON GOING | 0% | 2024 | 5 | [6 empty] | 3 |  |  | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 0% | 0% | 8.696% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione Oracle FCCS | Abstract | P. Pieroni | F. De Pedis | Operations | BackEnd | 3 | 0 | ON GOING | 0% | 2024 | 5 | [6 empty] | 3 |  |  | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 0% | 0% | 8.696% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | ATD | OTHER | Formazione Oracle FCCS | Abstract | P. Pieroni | L. Franco | Operations | BackEnd | 3 | 0 | ON GOING | 0% | 2024 | 5 | [6 empty] | 3 |  |  | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 0% | 0% | 8.696% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 |  |  | N/A | DSL | FINANCE | Laboratorio per Lux |  | P. Pieroni | C. Paz | Delivery Projects | Analysis | 0 | 0 | CLOSED | 100% | 2024 | 14 | 14.4 | 16.8 | 16.8 | 5.7 | 6 | 8 | [6 empty] | 80% | 84% | 80% | 25.91% | 30% | 40% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 |  |  | N/A | DSL | FINANCE | Laboratorio per Lux |  | P. Pieroni | F. Atanasio | Operations | BackEnd | 0 | 0 | ON GOING | 0% | 2024 | 0 |  | 4.2 | 7.35 | [9 empty] | 0% | 21% | 35% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 |  |  | N/A | DSL | FINANCE | Laboratorio per Lux |  | P. Pieroni | L. Mangili | Operations | BackEnd | 0 | 0 | ON GOING | 0% | 2024 | 0 | 1.8 | 21 | 21 | [9 empty] | 10% | 105% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 |  |  | N/A | DSL | FINANCE | Laboratorio per Lux |  | P. Pieroni | M. Favalli | Operations | BackEnd | 0 | 0 | ON GOING | 0% | 2024 | 0 | 9 | 14.7 | 18.9 | 11.4 | [8 empty] | 50% | 73.5% | 90% | 51.82% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 |  |  | N/A | DSL | FINANCE | Laboratorio per Lux |  | P. Pieroni | P. Buonasorte | Operations | BackEnd | 0 | 0 | ON GOING | 0% | 2024 | 0 | 9 | 14.7 | 18.9 | [9 empty] | 50% | 73.5% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-05-31 | N/A | ABS0007 | FINANCE | POC per Lux | EssilorLuxottica | P. Pieroni | C. Paz | Delivery Projects | Analysis | 0 | 0 | ON GOING | 0% | 2024 | 0 | 9 | 1.5 | 1.5 | 5.7 | [8 empty] | 50% | 7.5% | 7.143% | 25.91% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-05-31 | N/A | ABS0007 | FINANCE | POC per Lux | EssilorLuxottica | P. Pieroni | F. Atanasio | Operations | BackEnd | 0 | 0 | ON GOING | 0% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-05-31 | N/A | ABS0007 | FINANCE | POC per Lux | EssilorLuxottica | P. Pieroni | L. Mangili | Operations | BackEnd | 0 | 0 | ON GOING | 0% | 2024 | 0 | 1.8 | 1.5 | 1.5 | [9 empty] | 10% | 7.5% | 7.143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-05-31 | N/A | ABS0007 | FINANCE | POC per Lux | EssilorLuxottica | P. Pieroni | M. Favalli | Operations | BackEnd | 0 | 0 | ON GOING | 0% | 2024 | 0 | 9 | 1.5 | 1.5 | 9.5 | [8 empty] | 50% | 7.5% | 7.143% | 43.18% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-05-31 | N/A | ABS0007 | FINANCE | POC per Lux | EssilorLuxottica | P. Pieroni | P. Buonasorte | Operations | BackEnd | 0 | 0 | ON GOING | 0% | 2024 | 0 | 9 | 1.5 | 1.5 | [9 empty] | 50% | 7.5% | 7.143% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Time&Materials | 2024 | 2024-04-01 | 2024-12-31 | ABS24342 | ABS24342 | EPM | RTT_Supporto_Piattaforma_Oracle_EPM | RTT | P. Pieroni | M. Favalli | Operations | BackEnd | 10 | 10 | CLOSED | 100% | 2024 | 5 | [6 empty] | 5 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Time&Materials | 2024 | 2024-04-01 | 2024-12-31 | ABS24342 | ABS24342 | EPM | RTT_Supporto_Piattaforma_Oracle_EPM | RTT | P. Pieroni | P. Pieroni | Operations | BackEnd | 10 | 10 | CLOSED | 100% | 2024 | 5.5 |  |  |  | 2 | 1 | 4 | 0.5 | [5 empty] | 0% | 0% | 0% | 9.091% | 5% | 20% | 2.174% | 0% | 0% | 0% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-09-01 | 2024-11-30 | N/A | ATD | OTHER | Training on the Job FCCS - Pro Vision Group (xView) | Abstract | P. Pieroni | F. Atanasio | Operations | BackEnd | 10 | 0 | ON GOING | 0% | 2024 | 10 | [8 empty] | 3 | 5 | 2 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 21.74% | 9.524% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-09-01 | 2024-11-30 | N/A | ATD | OTHER | Training on the Job FCCS - Pro Vision Group (xView) | Abstract | P. Pieroni | F. De Pedis | Operations | BackEnd | 10 | 0 | ON GOING | 0% | 2024 | 10 | [8 empty] | 3 | 5 | 2 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 21.74% | 9.524% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-09-01 | 2024-11-30 | N/A | ATD | OTHER | Training on the Job FCCS - Pro Vision Group (xView) | Abstract | P. Pieroni | M. Sorrentino | Consolidated & Tax | BackEnd | 10 | 0 | ON GOING | 0% | 2024 | 10 | [8 empty] | 3 | 5 | 2 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 21.74% | 9.524% | 0%
CONTRACT | AMS |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | EURMP | EPM | URMET - AMS Essbase | URMET | P. Pieroni | A. Di Pietro | Operations | BackEnd | 30 | 0 | ON GOING | 0% | 2024 | 1 | 0.9 | 1.5 | 2.1 | 0.95 | 1 | [7 empty] | 5% | 7.5% | 10% | 4.318% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2024-01-01 | 2024-12-31 | N/A | EURMP | EPM | URMET - AMS Essbase | URMET | P. Pieroni | P. Pieroni | Operations | Analysis | 30 | 0 | ON GOING | 0% | 2024 | 1 | 0.9 | 1.5 | 2.1 | 0.95 | 1 | [7 empty] | 5% | 7.5% | 10% | 4.318% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ |  | 2024 |  |  | N/A | N/A | R&D | R&D Lucy Control Tower con Generative AI | EssilorLuxottica | R. RUGGERI | A. Imbimbo | Operations | Data Scientist | 35 | 27 | CLOSED | 100% | 2024 | 22 |  |  |  | 5 | 7 | 7 | 7 |  | 1 |  |  |  | 0% | 0% | 0% | 22.73% | 35% | 35% | 30.43% | 0% | 4.762% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-07-15 | 2024-10-15 | N/A | N/A | EPM | Essilor Wave1 - Upload Statutory Data From FDW | EssilorLuxottica | S. Preziosa | A. Albanese | Delivery Projects | Analysis | 20 | 0 | ON HOLD | 0% | 2024 | 7 | [6 empty] | 2 | 1 | 2 | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 8.333% | 9.524% | 8.696% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-10-15 | N/A | N/A | EPM | Essilor Wave1 - Upload Statutory Data From FDW | EssilorLuxottica | S. Preziosa | P. Singh | AREA TECH | BackEnd | 20 | 0 | ON HOLD | 0% | 2024 | 10 | [6 empty] | 5 | 1 | 2 | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 8.333% | 9.524% | 8.696% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-10-15 | N/A | N/A | EPM | Essilor Wave1 - Upload Statutory Data From FDW | EssilorLuxottica | S. Preziosa | S. Preziosa | Delivery Projects | Analysis | 20 | 0 | ON HOLD | 0% | 2024 | 10 | [6 empty] | 5 | 1 | 2 | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 8.333% | 9.524% | 8.696% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24044 | ABA2W | RETAIL | BULLSEYE AMS 2024 | EssilorLuxottica | T. Porzio | A. Ferrari | Operations | DataManagement | 200 | 78.3 | CLOSED | 0% | 2024 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 0% | 4.762% | 4.348% | 4.762% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24044 | ABA2W | RETAIL | BULLSEYE AMS 2024 | EssilorLuxottica | T. Porzio | A. Lorena | Operations | FrontEnd | 200 | 78.3 | CLOSED | 0% | 2024 | 14 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 8.696% | 8.333% | 9.524% | 8.696% | 9.524% | 4.545%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24044 | ABA2W | RETAIL | BULLSEYE AMS 2024 | EssilorLuxottica | T. Porzio | A. PIROLA | Operations | FrontEnd | 200 | 78.3 | CLOSED | 0% | 2024 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24044 | ABA2W | RETAIL | BULLSEYE AMS 2024 | EssilorLuxottica | T. Porzio | A. Vladi | Operations | DataManagement | 200 | 78.3 | CLOSED | 0% | 2024 | 16 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 8.696% | 16.67% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24044 | ABA2W | RETAIL | BULLSEYE AMS 2024 | EssilorLuxottica | T. Porzio | F. D'Alberto | Operations | DataManagement/SQL | 200 | 78.3 | CLOSED | 0% | 2024 | 45 |  | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 6 | 6 | 6 | 5 | 0% | 30% | 28.57% | 27.27% | 30% | 30% | 26.09% | 33.33% | 28.57% | 26.09% | 28.57% | 22.73%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24044 | ABA2W | RETAIL | BULLSEYE AMS 2024 | EssilorLuxottica | T. Porzio | F. Origlia | Operations | Architecture Analysis | 200 | 78.3 | CLOSED | 0% | 2024 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [7 empty] | 2.778% | 2.5% | 2.381% | 2.273% | 2.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24044 | ABA2W | RETAIL | BULLSEYE AMS 2024 | EssilorLuxottica | T. Porzio | F. Origlia | Operations | BackEnd | 200 | 78.3 | CLOSED | 0% | 2024 | 1 | 1 | 1 | 1 | 1 | 1 | [7 empty] | 5.556% | 5% | 4.762% | 4.545% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24044 | ABA2W | RETAIL | BULLSEYE AMS 2024 | EssilorLuxottica | T. Porzio | F. Spacagna | Operations | BackEnd | 200 | 78.3 | CLOSED | 0% | 2024 | 7 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 9.091%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24044 | ABA2W | RETAIL | BULLSEYE AMS 2024 | EssilorLuxottica | T. Porzio | L. Franceschini | Delivery Projects | PM - Project Governance | 200 | 78.3 | CLOSED | 0% | 2024 | 2 | 1 | 2 | 2 | 2 | 2 | [7 empty] | 5.556% | 10% | 9.524% | 9.091% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24044 | ABA2W | RETAIL | BULLSEYE AMS 2024 | EssilorLuxottica | T. Porzio | M. Vianelli | Delivery Projects | Analysis | 200 | 78.3 | CLOSED | 0% | 2024 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 |  | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 8.696% | 0% | 9.524% | 8.696% | 9.524% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24044 | ABA2W | RETAIL | BULLSEYE AMS 2024 | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 200 | 78.3 | CLOSED | 0% | 2024 | 21.5 | [5 empty] | 3 | 3 | 0.5 | 2 | 3 | 5 | 5 | 0% | 0% | 0% | 0% | 0% | 15% | 13.04% | 4.167% | 9.524% | 13.04% | 23.81% | 22.73%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24353 | ABS24353 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 1H | EssilorLuxottica | T. Porzio | A. Ferrari | Operations | BackEnd | 100 | 70 | CLOSED | 100% | 2024 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24353 | ABS24353 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 1H | EssilorLuxottica | T. Porzio | A. Lorena | Operations | FrontEnd | 100 | 70 | CLOSED | 100% | 2024 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | [6 empty] | 11.11% | 10% | 9.524% | 9.091% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24353 | ABS24353 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 1H | EssilorLuxottica | T. Porzio | A. Nastasi | Operations | DataManagement | 100 | 70 | CLOSED | 100% | 2024 | 0 | 2 | 2 | 2 | [9 empty] | 11.11% | 10% | 9.524% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24353 | ABS24353 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 1H | EssilorLuxottica | T. Porzio | A. PIROLA | Operations | FrontEnd | 100 | 70 | CLOSED | 100% | 2024 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24353 | ABS24353 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 1H | EssilorLuxottica | T. Porzio | A. Vladi | Operations | Team Leadership | 100 | 70 | CLOSED | 100% | 2024 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24353 | ABS24353 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 1H | EssilorLuxottica | T. Porzio | F. D'Alberto | Operations | BackEnd | 100 | 70 | CLOSED | 100% | 2024 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | [6 empty] | 27.78% | 25% | 23.81% | 22.73% | 25% | 25% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24353 | ABS24353 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 1H | EssilorLuxottica | T. Porzio | L. Franceschini | Delivery Projects | PM - Project Governance | 100 | 70 | CLOSED | 100% | 2024 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24353 | ABS24353 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 1H | EssilorLuxottica | T. Porzio | M. Vianelli | Delivery Projects | Analysis | 100 | 70 | CLOSED | 100% | 2024 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24354 | ABS24354 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 2H | EssilorLuxottica | T. Porzio | A. Ferrari | Operations | BackEnd | 100 | 30.5 | CLOSED | 0% | 2024 | 13 | [9 empty] | 5 | 5 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 23.81% | 13.64%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24354 | ABS24354 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 2H | EssilorLuxottica | T. Porzio | A. Lorena | Operations | FrontEnd | 100 | 30.5 | CLOSED | 0% | 2024 | 9 | [9 empty] | 3 | 3 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 14.29% | 13.64%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24354 | ABS24354 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 2H | EssilorLuxottica | T. Porzio | A. Nastasi | Operations | DataManagement | 100 | 30.5 | CLOSED | 0% | 2024 | 6 | [9 empty] | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 9.524% | 9.091%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24354 | ABS24354 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 2H | EssilorLuxottica | T. Porzio | A. PIROLA | Operations | FrontEnd | 100 | 30.5 | CLOSED | 0% | 2024 | 1.5 | [9 empty] | 0.5 | 0.5 | 0.5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.174% | 2.381% | 2.273%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24354 | ABS24354 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 2H | EssilorLuxottica | T. Porzio | A. Vladi | Operations | Team Leadership | 100 | 30.5 | CLOSED | 0% | 2024 | 3 | [9 empty] | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 4.762% | 4.545%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24354 | ABS24354 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 2H | EssilorLuxottica | T. Porzio | F. D'Alberto | Operations | BackEnd | 100 | 30.5 | CLOSED | 0% | 2024 | 18 | [9 empty] | 6 | 6 | 6 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 26.09% | 28.57% | 27.27%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24354 | ABS24354 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 2H | EssilorLuxottica | T. Porzio | M. Vianelli | Delivery Projects | Analysis | 100 | 30.5 | CLOSED | 0% | 2024 | 6 | [9 empty] | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 9.524% | 9.091%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24354 | ABS24354 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 2H | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 100 | 30.5 | CLOSED | 0% | 2024 | 9 | [9 empty] | 3 | 3 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 14.29% | 13.64%
CONTRACT | AMS | Waterfall | 2024 | 2023-07-01 | 2024-06-30 | ABS24042 | AEEQ2 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | A. Di Pietro | Operations | BackEnd | 134 | 64 | CLOSED | 0% | 2024 | 5 |  | 3.15 | 2.1 | 2.85 | 3 | 2 | [6 empty] | 0% | 15.75% | 10% | 12.95% | 15% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2023-07-01 | 2024-06-30 | ABS24042 | AEEQ2 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | G. Minervini | Operations | BackEnd - Junior | 134 | 64 | CLOSED | 0% | 2024 | 8 | 3.6 | 4.2 | 4.2 | 3.8 | 4 | 4 | [6 empty] | 20% | 21% | 20% | 17.27% | 20% | 20% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2023-07-01 | 2024-06-30 | ABS24042 | AEEQ2 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | N. Fragale | Operations | Analysis | 134 | 64 | CLOSED | 0% | 2024 | 8 |  | 2 | 4.2 | 3.8 | 4 | 4 | [6 empty] | 0% | 10% | 20% | 17.27% | 20% | 20% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2023-07-01 | 2024-06-30 | ABS24042 | AEEQ2 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | O. BEN OTHMANE | Operations | BackEnd | 134 | 64 | CLOSED | 0% | 2024 | 8 | 3.6 | 4.2 | 4.2 | 3.8 | 4 | 4 | [6 empty] | 20% | 21% | 20% | 17.27% | 20% | 20% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2023-07-01 | 2024-06-30 | ABS24042 | AEEQ2 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | P. Pieroni | Operations | BackEnd | 134 | 64 | CLOSED | 0% | 2024 | 9 | 2.7 | 3.15 |  | 2.85 | 3 | 2 | 2 | 2 |  |  |  |  | 15% | 15.75% | 0% | 12.95% | 15% | 10% | 8.696% | 16.67% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2023-07-01 | 2024-06-30 | ABS24042 | AEEQ2 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | S. Preziosa | Delivery Projects | PM - Project Governance | 134 | 64 | CLOSED | 0% | 2024 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2023-07-01 | 2024-06-30 | ABS24042 | AEEQ2 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | V. Raso | Operations | BackEnd | 134 | 64 | CLOSED | 0% | 2024 | 8 | 3.6 | 4.2 | 4.2 | 3.8 | 4 | 4 | [6 empty] | 20% | 21% | 20% | 17.27% | 20% | 20% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS25063 | ABS25063 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2024 | EssilorLuxottica | T. Porzio | A. Di Pietro | Operations | BackEnd | 150 | 36 | CLOSED | 20% | 2024 | 14 | [6 empty] | 5 | 1 | 5 | 1 |  | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 8.333% | 23.81% | 4.348% | 0% | 9.091%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS25063 | ABS25063 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2024 | EssilorLuxottica | T. Porzio | E. Storti | Delivery Projects | BackEnd | 150 | 36 | CLOSED | 20% | 2024 | 11.5 | [6 empty] | 0.5 |  | 1 | 1 | 4 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 2.174% | 0% | 4.762% | 4.348% | 19.05% | 22.73%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS25063 | ABS25063 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2024 | EssilorLuxottica | T. Porzio | L. Franco | Operations | BackEnd | 150 | 36 | CLOSED | 20% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS25063 | ABS25063 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2024 | EssilorLuxottica | T. Porzio | L. Mangili | Operations | BackEnd | 150 | 36 | CLOSED | 20% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS25063 | ABS25063 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2024 | EssilorLuxottica | T. Porzio | M. Favalli | Operations | BackEnd - Junior | 150 | 36 | CLOSED | 20% | 2024 | 5 | [11 empty] | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 22.73%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS25063 | ABS25063 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2024 | EssilorLuxottica | T. Porzio | N. Fragale | Operations | BackEnd | 150 | 36 | CLOSED | 20% | 2024 | 16 | [6 empty] | 2 |  | 2 | 5 | 4 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 0% | 9.524% | 21.74% | 19.05% | 13.64%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS25063 | ABS25063 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2024 | EssilorLuxottica | T. Porzio | O. BEN OTHMANE | Operations | BackEnd - Junior | 150 | 36 | CLOSED | 20% | 2024 | 29 | [6 empty] | 9 | 2 | 9 | 4 | 2 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 39.13% | 16.67% | 42.86% | 17.39% | 9.524% | 13.64%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS25063 | ABS25063 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2024 | EssilorLuxottica | T. Porzio | P. Pieroni | Operations | BackEnd | 150 | 36 | CLOSED | 20% | 2024 | 15.05 | [6 empty] | 3.45 | 0.5 | 2.1 | 4 | 3 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 15% | 4.167% | 10% | 17.39% | 14.29% | 9.091%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS25063 | ABS25063 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2024 | EssilorLuxottica | T. Porzio | S. Preziosa | Delivery Projects | Analysis | 150 | 36 | CLOSED | 20% | 2024 | 14 | [6 empty] | 2 |  | 2 | 2 | 3 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 0% | 9.524% | 8.696% | 14.29% | 22.73%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS25063 | ABS25063 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2024 | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 150 | 36 | CLOSED | 20% | 2024 | 5 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 0% | 4.762% | 4.348% | 4.762% | 4.545%
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | N/A | N/A | EPM | Emerald - CR PLUS 2025 H1 | EssilorLuxottica | T. Porzio | C. Esposito | Consolidated & Tax | BackEnd | 40 | 0 | TO START | 0% | 2024 | 2 | [11 empty] | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.091%
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | N/A | N/A | EPM | Emerald - CR PLUS 2025 H1 | EssilorLuxottica | T. Porzio | E. Tosetto | Consolidated & Tax | BackEnd | 40 | 0 | TO START | 0% | 2024 | 2 | [11 empty] | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.091%
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | N/A | N/A | EPM | Emerald - CR PLUS 2025 H1 | EssilorLuxottica | T. Porzio | L. Pigazzini | Consolidated & Tax | BackEnd - Junior | 40 | 0 | TO START | 0% | 2024 | 2 | [11 empty] | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.091%
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | N/A | N/A | EPM | Emerald - CR PLUS 2025 H1 | EssilorLuxottica | T. Porzio | M. Salcini | Consolidated & Tax | Analysis | 40 | 0 | TO START | 0% | 2024 | 2 | [11 empty] | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.091%
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | N/A | N/A | EPM | Emerald - CR PLUS 2025 H1 | EssilorLuxottica | T. Porzio | M. Sorrentino | Consolidated & Tax | BackEnd | 40 | 0 | TO START | 0% | 2024 | 2 | [11 empty] | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.091%
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | N/A | N/A | EPM | Emerald - CR PLUS 2025 H1 | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 40 | 0 | TO START | 0% | 2024 | 2 | [11 empty] | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.091%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24333 | ABS24333 | EPM | HFM Ariston AMS 2024 2 Semestre | ARISTON | T. Porzio | G. Galati | Delivery AMS | BackEnd | 45 | 8.28 | ON GOING | 0% | 2024 | 6 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24333 | ABS24333 | EPM | HFM Ariston AMS 2024 2 Semestre | ARISTON | T. Porzio | M. Salcini | Consolidated & Tax | Analysis | 45 | 8.28 | ON GOING | 0% | 2024 | 4.5 | [6 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 2.174% | 4.167% | 2.381% | 2.174% | 2.381% | 9.091%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24333 | ABS24333 | EPM | HFM Ariston AMS 2024 2 Semestre | ARISTON | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 45 | 8.28 | ON GOING | 0% | 2024 | 1 | [6 empty] | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0.8696% | 0% | 0.9524% | 0.8696% | 0.9524% | 0.9091%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | A. Di Pietro | Operations | BackEnd | 1812 | 1872 | CLOSED | 0% | 2024 | 60 | 14 | 17 | 17 | 15 | 16 | 8 | 8 | 6 | 5 | 5 | 5 | 7 | 77.78% | 85% | 80.95% | 68.18% | 80% | 40% | 34.78% | 50% | 23.81% | 21.74% | 23.81% | 31.82%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | C. Esposito | Consolidated & Tax | BackEnd | 1812 | 1872 | CLOSED | 0% | 2024 | 84 | 14 | 17 | 17 | 1 | 1 | 1 | 15 | 4 | 17 | 16 | 15 | 15 | 77.78% | 85% | 80.95% | 4.545% | 5% | 5% | 65.22% | 33.33% | 80.95% | 69.57% | 71.43% | 68.18%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | E. Storti | Delivery Projects | Analysis | 1812 | 1872 | CLOSED | 0% | 2024 | 8 | 14 | 16 | 16 | 14 | 5 | 3 | [6 empty] | 77.78% | 80% | 76.19% | 63.64% | 25% | 15% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | E. Tosetto | Consolidated & Tax | BackEnd | 1812 | 1872 | CLOSED | 0% | 2024 | 116 | 14 | 17 | 17 | 15 | 16 | 5 | 18 | 1 | 14 | 23 | 22 | 17 | 77.78% | 85% | 80.95% | 68.18% | 80% | 25% | 78.26% | 8.333% | 66.67% | 100% | 104.8% | 77.27%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | F. De Pedis | Operations | BackEnd | 1812 | 1872 | CLOSED | 0% | 2024 | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 0% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | F. Lombardini | Consolidated & Tax | Analysis | 1812 | 1872 | CLOSED | 0% | 2024 | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 0% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | G. Galati | Delivery AMS | BackEnd | 1812 | 1872 | CLOSED | 0% | 2024 | 7 | 3 | 3 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 16.67% | 15% | 4.762% | 4.545% | 5% | 5% | 4.348% | 0% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | G. Minervini | Operations | BackEnd - Junior | 1812 | 1872 | CLOSED | 0% | 2024 | 115 | 14 | 17 | 17 | 15 | 16 | 16 | 18 | 6 | 17 | 23 | 2 | 17 | 77.78% | 85% | 80.95% | 68.18% | 80% | 80% | 78.26% | 50% | 80.95% | 100% | 9.524% | 77.27%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | L. Franco | Operations | BackEnd | 1812 | 1872 | CLOSED | 0% | 2024 | 10 | [5 empty] | 5 | 5 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 25% | 21.74% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | L. Pigazzini | Consolidated & Tax | BackEnd - Junior | 1812 | 1872 | CLOSED | 0% | 2024 | 61 | [8 empty] | 19 | 23 | 2 | 17 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90.48% | 100% | 9.524% | 77.27%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | M. Salcini | Consolidated & Tax | Analysis | 1812 | 1872 | CLOSED | 0% | 2024 | 41 | 12 | 15 | 15 | 13 | 12 | 8 | 2 | 5 | 3 | 5 | 5 | 1 | 66.67% | 75% | 71.43% | 59.09% | 60% | 40% | 8.696% | 41.67% | 14.29% | 21.74% | 23.81% | 4.545%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | M. Sorrentino | Consolidated & Tax | Backend | 1812 | 1872 | CLOSED | 0% | 2024 | 39 | 12 | 15 | 15 | 13 | 12 | 8 | 2 | 6 | 3 | 1 | 6 | 1 | 66.67% | 75% | 71.43% | 59.09% | 60% | 40% | 8.696% | 50% | 14.29% | 4.348% | 28.57% | 4.545%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | N. Fragale | Operations | BackEnd | 1812 | 1872 | CLOSED | 0% | 2024 | 121 | 14 | 17 | 17 | 15 | 16 | 16 | 18 | 6 | 17 | 18 | 16 | 14 | 77.78% | 85% | 80.95% | 68.18% | 80% | 80% | 78.26% | 50% | 80.95% | 78.26% | 76.19% | 63.64%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | O. BEN OTHMANE | Operations | BackEnd - Junior | 1812 | 1872 | CLOSED | 0% | 2024 | 108 | 14 | 17 | 17 | 15 | 16 | 16 | 18 | 6 | 17 | 19 | 2 | 14 | 77.78% | 85% | 80.95% | 68.18% | 80% | 80% | 78.26% | 50% | 80.95% | 82.61% | 9.524% | 63.64%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | P. Buonasorte | Operations | BackEnd - Junior | 1812 | 1872 | CLOSED | 0% | 2024 | 33 | [5 empty] | 1 | 1 | 5 | 1 | 13 | 11 | 1 | 0% | 0% | 0% | 0% | 0% | 5% | 4.348% | 41.67% | 4.762% | 56.52% | 52.38% | 4.545%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | P. Pieroni | Operations | BackEnd | 1812 | 1872 | CLOSED | 0% | 2024 | 13 | 14 | 17 | 17 | 15 | 1 | 1 | 1 | 6 | 1 | 1 | 1 | 1 | 77.78% | 85% | 80.95% | 68.18% | 5% | 5% | 4.348% | 50% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | R. Freddi | Operations | BackEnd | 1812 | 1872 | CLOSED | 0% | 2024 | 0 | 2 | 2 | 2 | 2 | [8 empty] | 11.11% | 10% | 9.524% | 9.091% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | S. Preziosa | Delivery Projects | Analysis | 1812 | 1872 | CLOSED | 0% | 2024 | 64 | 13 | 16 | 16 | 14 | 9 | 8 | 9 | 6 | 7 | 7 | 9 | 9 | 72.22% | 80% | 76.19% | 63.64% | 45% | 40% | 39.13% | 50% | 33.33% | 30.43% | 42.86% | 40.91%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 1812 | 1872 | CLOSED | 0% | 2024 | 30 | [6 empty] | 5 | 2 | 1 | 8 | 8 | 6 | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 16.67% | 4.762% | 34.78% | 38.1% | 27.27%
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | V. Raso | Operations | BackEnd | 1812 | 1872 | CLOSED | 0% | 2024 | 115 | 14 | 17 | 17 | 15 | 16 | 16 | 18 | 6 | 17 | 23 | 2 | 17 | 77.78% | 85% | 80.95% | 68.18% | 80% | 80% | 78.26% | 50% | 80.95% | 100% | 9.524% | 77.27%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24359 | ABS24359 | EPM | LUX–DI-EPM–enhancements plus 10 HFM Q3Q4 2024 | EssilorLuxottica | T. Porzio | C. Esposito | Consolidated & Tax | BackEnd | 40 | 18 | CLOSED | 0% | 2024 | 7 | [6 empty] | 3 |  |  | 1 | 1 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 0% | 0% | 4.348% | 4.762% | 9.091%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24359 | ABS24359 | EPM | LUX–DI-EPM–enhancements plus 10 HFM Q3Q4 2024 | EssilorLuxottica | T. Porzio | M. Salcini | Consolidated & Tax | Analysis | 40 | 18 | CLOSED | 0% | 2024 | 9 | [6 empty] | 3 | 1 |  | 1 | 1 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 8.333% | 0% | 4.348% | 4.762% | 13.64%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24359 | ABS24359 | EPM | LUX–DI-EPM–enhancements plus 10 HFM Q3Q4 2024 | EssilorLuxottica | T. Porzio | M. Sorrentino | Consolidated & Tax | Backend | 40 | 18 | CLOSED | 0% | 2024 | 10 | [6 empty] | 3 |  |  | 2 | 2 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 0% | 0% | 8.696% | 9.524% | 13.64%
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24359 | ABS24359 | EPM | LUX–DI-EPM–enhancements plus 10 HFM Q3Q4 2024 | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 40 | 18 | CLOSED | 0% | 2024 | 1.5 | [9 empty] | 0.5 | 0.5 | 0.5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.174% | 2.381% | 2.273%
CONTRACT | AMS |  | 2024 | 2024-07-01 | 2024-12-31 | ABS24332 | ABS24332 | EPM | Transmec AMS HFM 2024/2025 | Transmec | T. Porzio | C. Esposito | Consolidated & Tax | BackEnd | 15 | 3.75 | ON GOING | 0% | 2024 | 9 | [6 empty] | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0% | 0% | 0% | 0% | 0% | 0% | 6.522% | 12.5% | 7.143% | 6.522% | 7.143% | 6.818%
CONTRACT | AMS |  | 2024 | 2024-07-01 | 2024-12-31 | ABS24332 | ABS24332 | EPM | Transmec AMS HFM 2024/2025 | Transmec | T. Porzio | M. Sorrentino | Consolidated & Tax | Analysis | 15 | 3.75 | ON GOING | 0% | 2024 | 4.5 | [6 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 2.174% | 4.167% | 2.381% | 2.174% | 2.381% | 9.091%
CONTRACT | AMS |  | 2024 | 2024-07-01 | 2024-12-31 | ABS24332 | ABS24332 | EPM | Transmec AMS HFM 2024/2025 | Transmec | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 15 | 3.75 | ON GOING | 0% | 2024 | 1.2 | [6 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0.8696% | 1.667% | 0.9524% | 0.8696% | 0.9524% | 0.9091%
CONTRACT | AMS |  | 2023-2024 | 2023-10-01 | 2024-09-24 | ABS24024 | BS23402 | EPM | WEBUILD AMS HFM 10/23 - 09/24 | WeBuild | T. Porzio | C. Esposito | Consolidated & Tax | BackEnd | 60 | 47 | CLOSED | 0% | 2024 | 14 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 |  |  |  | 16.67% | 15% | 14.29% | 13.64% | 15% | 15% | 13.04% | 16.67% | 14.29% | 0% | 0% | 0%
CONTRACT | AMS |  | 2023-2024 | 2023-10-01 | 2024-09-24 | ABS24024 | BS23402 | EPM | WEBUILD AMS HFM 10/23 - 09/24 | WeBuild | T. Porzio | M. Salcini | Consolidated & Tax | Analysis | 60 | 47 | CLOSED | 0% | 2024 | 5 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 |  |  |  | 16.67% | 15% | 14.29% | 13.64% | 5% | 5% | 4.348% | 8.333% | 4.762% | 0% | 0% | 0%
CONTRACT | AMS |  | 2023-2024 | 2023-10-01 | 2024-09-24 | ABS24024 | BS23402 | EPM | WEBUILD AMS HFM 10/23 - 09/24 | WeBuild | T. Porzio | M. Sorrentino | Consolidated & Tax | Technical Leader | 60 | 47 | CLOSED | 0% | 2024 | 8 | 2 | 2 | 2 | 2 | 2 | 3 | 1 | 1 | 1 |  |  |  | 11.11% | 10% | 9.524% | 9.091% | 10% | 15% | 4.348% | 8.333% | 4.762% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024-2025 | 2024-10-01 | 2025-09-30 | ABS24404 | ABS24404 | EPM | WEBUILD AMS HFM 10/24 - 09/25 | WeBuild | T. Porzio | C. Esposito | Consolidated & Tax | BackEnd | 15 | 0 | ON GOING | 0% | 2024 | 9 | [9 empty] | 3 | 3 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 14.29% | 13.64%
CONTRACT | AMS |  | 2024-2025 | 2024-10-01 | 2025-09-30 | ABS24404 | ABS24404 | EPM | WEBUILD AMS HFM 10/24 - 09/25 | WeBuild | T. Porzio | M. Salcini | Consolidated & Tax | Analysis | 15 | 0 | ON GOING | 0% | 2024 | 3 | [9 empty] | 0.5 | 0.5 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.174% | 2.381% | 9.091%
CONTRACT | AMS |  | 2024-2025 | 2024-10-01 | 2025-09-30 | ABS24404 | ABS24404 | EPM | WEBUILD AMS HFM 10/24 - 09/25 | WeBuild | T. Porzio | M. Sorrentino | Consolidated & Tax | Technical Leader | 15 | 0 | ON GOING | 0% | 2024 | 3 | [9 empty] | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS |  | 2024-2025 | 2024-10-01 | 2025-09-30 | ABS24404 | ABS24404 | EPM | WEBUILD AMS HFM 10/24 - 09/25 | WeBuild | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 15 | 0 | ON GOING | 0% | 2024 | 0.6 | [9 empty] | 0.2 | 0.2 | 0.2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.8696% | 0.9524% | 0.9091%
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-04-30 | N/A | ESE | OTHER | ESSILOR SEE4C FR | EssilorLuxottica | Xherahu Florida | R. Bondi | Operations | FrontEnd | 0 | 0 | CLOSED | 100% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-04-30 | N/A | ESE | OTHER | ESSILOR SEE4C US | EssilorLuxottica | Xherahu Florida | A. Strada | Operations | BackEnd | 0 | 0 | ON HOLD | 0% | 2024 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-04-30 | N/A | ESE | OTHER | ESSILOR SEE4C US | EssilorLuxottica | Xherahu Florida | R. Bondi | Operations | FrontEnd | 0 | 0 | ON GOING | 0% | 2024 | 4 |  |  |  |  | 4 | [7 empty] | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS24401 | ABS24401 | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - EVOLUTIVA DI 2024 | AO FERRARA | A. Coletti | A. Elia | UI | Front End | 100 | 258 | ON GOING | 90% | 2025 | 0 |  |  | 15 | 15 | [8 empty] | 0% | 0% | 71.43% | 68.18% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS24401 | ABS24401 | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - EVOLUTIVA DI 2024 | AO FERRARA | A. Coletti | L. Lazzari | SAP ECC | Account Manager | 100 | 258 | ON GOING | 90% | 2025 | 0 |  |  | 2 | 2 | [8 empty] | 0% | 0% | 9.524% | 9.091% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS24401 | ABS24401 | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - EVOLUTIVA DI 2024 | AO FERRARA | A. Coletti | M. Calabrese | Delivery Projects | PM - Project Governance | 100 | 258 | ON GOING | 90% | 2025 | 2 | 5 | 5 | 5 | 5 | 2 | [7 empty] | 27.78% | 25% | 23.81% | 22.73% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS24401 | ABS24401 | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - EVOLUTIVA DI 2024 | AO FERRARA | A. Coletti | R. Tortora | Operations | Front End | 100 | 258 | ON GOING | 90% | 2025 | 0 |  |  | 1 | 1 | [8 empty] | 0% | 0% | 4.762% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-12-01 | 2024-12-24 | ABS24565 | ABS24565 | LOGISTIC | CONTROL TOWER - Grand Vision Italy and Poland plant integration | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | Data Engineering | 30 | 29 | CLOSED | 100% | 2025 | 0 | 8 | [11 empty] | 44.44% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-12-01 | 2024-12-24 | ABS24565 | ABS24565 | LOGISTIC | CONTROL TOWER - Grand Vision Italy and Poland plant integration | EssilorLuxottica | A. Cuomo | J. Daci | Operations | BackEnd | 30 | 29 | CLOSED | 100% | 2025 | 0 | 8 | [11 empty] | 44.44% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-12-01 | 2024-12-24 | ABS24565 | ABS24565 | LOGISTIC | CONTROL TOWER - Grand Vision Italy and Poland plant integration | EssilorLuxottica | A. Cuomo | T. Lazzari | SAP ECC | ECC Developer | 30 | 29 | CLOSED | 100% | 2025 | 0 | 4 | [11 empty] | 22.22% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-20 | 2025-03-08 | ABS25101 | ABS25101 | LOGISTIC | Control Tower (Mercury) - LensBest website integration | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | Data Engineering | 32 | 30 | CLOSED | 100% | 2025 | 0 | 3 | 15 | 1 | [9 empty] | 16.67% | 75% | 4.762% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-20 | 2025-03-08 | ABS25101 | ABS25101 | LOGISTIC | Control Tower (Mercury) - LensBest website integration | EssilorLuxottica | A. Cuomo | T. Lazzari | SAP ECC | ECC Developer | 32 | 30 | CLOSED | 100% | 2025 | 0 | 5 | 15 | 3 | [9 empty] | 27.78% | 75% | 14.29% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-07 | 2025-03-08 | ABS25102 | ABS25102 | LOGISTIC | Control Tower (Mercury) - Rollout + CRs | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | Data Engineering | 105 | 97 | CLOSED | 100% | 2025 | 0 | 16 | 5 | 5 | [9 empty] | 88.89% | 25% | 23.81% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-07 | 2025-03-08 | ABS25102 | ABS25102 | LOGISTIC | Control Tower (Mercury) - Rollout + CRs | EssilorLuxottica | A. Cuomo | F. Tarquini | SAP ECC | ECC Analyst | 105 | 97 | CLOSED | 100% | 2025 | 0 | 2 | 15 | 5 | [9 empty] | 11.11% | 75% | 23.81% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-07 | 2025-03-08 | ABS25102 | ABS25102 | LOGISTIC | Control Tower (Mercury) - Rollout + CRs | EssilorLuxottica | A. Cuomo | J. Daci | Operations | BackEnd | 105 | 97 | CLOSED | 100% | 2025 | 0 | 16 | 2 | 5 | [9 empty] | 88.89% | 10% | 23.81% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-07 | 2025-03-08 | ABS25102 | ABS25102 | LOGISTIC | Control Tower (Mercury) - Rollout + CRs | EssilorLuxottica | A. Cuomo | T. Lazzari | SAP ECC | ECC Developer | 105 | 97 | CLOSED | 100% | 2025 | 0 | 11 | 5 | [10 empty] | 61.11% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-03-10 | 2025-09-12 | ABS25287 | ABS25287 | LOGISTIC | CONTROL TOWER MERCURY - REPLENISHMENT BBP | EssilorLuxottica | A. Cuomo | A. Camara | SAP ECC | ECC Analyst | 475 | 111 | ON GOING | 20% | 2025 | 38 |  |  | 8 | 8 | 10 | 10 | 7 | 6 | 5 |  |  |  | 0% | 0% | 38.1% | 36.36% | 50% | 50% | 30.43% | 50% | 23.81% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-03-10 | 2025-09-12 | ABS25287 | ABS25287 | LOGISTIC | CONTROL TOWER MERCURY - REPLENISHMENT BBP | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | Data Engineering | 475 | 111 | ON GOING | 20% | 2025 | 79 |  |  | 15 | 17 | 19 | 21 | 18 | 11 | 10 |  |  |  | 0% | 0% | 71.43% | 77.27% | 95% | 105% | 78.26% | 91.67% | 47.62% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-03-10 | 2025-09-12 | ABS25287 | ABS25287 | LOGISTIC | CONTROL TOWER MERCURY - REPLENISHMENT BBP | EssilorLuxottica | A. Cuomo | F. Ianni | SAP FIORI | Front End | 475 | 111 | ON GOING | 20% | 2025 | 19 |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 10 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 33.33% | 47.62% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-03-10 | 2025-09-12 | ABS25287 | ABS25287 | LOGISTIC | CONTROL TOWER MERCURY - REPLENISHMENT BBP | EssilorLuxottica | A. Cuomo | F. Taita | Delivery Projects | PM - Project Governance | 475 | 111 | ON GOING | 20% | 2025 | 15 |  |  | 0 | 0 | 0 | 0 | 5 | 5 | 5 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 41.67% | 23.81% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-03-10 | 2025-09-12 | ABS25287 | ABS25287 | LOGISTIC | CONTROL TOWER MERCURY - REPLENISHMENT BBP | EssilorLuxottica | A. Cuomo | F. Tarquini | SAP ECC | ECC Analyst | 475 | 111 | ON GOING | 20% | 2025 | 38 |  |  | 3 | 8 | 10 | 10 | 7 | 6 | 5 |  |  |  | 0% | 0% | 14.29% | 36.36% | 50% | 50% | 30.43% | 50% | 23.81% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-03-10 | 2025-09-12 | ABS25287 | ABS25287 | LOGISTIC | CONTROL TOWER MERCURY - REPLENISHMENT BBP | EssilorLuxottica | A. Cuomo | J. Daci | Operations | Data Management | 475 | 111 | ON GOING | 20% | 2025 | 69 |  |  | 16 | 17 | 4 | 21 | 23 | 11 | 10 |  |  |  | 0% | 0% | 76.19% | 77.27% | 20% | 105% | 100% | 91.67% | 47.62% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-03-10 | 2025-09-12 | ABS25287 | ABS25287 | LOGISTIC | CONTROL TOWER MERCURY - REPLENISHMENT BBP | EssilorLuxottica | A. Cuomo | M. Sabarese | SAP FIORI | Front End | 475 | 111 | ON GOING | 20% | 2025 | 19 |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 10 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 33.33% | 47.62% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-03-10 | 2025-09-12 | ABS25287 | ABS25287 | LOGISTIC | CONTROL TOWER MERCURY - REPLENISHMENT BBP | EssilorLuxottica | A. Cuomo | P. Cielo | SAP ECC | ECC Project Manager | 475 | 111 | ON GOING | 20% | 2025 | 38 |  |  | 5 | 8 | 10 | 10 | 7 | 6 | 5 |  |  |  | 0% | 0% | 23.81% | 36.36% | 50% | 50% | 30.43% | 50% | 23.81% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-03-10 | 2025-09-12 | ABS25287 | ABS25287 | LOGISTIC | CONTROL TOWER MERCURY - REPLENISHMENT BBP | EssilorLuxottica | A. Cuomo | T. Lazzari | SAP ECC | ECC Developer | 475 | 111 | ON GOING | 20% | 2025 | 25 |  |  | 2 | 1 | 1 | 3 | 5 | 6 | 10 |  |  |  | 0% | 0% | 9.524% | 4.545% | 5% | 15% | 21.74% | 50% | 47.62% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-01-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | Data Engineering | 190 | 177 | CLOSED | 100% | 2025 | 0 | 3.5 | [11 empty] | 19.44% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-01-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | A. Strada | Operations | BackEnd | 190 | 177 | CLOSED | 100% | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-01-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | A. Torone | Delivery AMS | Data Management | 190 | 177 | CLOSED | 100% | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-01-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | C. Paz | Delivery Projects | PMO - Project Management Officer | 190 | 177 | CLOSED | 100% | 2025 | 0 | 0.5 | [11 empty] | 2.778% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-01-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | F. Reale | Operations | FrontEnd | 190 | 177 | CLOSED | 100% | 2025 | 0 | 2 | [11 empty] | 11.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | Lucy | Lucy PTP AI: buyer 2025 | EssilorLuxottica | A. Graziani | A. Imbimbo | AI Operations | Data Scientist | 15 | 0 | PROPOSAL | 0 | 2025 | 0 | 1 | 1 | [10 empty] | 5.556% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | Lucy | Lucy PTP AI: buyer 2025 | EssilorLuxottica | A. Graziani | F. Malvezzi | AI Operations | Data Scientist | 15 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | Lucy | Lucy PTP AI: buyer 2025 | EssilorLuxottica | A. Graziani | G. Sironi | AI Operations | PM - Project Governance | 15 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | Lucy | Lucy PTP AI: buyer 2025 | EssilorLuxottica | A. Graziani | M. Gomitoni | AI Operations | Technical Leader | 15 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | Lucy | Lucy PTP AI: buyer 2025 | EssilorLuxottica | A. Graziani | V. Echarry | AI Operations | Data Scientist | 15 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | LUCY | Lucy | Lucy PTP AI: coding 2025 | EssilorLuxottica | A. Graziani | A. Imbimbo | AI Operations | Data Scientist | 150 | 0 | PROPOSAL | 0 | 2025 | 15 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | [5 empty] | 27.78% | 25% | 23.81% | 22.73% | 25% | 25% | 21.74% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | LUCY | Lucy | Lucy PTP AI: coding 2025 | EssilorLuxottica | A. Graziani | F. Malvezzi | AI Operations | Data Scientist | 60 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | LUCY | Lucy | Lucy PTP AI: coding 2025 | EssilorLuxottica | A. Graziani | G. Sironi | AI Operations | PM - Project Governance | 60 | 0 | PROPOSAL | 0 | 2025 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | LUCY | Lucy | Lucy PTP AI: coding 2025 | EssilorLuxottica | A. Graziani | M. Gomitoni | AI Operations | Technical Leader | 60 | 0 | PROPOSAL | 0 | 2025 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | LUCY | Lucy | Lucy PTP AI: coding 2025 | EssilorLuxottica | A. Graziani | V. Echarry | AI Operations | Data Scientist | 60 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | LUCY | Lucy | Lucy PTP AI: vendor 2025 | EssilorLuxottica | A. Graziani | A. Imbimbo | AI Operations | Data Scientist | 30 | 0 | PROPOSAL | 0 | 2025 | 0 | 2 | 2 | 2 | [9 empty] | 11.11% | 10% | 9.524% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | LUCY | Lucy | Lucy PTP AI: vendor 2025 | EssilorLuxottica | A. Graziani | F. Malvezzi | AI Operations | Data Scientist | 30 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | LUCY | Lucy | Lucy PTP AI: vendor 2025 | EssilorLuxottica | A. Graziani | G. Sironi | AI Operations | PM - Project Governance | 30 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | LUCY | Lucy | Lucy PTP AI: vendor 2025 | EssilorLuxottica | A. Graziani | M. Gomitoni | AI Operations | Technical Leader | 30 | 0 | PROPOSAL | 0 | 2025 | 0 | 1 | 1 | 1 | [9 empty] | 5.556% | 5% | 4.762% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | LUCY | Lucy | Lucy PTP AI: vendor 2025 | EssilorLuxottica | A. Graziani | V. Echarry | AI Operations | Data Scientist | 30 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | OTHER | FDP AI 2025 - Fraud Detection Plathform Updates | EssilorLuxottica | A. Morterra | A. Imbimbo | AI Operations | Data Scientist | 200 | 0 | PROPOSAL | 0% | 2025 | 25 | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 5 |  |  |  | 27.78% | 25% | 19.05% | 22.73% | 25% | 25% | 21.74% | 41.67% | 23.81% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | OTHER | FDP AI 2025 - Fraud Detection Plathform Updates | EssilorLuxottica | A. Morterra | F. Malvezzi | AI Operations | Data Scientist | 200 | 0 | PROPOSAL | 0% | 2025 | 40 | 1 | 1 | 5 | 8 | 10 | 10 | 10 | 5 | 5 |  |  |  | 5.556% | 5% | 23.81% | 36.36% | 50% | 50% | 43.48% | 41.67% | 23.81% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | OTHER | FDP AI 2025 - Fraud Detection Plathform Updates | EssilorLuxottica | A. Morterra | G. Sironi | AI Operations | PM - Project Governance | 200 | 0 | PROPOSAL | 0% | 2025 | 12 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 16.67% | 15% | 9.524% | 9.091% | 10% | 10% | 8.696% | 16.67% | 9.524% | 8.696% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | OTHER | FDP AI 2025 - Fraud Detection Plathform Updates | EssilorLuxottica | A. Morterra | L. Cariglia | AI Operations | Data Management | 200 | 0 | PROPOSAL | 0% | 2025 | 14 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 8.696% | 8.333% | 9.524% | 8.696% | 4.762% | 9.091%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | OTHER | FDP AI 2025 - Fraud Detection Plathform Updates | EssilorLuxottica | A. Morterra | M. Gomitoni | AI Operations | Technical Leader | 200 | 0 | PROPOSAL | 0% | 2025 | 19 | 4 | 4 | 4 | 5 | 5 | 5 | 3 | 3 | 3 |  |  |  | 22.22% | 20% | 19.05% | 22.73% | 25% | 25% | 13.04% | 25% | 14.29% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | OTHER | FDP AI 2025 - Fraud Detection Plathform Updates | EssilorLuxottica | A. Morterra | V. Echarry | AI Operations | Data Scientist | 200 | 0 | PROPOSAL | 0% | 2025 | 17 | 5 | 5 | 5 | 1 | 1 | 1 | 5 | 5 | 5 |  |  |  | 27.78% | 25% | 23.81% | 4.545% | 5% | 5% | 21.74% | 41.67% | 23.81% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25020 | ABS25020 | RETAIL | DMV AMS 2025 | EssilorLuxottica | A. Torone | A. Torone | Delivery Project | PM - Project Governance | 75 | 0 | TO START | 0% | 2025 | 30 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 4 | 4 | 4 | 4 | 22.22% | 20% | 19.05% | 18.18% | 20% | 20% | 17.39% | 16.67% | 19.05% | 17.39% | 19.05% | 18.18%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25020 | ABS25020 | RETAIL | DMV AMS 2025 | EssilorLuxottica | A. Torone | F. Reale | Operations | Data Management | 75 | 0 | TO START | 0% | 2025 | 38 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 5 | 5 | 5 | 5 | 27.78% | 25% | 23.81% | 22.73% | 25% | 25% | 21.74% | 25% | 23.81% | 21.74% | 23.81% | 22.73%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | HR | PAYROLL FRANCIA | EssilorLuxottica | A. Torone | F. Plebani | Operations | Data Management | 100 | 0 | ON GOING | 5% | 2025 | 30 |  | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 4 | 4 | 4 | 4 | 0% | 20% | 19.05% | 18.18% | 20% | 20% | 17.39% | 16.67% | 19.05% | 17.39% | 19.05% | 18.18%
INTERNAL PRJ | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | BS000QA | QA | Quality Assurance nella DI | Abstract | A. Torone | A. Torone | Delivery Project | PM - Project Governance | 0 | 0 | ON GOING | 0% | 2025 | 120 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 83.33% | 75% | 71.43% | 68.18% | 75% | 75% | 65.22% | 125% | 71.43% | 65.22% | 71.43% | 68.18%
INTERNAL PRJ | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | BS000QA | QA | Quality Assurance nella DI | Abstract | A. Torone | L. STEFANELLI | Delivery AMS | Tester | 0 | 0 | ON GOING | 0% | 2025 | 16 | 18 | 22 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 100% | 110% | 9.524% | 9.091% | 10% | 10% | 8.696% | 16.67% | 9.524% | 8.696% | 9.524% | 9.091%
INTERNAL PRJ | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | BS000QA | QA | Quality Assurance nella DI | Abstract | A. Torone | M. STRADA | Delivery AMS | Tester | 0 | 0 | ON GOING | 0% | 2025 | 16 | 18 | 22 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 100% | 110% | 9.524% | 9.091% | 10% | 10% | 8.696% | 16.67% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | AMS |  | 2024 | 2025-01-01 | 2025-06-30 | ABS24060 | ABS24060 | EPM | RDM - AMS Talentia | RDM | F. Lombardini | F. Lombardini | Consolidated & Tax | PM - Project Governance | 40 | 8 | ON GOING | 20% | 2025 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | [6 empty] | 16.67% | 5% | 4.762% | 9.091% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024 | 2025-01-01 | 2025-06-30 | ABS24060 | ABS24060 | EPM | RDM - AMS Talentia | RDM | F. Lombardini | G. Picerno | Consolidated & Tax | Back End | 40 | 8 | ON GOING | 20% | 2025 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | [6 empty] | 16.67% | 5% | 4.762% | 9.091% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024-2025 | 2024-07-01 | 2025-06-30 | ABS24334 | ABS24334 | EPM | Thom Browne | Thom Browne | F. Lombardini | F. Lombardini | Consolidated & Tax | Analyst | 20 | 0 | ON GOING | 0% | 2025 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | [6 empty] | 5.556% | 5% | 2.381% | 2.273% | 2.5% | 2.5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS |  | 2024-2025 | 2024-07-01 | 2025-06-30 | ABS24334 | ABS24334 | EPM | Thom Browne | Thom Browne | F. Lombardini | G. Picerno | Consolidated & Tax | Analyst | 20 | 0 | ON GOING | 0% | 2025 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2025-01-06 | 2025-05-31 | ABS24606 | ABS24606 | BIP | ARS - RXO enhacement 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Engineering | 34 | 30 | CLOSED | 100% | 2025 | 0 |  | 1 | 4 | [9 empty] | 0% | 5% | 19.05% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2025-01-06 | 2025-05-31 | ABS24606 | ABS24606 | BIP | ARS - RXO enhacement 2025 | EssilorLuxottica | F. Taita | M. Regini | Operations | BackEnd | 34 | 30 | CLOSED | 100% | 2025 | 0 | 2 | 5 | 7 | [9 empty] | 11.11% | 25% | 33.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2025-01-06 | 2025-05-31 | ABS24606 | ABS24606 | BIP | ARS - RXO enhacement 2025 | EssilorLuxottica | F. Taita | T. Baldi | Operations | BackEnd | 34 | 30 | CLOSED | 100% | 2025 | 0 | 3 | 3 | 5 | [9 empty] | 16.67% | 15% | 23.81% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-04 | 2025-06-30 | ABS25192 | ABS25192 | BIP | ARS - RXO Enhancement 2 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Engineering | 70 | 14 | ON GOING | 20% | 2025 | 13 |  |  |  | 4 | 4 | 4 | 4 |  | 1 |  |  |  | 0% | 0% | 0% | 18.18% | 20% | 20% | 17.39% | 0% | 4.762% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-04 | 2025-06-30 | ABS25192 | ABS25192 | BIP | ARS - RXO Enhancement 2 2025 | EssilorLuxottica | F. Taita | M. Regini | Operations | Back End | 70 | 14 | ON GOING | 20% | 2025 | 20 |  |  |  | 6 | 6 | 6 | 6 |  | 2 |  |  |  | 0% | 0% | 0% | 27.27% | 30% | 30% | 26.09% | 0% | 9.524% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-04 | 2025-06-30 | ABS25192 | ABS25192 | BIP | ARS - RXO Enhancement 2 2025 | EssilorLuxottica | F. Taita | T. Baldi | Operations | Back End | 70 | 14 | ON GOING | 20% | 2025 | 21 |  |  |  | 6 | 6 | 6 | 6 |  | 3 |  |  |  | 0% | 0% | 0% | 27.27% | 30% | 30% | 26.09% | 0% | 14.29% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-02-15 | 2025-12-31 | ABS25114 | ABS25114 | BIP | BIP rollout support 2 2025 | EssilorLuxottica | F. Taita | A. Seira | Operations | Backend | 60 | 58 | CLOSED | 96.67% | 2025 | 0 |  | 1 | 21 | 18 | [8 empty] | 0% | 5% | 100% | 81.82% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-02-15 | 2025-12-31 | ABS25114 | ABS25114 | BIP | BIP rollout support 2 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | DataManagement | 60 | 58 | CLOSED | 96.67% | 2025 | 0 |  | 6 | 6 | 3 | [8 empty] | 0% | 30% | 28.57% | 13.64% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-02-15 | 2025-12-31 | ABS25114 | ABS25114 | BIP | BIP rollout support 2 2025 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | Backend | 60 | 58 | CLOSED | 96.67% | 2025 | 0 |  | 6 | 14 | 3 | [8 empty] | 0% | 30% | 66.67% | 13.64% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-02-15 | 2025-12-31 | ABS25114 | ABS25114 | BIP | BIP rollout support 2 2025 | EssilorLuxottica | F. Taita | T. Baldi | Operations | Backend | 60 | 58 | CLOSED | 96.67% | 2025 | 0 |  | 6 | 12 | 4 | [8 empty] | 0% | 30% | 57.14% | 18.18% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-04-01 | 2025-12-31 | ABS25231 | ABS25231 | BIP | BIP rollout support 3 2025 | EssilorLuxottica | F. Taita | A. Seira | Operations | Back End | 60 | 22 | ON GOING | 36.67% | 2025 | 31 |  |  |  |  | 11 | 11 | 9 | [5 empty] | 0% | 0% | 0% | 0% | 55% | 55% | 39.13% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-04-01 | 2025-12-31 | ABS25231 | ABS25231 | BIP | BIP rollout support 3 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Management | 60 | 22 | ON GOING | 36.67% | 2025 | 6 |  |  |  |  | 2 | 2 | 2 | [5 empty] | 0% | 0% | 0% | 0% | 10% | 10% | 8.696% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-04-01 | 2025-12-31 | ABS25231 | ABS25231 | BIP | BIP rollout support 3 2025 | EssilorLuxottica | F. Taita | L. Altobelli | Operations | Back End | 60 | 22 | ON GOING | 36.67% | 2025 | 13 |  |  |  |  | 5 | 5 | 3 | [5 empty] | 0% | 0% | 0% | 0% | 25% | 25% | 13.04% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-04-01 | 2025-12-31 | ABS25231 | ABS25231 | BIP | BIP rollout support 3 2025 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | Back End | 60 | 22 | ON GOING | 36.67% | 2025 | 21 |  |  |  |  | 7 | 7 | 7 | [5 empty] | 0% | 0% | 0% | 0% | 35% | 35% | 30.43% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-04-01 | 2025-12-31 | ABS25231 | ABS25231 | BIP | BIP rollout support 3 2025 | EssilorLuxottica | F. Taita | T. Baldi | Operations | Back End | 60 | 22 | ON GOING | 36.67% | 2025 | 15 |  |  |  |  | 5 | 5 | 5 | [5 empty] | 0% | 0% | 0% | 0% | 25% | 25% | 21.74% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-10-15 | 2025-12-31 | N/A | N/A | BIP | BIP rollout support 6 2025 | EssilorLuxottica | F. Taita | A. Seira | Operations | Back End | 60 | 0 | TO START | 0% | 2025 | 20 | [10 empty] | 10 | 10 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 47.62% | 45.45%
CONTRACT | AMS | Waterfall | 2025 | 2025-10-15 | 2025-12-31 | N/A | N/A | BIP | BIP rollout support 6 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Management | 60 | 0 | TO START | 0% | 2025 | 10 | [10 empty] | 5 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 23.81% | 22.73%
CONTRACT | AMS | Waterfall | 2025 | 2025-10-15 | 2025-12-31 | N/A | N/A | BIP | BIP rollout support 6 2025 | EssilorLuxottica | F. Taita | L. altobelli | Operations | Back End | 60 | 0 | TO START | 0% | 2025 | 14 | [10 empty] | 7 | 7 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 33.33% | 31.82%
CONTRACT | AMS | Waterfall | 2025 | 2025-10-15 | 2025-12-31 | N/A | N/A | BIP | BIP rollout support 6 2025 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | Back End | 60 | 0 | TO START | 0% | 2025 | 20 | [10 empty] | 10 | 10 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 47.62% | 45.45%
CONTRACT | AMS | Waterfall | 2025 | 2025-10-15 | 2025-12-31 | N/A | N/A | BIP | BIP rollout support 6 2025 | EssilorLuxottica | F. Taita | T. Baldi | Operations | Back End | 60 | 0 | TO START | 0% | 2025 | 14 | [10 empty] | 7 | 7 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 33.33% | 31.82%
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-10-31 | ABS25236 | ABS25236 | LOGISTIC | EL Complete Pair France LABEX ARS RXO | EssilorLuxottica | F. Taita | T. Baldi | Operations | Data Engineering | 45 | 9 | ON GOING | 20% | 2025 | 17 |  |  |  | 2 | 5 | 5 | 5 |  | 2 |  |  |  | 0% | 0% | 0% | 9.091% | 25% | 25% | 21.74% | 0% | 9.524% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-10-31 | ABS25236 | ABS25236 | LOGISTIC | EL Complete Pair France LABEX ARS RXO | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Engineering | 45 | 9 | ON GOING | 20% | 2025 | 14 |  |  |  | 2 | 4 | 4 | 4 |  | 2 |  |  |  | 0% | 0% | 0% | 9.091% | 20% | 20% | 17.39% | 0% | 9.524% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-10-31 | ABS25236 | ABS25236 | LOGISTIC | EL Complete Pair France LABEX ARS RXO | EssilorLuxottica | F. Taita | M. Regini | Operations | Data Engineering | 45 | 9 | ON GOING | 20% | 2025 | 10 |  |  |  |  | 3 | 3 | 3 |  | 1 |  |  |  | 0% | 0% | 0% | 0% | 15% | 15% | 13.04% | 0% | 4.762% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2025 | 2025-05-01 | 2025-10-31 | ABS25236 | ABS25236 | LOGISTIC | EL Complete Pair France LABEX PLANNING FILES | EssilorLuxottica | F. Taita | A. Seira | Operations | Back End | 100 | 12 | ON GOING | 12% | 2025 | 24 |  |  |  |  | 7 | 7 | 7 |  | 3 |  |  |  | 0% | 0% | 0% | 0% | 35% | 35% | 30.43% | 0% | 14.29% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-10-31 | ABS25236 | ABS25236 | LOGISTIC | EL Complete Pair France LABEX PLANNING FILES | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Engineering | 100 | 12 | ON GOING | 12% | 2025 | 18 |  |  |  | 3 | 5 | 5 | 5 |  | 3 |  |  |  | 0% | 0% | 0% | 13.64% | 25% | 25% | 21.74% | 0% | 14.29% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2025 | 2025-05-01 | 2025-10-31 | ABS25236 | ABS25236 | LOGISTIC | EL Complete Pair France LABEX PLANNING FILES | EssilorLuxottica | F. Taita | L. Altobelli | Operations | Data Engineering | 100 | 12 | ON GOING | 12% | 2025 | 28 |  |  |  |  | 7 | 8 | 8 |  | 5 |  |  |  | 0% | 0% | 0% | 0% | 35% | 40% | 34.78% | 0% | 23.81% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-10-31 | ABS25236 | ABS25236 | LOGISTIC | EL Complete Pair France LABEX PLANNING FILES | EssilorLuxottica | F. Taita | L. Stroppa | Operations | Data Engineering | 100 | 12 | ON GOING | 12% | 2025 | 29 |  |  |  | 3 | 8 | 8 | 8 |  | 5 |  |  |  | 0% | 0% | 0% | 13.64% | 40% | 40% | 34.78% | 0% | 23.81% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-10-31 | ABS25236 | ABS25236 | LOGISTIC | EL Complete Pair France LABEX SHORT TRIP | EssilorLuxottica | F. Taita | C. Piraccini | Operations | Data Engineering | 15 | 1 | ON GOING | 6.667% | 2025 | 11 |  |  |  | 2 | 4 | 3 | 3 |  | 1 |  |  |  | 0% | 0% | 0% | 9.091% | 20% | 15% | 13.04% | 0% | 4.762% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-10-31 | ABS25236 | ABS25236 | LOGISTIC | EL Complete Pair France LABEX SHORT TRIP | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Engineering | 15 | 1 | ON GOING | 6.667% | 2025 | 4 |  |  |  | 2 | 1 | 1 | 1 |  | 1 |  |  |  | 0% | 0% | 0% | 9.091% | 5% | 5% | 4.348% | 0% | 4.762% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | BIP | BIP rollot support 4 2025 | EssilorLuxottica | F. Taita | A. Seira | Operations | Back End | 60 | 0 | TO START | 0% | 2025 | 28 | [6 empty] | 10 | 8 | 10 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 43.48% | 66.67% | 47.62% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | BIP | BIP rollot support 4 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Management | 60 | 0 | TO START | 0% | 2025 | 15 | [6 empty] | 5 | 5 | 5 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 41.67% | 23.81% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | BIP | BIP rollot support 4 2025 | EssilorLuxottica | F. Taita | L. altobelli | Operations | Back End | 60 | 0 | TO START | 0% | 2025 | 9 | [6 empty] | 3 | 3 | 3 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 25% | 14.29% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | BIP | BIP rollot support 4 2025 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | Back End | 60 | 0 | TO START | 0% | 2025 | 18 | [6 empty] | 9 |  | 9 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 39.13% | 0% | 42.86% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | BIP | BIP rollot support 4 2025 | EssilorLuxottica | F. Taita | T. Baldi | Operations | Back End | 60 | 0 | TO START | 0% | 2025 | 8 | [6 empty] | 4 |  | 4 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 17.39% | 0% | 19.05% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25037 | ABS25037 | BIP | First BIP rollout support 2025 | EssilorLuxottica | F. Taita | A. Seira | Operations | Backend | 58 | 58 | CLOSED | 100% | 2025 | 0 | 16 | 16 | [10 empty] | 88.89% | 80% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25037 | ABS25037 | BIP | First BIP rollout support 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | DataManagement | 58 | 58 | CLOSED | 100% | 2025 | 0 | 3 | 6 | [10 empty] | 16.67% | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25037 | ABS25037 | BIP | First BIP rollout support 2025 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | Backend | 58 | 58 | CLOSED | 100% | 2025 | 0 | 16 | 9 | [10 empty] | 88.89% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25037 | ABS25037 | BIP | First BIP rollout support 2025 | EssilorLuxottica | F. Taita | T. Baldi | Operations | Backend | 58 | 58 | CLOSED | 100% | 2025 | 0 | 15 | 6 | [10 empty] | 83.33% | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-05-15 | 2025-12-31 | N/A | N/A | BIP | BIP rollout support 5 2025 | EssilorLuxottica | F. Taita | A. Seira | Operations | Back End | 60 | 0 | TO START | 0% | 2025 | 18 | [8 empty] | 9 | 9 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 42.86% | 39.13% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-05-15 | 2025-12-31 | N/A | N/A | BIP | BIP rollout support 5 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Management | 60 | 0 | TO START | 0% | 2025 | 10 | [8 empty] | 5 | 5 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 23.81% | 21.74% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-05-15 | 2025-12-31 | N/A | N/A | BIP | BIP rollout support 5 2025 | EssilorLuxottica | F. Taita | L. altobelli | Operations | Back End | 60 | 0 | TO START | 0% | 2025 | 8 | [8 empty] | 4 | 4 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 19.05% | 17.39% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-05-15 | 2025-12-31 | N/A | N/A | BIP | BIP rollout support 5 2025 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | Back End | 60 | 0 | TO START | 0% | 2025 | 20 | [8 empty] | 10 | 10 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 47.62% | 43.48% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-05-15 | 2025-12-31 | N/A | N/A | BIP | BIP rollout support 5 2025 | EssilorLuxottica | F. Taita | T. Baldi | Operations | Back End | 60 | 0 | TO START | 0% | 2025 | 4 | [8 empty] | 2 | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.524% | 8.696% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25086 | ABS25086 | LOGISTIC | LMS LIGHT 2025 | EssilorLuxottica | F. Taita | C. Piraccini | Operations | Data Engineering | 228 | 93 | ON GOING | 40.79% | 2025 | 71 | 5 | 6 | 8 | 8 | 8 | 10 | 10 | 5 | 10 | 10 | 10 | 8 | 27.78% | 30% | 38.1% | 36.36% | 40% | 50% | 43.48% | 41.67% | 47.62% | 43.48% | 47.62% | 36.36%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25086 | ABS25086 | LOGISTIC | LMS LIGHT 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Engineering | 228 | 93 | ON GOING | 40.79% | 2025 | 22 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 1 | 3 | 3 | 3 | 3 | 5.556% | 10% | 9.524% | 9.091% | 15% | 15% | 13.04% | 8.333% | 14.29% | 13.04% | 14.29% | 13.64%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25086 | ABS25086 | LOGISTIC | LMS LIGHT 2025 | EssilorLuxottica | F. Taita | M. Regini | Operations | Back End | 228 | 93 | ON GOING | 40.79% | 2025 | 66 | 5 | 5 | 5 | 6 | 6 | 10 | 10 | 5 | 9 | 9 | 9 | 8 | 27.78% | 25% | 23.81% | 27.27% | 30% | 50% | 43.48% | 41.67% | 42.86% | 39.13% | 42.86% | 36.36%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25086 | ABS25086 | LOGISTIC | LMS LIGHT 2025 | EssilorLuxottica | F. Taita | R. Bondi | Operations | Data Engineering | 228 | 93 | ON GOING | 40.79% | 2025 | 2 |  |  |  | 1 | 2 | [7 empty] | 0% | 0% | 0% | 4.545% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 2024-12-31 | ABS24164 | ALT | LOGISTIC | LMS TIJUANA | EssilorLuxottica | F. Taita | C. Piraccini | Operations | Data Engineering | 185 | 94 | ON GOING | 71% | 2025 | 12 | 3 | 6 | 6 | 6 | 6 | 6 | [6 empty] | 16.67% | 30% | 28.57% | 27.27% | 30% | 30% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-04-01 | 2024-12-31 | ABS24164 | ALT | LOGISTIC | LMS TIJUANA | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Engineering | 185 | 94 | ON GOING | 71% | 2025 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 2024-12-31 | ABS24164 | ALT | LOGISTIC | LMS TIJUANA | EssilorLuxottica | F. Taita | M. Regini | Operations | Back End | 185 | 94 | ON GOING | 71% | 2025 | 9 | 3 | 5 | 5 | 5 | 5 | 4 | [6 empty] | 16.67% | 25% | 23.81% | 22.73% | 25% | 20% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-06-01 | 2025-12-31 | N/A | N/A | LOGISTIC | LMS Tijuana wave 2 2025 | EssilorLuxottica | F. Taita | C. Piraccini | Operations | Data Engineering | 30 | 0 | TO START | 0% | 2025 | 8 | [6 empty] | 3 | 2 | 3 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 16.67% | 14.29% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-06-01 | 2025-12-31 | N/A | N/A | LOGISTIC | LMS Tijuana wave 2 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Engineering | 30 | 0 | TO START | 0% | 2025 | 4 | [5 empty] | 1 | 1 | 1 | 1 |  |  |  | 0% | 0% | 0% | 0% | 0% | 5% | 4.348% | 8.333% | 4.762% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-06-01 | 2025-12-31 | N/A | N/A | LOGISTIC | LMS Tijuana wave 2 2025 | EssilorLuxottica | F. Taita | M. Regini | Operations | Back End | 30 | 0 | TO START | 0% | 2025 | 15 | [5 empty] | 4 | 4 | 3 | 4 |  |  |  | 0% | 0% | 0% | 0% | 0% | 20% | 17.39% | 25% | 19.05% | 0% | 0% | 0%
CONTRACT | TIME MATERIAL | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25031 | ABS25031 | LOGISTIC | LUX DM Supporto ELECTRA 2025 - Enhancement & Rollout | EssilorLuxottica | F. Taita | C. Piraccini | Operations | Back End | 70 | 27 | ON GOING | 38.57% | 2025 | 12 |  | 2 | 1 | 5 | 5 | 2 | 1 | 1 | 1 | 1 | 1 |  | 0% | 10% | 4.762% | 22.73% | 25% | 10% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 0%
CONTRACT | TIME MATERIAL | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25031 | ABS25031 | LOGISTIC | LUX DM Supporto ELECTRA 2025 - Enhancement & Rollout | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Management | 70 | 27 | ON GOING | 38.57% | 2025 | 3 |  | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 0% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | TIME MATERIAL | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25031 | ABS25031 | LOGISTIC | LUX DM Supporto ELECTRA 2025 - Enhancement & Rollout | EssilorLuxottica | F. Taita | M. Regini | Operations | Back End | 70 | 27 | ON GOING | 38.57% | 2025 | 29 |  | 5 | 5 | 5 | 5 | 5 | 5 |  | 5 | 5 | 4 |  | 0% | 25% | 23.81% | 22.73% | 25% | 25% | 21.74% | 0% | 23.81% | 21.74% | 19.05% | 0%
CONTRACT | PRJ | Scrum | 2025 | 2025-01-01 | 2025-12-31 | ABS25083 | ABS25083 | LOGISTIC | OPTIMIZATION OF RTTF CHAINS | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | PM - Project Governance | 13 | 11 | CLOSED | 100% | 2025 | 0 | 1 | 2 | 1 | [9 empty] | 5.556% | 10% | 4.762% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2025 | 2025-01-01 | 2025-12-31 | ABS25083 | ABS25083 | LOGISTIC | OPTIMIZATION OF RTTF CHAINS | EssilorLuxottica | F. Taita | M. Vimercati | Operations | FrontEnd | 13 | 11 | CLOSED | 100% | 2025 | 0 |  | 1 | [10 empty] | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2025 | 2025-01-01 | 2025-12-31 | ABS25083 | ABS25083 | LOGISTIC | OPTIMIZATION OF RTTF CHAINS | EssilorLuxottica | F. Taita | S. Ben Younes | Operations | BackEnd | 13 | 11 | CLOSED | 100% | 2025 | 0 |  | 7 | 1 | [9 empty] | 0% | 35% | 4.762% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2025 | 2025-01-01 | 2025-12-31 | ABS25120 | ABS25120 | LOGISTIC | RTTF SUPPORT 2025 | EssilorLuxottica | F. Taita | A. Seira | Operations | Back End | 60 | 30 | ON GOING | 50% | 2025 | 14 |  |  | 3 | 3 | 3 | 8 | 3 | [5 empty] | 0% | 0% | 14.29% | 13.64% | 15% | 40% | 13.04% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2025 | 2025-01-01 | 2025-12-31 | ABS25120 | ABS25120 | LOGISTIC | RTTF SUPPORT 2025 | EssilorLuxottica | F. Taita | F. Reale | Operations | Front End | 60 | 30 | ON GOING | 50% | 2025 | 8 |  |  | 2 | 2 | 3 | 5 | [6 empty] | 0% | 0% | 9.524% | 9.091% | 15% | 25% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2025 | 2025-01-01 | 2025-12-31 | ABS25120 | ABS25120 | LOGISTIC | RTTF SUPPORT 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | PM - Project Governance | 60 | 30 | ON GOING | 50% | 2025 | 7 |  |  | 3 | 3 | 3 | 3 | 1 | [5 empty] | 0% | 0% | 14.29% | 13.64% | 15% | 15% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Scrum | 2025 | 2025-01-01 | 2025-12-31 | ABS25120 | ABS25120 | LOGISTIC | RTTF SUPPORT 2025 | EssilorLuxottica | F. Taita | S. Ben Younes | Operations | Back End | 60 | 30 | ON GOING | 50% | 2025 | 20 |  |  | 7 | 8 | 8 | 5 | 7 | [5 empty] | 0% | 0% | 33.33% | 36.36% | 40% | 25% | 30.43% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | RETAIL | VAPP CR Plus Q3Q4 2025 | EssilorLuxottica | F. Vassallo | A. Pirola | Operations | Front End | 250 | 0 | PROPOSAL | 0% | 2025 | 1 | [8 empty] | 1 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | RETAIL | VAPP CR Plus Q3Q4 2025 | EssilorLuxottica | F. Vassallo | D. Heba | Operations | Back End | 250 | 0 | PROPOSAL | 0% | 2025 | 27 | [8 empty] | 11 | 8 | 1 | 7 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 52.38% | 34.78% | 4.762% | 31.82%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | RETAIL | VAPP CR Plus Q3Q4 2025 | EssilorLuxottica | F. Vassallo | F. Vassallo | Delivery AMS | PM - Project Governance | 250 | 0 | PROPOSAL | 0% | 2025 | 38 | [6 empty] | 8 | 5 | 5 | 5 | 15 |  | 0% | 0% | 0% | 0% | 0% | 0% | 34.78% | 41.67% | 23.81% | 21.74% | 71.43% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | RETAIL | VAPP CR Plus Q3Q4 2025 | EssilorLuxottica | F. Vassallo | M. Mannarino | Operations | Data Engineering | 250 | 0 | PROPOSAL | 0% | 2025 | 36 | [6 empty] | 1 | 5 | 9 | 11 | 8 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 41.67% | 42.86% | 47.83% | 38.1% | 9.091%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | RETAIL | VAPP CR Plus Q3Q4 2025 | EssilorLuxottica | F. Vassallo | M. Vianelli | Delivery Projects | Analyst | 250 | 0 | PROPOSAL | 0% | 2025 | 19 | [8 empty] | 5 | 5 | 5 | 4 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 23.81% | 21.74% | 23.81% | 18.18%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | RETAIL | VAPP CR Plus Q3Q4 2025 | EssilorLuxottica | F. Vassallo | R. Grandi | Operations | Data Management | 250 | 0 | PROPOSAL | 0% | 2025 | 6 | [8 empty] | 1 | 5 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762% | 21.74% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25002 | ABS25002 | RETAIL | VAPP AMS App 2025 | EssilorLuxottica | F. Vassallo | A. Pirola | Operations | Front End | 800 | 287 | ON GOING | 35% | 2025 | 16 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 8.696% | 16.67% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25002 | ABS25002 | RETAIL | VAPP AMS App 2025 | EssilorLuxottica | F. Vassallo | C. Piraccini | Operations | Data Management | 800 | 287 | ON GOING | 35% | 2025 | 44 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 7 | 7 | 0% | 0% | 23.81% | 22.73% | 25% | 25% | 21.74% | 41.67% | 23.81% | 21.74% | 33.33% | 31.82%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25002 | ABS25002 | RETAIL | VAPP AMS App 2025 | EssilorLuxottica | F. Vassallo | D. Heba | Operations | Back End | 800 | 287 | ON GOING | 35% | 2025 | 55 | 16 | 16 | 17 | 5 | 5 | 5 | 5 | 8 | 8 | 8 | 8 | 8 | 88.89% | 80% | 80.95% | 22.73% | 25% | 25% | 21.74% | 66.67% | 38.1% | 34.78% | 38.1% | 36.36%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25002 | ABS25002 | RETAIL | VAPP AMS App 2025 | EssilorLuxottica | F. Vassallo | F. Vassallo | Delivery AMS | PM - Project Governance | 800 | 287 | ON GOING | 35% | 2025 | 127 | 18 | 18 | 2 | 15 | 18 | 15 | 15 | 10 | 18 | 18 | 18 | 15 | 100% | 90% | 9.524% | 68.18% | 90% | 75% | 65.22% | 83.33% | 85.71% | 78.26% | 85.71% | 68.18%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25002 | ABS25002 | RETAIL | VAPP AMS App 2025 | EssilorLuxottica | F. Vassallo | G. Mordà | Operations | Data Management | 800 | 287 | ON GOING | 35% | 2025 | 16 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 8.696% | 16.67% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25002 | ABS25002 | RETAIL | VAPP AMS App 2025 | EssilorLuxottica | F. Vassallo | M. Mannarino | Operations | Back End | 800 | 287 | ON GOING | 35% | 2025 | 40 | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 33.33% | 30% | 28.57% | 27.27% | 25% | 25% | 21.74% | 41.67% | 23.81% | 21.74% | 23.81% | 22.73%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25002 | ABS25002 | RETAIL | VAPP AMS App 2025 | EssilorLuxottica | F. Vassallo | M. Vianelli | Delivery Projects | Analyst | 800 | 287 | ON GOING | 35% | 2025 | 40 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 16.67% | 25% | 23.81% | 22.73% | 25% | 25% | 21.74% | 41.67% | 23.81% | 21.74% | 23.81% | 22.73%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25002 | ABS25002 | RETAIL | VAPP AMS App 2025 | EssilorLuxottica | F. Vassallo | P. Anzellotti | Operations | Technical Leader | 800 | 287 | ON GOING | 35% | 2025 | 0 | 2 | 2 | 2 | [9 empty] | 11.11% | 10% | 9.524% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25002 | ABS25002 | RETAIL | VAPP AMS App 2025 | EssilorLuxottica | F. Vassallo | R. Grandi | Operations | Data Management | 800 | 287 | ON GOING | 35% | 2025 | 72 | 15 | 18 | 15 | 8 | 10 | 8 | 8 | 8 | 8 | 10 | 10 | 10 | 83.33% | 90% | 71.43% | 36.36% | 50% | 40% | 34.78% | 66.67% | 38.1% | 43.48% | 47.62% | 45.45%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25032 | ABS25032 | RETAIL | VAPP CR Plus Q1Q2 2025 | EssilorLuxottica | F. Vassallo | A. Pirola | Operations | Front End | 190 | 56 | ON GOING | 30% | 2025 | 20 |  |  | 1 | 1 | 5 | 10 | 5 | [5 empty] | 0% | 0% | 4.762% | 4.545% | 25% | 50% | 21.74% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25032 | ABS25032 | RETAIL | VAPP CR Plus Q1Q2 2025 | EssilorLuxottica | F. Vassallo | S. Beltrami | Operations | Front End | 190 | 56 | ON GOING | 30% | 2025 | 4 |  |  |  |  | 2 | 2 | [6 empty] | 0% | 0% | 0% | 0% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25032 | ABS25032 | RETAIL | VAPP CR Plus Q1Q2 2025 | EssilorLuxottica | F. Vassallo | C. Piraccini | Operations | Data Management | 190 | 56 | ON GOING | 30% | 2025 | 10 |  |  | 1 | 7 | 2 | 5 | 3 | [5 empty] | 0% | 0% | 4.762% | 31.82% | 10% | 25% | 13.04% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25032 | ABS25032 | RETAIL | VAPP CR Plus Q1Q2 2025 | EssilorLuxottica | F. Vassallo | D. Heba | Operations | Back End | 190 | 56 | ON GOING | 30% | 2025 | 18 | 2 | 1 | 3 | 7 | 10 | 5 | 3 | [5 empty] | 11.11% | 5% | 14.29% | 31.82% | 50% | 25% | 13.04% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25032 | ABS25032 | RETAIL | VAPP CR Plus Q1Q2 2025 | EssilorLuxottica | F. Vassallo | F. Vassallo | Delivery AMS | PM - Project Governance | 190 | 56 | ON GOING | 30% | 2025 | 7 | 2 |  | 1 | 2 | 3 | 2 | 2 | [5 empty] | 11.11% | 0% | 4.762% | 9.091% | 15% | 10% | 8.696% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25032 | ABS25032 | RETAIL | VAPP CR Plus Q1Q2 2025 | EssilorLuxottica | F. Vassallo | M. Mannarino | Operations | Data Engineering | 190 | 56 | ON GOING | 30% | 2025 | 21 | 6 | 4 | 3 | 5 | 10 | 6 | 5 | [5 empty] | 33.33% | 20% | 14.29% | 22.73% | 50% | 30% | 21.74% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25032 | ABS25032 | RETAIL | VAPP CR Plus Q1Q2 2025 | EssilorLuxottica | F. Vassallo | M. Vianelli | Delivery Projects | Analyst | 190 | 56 | ON GOING | 30% | 2025 | 9 |  |  | 3 | 4 | 3 | 2 | 4 | [5 empty] | 0% | 0% | 14.29% | 18.18% | 15% | 10% | 17.39% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25032 | ABS25032 | RETAIL | VAPP CR Plus Q1Q2 2025 | EssilorLuxottica | F. Vassallo | R. Grandi | Operations | Data Management | 190 | 56 | ON GOING | 30% | 2025 | 13 |  |  | 3 | 10 | 5 | 5 | 3 | [5 empty] | 0% | 0% | 14.29% | 45.45% | 25% | 25% | 13.04% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | A. Pirola | Operations | Front End | 75 | 14 | ON GOING | 19% | 2025 | 0 | 2 | [11 empty] | 11.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | C. Piraccini | Operations | Data Management | 75 | 14 | ON GOING | 19% | 2025 | 0 | 6 | [11 empty] | 33.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | D. Heba | Operations | Back End | 75 | 14 | ON GOING | 19% | 2025 | 0 | 3 | [11 empty] | 16.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | F. Vassallo | Delivery AMS | PM - Project Governance | 75 | 14 | ON GOING | 19% | 2025 | 0 | 3 | [11 empty] | 16.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | M. Mannarino | Operations | Data Engineering | 75 | 14 | ON GOING | 19% | 2025 | 0 | 3 | [11 empty] | 16.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | M. Vianelli | Consulting | Analyst | 75 | 14 | ON GOING | 19% | 2025 | 0 | 2 | [11 empty] | 11.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | R. Grandi | Operations | Data Management | 75 | 14 | ON GOING | 19% | 2025 | 0 | 1 | [11 empty] | 5.556% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Watefall | 2024-2025 | 2025-10-01 | 2025-09-30 | ABS24217 | ABS24217 | CRM | Global CS B2B AMS 2024-2025 | EssilorLuxottica | G. Galati | G. Galati | Delivery AMS | PM - Project Governance | 12 | 0 | ON GOING | 0% | 2025 | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  | 0.25 |  |  |  | 1.389% | 1.25% | 1.19% | 1.136% | 1.25% | 1.25% | 1.087% | 0% | 1.19% | 0% | 0% | 0%
CONTRACT | AMS | Watefall | 2024-2025 | 2025-10-01 | 2025-09-30 | ABS24217 | ABS24217 | CRM | Global CS B2B AMS 2024-2025 | EssilorLuxottica | G. Galati | M. Toci | Operations | Back End | 12 | 0 | ON GOING | 0% | 2025 | 3 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 |  | 0.75 |  |  |  | 4.167% | 3.75% | 3.571% | 3.409% | 3.75% | 3.75% | 3.261% | 0% | 3.571% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | Logistic | CTRL-Tower Atlanta AMS 2025 | EssilorLuxottica | G. Luongo | A. Crescimone | Operations | Back End | 212 | 21 | ON GOING | 0% | 2025 | 16 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 5.556% | 5% | 4.762% | 4.545% | 10% | 10% | 8.696% | 16.67% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | Logistic | CTRL-Tower Atlanta AMS 2025 | EssilorLuxottica | G. Luongo | A. Saija | Operations | Back End | 212 | 21 | ON GOING | 0% | 2025 | 0 | 1 | 1 | 1 | 1 | [8 empty] | 5.556% | 5% | 4.762% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | Logistic | CTRL-Tower Atlanta AMS 2025 | EssilorLuxottica | G. Luongo | G. Luongo | Delivery AMS | PM - Project Governance | 212 | 21 | ON GOING | 0% | 2025 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | Logistic | CTRL-Tower Atlanta AMS 2025 | EssilorLuxottica | G. Luongo | J. Daci | Operations | Data Management | 212 | 21 | ON GOING | 0% | 2025 | 16 | 0 | 0 | 0 | 2 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 9.091% | 80% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | Logistic | CTRL-Tower Atlanta AMS 2025 | EssilorLuxottica | G. Luongo | L. Gullotto | Operations | Back End | 212 | 21 | ON GOING | 0% | 2025 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | Logistic | CTRL-Tower Atlanta AMS 2025 | EssilorLuxottica | G. Luongo | P. Assirelli | Operations | Technical Leader | 212 | 21 | ON GOING | 0% | 2025 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25023 | ABS25023 | RETAIL | OneLRA AMS 2025 | EssilorLuxottica | G. Luongo | A. Crescimone | Operations | Back End | 1610 | 320 | ON GOING | 0% | 2025 | 103 | 17 | 19 | 2 | 21 | 2 | 18 | 21 | 1 | 19 | 21 | 19 | 2 | 94.44% | 95% | 9.524% | 95.45% | 10% | 90% | 91.3% | 8.333% | 90.48% | 91.3% | 90.48% | 9.091%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25023 | ABS25023 | RETAIL | OneLRA AMS 2025 | EssilorLuxottica | G. Luongo | A. Saija | Operations | Back End | 1610 | 320 | ON GOING | 0% | 2025 | 20 | 6 | 2 | 21 | 18 | 20 | [7 empty] | 33.33% | 10% | 100% | 81.82% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25023 | ABS25023 | RETAIL | OneLRA AMS 2025 | EssilorLuxottica | G. Luongo | B. Capotorto | Operations | Analyst | 1610 | 320 | ON GOING | 0% | 2025 | 109 | 14 | 18 | 19 | 15 | 15 | 13 | 16 | 6 | 14 | 16 | 14 | 15 | 77.78% | 90% | 90.48% | 68.18% | 75% | 65% | 69.57% | 50% | 66.67% | 69.57% | 66.67% | 68.18%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25023 | ABS25023 | RETAIL | OneLRA AMS 2025 | EssilorLuxottica | G. Luongo | G. Luongo | Delivery AMS | PM - Project Governance | 1610 | 320 | ON GOING | 0% | 2025 | 104 | 2 | 22 | 2 | 19 | 19 | 17 | 2 | 9 | 18 | 2 | 18 | 19 | 11.11% | 110% | 9.524% | 86.36% | 95% | 85% | 8.696% | 75% | 85.71% | 8.696% | 85.71% | 86.36%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25023 | ABS25023 | RETAIL | OneLRA AMS 2025 | EssilorLuxottica | G. Luongo | G. Mordà | Operations | Reperibilità | 1610 | 320 | ON GOING | 0% | 2025 | 14 | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 10% | 8.696% | 16.67% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25023 | ABS25023 | RETAIL | OneLRA AMS 2025 | EssilorLuxottica | G. Luongo | L. Altobelli | Operations | Back End | 1610 | 320 | ON GOING | 0% | 2025 | 78 |  |  |  | 11 | 8.5 | 9 | 10.5 | 6 | 11 | 11 | 11 | 11 | 0% | 0% | 0% | 50% | 42.5% | 45% | 45.65% | 50% | 52.38% | 47.83% | 52.38% | 50%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25023 | ABS25023 | RETAIL | OneLRA AMS 2025 | EssilorLuxottica | G. Luongo | L. Gullotto | Operations | Back End | 1610 | 320 | ON GOING | 0% | 2025 | 116 | 17 | 19 | 13 | 16 | 16 | 14 | 17 | 6 | 15 | 17 | 15 | 16 | 94.44% | 95% | 61.9% | 72.73% | 80% | 70% | 73.91% | 50% | 71.43% | 73.91% | 71.43% | 72.73%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25023 | ABS25023 | RETAIL | OneLRA AMS 2025 | EssilorLuxottica | G. Luongo | P. Assirelli | Operations | Analyst | 1610 | 320 | ON GOING | 0% | 2025 | 60 | 2 | 15 | 13 | 11 | 6 | 9 | 12 | 5 | 5 | 12 | 5 | 6 | 11.11% | 75% | 61.9% | 50% | 30% | 45% | 52.17% | 41.67% | 23.81% | 52.17% | 23.81% | 27.27%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25023 | ABS25023 | RETAIL | OneLRA AMS 2025 | EssilorLuxottica | G. Luongo | P. Gamboni | Operations | Back End | 1610 | 320 | ON GOING | 0% | 2025 | 118 |  |  |  | 22 | 22 | 2 | 18 | 9 | 16 | 18 | 16 | 17 | 0% | 0% | 0% | 100% | 110% | 10% | 78.26% | 75% | 76.19% | 78.26% | 76.19% | 77.27%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-04-30 | ABS25030 | ABS25030 | RETAIL | ONELRA Enhancements plus5 2025 Q1 | EssilorLuxottica | G. Luongo | B. Capotorto | Operations | BackEnd | 78 | 75 | CLOSED | 100% | 2025 | 0 | 4 | 2 | 2 | [9 empty] | 22.22% | 10% | 9.524% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-04-30 | ABS25030 | ABS25030 | RETAIL | ONELRA Enhancements plus5 2025 Q1 | EssilorLuxottica | G. Luongo | C. Piraccini | Operations | BackEnd | 78 | 75 | CLOSED | 100% | 2025 | 0 |  | 1 | [10 empty] | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-04-30 | ABS25030 | ABS25030 | RETAIL | ONELRA Enhancements plus5 2025 Q1 | EssilorLuxottica | G. Luongo | G. Luongo | Delivery AMS | PM - Project Governance | 78 | 75 | CLOSED | 100% | 2025 | 0 | 2 | 2 | 2 | [9 empty] | 11.11% | 10% | 9.524% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-04-30 | ABS25030 | ABS25030 | RETAIL | ONELRA Enhancements plus5 2025 Q1 | EssilorLuxottica | G. Luongo | L. Gullotto | Operations | BackEnd | 78 | 75 | CLOSED | 100% | 2025 | 0 |  |  | 7 | [9 empty] | 0% | 0% | 33.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-04-30 | ABS25030 | ABS25030 | RETAIL | ONELRA Enhancements plus5 2025 Q1 | EssilorLuxottica | G. Luongo | M. Regini | Operations | BackEnd | 78 | 75 | CLOSED | 100% | 2025 | 0 |  | 1 | [10 empty] | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-04-30 | ABS25030 | ABS25030 | RETAIL | ONELRA Enhancements plus5 2025 Q1 | EssilorLuxottica | G. Luongo | P. Assirelli | Operations | Technical Leader | 78 | 75 | CLOSED | 100% | 2025 | 0 | 15 | 4 | 7 | [9 empty] | 83.33% | 20% | 33.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-04-01 | 2025-06-30 | N/A | N/A | RETAIL | ONELRA Enhancements plus5 2025 Q2 | EssilorLuxottica | G. Luongo | B. Capotorto | Operations | Back End | 100 | 0 | ON GOING | 0% | 2025 | 14 |  |  |  | 7 | 7 | 7 | [6 empty] | 0% | 0% | 0% | 31.82% | 35% | 35% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-04-01 | 2025-06-30 | N/A | N/A | RETAIL | ONELRA Enhancements plus5 2025 Q2 | EssilorLuxottica | G. Luongo | G. Luongo | Delivery AMS | PM - Project Governance | 100 | 0 | ON GOING | 0% | 2025 | 4 |  |  |  | 2 | 2 | 2 | [6 empty] | 0% | 0% | 0% | 9.091% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-04-01 | 2025-06-30 | N/A | N/A | RETAIL | ONELRA Enhancements plus5 2025 Q2 | EssilorLuxottica | G. Luongo | L. Gullotto | Operations | Back End | 100 | 0 | ON GOING | 0% | 2025 | 10 |  |  |  | 5 | 5 | 5 | [6 empty] | 0% | 0% | 0% | 22.73% | 25% | 25% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-04-01 | 2025-06-30 | N/A | N/A | RETAIL | ONELRA Enhancements plus5 2025 Q2 | EssilorLuxottica | G. Luongo | P. Assirelli | Operations | Technical Leader | 100 | 0 | ON GOING | 0% | 2025 | 16 |  |  |  | 1 | 15 | 1 | [6 empty] | 0% | 0% | 0% | 4.545% | 75% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-09-30 | N/A | N/A | RETAIL | ONELRA Enhancements plus5 2025 Q3 | EssilorLuxottica | G. Luongo | B. Capotorto | Operations | Back End | 100 | 0 | TO START | 10% | 2025 | 20 | [6 empty] | 7 | 6 | 7 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 30.43% | 50% | 33.33% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-09-30 | N/A | N/A | RETAIL | ONELRA Enhancements plus5 2025 Q3 | EssilorLuxottica | G. Luongo | G. Luongo | Delivery AMS | PM - Project Governance | 100 | 0 | TO START | 10% | 2025 | 6 | [6 empty] | 2 | 2 | 2 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 16.67% | 9.524% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-09-30 | N/A | N/A | RETAIL | ONELRA Enhancements plus5 2025 Q3 | EssilorLuxottica | G. Luongo | L. Gullotto | Operations | Back End | 100 | 0 | TO START | 10% | 2025 | 15 | [6 empty] | 5 | 5 | 5 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 41.67% | 23.81% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-09-30 | N/A | N/A | RETAIL | ONELRA Enhancements plus5 2025 Q3 | EssilorLuxottica | G. Luongo | P. Assirelli | Operations | Technical Leader | 100 | 0 | TO START | 10% | 2025 | 22 | [6 empty] | 1 | 6 | 15 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 50% | 71.43% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-09-30 | N/A | N/A | RETAIL | ONELRA Enhancements plus5 2025 Q3 | EssilorLuxottica | G. Luongo | P. Gamboni | Operations | Back End | 100 | 0 | TO START | 10% | 2025 | 13 | [6 empty] | 5 | 3 | 5 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 25% | 23.81% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-10-01 | 2025-12-31 | N/A | N/A | RETAIL | ONELRA Enhancements plus5 2025 Q4 | EssilorLuxottica | G. Luongo | B. Capotorto | Operations | Back End | 100 | 0 | TO START | 10% | 2025 | 21 | [9 empty] | 7 | 7 | 7 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30.43% | 33.33% | 31.82%
A CONSUMO | AMS | Waterfall | 2025 | 2025-10-01 | 2025-12-31 | N/A | N/A | RETAIL | ONELRA Enhancements plus5 2025 Q4 | EssilorLuxottica | G. Luongo | G. Luongo | Delivery AMS | PM - Project Governance | 100 | 0 | TO START | 10% | 2025 | 6 | [9 empty] | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 9.524% | 9.091%
A CONSUMO | AMS | Waterfall | 2025 | 2025-10-01 | 2025-12-31 | N/A | N/A | RETAIL | ONELRA Enhancements plus5 2025 Q4 | EssilorLuxottica | G. Luongo | L. Gullotto | Operations | Back End | 100 | 0 | TO START | 10% | 2025 | 15 | [9 empty] | 5 | 5 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 23.81% | 22.73%
A CONSUMO | AMS | Waterfall | 2025 | 2025-10-01 | 2025-12-31 | N/A | N/A | RETAIL | ONELRA Enhancements plus5 2025 Q4 | EssilorLuxottica | G. Luongo | P. Assirelli | Operations | Technical Leader | 100 | 0 | TO START | 10% | 2025 | 31 | [9 empty] | 1 | 15 | 15 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 71.43% | 68.18%
A CONSUMO | AMS | Waterfall | 2025 | 2025-10-01 | 2025-12-31 | N/A | N/A | RETAIL | ONELRA Enhancements plus5 2025 Q4 | EssilorLuxottica | G. Luongo | P. Gamboni | Operations | Back End | 100 | 0 | TO START | 10% | 2025 | 15 | [9 empty] | 5 | 5 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 23.81% | 22.73%
INTERNAL TRAINING | FORMAZIONE |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | ATD | OTHER | Training SAP BW/4HANA | Abstract | G. Luongo | G. Mordà | Operations | Back End - Junior | 0 | 0 | ON GOING | 0% | 2025 | 8 |  |  |  | 5 | 5 | 3 | [6 empty] | 0% | 0% | 0% | 22.73% | 25% | 15% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | RETAIL | Edison Targeting & Churn | Edison | G. Sironi | A. Imbimbo | AI Operations | Data Scientist | 110 | 0 | PROPOSAL | 0% | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | RETAIL | Edison Targeting & Churn | Edison | G. Sironi | F. Malvezzi | AI Operations | Data Scientist | 110 | 0 | PROPOSAL | 0% | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | RETAIL | Edison Targeting & Churn | Edison | G. Sironi | G. Sironi | AI Operations | PM - Project Governance | 110 | 0 | PROPOSAL | 0% | 2025 | 6 |  |  |  | 2 | 2 | 2 | 1 | 1 |  |  |  |  | 0% | 0% | 0% | 9.091% | 10% | 10% | 4.348% | 8.333% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | RETAIL | Edison Targeting & Churn | Edison | G. Sironi | M. Gomitoni | AI Operations | Technical Leader | 110 | 0 | PROPOSAL | 0% | 2025 | 10 |  |  |  | 5 | 4 | 3 | 3 | [5 empty] | 0% | 0% | 0% | 22.73% | 20% | 15% | 13.04% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | RETAIL | Edison Targeting & Churn | Edison | G. Sironi | V. Echarry | AI Operations | Data Scientist | 110 | 0 | PROPOSAL | 0% | 2025 | 20 |  |  |  | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 0% | 0% | 0% | 22.73% | 25% | 25% | 21.74% | 41.67% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 - Modelling CR | EssilorLuxottica | G. SIRONI | A. Imbimbo | Operations | Data Scientist | 105 | 0 | PROPOSAL | 0% | 2025 | 4 |  |  |  | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 0% | 0% | 0% | 4.545% | 5% | 5% | 4.348% | 0% | 4.762% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 - Modelling CR | EssilorLuxottica | G. SIRONI | A. Pirola | Operations | Front End | 105 | 0 | PROPOSAL | 0% | 2025 | 8 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 2 | 1 |  |  |  | 5.556% | 5% | 4.762% | 9.091% | 5% | 10% | 8.696% | 16.67% | 4.762% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 - Modelling CR | EssilorLuxottica | G. SIRONI | G. Lopez | Operations | Front End | 105 | 0 | PROPOSAL | 0% | 2025 | 0 | 1 | 1 | 5 | [9 empty] | 5.556% | 5% | 23.81% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 - Modelling CR | EssilorLuxottica | G. SIRONI | G. Mordà | Operations | Data Management | 105 | 0 | PROPOSAL | 0% | 2025 | 0 | 1 | 1 | 1 | [9 empty] | 5.556% | 5% | 4.762% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 - Modelling CR | EssilorLuxottica | G. SIRONI | G. Sironi | Operations | PM - Project Governance | 105 | 0 | PROPOSAL | 0% | 2025 | 0 | 1 | 1 | 1 | [9 empty] | 5.556% | 5% | 4.762% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 - Modelling CR | EssilorLuxottica | G. SIRONI | M. Vianelli | Delivery Projects | Analyst | 105 | 0 | PROPOSAL | 0% | 2025 | 6 | 1 |  |  | 1 | 3 | 1 | 1 |  | 1 |  |  |  | 5.556% | 0% | 0% | 4.545% | 15% | 5% | 4.348% | 0% | 4.762% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 - Modelling CR | EssilorLuxottica | G. SIRONI | N. Pescione | Operations | Back End | 105 | 0 | PROPOSAL | 0% | 2025 | 0 | 1 | 1 | 5 | [9 empty] | 5.556% | 5% | 23.81% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 - Modelling CR | EssilorLuxottica | G. SIRONI | P. Anzellotti | Operations | Team Leadership Support | 105 | 0 | PROPOSAL | 0% | 2025 | 0 | 3 | 3 | 3 | [9 empty] | 16.67% | 15% | 14.29% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | RETAIL | ELRTT - RETAIL TESTING TOOL W4 | EssilorLuxottica | G. SIRONI | A. Imbimbo | Operations | Data Scientist | 105 | 0 | PROPOSAL | 0% | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | RETAIL | ELRTT - RETAIL TESTING TOOL W4 | EssilorLuxottica | G. SIRONI | G. Lopez | Operations | Front End | 105 | 0 | PROPOSAL | 0% | 2025 | 22 |  |  |  |  | 5 | 5 | 5 | 2 | 5 |  |  |  | 0% | 0% | 0% | 0% | 25% | 25% | 21.74% | 16.67% | 23.81% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | RETAIL | ELRTT - RETAIL TESTING TOOL W4 | EssilorLuxottica | G. SIRONI | G. Mordà | Operations | Data Management | 105 | 0 | PROPOSAL | 0% | 2025 | 1 |  |  |  | 1 | 1 | [7 empty] | 0% | 0% | 0% | 4.545% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | RETAIL | ELRTT - RETAIL TESTING TOOL W4 | EssilorLuxottica | G. SIRONI | G. Sironi | Operations | PM - Project Governance | 105 | 0 | PROPOSAL | 0% | 2025 | 4 |  |  |  | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 0% | 0% | 0% | 4.545% | 5% | 5% | 4.348% | 0% | 4.762% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | RETAIL | ELRTT - RETAIL TESTING TOOL W4 | EssilorLuxottica | G. SIRONI | N. Pescione | Operations | Back End | 105 | 0 | PROPOSAL | 0% | 2025 | 17 |  |  |  | 5 | 1 | 1 | 5 | 5 | 5 |  |  |  | 0% | 0% | 0% | 22.73% | 5% | 5% | 21.74% | 41.67% | 23.81% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | RETAIL | ELRTT - RETAIL TESTING TOOL W4 | EssilorLuxottica | G. SIRONI | P. Anzellotti | Operations | Team Leadership Support | 105 | 0 | PROPOSAL | 0% | 2025 | 9 |  |  |  | 3 | 3 | 3 | 2 | 1 |  |  |  |  | 0% | 0% | 0% | 13.64% | 15% | 15% | 8.696% | 8.333% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-06-01 | N/A | N/A | Lucy | Lucy Control Tower GenAI - Productionalization | EssilorLuxottica | G. SIRONI | A. Imbimbo | AI Operations | Data Scientist | 60 | 0 | PROPOSAL | 0% | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-06-01 | N/A | N/A | Lucy | Lucy Control Tower GenAI - Productionalization | EssilorLuxottica | G. SIRONI | M. Gomitoni | AI Operations | Data Scientist | 60 | 0 | PROPOSAL | 0% | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | LUCY | Lucy | Lucy4 Lease AI | EssilorLuxottica | G. Sironi | A. Imbimbo | AI Operations | Data Scientist | 100 | 0 | ON GOING | 0 | 2025 | 20 |  |  | 5 | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 0% | 0% | 23.81% | 22.73% | 25% | 25% | 21.74% | 41.67% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | LUCY | Lucy | Lucy4 Lease AI | EssilorLuxottica | G. Sironi | F. Malvezzi | AI Operations | Data Scientist | 100 | 0 | ON GOING | 0 | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | LUCY | Lucy | Lucy4 Lease AI | EssilorLuxottica | G. Sironi | G. Sironi | AI Operations | PM - Project Governance | 100 | 0 | ON GOING | 0 | 2025 | 12 |  |  | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  | 0% | 0% | 14.29% | 13.64% | 15% | 15% | 13.04% | 25% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | LUCY | Lucy | Lucy4 Lease AI | EssilorLuxottica | G. Sironi | M. Gomitoni | AI Operations | Technical Leader | 100 | 0 | ON GOING | 0 | 2025 | 20 |  |  | 5 | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 0% | 0% | 23.81% | 22.73% | 25% | 25% | 21.74% | 41.67% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | LUCY | Lucy | Lucy4 Lease AI | EssilorLuxottica | G. Sironi | V. Echarry | AI Operations | Data Scientist | 100 | 0 | ON GOING | 0 | 2025 | 20 |  |  | 5 | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 0% | 0% | 23.81% | 22.73% | 25% | 25% | 21.74% | 41.67% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | RETAIL | RC & Rec - Migration & New Features 2025 | EssilorLuxottica | G. SIRONI | A. Imbimbo | AI Operations | Data Scientist | 150 | 0 | PROPOSAL | 0% | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | RETAIL | RC & Rec - Migration & New Features 2025 | EssilorLuxottica | G. SIRONI | F. Malvezzi | AI Operations | Data Scientist | 150 | 0 | PROPOSAL | 0% | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | RETAIL | RC & Rec - Migration & New Features 2025 | EssilorLuxottica | G. SIRONI | G. Sabbatini | AI Operations | Data Engineering | 150 | 0 | PROPOSAL | 0% | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | RETAIL | RC & Rec - Migration & New Features 2025 | EssilorLuxottica | G. SIRONI | G. Sironi | AI Operations | PM - Project Governance | 150 | 0 | PROPOSAL | 0% | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | RETAIL | RC & Rec - Migration & New Features 2025 | EssilorLuxottica | G. SIRONI | M. Gomitoni | AI Operations | Technical Leader | 150 | 0 | PROPOSAL | 0% | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | RETAIL | RC & Rec - Migration & New Features 2025 | EssilorLuxottica | G. SIRONI | V. Echarry | AI Operations | Data Scientist | 150 | 0 | PROPOSAL | 0% | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | RETAIL | Red Carpet Events 2025 | EssilorLuxottica | G. SIRONI | A. Imbimbo | Operations | Data Scientist | 80 | 0 | PROPOSAL | 0% | 2025 | 2 |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  | 0% | 5% | 0% | 0% | 0% | 0% | 4.348% | 0% | 0% | 0% | 4.762% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | RETAIL | Red Carpet Events 2025 | EssilorLuxottica | G. SIRONI | F. Malvezzi | Operations | Data Scientist | 80 | 0 | PROPOSAL | 0% | 2025 | 24 | 2 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 5 | 2 | 11.11% | 30% | 14.29% | 13.64% | 15% | 15% | 13.04% | 25% | 9.524% | 13.04% | 23.81% | 9.091%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | RETAIL | Red Carpet Events 2025 | EssilorLuxottica | G. SIRONI | G. Sabbatini | Operations | Data Engineering | 80 | 0 | PROPOSAL | 0% | 2025 | 6 | 1 | 1 |  |  |  | 1 | 1 |  | 1 | 1 | 1 | 1 | 5.556% | 5% | 0% | 0% | 0% | 5% | 4.348% | 0% | 4.762% | 4.348% | 4.762% | 4.545%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | RETAIL | Red Carpet Events 2025 | EssilorLuxottica | G. SIRONI | G. Sironi | Operations | PM - Project Governance | 80 | 0 | PROPOSAL | 0% | 2025 | 8 | 1 | 2 |  |  |  | 1 | 2 |  | 1 | 1 | 2 | 1 | 5.556% | 10% | 0% | 0% | 0% | 5% | 8.696% | 0% | 4.762% | 4.348% | 9.524% | 4.545%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | RETAIL | Red Carpet Events 2025 | EssilorLuxottica | G. SIRONI | M. Gomitoni | Operations | Technical Leader | 80 | 0 | PROPOSAL | 0% | 2025 | 8 | 1 | 2 |  |  |  | 1 | 2 |  | 1 | 1 | 2 | 1 | 5.556% | 10% | 0% | 0% | 0% | 5% | 8.696% | 0% | 4.762% | 4.348% | 9.524% | 4.545%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | RETAIL | Red Carpet Events 2025 | EssilorLuxottica | G. SIRONI | V. Echarry | Operations | Data Scientist | 80 | 0 | PROPOSAL | 0 | 2025 | 24 |  | 6 |  |  | 3 | 3 | 3 | 3 | 2 | 3 | 5 | 2 | 0% | 30% | 0% | 0% | 15% | 15% | 13.04% | 25% | 9.524% | 13.04% | 23.81% | 9.091%
CONTRACT | PRJ |  | 2025 | 2025-04-01 | 2025-09-01 | ABS25208 | ABS25208 | LOGISTIC | CT Electra Complete Pair and LABEX | EssilorLuxottica | L. BARIANI | A. Strada | Operations | Back End | 30 | 0 | ON GOING | 0% | 2025 | 1 |  |  |  | 12 | 1 | [7 empty] | 0% | 0% | 0% | 54.55% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-04-01 | 2025-09-01 | ABS25208 | ABS25208 | LOGISTIC | CT Electra Complete Pair and LABEX | EssilorLuxottica | L. BARIANI | L. BARIANI | Operations | PM - Project Governance | 30 | 0 | ON GOING | 0% | 2025 | 1 |  |  |  | 2 | 1 | [7 empty] | 0% | 0% | 0% | 9.091% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-04-01 | 2025-09-01 | ABS25208 | ABS25208 | LOGISTIC | CT Electra Complete Pair and LABEX | EssilorLuxottica | L. BARIANI | M. Sabarese | Operations | Front End | 30 | 0 | ON GOING | 0% | 2025 | 2 |  |  |  | 3 | 2 | [7 empty] | 0% | 0% | 0% | 13.64% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | A. BRANDIZZI | Operations | FrontEnd | 800 | 0 | CLOSED | 0 | 2025 | 0 | 17 | 2 | 22 | [9 empty] | 94.44% | 10% | 104.8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | A. TORONE | Delivery AMS | Analysis | 800 | 190 | CLOSED | 0 | 2025 | 0 | 6 | 6 | 6 | [9 empty] | 33.33% | 30% | 28.57% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | C. DI LORENZO | Delivery Projects | Analysis | 800 | 190 | CLOSED | 0 | 2025 | 0 | 6 | 6 | 6 | [9 empty] | 33.33% | 30% | 28.57% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | C. TIBERTI | Operations | Analysis | 800 | 190 | CLOSED | 0 | 2025 | 0 | 22 | 22 | 22 | [9 empty] | 122.2% | 110% | 104.8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | F. SCOGNAMIGLIO | Operations | Data Engineering | 800 | 0 | CLOSED | 0 | 2025 | 0 | 17 | 2 | 2 | [9 empty] | 94.44% | 10% | 9.524% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | F. SPACAGNA | Operations | Data Engineering | 800 | 0 | CLOSED | 0 | 2025 | 0 | 6 | 6 | 6 | [9 empty] | 33.33% | 30% | 28.57% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | G. TARTAGLIA | Operations | BackEnd | 800 | 0 | CLOSED | 0 | 2025 | 0 | 17 | 2 | 22 | [9 empty] | 94.44% | 10% | 104.8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | I. OSTYMCHUCK | Operations | Data Engineering | 800 | 0 | CLOSED | 0 | 2025 | 0 | 17 | 2 | 2 | [9 empty] | 94.44% | 10% | 9.524% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | J. SORGATO | #N/A | Analysis | 800 | 190 | CLOSED | 0 | 2025 | 0 | 4 | 4 | 4 | [9 empty] | 22.22% | 20% | 19.05% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | L. BARIANI | Delivery Projects | PM - Project Governance | 800 | 190 | CLOSED | 0 | 2025 | 0 | 6 | 6 | 6 | [9 empty] | 33.33% | 30% | 28.57% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | L. BARIANI | Delivery Projects | Analysis | 800 | 190 | CLOSED | 0 | 2025 | 0 | 12 | 15 | 15 | [9 empty] | 66.67% | 75% | 71.43% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | L. CATTANEO | #N/A | Analysis | 800 | 190 | CLOSED | 0 | 2025 | 0 | 4 | 4 | 4 | [9 empty] | 22.22% | 20% | 19.05% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | M. Porcu | Operations | Technical Leader | 800 | 0 | CLOSED | 0 | 2025 | 0 | 15 | 15 | 15 | [9 empty] | 83.33% | 75% | 71.43% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | M. TOCI | Operations | BackEnd | 800 | 0 | CLOSED | 0 | 2025 | 0 | 17 | 2 | 2 | [9 empty] | 94.44% | 10% | 9.524% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | O. SAGAZIO | Operations | PM - Project Governance | 800 | 0 | CLOSED | 0 | 2025 | 0 | 6 | 6 | 6 | [9 empty] | 33.33% | 30% | 28.57% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | S. Beltrami | Operations | BackEnd | 800 | 0 | CLOSED | 0 | 2025 | 0 | 6 | 6 | 6 | [9 empty] | 33.33% | 30% | 28.57% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | S. BEN YOUNES | Operations | Analysis | 800 | 190 | CLOSED | 0 | 2025 | 0 | 6 | 6 | 6 | [9 empty] | 33.33% | 30% | 28.57% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | S. DELLE FAVE | Operations | FrontEnd | 800 | 0 | CLOSED | 0 | 2025 | 0 | 17 | 2 | 22 | [9 empty] | 94.44% | 10% | 104.8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ | Waterfall | 2025 | 2025-02-02 | 2025-03-06 | ABS25041 | N/A | EPM | Nuance & Meta Integration | EssilorLuxottica | L. BARIANI | E. STORTI | Delivery Projects | Analyst | 20 | 0 | ON GOING | 50% | 2025 | 0 |  | 6 | [10 empty] | 0% | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ | Waterfall | 2025 | 2025-02-02 | 2025-03-06 | ABS25041 | N/A | EPM | Nuance & Meta Integration | EssilorLuxottica | L. BARIANI | G. MINERVINI | Operations | Back End | 20 | 0 | ON GOING | 50% | 2025 | 0 |  | 5 | [10 empty] | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ | Waterfall | 2025 | 2025-02-02 | 2025-03-06 | ABS25041 | N/A | EPM | Nuance & Meta Integration | EssilorLuxottica | L. BARIANI | L. BARIANI | Delivery Projects | PM - Project Governance | 20 | 0 | ON GOING | 50% | 2025 | 0 |  | 2 | [10 empty] | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ | Waterfall | 2025 | 2025-02-02 | 2025-03-06 | ABS25041 | N/A | EPM | Nuance & Meta Integration | EssilorLuxottica | L. BARIANI | N. FRAGALE | Operations | Back End | 20 | 0 | ON GOING | 50% | 2025 | 0 |  | 5 | [10 empty] | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ | Waterfall | 2025 | 2025-02-02 | 2025-03-06 | ABS25041 | N/A | EPM | Nuance & Meta Integration | EssilorLuxottica | L. BARIANI | P. PIERONI | Operations | Solution Architect | 20 | 0 | ON GOING | 50% | 2025 | 0 |  | 2 | [10 empty] | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ | Waterfall | 2025 | 2025-02-02 | 2025-03-06 | ABS25041 | N/A | EPM | Nuance & Meta Integration | EssilorLuxottica | L. BARIANI | S. PREZIOSA | Delivery Projects | Analyst | 20 | 0 | ON GOING | 50% | 2025 | 0 |  | 2 | [10 empty] | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ |  | 2025 | 2025-05-18 | 2025-07-30 | N/A | N/A | EPM | One View - FDW | EssilorLuxottica | L. Bariani | L. Bariani | Delivery Projects | PM - Project Governance | 90 | 0 | PROPOSAL | 0% | 2025 | 16 |  |  |  |  | 5 | 6 | 5 | [5 empty] | 0% | 0% | 0% | 0% | 25% | 30% | 21.74% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ |  | 2025 | 2025-05-18 | 2025-07-30 | N/A | N/A | EPM | One View - FDW | EssilorLuxottica | L. Bariani | A. Strada | Operations | Back End | 90 | 0 | PROPOSAL | 0% | 2025 | 6 |  |  |  |  | 2 | 2 | 2 | [5 empty] | 0% | 0% | 0% | 0% | 10% | 10% | 8.696% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ |  | 2025 | 2025-05-18 | 2025-07-30 | N/A | N/A | EPM | One View - FDW | EssilorLuxottica | L. Bariani | C. Piraccini | Operations | Back End | 90 | 0 | PROPOSAL | 0% | 2025 | 21 |  |  |  |  | 5 | 8 | 8 | [5 empty] | 0% | 0% | 0% | 0% | 25% | 40% | 34.78% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ |  | 2025 | 2025-05-18 | 2025-07-30 | N/A | N/A | EPM | One View - FDW | EssilorLuxottica | L. Bariani | M. Regini | Operations | Back End | 90 | 0 | PROPOSAL | 0% | 2025 | 21 |  |  |  |  | 5 | 8 | 8 | [5 empty] | 0% | 0% | 0% | 0% | 25% | 40% | 34.78% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ |  | 2025 | 2025-05-18 | 2025-07-30 | N/A | N/A | EPM | One View - FDW | EssilorLuxottica | L. Bariani | S. BEN YOUNES | Delivery Projects | Back End | 90 | 0 | PROPOSAL | 0% | 2025 | 26 |  |  |  |  | 8 | 9 | 9 | [5 empty] | 0% | 0% | 0% | 0% | 40% | 45% | 39.13% | 0% | 0% | 0% | 0% | 0%
LEAD | PRESALES - DELIVERY |  | 2024-2025 | 2024-09-01 | 2025-01-31 | ABS24523 | ABS24523 | EPM | Tax Cube | EssilorLuxottica | L. Bariani | A. Di Pietro | Operations | Back End | 180 | 0 | ON HOLD | 0% | 2025 | 0 | 1 | [11 empty] | 5.556% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRESALES - DELIVERY |  | 2024-2025 | 2024-09-01 | 2025-01-31 | ABS24523 | ABS24523 | EPM | Tax Cube | EssilorLuxottica | L. Bariani | E. Storti | Delivery Projects | Analyst | 180 | 0 | ON HOLD | 0% | 2025 | 0 | 4 | [11 empty] | 22.22% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRESALES - DELIVERY |  | 2024-2025 | 2024-09-01 | 2025-01-31 | ABS24523 | ABS24523 | EPM | Tax Cube | EssilorLuxottica | L. Bariani | F. Atanasio | Operations | Back End | 180 | 0 | ON HOLD | 0% | 2025 | 0 | 1 | [11 empty] | 5.556% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25xxx | ABW2E | RETAIL | BULLSEYE ROLLOUT EMEA (IT-UK-DACH) | EssilorLuxottica | L. Franceschini | A. Vladi | Operations | Data Management - ETL | 100 | 13 | ON HOLD | 0% | 2025 | 15 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 5 | 5 | 5.556% | 5% | 4.762% | 4.545% | 5% | 0% | 4.348% | 8.333% | 4.762% | 4.348% | 23.81% | 22.73%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25xxx | ABW2E | RETAIL | BULLSEYE ROLLOUT EMEA (IT-UK-DACH) | EssilorLuxottica | L. Franceschini | F. D'Alberto | Operations | Data Analyst | 100 | 13 | ON HOLD | 0% | 2025 | 10 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 11.11% | 10% | 9.524% | 9.091% | 10% | 5% | 8.696% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25xxx | ABW2E | RETAIL | BULLSEYE ROLLOUT EMEA (IT-UK-DACH) | EssilorLuxottica | L. Franceschini | F. Spacagna | Operations | Solution Architect | 100 | 13 | ON HOLD | 0% | 2025 | 16 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 3 | 5.556% | 5% | 9.524% | 9.091% | 5% | 5% | 4.348% | 8.333% | 4.762% | 17.39% | 19.05% | 13.64%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25xxx | ABW2E | RETAIL | BULLSEYE ROLLOUT EMEA (IT-UK-DACH) | EssilorLuxottica | L. Franceschini | G. Franchi | Operations | Back End - Java | 100 | 13 | ON HOLD | 0% | 2025 | 4 | 1 | 2 | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 5.556% | 10% | 4.762% | 0% | 5% | 0% | 4.348% | 0% | 4.762% | 0% | 4.762% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25xxx | ABW2E | RETAIL | BULLSEYE ROLLOUT EMEA (IT-UK-DACH) | EssilorLuxottica | L. Franceschini | L. Franceschini | Delivery Projects | PM - Project Governance | 100 | 13 | ON HOLD | 0% | 2025 | 15 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | 11.11% | 10% | 9.524% | 9.091% | 15% | 10% | 8.696% | 16.67% | 4.762% | 8.696% | 4.762% | 9.091%
CONTRACT | PRJ | Waterfall | 2025 | 2024-01-01 | 2025-06-30 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | A. Nastasi | Operations | Data Management | 780 | 735 | ON HOLD | 0% | 2025 | 0 | 1 | 1 | 5 | 5 | [8 empty] | 5.556% | 5% | 23.81% | 22.73% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-01-01 | 2025-06-30 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | A. Pirola | Operations | Front End | 780 | 735 | ON HOLD | 0% | 2025 | 0 | 1 | 1 | 2 | 2 | [8 empty] | 5.556% | 5% | 9.524% | 9.091% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-01-01 | 2025-06-30 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | A. Vladi | Operations | Technical Leader - Data Management | 780 | 735 | ON HOLD | 0% | 2025 | 0 | 15 | 18 | 18 | 19 | [8 empty] | 83.33% | 90% | 85.71% | 86.36% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-01-01 | 2025-06-30 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | C. Elia | Operations | Data Management | 780 | 735 | ON HOLD | 0% | 2025 | 14 | 7 | 8 | 8 | 8 | [5 empty] | 6 | 4 | 4 | 38.89% | 40% | 38.1% | 36.36% | 0% | 0% | 0% | 0% | 0% | 26.09% | 19.05% | 18.18%
CONTRACT | PRJ | Waterfall | 2025 | 2024-01-01 | 2025-06-30 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | F. D'Alberto | Operations | Data Management | 780 | 735 | ON HOLD | 0% | 2025 | 0 | 1 | 15 | 15 | 15 | [8 empty] | 5.556% | 75% | 71.43% | 68.18% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-01-01 | 2025-06-30 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | F. Spacagna | Operations | Solution Architect | 780 | 735 | ON HOLD | 0% | 2025 | 0 | 13 | 12 | 12 | 12 | [8 empty] | 72.22% | 60% | 57.14% | 54.55% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-01-01 | 2025-06-30 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | G. Franchi | Operations | Back End | 780 | 735 | ON HOLD | 0% | 2025 | 0 | 15 | 15 | 15 | 15 | [8 empty] | 83.33% | 75% | 71.43% | 68.18% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-01-01 | 2025-06-30 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | L. Franceschini | Delivery Projects | PM - Project Governance | 780 | 735 | ON HOLD | 0% | 2025 | 64 | 2 | 2 | 2 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 11.11% | 10% | 9.524% | 9.091% | 40% | 40% | 34.78% | 66.67% | 38.1% | 34.78% | 38.1% | 36.36%
CONTRACT | PRJ | Waterfall | 2025 | 2024-01-01 | 2025-06-30 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | M. Vianelli | Delivery Projects | Analyst | 780 | 735 | ON HOLD | 0% | 2025 | 0 | 3 | 4 | 4 | 4 | [8 empty] | 16.67% | 20% | 19.05% | 18.18% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-09-30 | ABS25191 | N/A | RETAIL | Bullseye Wave 3 - DTBRK Integration | EssilorLuxottica | L. Franceschini | A. Pirola | Operations | Front End | 70 | 0 | PROPOSAL | 0% | 2025 | 1 |  |  |  | 1 | 1 | [7 empty] | 0% | 0% | 0% | 4.545% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-09-30 | ABS25191 | N/A | RETAIL | Bullseye Wave 3 - DTBRK Integration | EssilorLuxottica | L. Franceschini | A. Vladi | Operations | Technical Leader - Data Management | 70 | 0 | PROPOSAL | 0% | 2025 | 15 | 2 | 2 | 5 | 5 | 5 | 5 | 5 | [5 empty] | 11.11% | 10% | 23.81% | 22.73% | 25% | 25% | 21.74% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-09-30 | ABS25191 | N/A | RETAIL | Bullseye Wave 3 - DTBRK Integration | EssilorLuxottica | L. Franceschini | F. D'Alberto | Operations | Data Management | 70 | 0 | PROPOSAL | 0% | 2025 | 5 |  |  |  | 5 | 5 | [7 empty] | 0% | 0% | 0% | 22.73% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-09-30 | ABS25191 | N/A | RETAIL | Bullseye Wave 3 - DTBRK Integration | EssilorLuxottica | L. Franceschini | F. Spacagna | Operations | Solution Architect | 70 | 0 | PROPOSAL | 0% | 2025 | 3 | [5 empty] | 1 | 1 |  | 1 |  |  |  | 0% | 0% | 0% | 0% | 0% | 5% | 4.348% | 0% | 4.762% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-09-30 | ABS25191 | N/A | RETAIL | Bullseye Wave 3 - DTBRK Integration | EssilorLuxottica | L. Franceschini | G. Franchi | Operations | Back End | 70 | 0 | PROPOSAL | 0% | 2025 | 15 |  |  |  | 5 | 5 | 5 | 5 | [5 empty] | 0% | 0% | 0% | 22.73% | 25% | 25% | 21.74% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-09-30 | ABS25191 | N/A | RETAIL | Bullseye Wave 3 - DTBRK Integration | EssilorLuxottica | L. Franceschini | L. Franceschini | Delivery Projects | PM - Project Governance | 70 | 0 | PROPOSAL | 0% | 2025 | 10 |  |  |  |  | 3 | 3 | 4 | [5 empty] | 0% | 0% | 0% | 0% | 15% | 15% | 17.39% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-09-30 | ABS25191 | N/A | RETAIL | Bullseye Wave 3 - DTBRK Integration | EssilorLuxottica | L. Franceschini | TBD | Operations | Data Management | 70 | 0 | PROPOSAL | 0% | 2025 | 5 |  |  |  | 5 | 5 | [7 empty] | 0% | 0% | 0% | 22.73% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2024-02-28 | ABS25121 | ABS25121 | FINANCE | EDEN W2 - integrazione | EssilorLuxottica | L. Franceschini | A. Strada | Operations | Data Management | 49 | 2 | ON GOING | 0% | 2025 | 0 |  | 1 | 1 | [9 empty] | 0% | 5% | 4.762% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2024-02-28 | ABS25121 | ABS25121 | FINANCE | EDEN W2 - integrazione | EssilorLuxottica | L. Franceschini | D. De Pecol | Operations | Front End | 49 | 2 | ON GOING | 0% | 2025 | 5 |  |  | 8 | 8 | 5 | [7 empty] | 0% | 0% | 38.1% | 36.36% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2024-02-28 | ABS25121 | ABS25121 | FINANCE | EDEN W2 - integrazione | EssilorLuxottica | L. Franceschini | L. Franceschini | Delivery Projects | PM - Project Governance | 49 | 2 | ON GOING | 0% | 2025 | 8 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2024-02-28 | ABS25121 | ABS25121 | FINANCE | EDEN W2 - integrazione | EssilorLuxottica | L. Franceschini | R. Bondi | Operations | Front End | 49 | 2 | ON GOING | 0% | 2025 | 0 |  |  | 1 | 1 | [8 empty] | 0% | 0% | 4.762% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2024-02-28 | ABS25121 | ABS25121 | FINANCE | EDEN W2 - integrazione | EssilorLuxottica | L. Franceschini | S. Ben Younes | Operations | Data Management | 49 | 2 | ON GOING | 0% | 2025 | 5 |  | 2 | 7 | 7 | 5 | [7 empty] | 0% | 10% | 33.33% | 31.82% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS0015 | RETAIL | Shield - POC Data Science | EssilorLuxottica | L. Franceschini | A. Imbimbo | Operations | Data Scientist | 160 | 14 | ON GOING | 0% | 2025 | 20 |  |  |  |  | 5 | 5 | 5 |  | 5 |  |  |  | 0% | 0% | 0% | 0% | 25% | 25% | 21.74% | 0% | 23.81% | 0% | 0% | 0%
PROSPECT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS0015 | RETAIL | Shield - POC Data Science | EssilorLuxottica | L. Franceschini | A. Pirola | Operations | Front End | 160 | 14 | ON GOING | 0% | 2025 | 6 |  |  |  |  | 2 | 2 | 1 |  | 1 |  |  |  | 0% | 0% | 0% | 0% | 10% | 10% | 4.348% | 0% | 4.762% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS0015 | RETAIL | Shield - POC Data Science | EssilorLuxottica | L. Franceschini | A. Vladi | Operations | Data Engineering | 160 | 14 | ON GOING | 0% | 2025 | 20 |  |  |  |  | 5 | 5 | 5 |  | 5 |  |  |  | 0% | 0% | 0% | 0% | 25% | 25% | 21.74% | 0% | 23.81% | 0% | 0% | 0%
PROSPECT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS0015 | RETAIL | Shield - POC Data Science | EssilorLuxottica | L. Franceschini | F. Spacagna | Operations | Solution Architect | 160 | 14 | ON GOING | 0% | 2025 | 12 |  |  |  |  | 3 | 3 | 3 |  | 3 |  |  |  | 0% | 0% | 0% | 0% | 15% | 15% | 13.04% | 0% | 14.29% | 0% | 0% | 0%
PROSPECT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS0015 | RETAIL | Shield - POC Data Science | EssilorLuxottica | L. Franceschini | G. Sironi | Operations | Team Leadership | 160 | 14 | ON GOING | 0% | 2025 | 20 |  |  |  |  | 5 | 5 | 5 |  | 5 |  |  |  | 0% | 0% | 0% | 0% | 25% | 25% | 21.74% | 0% | 23.81% | 0% | 0% | 0%
PROSPECT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS0015 | RETAIL | Shield - POC Data Science | EssilorLuxottica | L. Franceschini | L. Franceschini | Delivery Projects | PM - Project Governance | 160 | 14 | ON GOING | 0% | 2025 | 8 |  |  |  |  | 2 | 2 | 2 |  | 2 |  |  |  | 0% | 0% | 0% | 0% | 10% | 10% | 8.696% | 0% | 9.524% | 0% | 0% | 0%
PROSPECT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS0015 | RETAIL | Shield - POC Data Science | EssilorLuxottica | L. Franceschini | TBD | #N/A | Back End | 160 | 14 | ON GOING | 0% | 2025 | 20 |  |  |  |  | 5 | 5 | 5 |  | 5 |  |  |  | 0% | 0% | 0% | 0% | 25% | 25% | 21.74% | 0% | 23.81% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2025-01-01 | 2025-12-31 | N/A | U20R | ERP | UNIEURO | UNIEURO | L. Franceschini | L. Franceschini | Delivery Projects | PM - Project Governance | 100 | 55 | ON GOING | 0% | 2025 | 13 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 1 | 2 | 1 | 1 |  | 11.11% | 10% | 9.524% | 13.64% | 15% | 15% | 8.696% | 8.333% | 9.524% | 4.348% | 4.762% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-09 | 2025-04-30 | N/A | ABS0008-103 | HR | Dashboard CSR | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analyst | 82 | 0 | ON GOING | 0% | 2025 | 19 |  |  |  | 5 | 8 | 8 | 3 | [5 empty] | 0% | 0% | 0% | 22.73% | 40% | 40% | 13.04% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-09 | 2025-04-30 | N/A | ABS0008-103 | HR | Dashboard CSR | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 82 | 0 | ON GOING | 0% | 2025 | 10 |  |  |  | 3 | 4 | 3 | 1 | 1 | 1 |  |  |  | 0% | 0% | 0% | 13.64% | 20% | 15% | 4.348% | 8.333% | 4.762% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-03-09 | 2025-04-30 | N/A | ABS0008-103 | HR | Dashboard CSR | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 82 | 0 | ON GOING | 0% | 2025 | 4 |  |  |  | 1 | 2 | 1 | 1 | [5 empty] | 0% | 0% | 0% | 4.545% | 10% | 5% | 4.348% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-03-09 | 2025-04-30 | N/A | ABS0008-103 | HR | Dashboard CSR | EssilorLuxottica | L. Roberto | M. Vimercati | Operations | Data Management | 82 | 0 | ON GOING | 0% | 2025 | 27 |  |  |  | 6 | 12 | 15 | [6 empty] | 0% | 0% | 0% | 27.27% | 60% | 75% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-03-09 | 2025-04-30 | N/A | ABS0008-103 | HR | Dashboard CSR | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Front End | 82 | 0 | ON GOING | 0% | 2025 | 20 |  |  |  | 1 | 6 | 10 | 4 | [5 empty] | 0% | 0% | 0% | 4.545% | 30% | 50% | 17.39% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ | Waterfall | 2025 | 2025-05-04 | 2025-07-31 | N/A | ABS0008-99 | HR | Dashboard data quality | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Business anlysis | 0 | 0 | PROPOSAL | 0% | 2025 | 9 | [5 empty] | 3 | 3 | 3 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 15% | 13.04% | 25% | 0% | 0% | 0% | 0%
LEAD | PRJ | Waterfall | 2025 | 2025-05-04 | 2025-07-31 | N/A | ABS0008-99 | HR | Dashboard data quality | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 0 | 0 | PROPOSAL | 0% | 2025 | 5 | [5 empty] | 1 |  |  | 2 | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 9.524% | 8.696% | 0% | 0%
LEAD | PRJ | Waterfall | 2025 | 2025-05-04 | 2025-07-31 | N/A | N/A | HR | Dashboard Salary (dati vendite) | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Business anlysis | 0 | 0 | PROPOSAL | 0% | 2025 | 6 | [5 empty] | 2 | 2 | 2 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 10% | 8.696% | 16.67% | 0% | 0% | 0% | 0%
LEAD | PRJ | Waterfall | 2025 | 2025-05-04 | 2025-07-31 | N/A | N/A | HR | Dashboard Salary (dati vendite) | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 0 | 0 | PROPOSAL | 0% | 2025 | 8 | [5 empty] | 2 |  |  |  | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 8.696% | 9.524% | 9.091%
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 31/06/2025 | N/A | ABS0008-174 | HR | Evolutive Dashboard Aprile(post golive) | EssilorLuxottica | L. Roberto | D. DE PECOL | #N/A | Data Management | 6.5 | 0 | ON GOING | 100% | 2025 | 0 |  |  |  | 2 | [8 empty] | 0% | 0% | 0% | 9.091% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 31/06/2025 | N/A | ABS0008-174 | HR | Evolutive Dashboard Aprile(post golive) | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Business Analysis | 6.5 | 0 | ON GOING | 100% | 2025 | 0 |  |  |  | 1 | [8 empty] | 0% | 0% | 0% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 31/06/2025 | N/A | ABS0008-174 | HR | Evolutive Dashboard Aprile(post golive) | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 6.5 | 0 | ON GOING | 90% | 2025 | 0 |  |  |  | 1 | [8 empty] | 0% | 0% | 0% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 31/06/2025 | N/A | ABS0008-174 | HR | Evolutive Dashboard Aprile(post golive) | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 6.5 | 0 | ON GOING | 100% | 2025 | 0 |  |  |  | 1 | [8 empty] | 0% | 0% | 0% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 31/06/2025 | N/A | ABS0008-174 | HR | Evolutive Dashboard Aprile(post golive) | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Data Management | 6.5 | 0 | ON GOING | 100% | 2025 | 0 |  |  |  | 2 | [8 empty] | 0% | 0% | 0% | 9.091% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 31/06/2025 | N/A | ABS0008-202 | HR | Evolutive Dashboard Maggio(post golive) | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Business Analysis | 13 | 0 | ON GOING | 100% | 2025 | 1 |  |  |  | 1 | 1 | [7 empty] | 0% | 0% | 0% | 4.545% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 31/06/2025 | N/A | ABS0008-201 | HR | Evolutive Dashboard Maggio(post golive) | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 13 | 0 | ON GOING | 0% | 2025 | 5 |  |  |  | 1 | 3 | 2 | [6 empty] | 0% | 0% | 0% | 4.545% | 15% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 31/06/2025 | N/A | ABS0008-201 | HR | Evolutive Dashboard Maggio(post golive) | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 13 | 0 | ON GOING | 100% | 2025 | 1 |  |  |  | 1 | 1 | [7 empty] | 0% | 0% | 0% | 4.545% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 31/06/2025 | N/A | ABS0008-203 | HR | Evolutive Dashboard Maggio(post golive) | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Data Management | 13 | 0 | ON GOING | 100% | 2025 | 6 |  |  |  | 4 | 5 |  | 1 | [5 empty] | 0% | 0% | 0% | 18.18% | 25% | 0% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 | N/A | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analyst | 100 | 0 | ON GOING | 0% | 2025 | 3 | 2 |  |  | 1 | 1 | 2 | [6 empty] | 11.11% | 0% | 0% | 4.545% | 5% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 | N/A | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Management | 100 | 0 | ON GOING | 0% | 2025 | 0 | 2 |  | 2 | [9 empty] | 11.11% | 0% | 9.524% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 | N/A | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PM - Project Governance | 100 | 0 | ON GOING | 0% | 2025 | 7 | 1 |  | 1 | 2 | 3 | 4 | [6 empty] | 5.556% | 0% | 4.762% | 9.091% | 15% | 20% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 | N/A | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 100 | 0 | ON GOING | 0% | 2025 | 17 |  |  |  | 8 | 15 | 2 | [6 empty] | 0% | 0% | 0% | 36.36% | 75% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 | N/A | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | L. Carloni | Operations | Back End | 100 | 0 | ON GOING | 0% | 2025 | 1.5 |  |  |  |  | 1.5 | [7 empty] | 0% | 0% | 0% | 0% | 7.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 | N/A | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 100 | 0 | ON GOING | 0% | 2025 | 5 | 1 |  | 1 | 2 | 2 | 2 | 1 | [5 empty] | 5.556% | 0% | 4.762% | 9.091% | 10% | 10% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 | N/A | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | M. Porcu | Operations | Technical Leader | 100 | 0 | ON GOING | 0% | 2025 | 1.5 |  |  |  |  | 1.5 | [7 empty] | 0% | 0% | 0% | 0% | 7.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 | N/A | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | M. Toci | Operations | Back End | 100 | 0 | ON GOING | 0% | 2025 | 1.5 |  |  |  |  | 1.5 | [7 empty] | 0% | 0% | 0% | 0% | 7.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 | N/A | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | M. Vimercati | Operations | Data Management | 100 | 0 | ON GOING | 0% | 2025 | 1 |  |  |  | 1 | 1 | [7 empty] | 0% | 0% | 0% | 4.545% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 | N/A | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Front End | 100 | 0 | ON GOING | 0% | 2025 | 3 |  |  |  | 3 | 3 | [7 empty] | 0% | 0% | 0% | 13.64% | 15% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 | N/A | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analyst | 100 | 0 | ON GOING | 0% | 2025 | 11 | 5 | 4 | 4 | 6 | 8 | 2 | 1 | [5 empty] | 27.78% | 20% | 19.05% | 27.27% | 40% | 10% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 | N/A | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | S. Beltrami | Operations | Front End | 100 | 0 | ON GOING | 0% | 2025 | 1.5 |  |  |  |  | 1.5 | [7 empty] | 0% | 0% | 0% | 0% | 7.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | A. Torone | Delivery Projects | Analyst | 100 | 0 | ON GOING | 0% | 2025 | 0 | 3.5 | 3.5 | [10 empty] | 19.44% | 17.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Management | 100 | 7 | ON GOING | 40% | 2025 | 1 | 1 | 1 |  | 1 | 1 | [7 empty] | 5.556% | 5% | 0% | 4.545% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 100 | 7 | ON GOING | 40% | 2025 | 3 | 2 | 2 |  | 2 | 2 | 1 | [6 empty] | 11.11% | 10% | 0% | 9.091% | 10% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 100 | 7 | ON GOING | 40% | 2025 | 5 | 1 | 1 |  | 5 | 3 | 2 | [6 empty] | 5.556% | 5% | 0% | 22.73% | 15% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 100 | 7 | ON GOING | 40% | 2025 | 3 | 2 | 2 |  | 2 | 2 | 1 | [6 empty] | 11.11% | 10% | 0% | 9.091% | 10% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | P. SINGH | Operations | Data Management | 100 | 7 | ON GOING | 40% | 2025 | 8 |  |  |  | 5 | 8 | [7 empty] | 0% | 0% | 0% | 22.73% | 40% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analyst | 100 | 7 | ON GOING | 40% | 2025 | 4 | 1 | 1 | 1 | 4 | 3 | 1 | [6 empty] | 5.556% | 5% | 4.762% | 18.18% | 15% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | R. Tortora | Operations | Data Management | 100 | 7 | ON GOING | 40% | 2025 | 1 |  |  |  | 2 | 1 | [7 empty] | 0% | 0% | 0% | 9.091% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-10-21 | 2024-11-30 | ABS25085 | ABS25085 | HR | HR - LandingPage wave1 | EssilorLuxottica | L. Roberto | C. Elia | Operations | Back End | 65 | 36 | ON HOLD | 90% | 2025 | 0 | 2 | 1 | [10 empty] | 11.11% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-10-21 | 2024-11-30 | ABS25085 | ABS25085 | HR | HR - LandingPage wave1 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 65 | 36 | ON HOLD | 90% | 2025 | 0 | 1 | 1 | [10 empty] | 5.556% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-10-21 | 2024-11-30 | ABS25085 | ABS25085 | HR | HR - LandingPage wave1 | EssilorLuxottica | L. Roberto | M. Porcu | Operations | Back End | 65 | 36 | ON HOLD | 90% | 2025 | 0 | 2 | 1 | [10 empty] | 11.11% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-10-21 | 2024-11-30 | ABS25085 | ABS25085 | HR | HR - LandingPage wave1 | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analyst | 65 | 36 | ON HOLD | 90% | 2025 | 0 | 1 | 1 | [10 empty] | 5.556% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ | Agile | 2025 | 2025-03-02 | 2025-05-23 | N/A | ABS0008-194 | HR | HR - OrgView | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 0 | 0 | PROPOSAL |  | 2025 | 2 |  |  |  | 1 | 1 | 1 | [6 empty] | 0% | 0% | 0% | 4.545% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ | Agile | 2025 | 2025-03-02 | 2025-05-23 | N/A | ABS0008-194 | HR | HR - OrgView | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analyst | 0 | 0 | PROPOSAL |  | 2025 | 6 |  |  |  | 2 | 3 | 3 | [6 empty] | 0% | 0% | 0% | 9.091% | 15% | 15% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-12-02 | 2025-03-18 | ABS25085 | ABS25085 | HR | HR - Revisione DMGLOBAL | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Management | 109 | 91 | CLOSED | 100% | 2025 | 1 | 3 | 1 | 15 | 15 | 1 | [7 empty] | 16.67% | 5% | 71.43% | 68.18% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-12-02 | 2025-03-18 | ABS25085 | ABS25085 | HR | HR - Revisione DMGLOBAL | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 109 | 91 | CLOSED | 100% | 2025 | 2 | 1 | 2 | 1 | 2 | 2 | [7 empty] | 5.556% | 10% | 4.762% | 9.091% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-12-02 | 2025-03-18 | ABS25085 | ABS25085 | HR | HR - Revisione DMGLOBAL | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 109 | 91 | CLOSED | 100% | 2025 | 4 | 2 | 8 | 6 | 4 | 4 | [7 empty] | 11.11% | 40% | 28.57% | 18.18% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-12-02 | 2025-03-18 | ABS25085 | ABS25085 | HR | HR - Revisione DMGLOBAL | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 109 | 91 | CLOSED | 100% | 2025 | 1 | 1 | 1 | 1 | 1 | 1 | [7 empty] | 5.556% | 5% | 4.762% | 4.545% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-12-02 | 2025-03-18 | ABS25085 | ABS25085 | HR | HR - Revisione DMGLOBAL | EssilorLuxottica | L. Roberto | M. VIMERCATI | Operations | Data Management | 109 | 91 | CLOSED | 100% | 2025 | 0 | 2 | 3 | [10 empty] | 11.11% | 15% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-12-02 | 2025-03-18 | ABS25085 | ABS25085 | HR | HR - Revisione DMGLOBAL | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analyst | 109 | 91 | CLOSED | 100% | 2025 | 2 | 1 | 1 | 1 | 1 | 2 | [7 empty] | 5.556% | 5% | 4.762% | 4.545% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | N/A | ABS0008-16 | HR | HR - Revisione PA0002 | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Management | 29 | 19 | CLOSED | 100% | 2025 | 0 | 3 | [11 empty] | 16.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | N/A | ABS0008-16 | HR | HR - Revisione PA0002 | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 29 | 19 | CLOSED | 100% | 2025 | 0 | 1 | 1 | [10 empty] | 5.556% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | N/A | ABS0008-16 | HR | HR - Revisione PA0002 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | Project Governance | 29 | 12 | CLOSED | 90% | 2025 | 0 | 1 | 1 | [10 empty] | 5.556% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | N/A | ABS0008-16 | HR | HR - Revisione PA0002 | EssilorLuxottica | L. Roberto | M. VIMERCATI | Operations | Data Management | 29 | 19 | CLOSED | 100% | 2025 | 0 | 3 | 2 | [10 empty] | 16.67% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 31/06/2025 | ABS24299 | ABS0008-138 | HR | Hypercare dismissione QLIK | EssilorLuxottica | L. Roberto | D. De Pecol | #N/A | Data Management | 570 | 567 | On Going | 95% | 2025 | 0 |  |  | 1 | 1 | [8 empty] | 0% | 0% | 4.762% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 31/06/2025 | ABS24299 | ABS0008-138 | HR | Hypercare dismissione QLIK | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Business anlysis | 570 | 567 | On Going | 95% | 2025 | 0 |  |  | 4 | 5 | [8 empty] | 0% | 0% | 19.05% | 22.73% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 31/06/2025 | ABS24299 | ABS0008-138 | HR | Hypercare dismissione QLIK | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 570 | 567 | ON GOING | 95% | 2025 | 1 |  |  | 4 | 2 |  | 1 | [6 empty] | 0% | 0% | 19.05% | 9.091% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 31/06/2025 | ABS24299 | ABS0008-138 | HR | Hypercare dismissione QLIK | EssilorLuxottica | L. Roberto | L. Roberto | Operations | Project Governance - PMO | 570 | 567 | On Going | 95% | 2025 | 1 |  |  | 2 | 1 | 1 | [7 empty] | 0% | 0% | 9.524% | 4.545% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 31/06/2025 | ABS24299 | ABS0008-138 | HR | Hypercare dismissione QLIK | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Data Management | 570 | 567 | On Going | 95% | 2025 | 0 |  |  | 1 | 1 | [8 empty] | 0% | 0% | 4.762% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  |  |  |  | ABS23222 | AIW3TRI | OTHER | Image Processing Tool - Wave 3 | EssilorLuxottica | L. Roberto | A. Ferrari | Operations | Data Engineering | 151 | 0 | TO START | 0% | 2025 | 20 | [5 empty] | 1 | 17.5 | 1.5 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 5% | 76.09% | 12.5% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  |  |  |  | ABS23222 | AIW3TRI | OTHER | Image Processing Tool - Wave 3 | EssilorLuxottica | L. Roberto | M. Porcu | Operations | Solution Architect | 151 | 0 | TO START | 0% | 2025 | 11.2 | [5 empty] | 2.4 | 4.6 | 4.2 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 12% | 20% | 35% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  |  |  |  | ABS23222 | AIW3TRI | OTHER | Image Processing Tool - Wave 3 | EssilorLuxottica | L. Roberto | M. Toci | Operations | Back End | 151 | 0 | TO START | 0% | 2025 | 22.4 | [5 empty] | 9.2 | 4.8 | 8.4 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 46% | 20.87% | 70% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  |  |  |  | ABS23222 | AIW3TRI | OTHER | Image Processing Tool - Wave 3 | EssilorLuxottica | L. Roberto | S. Beltrami | Operations |  | 151 | 0 | TO START | 0% | 2025 | 22.4 | [5 empty] | 9.2 | 4.8 | 8.4 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 46% | 20.87% | 70% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-01-17 | 2025-04-03 | N/A | ABS0008-147 | HR | Migrazione autenticazione One Org su NAM | EssilorLuxottica | L. Roberto | C. Di Lorenzo | Delivery Projects | Analyst | 9 | 0 | ON HOLD | 0% | 2025 | 0 |  | 0.5 | 0.5 | [9 empty] | 0% | 2.5% | 2.381% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-01-17 | 2025-04-03 | N/A | ABS0008-147 | HR | Migrazione autenticazione One Org su NAM | EssilorLuxottica | L. Roberto | M. Porcu | Operations | Technical Leader | 9 | 0 | ON HOLD | 0% | 2025 | 0 |  | 1 | 1 | 1 | [8 empty] | 0% | 5% | 4.762% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-01-17 | 2025-04-03 | N/A | ABS0008-147 | HR | Migrazione autenticazione One Org su NAM | EssilorLuxottica | L. Roberto | M. Toci | Operations | Back End | 9 | 0 | ON HOLD | 0% | 2025 | 0 |  |  | 3 | 3 | [8 empty] | 0% | 0% | 14.29% | 13.64% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | A. BRANDIZZI | Operations | Front End | 450 | 244 | ON GOING | 45% | 2025 | 45 | 1 | 1 | 15 | 15 | 15 | 15 | 15 | [5 empty] | 5.556% | 5% | 71.43% | 68.18% | 75% | 75% | 65.22% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | A. Lorena | Operations | Front End | 450 | 244 | ON GOING | 45% | 2025 | 2 | 1 | 1 | 1 | 4 |  | 1 | 1 | [5 empty] | 5.556% | 5% | 4.762% | 18.18% | 0% | 5% | 4.348% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | A. Pirola | Operations | Back End | 450 | 244 | ON GOING | 45% | 2025 | 3 | 1 | 15 | 15 | 15 | 1 | 1 | 1 | [5 empty] | 5.556% | 75% | 71.43% | 68.18% | 5% | 5% | 4.348% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | C. Di Lorenzo | Delivery Projects | Analyst | 450 | 244 | ON GOING | 45% | 2025 | 12 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | [5 empty] | 16.67% | 15% | 19.05% | 18.18% | 20% | 20% | 17.39% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | F. Scognamiglio | Operations | Back End | 450 | 244 | ON GOING | 45% | 2025 | 57 |  |  |  | 15 | 15 | 20 | 22 | [5 empty] | 0% | 0% | 0% | 68.18% | 75% | 100% | 95.65% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | G. De Feo | Delivery Projects | PM - Project Governance | 450 | 244 | ON GOING | 45% | 2025 | 31 | 4 | 3 | 3 | 3 | 4 | 4 | 5 | 2 | 4 | 4 | 4 | 4 | 22.22% | 15% | 14.29% | 13.64% | 20% | 20% | 21.74% | 16.67% | 19.05% | 17.39% | 19.05% | 18.18%
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | G. Lopez | Operations | Front End | 450 | 244 | ON GOING | 45% | 2025 | 30 | 15 | 15 | 15 |  |  | 15 | 15 | [5 empty] | 83.33% | 75% | 71.43% | 0% | 0% | 75% | 65.22% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | G. TARTAGLIA | Operations | Back End | 450 | 244 | ON GOING | 45% | 2025 | 42 | 15 | 15 | 15 |  |  | 20 | 22 | [5 empty] | 83.33% | 75% | 71.43% | 0% | 0% | 100% | 95.65% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | M. TOCI | Operations | Back End | 450 | 244 | ON GOING | 45% | 2025 | 17 | 3 | 3 | 3 |  |  | 8 | 9 | [5 empty] | 16.67% | 15% | 14.29% | 0% | 0% | 40% | 39.13% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | N. Pescione | Operations | Back End | 450 | 244 | ON GOING | 45% | 2025 | 0 | 15 | [11 empty] | 83.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | P. Anzellotti | Operations | Technical Leader | 450 | 244 | ON GOING | 45% | 2025 | 15 | 6 | 3 | 3 | 3 | 3 | 6 | 6 | [5 empty] | 33.33% | 15% | 14.29% | 13.64% | 15% | 30% | 26.09% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | S. Beltrami | Operations | Front End | 450 | 244 | ON GOING | 45% | 2025 | 0 | 3 | 3 | 3 | [9 empty] | 16.67% | 15% | 14.29% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | S. Delle Fave | Operations | Front End | 450 | 244 | ON GOING | 45% | 2025 | 30 | 3 | 3 | 3 |  |  | 15 | 15 | [5 empty] | 16.67% | 15% | 14.29% | 0% | 0% | 75% | 65.22% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-05-31 | N/A | IAA | HR | MY PLACE | Abstract | L. Roberto | C. Di Lorenzo | Delivery Projects | Business Analysis | 0 | 0 | ON GOING | 0% | 2025 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [5 empty] | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 8.696% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-05-31 | N/A | IAA | HR | MY PLACE | Abstract | L. Roberto | L. Roberto | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0% | 2025 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
INTERNAL PRJ | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-05-31 | N/A | IAA | HR | MY PLACE | Abstract | L. Roberto | M. Simeone | Operations | Front End | 0 | 0 | ON GOING | 0% | 2025 | 45 | 18 | 15 | 13 | 15 | 15 | 15 | 15 | [5 empty] | 100% | 75% | 61.9% | 68.18% | 75% | 75% | 65.22% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-05-31 | N/A | IAA | HR | MY PLACE - MY CAREER | Abstract | L. Roberto | L. Roberto | Operations | PM - Project Governance | 450 | 244 | ON GOING | 45% | 2025 | 2 | 4 | 3 | 3 |  |  | 1 | 1 | [5 empty] | 22.22% | 15% | 14.29% | 0% | 0% | 5% | 4.348% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ | Agile | 2025 | 2025-02-20 | 2025-05-10 | N/A | N/A | HR | One Org HR - desktop version | EssilorLuxottica | L. Roberto | A. Lorena | Operations | Front End | 185 | 0 | PROPOSAL | 0% | 2025 | 26 | [5 empty] | 6 | 12 | 1 | 1 | 6 |  |  | 0% | 0% | 0% | 0% | 0% | 30% | 52.17% | 8.333% | 4.762% | 26.09% | 0% | 0%
LEAD | PRJ | Agile | 2025 | 2025-02-20 | 2025-05-10 | N/A | N/A | HR | One Org HR - desktop version | EssilorLuxottica | L. Roberto | C. Di Lorenzo | Delivery Projects | Analyst | 185 | 0 | PROPOSAL | 0% | 2025 | 2 | 2 | 5 | 2 | 2 |  | 2 | [6 empty] | 11.11% | 25% | 9.524% | 9.091% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ | Agile | 2025 | 2025-02-20 | 2025-05-10 | N/A | N/A | HR | One Org HR - desktop version | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PM - Project Governance | 185 | 0 | PROPOSAL | 0% | 2025 | 11 |  | 2 | 1 | 1 |  | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 0% | 10% | 4.762% | 4.545% | 0% | 10% | 8.696% | 8.333% | 9.524% | 8.696% | 4.762% | 4.545%
LEAD | PRJ | Agile | 2025 | 2025-02-20 | 2025-05-10 | N/A | N/A | HR | One Org HR - desktop version | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 185 | 0 | PROPOSAL | 0% | 2025 | 6 | [5 empty] | 2 | 1 | 1 | 2 |  |  |  | 0% | 0% | 0% | 0% | 0% | 10% | 4.348% | 8.333% | 9.524% | 0% | 0% | 0%
LEAD | PRJ | Agile | 2025 | 2025-02-20 | 2025-05-10 | N/A | N/A | HR | One Org HR - desktop version | EssilorLuxottica | L. Roberto | M. Porcu | Operations | Back End | 185 | 0 | PROPOSAL | 0% | 2025 | 10 | [5 empty] | 1.5 | 2 | 2 | 3 | 1.5 |  |  | 0% | 0% | 0% | 0% | 0% | 7.5% | 8.696% | 16.67% | 14.29% | 6.522% | 0% | 0%
LEAD | PRJ | Agile | 2025 | 2025-02-20 | 2025-05-10 | N/A | N/A | HR | One Org HR - desktop version | EssilorLuxottica | L. Roberto | M. TOCI | Operations | Back End | 185 | 0 | PROPOSAL | 0% | 2025 | 10 | [5 empty] | 2 | 2 | 2 | 2 | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 10% | 8.696% | 16.67% | 9.524% | 8.696% | 0% | 0%
LEAD | PRJ | Agile | 2025 | 2025-02-20 | 2025-05-10 | N/A | N/A | HR | One Org HR - desktop version | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analyst | 185 | 0 | PROPOSAL | 0% | 2025 | 10 |  |  |  | 2 |  | 4 | 2 | 2 | 2 |  |  |  | 0% | 0% | 0% | 9.091% | 0% | 20% | 8.696% | 16.67% | 9.524% | 0% | 0% | 0%
LEAD | PRJ | Agile | 2025 | 2025-02-20 | 2025-05-10 | N/A | N/A | HR | One Org HR - desktop version | EssilorLuxottica | L. Roberto | S. Beltrami | Operations | Front End | 185 | 0 | PROPOSAL | 0% | 2025 | 26 | [5 empty] | 6 | 12 | 1 | 1 | 6 |  |  | 0% | 0% | 0% | 0% | 0% | 30% | 52.17% | 8.333% | 4.762% | 26.09% | 0% | 0%
LEAD | PRJ | Agile | 2025 | 2025-02-20 | 2025-05-10 | N/A | N/A | HR | One Org HR - desktop version | EssilorLuxottica | L. Roberto | TBD | #N/A | UX/UI | 185 | 0 | PROPOSAL | 0% | 2025 | 15 |  |  |  | 15 | 5 |  | 5 | 5 |  |  |  |  | 0% | 0% | 0% | 68.18% | 25% | 0% | 21.74% | 41.67% | 0% | 0% | 0% | 0%
LEAD | PRJ | Agile | 2025 | 2025-03-01 | 2025-05-10 | N/A | N/A | HR | One Org HR - G+ | EssilorLuxottica | L. Roberto | C. Di Lorenzo | Delivery Projects | Analyst | 0 | 0 | PROPOSAL | 0% | 2025 | 6 |  |  | 5 |  |  | 3 | 3 | [5 empty] | 0% | 0% | 23.81% | 0% | 0% | 15% | 13.04% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ | Agile | 2025 | 2025-03-01 | 2025-05-10 | N/A | N/A | HR | One Org HR - G+ | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PM - Project Governance | 0 | 0 | PROPOSAL | 0% | 2025 | 4 |  |  | 2 |  |  | 2 | 2 | [5 empty] | 0% | 0% | 9.524% | 0% | 0% | 10% | 8.696% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ | Agile | 2025 | 2025-03-01 | 2025-05-10 | N/A | N/A | HR | One Org HR - G+ | EssilorLuxottica | L. Roberto | M. Porcu | Operations | Technical Leader | 0 | 0 | PROPOSAL | 0% | 2025 | 6 |  |  | 3 |  |  | 3 | 3 | [5 empty] | 0% | 0% | 14.29% | 0% | 0% | 15% | 13.04% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ | Agile | 2025 | 2025-03-01 | 2025-05-10 | N/A | N/A | HR | One Org HR - G+ | EssilorLuxottica | L. Roberto | M. TOCI | Operations | Back End | 0 | 0 | PROPOSAL | 0% | 2025 | 6 |  |  | 5 |  |  | 1 | 5 | [5 empty] | 0% | 0% | 23.81% | 0% | 0% | 5% | 21.74% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ | Agile | 2025 | 2025-03-01 | 2025-05-10 | N/A | N/A | HR | One Org HR - sort di tutte le linee | EssilorLuxottica | L. Roberto | C. Di Lorenzo | Delivery Projects | Analyst | 75 | 0 | PROPOSAL | 0% | 2025 | 7 |  | 2 |  |  |  | 3 | 2 | 2 |  |  |  |  | 0% | 10% | 0% | 0% | 0% | 15% | 8.696% | 16.67% | 0% | 0% | 0% | 0%
LEAD | PRJ | Agile | 2025 | 2025-03-01 | 2025-05-10 | N/A | N/A | HR | One Org HR - sort di tutte le linee | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PM - Project Governance | 75 | 0 | PROPOSAL | 0% | 2025 | 4 |  | 1 |  |  |  | 1 | 1 | 2 |  |  |  |  | 0% | 5% | 0% | 0% | 0% | 5% | 4.348% | 16.67% | 0% | 0% | 0% | 0%
LEAD | PRJ | Agile | 2025 | 2025-03-01 | 2025-05-10 | N/A | N/A | HR | One Org HR - sort di tutte le linee | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 75 | 0 | PROPOSAL | 0% | 2025 | 4 |  | 1 |  |  |  | 1 | 1 | 2 |  |  |  |  | 0% | 5% | 0% | 0% | 0% | 5% | 4.348% | 16.67% | 0% | 0% | 0% | 0%
LEAD | PRJ | Agile | 2025 | 2025-03-01 | 2025-05-10 | N/A | N/A | HR | One Org HR - sort di tutte le linee | EssilorLuxottica | L. Roberto | M. Porcu | Operations | Back End | 75 | 0 | PROPOSAL | 0% | 2025 | 6 | [5 empty] | 2 | 2 | 2 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 10% | 8.696% | 16.67% | 0% | 0% | 0% | 0%
LEAD | PRJ | Agile | 2025 | 2025-03-01 | 2025-05-10 | N/A | N/A | HR | One Org HR - sort di tutte le linee | EssilorLuxottica | L. Roberto | M. TOCI | Operations | Back End | 75 | 0 | PROPOSAL | 0% | 2025 | 20 | [5 empty] | 12 | 5 | 3 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 60% | 21.74% | 25% | 0% | 0% | 0% | 0%
LEAD | PRJ | Agile | 2025 | 2025-03-01 | 2025-05-10 | N/A | N/A | HR | One Org HR - sort di tutte le linee | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analyst | 75 | 0 | PROPOSAL | 0% | 2025 | 4 |  | 1 |  |  |  | 2 | 1 | 1 |  |  |  |  | 0% | 5% | 0% | 0% | 0% | 10% | 4.348% | 8.333% | 0% | 0% | 0% | 0%
LEAD | PRJ | Agile | 2025 | 2025-03-01 | 2025-05-10 | N/A | N/A | HR | One Org HR - sort di tutte le linee | EssilorLuxottica | L. Roberto | S. Beltrami | Operations | Front End | 75 | 0 | PROPOSAL | 0% | 2025 | 11 | [5 empty] | 8 | 1 | 2 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 40% | 4.348% | 16.67% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-10-01 | 2024-12-31 | ABS25085 | ABS25085 | HR | Qlik - Project Dismissione - DE&I phase 1 | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analysis | 80 | 36 | CLOSED | 100% | 2025 | 0 | 4 | 1 | [10 empty] | 22.22% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-10-01 | 2024-12-31 | ABS25085 | ABS25085 | HR | Qlik - Project Dismissione - DE&I phase 1 | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | Project Governance | 80 | 36 | CLOSED | 100% | 2025 | 0 | 2 | 1 | [10 empty] | 11.11% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-10-01 | 2024-12-31 | ABS25085 | ABS25085 | HR | Qlik - Project Dismissione - DE&I phase 1 | EssilorLuxottica | L. Roberto | R. Bondi | Operations | FrontEnd | 80 | 36 | CLOSED | 100% | 2025 | 0 | 3 | 1 | [10 empty] | 16.67% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ | Agile | 2025 | 2025-01-07 | 2025-02-28 | N/A | N/A | HR | Qlik - Project Dismissione - DE&I phase 2 | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analyst | 0 | 0 | PROPOSAL | 0% | 2025 | 12 | 2 | [6 empty] | 5 | 5 | 2 |  |  | 11.11% | 0% | 0% | 0% | 0% | 25% | 21.74% | 16.67% | #REF! | 0% | #REF! | 0%
LEAD | PRJ | Agile | 2025 | 2025-01-07 | 2025-02-28 | N/A | N/A | HR | Qlik - Project Dismissione - DE&I phase 2 | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PM - Project Governance | 0 | 0 | PROPOSAL | 0% | 2025 | 5 | [6 empty] | 2 | 2 | 1 |  |  |  | 0% | 0% | 0% | 0% | 0% | 10% | 8.696% | 8.333% | 0% | 0% | #REF! | 0%
LEAD | PRJ | Agile | 2025 | 2025-01-07 | 2025-02-28 | N/A | N/A | HR | Qlik - Project Dismissione - DE&I phase 2 | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 0 | 0 | PROPOSAL | 0% | 2025 | 8 | [6 empty] | 5 | 2 | 1 |  |  |  | 0% | 0% | 0% | 0% | 0% | 25% | 8.696% | 8.333% | 0% | 0% | #REF! | 0%
LEAD | PRJ | Agile | 2025 | 2025-01-07 | 2025-02-28 | N/A | N/A | HR | Qlik - Project Dismissione - DE&I phase 2 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 0 | 0 | PROPOSAL | 0% | 2025 | 4 | 1 | [5 empty] | 2 | 2 |  |  |  |  | 5.556% | 0% | 0% | 0% | 0% | 10% | 8.696% | 0% | 0% | 0% | #REF! | 0%
LEAD | PRJ | Agile | 2025 | 2025-01-07 | 2025-02-28 | N/A | N/A | HR | Qlik - Project Dismissione - DE&I phase 2 | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Front End | 0 | 0 | PROPOSAL | 0% | 2025 | 9 | [7 empty] | 6 | 1 | 2 |  |  | 0% | 0% | 0% | 0% | 0% | 30% | 4.348% | 16.67% | #REF! | 0% | #REF! | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - Training - support | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analysis | 570 | 567 | CLOSED | 100% | 2025 | 0 |  | 4 | [10 empty] | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - Training - support | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | Project Governance - PMO | 570 | 567 | CLOSED | 100% | 2025 | 0 |  | 2 | [10 empty] | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - Training - support | EssilorLuxottica | L. Roberto | L. Roberto | Operations | Project Governance | 570 | 567 | CLOSED | 100% | 2025 | 0 |  | 2 | [10 empty] | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - Training - support | EssilorLuxottica | L. Roberto | R. Bondi | Operations | FrontEnd | 570 | 567 | CLOSED | 100% | 2025 | 0 |  | 4 | [10 empty] | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | 0%
LEAD | PRJ | Agile | 2025 | 2025-03-07 | 2025-06-28 | N/A | N/A | HR | Qlik - Project Dismissione - WKF Country phase 2 | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analyst | 0 | 0 | PROPOSAL | 0% | 2025 | 21 | [7 empty] | 6 | 5 | 5 | 5 |  | 0% | 0% | 0% | 0% | 0% | 0% | 26.09% | 41.67% | 23.81% | 21.74% | #REF! | 0%
LEAD | PRJ | Agile | 2025 | 2025-03-07 | 2025-06-28 | N/A | N/A | HR | Qlik - Project Dismissione - WKF Country phase 2 | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PM - Project Governance | 0 | 0 | PROPOSAL | 0% | 2025 | 12 | [7 empty] | 3 | 3 | 3 | 3 |  | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 25% | 14.29% | 13.04% | #REF! | 0%
LEAD | PRJ | Agile | 2025 | 2025-03-07 | 2025-06-28 | N/A | N/A | HR | Qlik - Project Dismissione - WKF Country phase 2 | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Engineering | 0 | 0 | PROPOSAL | 0% | 2025 | 19 | [7 empty] | 4 | 5 | 5 | 5 |  | 0% | 0% | 0% | 0% | 0% | 0% | 17.39% | 41.67% | 23.81% | 21.74% | #REF! | 0%
LEAD | PRJ | Agile | 2025 | 2025-03-07 | 2025-06-28 | N/A | N/A | HR | Qlik - Project Dismissione - WKF Country phase 2 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 0 | 0 | PROPOSAL | 0% | 2025 | 6 | [7 empty] | 1 | 2 | 2 | 1 |  | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 16.67% | 9.524% | 4.348% | #REF! | 0%
LEAD | PRJ | Agile | 2025 | 2025-03-07 | 2025-06-28 | N/A | N/A | HR | Qlik - Project Dismissione - WKF Country phase 2 | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Front End | 0 | 0 | PROPOSAL | 0% | 2025 | 32 | [7 empty] | 8 | 8 | 8 | 8 |  | 0% | 0% | 0% | 0% | 0% | 0% | 34.78% | 66.67% | 38.1% | 34.78% | #REF! | 0%
LEAD | PRJ | Agile | 2025 | 2025-02-07 | 2025-03-28 | N/A | N/A | HR | Qlik - Project Dismissione - WKF Global phase 2 | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analyst | 0 | 0 | PROPOSAL | 0% | 2025 | 11 | [7 empty] | 6 | 5 |  |  |  | 0% | 0% | 0% | 0% | 0% | 30% | 21.74% | #REF! | 0% | 0% | #REF! | 0%
LEAD | PRJ | Agile | 2025 | 2025-02-07 | 2025-03-28 | N/A | N/A | HR | Qlik - Project Dismissione - WKF Global phase 2 | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PM - Project Governance | 0 | 0 | PROPOSAL | 0% | 2025 | 6 | [7 empty] | 3 | 3 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 25% | 0% | 0% | #REF! | 0%
LEAD | PRJ | Agile | 2025 | 2025-02-07 | 2025-03-28 | N/A | N/A | HR | Qlik - Project Dismissione - WKF Global phase 2 | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Engineering | 0 | 0 | PROPOSAL | 0% | 2025 | 8 | [6 empty] | 3 | 3 | 2 |  |  |  | 0% | 0% | 0% | 0% | 0% | 15% | 13.04% | 16.67% | 0% | 0% | #REF! | 0%
LEAD | PRJ | Agile | 2025 | 2025-02-07 | 2025-03-28 | N/A | N/A | HR | Qlik - Project Dismissione - WKF Global phase 2 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 0 | 0 | PROPOSAL | 0% | 2025 | 2 | [6 empty] | 1 | 1 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 5% | 4.348% | 0% | 0% | 0% | #REF! | 0%
LEAD | PRJ | Agile | 2025 | 2025-02-07 | 2025-03-28 | N/A | N/A | HR | Qlik - Project Dismissione - WKF Global phase 2 | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Front End | 0 | 0 | PROPOSAL | 0% | 2025 | 14 | [7 empty] | 8 | 6 |  |  |  | 0% | 0% | 0% | 0% | 0% | 40% | 26.09% | #REF! | 0% | 0% | #REF! | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analysis | 570 | 567 | CLOSED | 100% | 2025 | 0 | 5 | 2 | [10 empty] | 27.78% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye | EssilorLuxottica | L. Roberto | R. Bondi | Operations | FrontEnd | 570 | 567 | CLOSED | 100% | 2025 | 0 | 8 | 4 | [10 empty] | 44.44% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 570 | 567 | CLOSED | 100% | 2025 | 0 | 4 | 2 | [10 empty] | 22.22% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | C. Di Lorenzo | Delivery Projects | Analysis | 570 | 567 | CLOSED | 100% | 2025 | 0 | 2 | [11 empty] | 11.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | M. Porcu | Operations | Tech Lead | 570 | 567 | CLOSED | 100% | 2025 | 0 | 1 | [11 empty] | 5.556% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | M. Toci | Operations | BackEnd | 570 | 567 | CLOSED | 100% | 2025 | 0 | 4 | [11 empty] | 22.22% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 570 | 567 | CLOSED | 100% | 2025 | 0 | 2 | [11 empty] | 11.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | S. Beltrami | Operations | FrontEnd | 570 | 567 | CLOSED | 100% | 2025 | 0 | 4 | [11 empty] | 22.22% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 | N/A | ABS0008-140 | HR | Regole automatizzate - file hr controlling | EssilorLuxottica | L. Roberto | A. Nastasi | Operations | Data Management | 18 | 0 | ON GOING | 95% | 2025 | 2 |  |  |  | 4 | 2 | [7 empty] | 0% | 0% | 0% | 18.18% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 | N/A | ABS0008-140 | HR | Regole automatizzate - file hr controlling | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 18 | 0 | ON GOING | 95% | 2025 | 0 |  | 2 | 5 | 2 | [8 empty] | 0% | 10% | 23.81% | 9.091% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 | N/A | ABS0008-140 | HR | Regole automatizzate - file hr controlling | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 18 | 0 | ON GOING | 95% | 2025 | 2 |  | 1 | 1 | 1 | 1 | 1 | [6 empty] | 0% | 5% | 4.762% | 4.545% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 | N/A | ABS0008-140 | HR | Regole automatizzate - file hr controlling | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Front End | 18 | 0 | ON GOING | 95% | 2025 | 0 |  |  | 1 | 1 | [8 empty] | 0% | 0% | 4.762% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 | N/A | ABS0008-140 | HR | Regole automatizzate - file hr controlling | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analyst | 18 | 0 | ON GOING | 95% | 2025 | 4 |  | 2 | 1 | 1 | 1 | 2 | 1 | [5 empty] | 0% | 10% | 4.762% | 4.545% | 5% | 10% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-31 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 - AMS | EssilorLuxottica | L. Roberto | C. Di Lorenzo | Delivery Projects | Analyst | 65 | 0 | ON GOING | 0% | 2025 | 17 |  |  |  |  | 3 | 3 | 2 | 3 | 3 | 3 |  |  | 0% | 0% | 0% | 0% | 15% | 15% | 8.696% | 25% | 14.29% | 13.04% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-31 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 - AMS | EssilorLuxottica | L. Roberto | C. Elia | Operations | Back End | 65 | 0 | ON GOING | 0% | 2025 | 17 |  |  |  |  | 3 | 3 | 3 | 2 | 3 | 3 |  |  | 0% | 0% | 0% | 0% | 15% | 15% | 13.04% | 16.67% | 14.29% | 13.04% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-31 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 - AMS | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 65 | 0 | ON GOING | 0% | 2025 | 12 |  |  |  |  | 3 | 3 | 3 | 1 | 1 | 1 |  |  | 0% | 0% | 0% | 0% | 15% | 15% | 13.04% | 8.333% | 4.762% | 4.348% | 0% | 0%
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-31 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 - AMS | EssilorLuxottica | L. Roberto | M. Simeone | Operations | Back End | 65 | 0 | ON GOING | 0% | 2025 | 12 |  |  |  |  | 3 | 3 | 3 | 2 | 1 |  |  |  | 0% | 0% | 0% | 0% | 15% | 15% | 13.04% | 16.67% | 4.762% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-11-02 | 2025-01-31 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 w4 | EssilorLuxottica | L. Roberto | C. Di Lorenzo | Delivery Projects | Analysis | 58 | 66 | Closed | 100% | 2025 | 0 |  | 9 | 3 | 3 | [8 empty] | 0% | 45% | 14.29% | 13.64% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-11-02 | 2025-01-31 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 w4 | EssilorLuxottica | L. Roberto | C. Elia | Operations | BackEnd | 58 | 66 | Closed | 100% | 2025 | 8 |  | 1 | 9 | 9 | 8 | [7 empty] | 0% | 5% | 42.86% | 40.91% | 40% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-11-02 | 2025-01-31 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 w4 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 58 | 66 | Closed | 100% | 2025 | 0 |  | 3 | 3 | 3 | [8 empty] | 0% | 15% | 14.29% | 13.64% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-11-02 | 2025-01-31 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 w4 | EssilorLuxottica | L. Roberto | S. Beltrami | Operations | FrontEnd | 58 | 66 | Closed | 100% | 2025 | 0 |  |  | 2 | 4 | [8 empty] | 0% | 0% | 9.524% | 18.18% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-11-02 | 2025-12-31 | ABS24539 | ABS24539 | CRM/CS | Trenord | Trenord | L. Roberto | L. Roberto | Operations | PM - Project Governance | 186 | 21 | ON GOING | 0% | 2025 | 48 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 33.33% | 30% | 28.57% | 27.27% | 30% | 30% | 26.09% | 50% | 28.57% | 26.09% | 28.57% | 27.27%
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | A. Carmisciano | Not Available | Solution Architect | 2020 | 532 | PROPOSAL | 15% | 2025 | 47 | 5 | 1 | 1 | 12.5 | 5 | 5 | 12.5 | 5 | 5 | 12.5 | 1 | 1 | 27.78% | 5% | 4.762% | 56.82% | 25% | 25% | 54.35% | 41.67% | 23.81% | 54.35% | 4.762% | 4.545%
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | A. Mattucci | Not Available | Senior Consultant | 2020 | 532 | PROPOSAL | 15% | 2025 | 14.5 |  |  | 5 | 12.5 | 1 | 1 | 12.5 | [5 empty] | 0% | 0% | 23.81% | 56.82% | 5% | 5% | 54.35% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | A. Torri | Not Available | Senior Consultant | 2020 | 532 | PROPOSAL | 15% | 2025 | 106 |  |  | 1.5 | 17.5 | 1 | 14 | 17.5 | 14 | 14 | 17.5 | 14 | 14 | 0% | 0% | 7.143% | 79.55% | 5% | 70% | 76.09% | 116.7% | 66.67% | 76.09% | 66.67% | 63.64%
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | D. Reich | Not Available | Senior Consultant | 2020 | 532 | PROPOSAL | 15% | 2025 | 30 |  |  | 3 | 5 | 0 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 0% | 0% | 14.29% | 22.73% | 0% | 20% | 21.74% | 33.33% | 19.05% | 21.74% | 19.05% | 18.18%
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | D. Scala | Not Available | Senior Consultant | 2020 | 532 | PROPOSAL | 15% | 2025 | 30 |  |  |  | 3 | 0 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 0% | 0% | 0% | 13.64% | 0% | 20% | 21.74% | 33.33% | 19.05% | 21.74% | 19.05% | 18.18%
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | F. Scognamiglio | Operations | Senior Consultant | 2020 | 532 | PROPOSAL | 15% | 2025 | 60 |  |  | 15 | 25 | 0 | 2 | 25 | 2 | 2 | 25 | 2 | 2 | 0% | 0% | 71.43% | 113.6% | 0% | 10% | 108.7% | 16.67% | 9.524% | 108.7% | 9.524% | 9.091%
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | G. Izzo | Not Available | Senior Developer | 2020 | 532 | PROPOSAL | 15% | 2025 | 15 |  |  |  | 2 | 0 | 2 | 2.5 | 2 | 2 | 2.5 | 2 | 2 | 0% | 0% | 0% | 9.091% | 0% | 10% | 10.87% | 16.67% | 9.524% | 10.87% | 9.524% | 9.091%
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | G. Mandrioli | Not Available | Analyst | 2020 | 532 | PROPOSAL | 15% | 2025 | 34.5 |  | 1 | 1 | 12.5 | 1 | 1 | 12.5 | 10 | 10 |  |  |  | 0% | 5% | 4.762% | 56.82% | 5% | 5% | 54.35% | 83.33% | 47.62% | 0% | 0% | 0%
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | G. Tuninetti | Not Available | Consultant | 2020 | 532 | PROPOSAL | 15% | 2025 | 20 | 6 | 12 | 12 | 15 | 5 | 12 | 3 | [5 empty] | 33.33% | 60% | 57.14% | 68.18% | 25% | 60% | 13.04% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | I. Lopez | Not Available | Consultant | 2020 | 532 | PROPOSAL | 15% | 2025 | 10 |  | 8 | 8 | 1 | 0 | 8 | 2 | [5 empty] | 0% | 40% | 38.1% | 4.545% | 0% | 40% | 8.696% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | L. Carloni | Operations | Senior Consultant | 2020 | 532 | PROPOSAL | 15% | 2025 | 60 |  |  | 15 | 25 | 0 | 2 | 25 | 2 | 2 | 25 | 2 | 2 | 0% | 0% | 71.43% | 113.6% | 0% | 10% | 108.7% | 16.67% | 9.524% | 108.7% | 9.524% | 9.091%
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | M. Calabrese | Delivery Projects | Analyst | 2020 | 532 | PROPOSAL | 15% | 2025 | 40 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 27.78% | 25% | 23.81% | 22.73% | 25% | 25% | 21.74% | 41.67% | 23.81% | 21.74% | 23.81% | 22.73%
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | P. Anzellotti | Operations | Solution Architect | 2020 | 532 | PROPOSAL | 15% | 2025 | 57 |  |  | 6 | 1 | 1 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0% | 0% | 28.57% | 4.545% | 5% | 40% | 34.78% | 66.67% | 38.1% | 34.78% | 38.1% | 36.36%
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | P. Cimino | Not Available | Consultant | 2020 | 532 | PROPOSAL | 15% | 2025 | 60 |  |  |  | 2 | 0 | 2 | 25 | 2 | 2 | 25 | 2 | 2 | 0% | 0% | 0% | 9.091% | 0% | 10% | 108.7% | 16.67% | 9.524% | 108.7% | 9.524% | 9.091%
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | S. Ben Younes | Operations | Consultant | 2020 | 532 | PROPOSAL | 15% | 2025 | 90 |  |  | 9 | 15 | 0 | 12 | 15 | 12 | 12 | 15 | 12 | 12 | 0% | 0% | 42.86% | 68.18% | 0% | 60% | 65.22% | 100% | 57.14% | 65.22% | 57.14% | 54.55%
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | V. Carcaterra | Not Available | Developer | 2020 | 532 | PROPOSAL | 15% | 2025 | 60 |  |  | 15 | 25 | 0 | 2 | 25 | 2 | 2 | 25 | 2 | 2 | 0% | 0% | 71.43% | 113.6% | 0% | 10% | 108.7% | 16.67% | 9.524% | 108.7% | 9.524% | 9.091%
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | Y. Cherednychenko | Not Available | Developer | 2020 | 532 | PROPOSAL | 15% | 2025 | 15 |  |  |  | 2 | 0 | 2 | 2.5 | 2 | 2 | 2.5 | 2 | 2 | 0% | 0% | 0% | 9.091% | 0% | 10% | 10.87% | 16.67% | 9.524% | 10.87% | 9.524% | 9.091%
LEAD | PRJ | WATERFALL | 2025 | 2025-02-01 | 2025-06-30 | N/A | N/A | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - AI 2025 | AO FERRARA | M. Calabrese | F. Spacagna | Operations | Solution Architect | 150 | 0 | PROPOSAL | 0% | 2025 | 25 | [7 empty] | 5 | 5 | 5 | 5 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 41.67% | 23.81% | 21.74% | 23.81% | 22.73%
LEAD | PRJ | WATERFALL | 2025 | 2025-02-01 | 2025-06-30 | N/A | N/A | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - AI 2025 | AO FERRARA | M. Calabrese | G. Sironi | Operations | Data Scientist | 150 | 0 | PROPOSAL | 0% | 2025 | 25 | [7 empty] | 5 | 5 | 5 | 5 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 41.67% | 23.81% | 21.74% | 23.81% | 22.73%
LEAD | PRJ | WATERFALL | 2025 | 2025-02-01 | 2025-06-30 | N/A | N/A | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - AI 2025 | AO FERRARA | M. Calabrese | M. Calabrese | Delivery Projects | PM - Project Governance | 150 | 0 | PROPOSAL | 0% | 2025 | 25 | [7 empty] | 5 | 5 | 5 | 5 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 41.67% | 23.81% | 21.74% | 23.81% | 22.73%
LEAD | PRJ | WATERFALL | 2025 | 2025-02-01 | 2025-06-30 | N/A | N/A | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - AI 2025 | AO FERRARA | M. Calabrese | M. Gomitoni | Operations | Data Scientist | 150 | 0 | PROPOSAL | 0% | 2025 | 25 | [7 empty] | 5 | 5 | 5 | 5 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 41.67% | 23.81% | 21.74% | 23.81% | 22.73%
LEAD | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - PLANNING 2025 | AO FERRARA | M. Calabrese | M. Calabrese | Delivery Projects | PM - Project Governance | 100 | 0 | PROPOSAL | 0% | 2025 | 15 | [6 empty] | 3 | 3 | 3 | 3 | 3 |  | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 25% | 14.29% | 13.04% | 14.29% | 0%
LEAD | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | N/A | N/A | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - PLANNING 2025 | AO FERRARA | M. Calabrese | R. Tortora | Operations | Technical Leader | 100 | 0 | PROPOSAL | 0% | 2025 | 25 | [6 empty] | 5 | 5 | 5 | 5 | 5 |  | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 41.67% | 23.81% | 21.74% | 23.81% | 0%
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS25040 | ABS24401 | healthcare | AOFE DI FERRARA - OFFERTA AMS SAC ANNO 2025 | AO FERRARA | M. Calabrese | A. Elia | UI | Front End | 300 | 0 | TO START | 90% | 2025 | 15 |  |  |  |  | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 10% | 10% | 8.696% | 8.333% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS25040 | ABS24401 | healthcare | AOFE DI FERRARA - OFFERTA AMS SAC ANNO 2025 | AO FERRARA | M. Calabrese | L. Lazzari | SAP ECC | Account Manager | 300 | 0 | TO START | 90% | 2025 | 80 |  |  |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0% | 0% | 0% | 0% | 50% | 50% | 43.48% | 83.33% | 47.62% | 43.48% | 47.62% | 45.45%
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS25040 | ABS24401 | healthcare | AOFE DI FERRARA - OFFERTA AMS SAC ANNO 2025 | AO FERRARA | M. Calabrese | M. Calabrese | Delivery Projects | PM - Project Governance | 300 | 0 | TO START | 90% | 2025 | 40 |  |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0% | 0% | 0% | 0% | 25% | 25% | 21.74% | 41.67% | 23.81% | 21.74% | 23.81% | 22.73%
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS25040 | ABS24401 | healthcare | AOFE DI FERRARA - OFFERTA AMS SAC ANNO 2025 | AO FERRARA | M. Calabrese | R. Tortora | Operations | Front End | 300 | 0 | TO START | 90% | 2025 | 80 |  |  |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0% | 0% | 0% | 0% | 50% | 50% | 43.48% | 83.33% | 47.62% | 43.48% | 47.62% | 45.45%
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS25039 | ABS24401 | healthcare | AUSL DI FERRARA - OFFERTA AMS SAC ANNO 2025 | AO FERRARA | M. Calabrese | A. Elia | UI | Front End | 300 | 0 | TO START | 90% | 2025 | 15 |  |  |  |  | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 10% | 10% | 8.696% | 8.333% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS25039 | ABS24401 | healthcare | AUSL DI FERRARA - OFFERTA AMS SAC ANNO 2025 | AO FERRARA | M. Calabrese | L. Lazzari | SAP ECC | Account Manager | 300 | 0 | TO START | 90% | 2025 | 80 |  |  |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0% | 0% | 0% | 0% | 50% | 50% | 43.48% | 83.33% | 47.62% | 43.48% | 47.62% | 45.45%
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS25039 | ABS24401 | healthcare | AUSL DI FERRARA - OFFERTA AMS SAC ANNO 2025 | AO FERRARA | M. Calabrese | M. Calabrese | Delivery Projects | PM - Project Governance | 300 | 0 | TO START | 90% | 2025 | 40 |  |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0% | 0% | 0% | 0% | 25% | 25% | 21.74% | 41.67% | 23.81% | 21.74% | 23.81% | 22.73%
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS25039 | ABS24401 | healthcare | AUSL DI FERRARA - OFFERTA AMS SAC ANNO 2025 | AO FERRARA | M. Calabrese | R. Tortora | Operations | Front End | 300 | 0 | TO START | 90% | 2025 | 80 |  |  |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0% | 0% | 0% | 0% | 50% | 50% | 43.48% | 83.33% | 47.62% | 43.48% | 47.62% | 45.45%
CONTRACT | PRJ |  | 2024-2025 | 2024-11-01 | 2024-06-30 | ABS24604 | N/A | EPM | KPMG - Ferrero - Supporto + CR | FERRERO | M. COCCHI | A. Di Pietro | Operations | Back End | 110 | 40 | ON GOING | 40% | 2025 | 2 | 19 | 15 | 1 | 1 | 1 | 1 | [6 empty] | 105.6% | 75% | 4.762% | 4.545% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-11-01 | 2024-06-30 | ABS24604 | N/A | EPM | KPMG - Ferrero - Supporto + CR | FERRERO | M. COCCHI | F. Atanasio | Operations | Back End | 110 | 40 | ON GOING | 40% | 2025 | 0 | 4 | [11 empty] | 22.22% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-11-01 | 2024-06-30 | ABS24604 | N/A | EPM | KPMG - Ferrero - Supporto + CR | FERRERO | M. COCCHI | L. Mangili | Operations | Back End | 110 | 40 | ON GOING | 40% | 2025 | 2 | 2 | 5 | 2 | 5 | 1 | 1 | [6 empty] | 11.11% | 25% | 9.524% | 22.73% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-11-01 | 2024-06-30 | ABS24604 | N/A | EPM | KPMG - Ferrero - Supporto + CR | FERRERO | M. COCCHI | M. Favalli | Operations | Back End | 110 | 40 | ON GOING | 40% | 2025 | 0 | 3 | [11 empty] | 16.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - Weekly Sales | FERRERO | M. COCCHI | L. Mangili | Operations | Back End | 305 | 300 | ON GOING | 90% | 2025 | 0 | 7 | [11 empty] | 38.89% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ |  | 2025 | 2025-05-01 | 2025-12-31 | N/A | N/A | EPM | KPMG - Vision Group - AMS | Vision Group | M. COCCHI | F. Atanasio | Operations | Back End | 60 | 0 | PROPOSAL | 0% | 2025 | 30 |  |  |  |  | 4 | 4 | 4 | 1 | 5 | 4 | 4 | 4 | 0% | 0% | 0% | 0% | 20% | 20% | 17.39% | 8.333% | 23.81% | 17.39% | 19.05% | 18.18%
LEAD | PRJ |  | 2025 | 2025-05-01 | 2025-12-31 | N/A | N/A | EPM | KPMG - Vision Group - AMS | Vision Group | M. COCCHI | L. Franco | Operations | Back End | 60 | 0 | PROPOSAL | 0% | 2025 | 30 |  |  |  |  | 4 | 4 | 4 | 1 | 5 | 4 | 4 | 4 | 0% | 0% | 0% | 0% | 20% | 20% | 17.39% | 8.333% | 23.81% | 17.39% | 19.05% | 18.18%
LEAD | PRJ |  | 2025 | 2025-01-01 | 2025-01-31 | N/A | N/A | EPM | KPMG - Vision Group - Consolidato Managerial / Store P&L - 2025 | Vision Group | M. COCCHI | A. Albanese | Delivery Projects | PM - Project Governance | 30 | 0 | PROPOSAL | 0% | 2025 | 0 | 0.5 | 0.5 | 0.5 | [9 empty] | 2.778% | 2.5% | 2.381% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ |  | 2025 | 2025-01-01 | 2025-01-31 | N/A | N/A | EPM | KPMG - Vision Group - Consolidato Managerial / Store P&L - 2025 | Vision Group | M. COCCHI | F. Atanasio | Operations | Back End | 30 | 0 | PROPOSAL | 0% | 2025 | 0 | 2 | 6 | 5 | [9 empty] | 11.11% | 30% | 23.81% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ |  | 2025 | 2025-01-01 | 2025-01-31 | N/A | N/A | EPM | KPMG - Vision Group - Consolidato Managerial / Store P&L - 2025 | Vision Group | M. COCCHI | L. Franco | Operations | Technical Leader | 30 | 0 | PROPOSAL | 0% | 2025 | 0 | 2 | 6 | 5 | [9 empty] | 11.11% | 30% | 23.81% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ |  | 2025 | 2025-01-01 | 2025-01-31 | N/A | N/A | EPM | KPMG - Vision Group - Consolidato Managerial / Store P&L - 2025 | Vision Group | M. COCCHI | M. Favalli | Operations | Back End | 30 | 0 | PROPOSAL | 0% | 2025 | 0 | 1 | [11 empty] | 5.556% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ |  | 2025 | 2025-01-01 | 2025-01-31 | N/A | N/A | EPM | KPMG - Vision Group - Consolidato Managerial / Store P&L - 2025 | Vision Group | M. COCCHI | S. Preziosa | Delivery Projects | Analyst | 30 | 0 | PROPOSAL | 0% | 2025 | 0 | 1 | [11 empty] | 5.556% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ |  | 2025 | 2025-04-01 | 2025-09-30 | N/A | N/A | EPM | KPMG - Vision Group Pianificazione PBCS | Vision Group | M. COCCHI | A. Albanese | Delivery Projects | PM - Project Governance | 300 | 0 | PROPOSAL | 0% | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ |  | 2025 | 2025-04-01 | 2025-09-30 | N/A | N/A | EPM | KPMG - Vision Group Pianificazione PBCS | Vision Group | M. COCCHI | F. Atanasio | Operations | Back End - Junior | 300 | 0 | PROPOSAL | 0% | 2025 | 80 |  |  |  | 1 | 15 | 15 | 15 | 5 | 15 | 15 |  |  | 0% | 0% | 0% | 4.545% | 75% | 75% | 65.22% | 41.67% | 71.43% | 65.22% | 0% | 0%
PROSPECT | PRJ |  | 2025 | 2025-04-01 | 2025-09-30 | N/A | N/A | EPM | KPMG - Vision Group Pianificazione PBCS | Vision Group | M. COCCHI | L. Franco | Operations | Solution Architect | 300 | 0 | PROPOSAL | 0% | 2025 | 42 |  |  |  | 7 | 7 | 6 | 8 | 6 | 7 | 8 |  |  | 0% | 0% | 0% | 31.82% | 35% | 30% | 34.78% | 50% | 33.33% | 34.78% | 0% | 0%
PROSPECT | PRJ |  | 2025 | 2025-04-01 | 2025-09-30 | N/A | N/A | EPM | KPMG - Vision Group Pianificazione PBCS | Vision Group | M. COCCHI | L. Mangili | Operations | Back End | 300 | 0 | PROPOSAL | 0% | 2025 | 10 |  |  |  | 1 | 1 | 1 | 1 | 5 | 1 | 1 |  |  | 0% | 0% | 0% | 4.545% | 5% | 5% | 4.348% | 41.67% | 4.762% | 4.348% | 0% | 0%
PROSPECT | PRJ |  | 2025 | 2025-04-01 | 2025-09-30 | N/A | N/A | EPM | KPMG - Vision Group Pianificazione PBCS | Vision Group | M. COCCHI | S. Preziosa | Delivery Projects | Analyst | 300 | 0 | PROPOSAL | 0% | 2025 | 6 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 0% | 0% | 0% | 4.545% | 5% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-10-15 | 2024-05-30 | ABS24025 | ABS24025 | EPM | Webuild - Migrazione HFM | WeBuild | M. COCCHI | A. Albanese | Delivery Projects | PM - Project Governance | 115 | 15 | ON GOING | 5% | 2025 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 2.778% | 2.5% | 2.381% | 2.273% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-10-15 | 2024-05-30 | ABS24025 | ABS24025 | EPM | Webuild - Migrazione HFM | WeBuild | M. COCCHI | Esterno Oracle | #N/A | PM - Project Governance | 115 | 15 | ON GOING | 5% | 2025 | 0 |  |  |  | 1 | [8 empty] | 0% | 0% | 0% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-10-15 | 2024-05-30 | ABS24025 | ABS24025 | EPM | Webuild - Migrazione HFM | WeBuild | M. COCCHI | F. De Pedis | Operations | Back End | 115 | 15 | ON GOING | 5% | 2025 | 1 | 18 | 15 | 15 | 2 | 1 | [7 empty] | 100% | 75% | 71.43% | 9.091% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2024-2025 | 2024-10-15 | 2024-05-30 | ABS24025 | ABS24025 | EPM | Webuild - Migrazione HFM | WeBuild | M. COCCHI | I. Bressan | Operations | Technical Leader | 115 | 15 | ON GOING | 5% | 2025 | 1 | 13 | 13 | 13 | 2 | 1 | [7 empty] | 72.22% | 65% | 61.9% | 9.091% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS0008-2 | LOGISTIC | Supporto Area Logistica | Abstract | M. Pallotti | C. Paz | Delivery Projects | PMO - Project Management Officer | 0 | 0 | ON GOING | 25% | 2025 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25033 | ABS25033-18 | HR | AMS - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | A. Ferrari | Operations | Data Engineering | 112 | 0 | TO START | 0% | 2025 | 1 | 0.5 | 0.5 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.778% | 2.5% | 4.762% | 4.545% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25033 | ABS25033-18 | HR | AMS - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | C. Di Lorenzo | Delivery Projects | Analyst | 112 | 0 | TO START | 0% | 2025 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.778% | 2.5% | 2.381% | 2.273% | 2.5% | 2.5% | 2.174% | 4.167% | 2.381% | 2.174% | 2.381% | 2.273%
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25033 | ABS25033-18 | HR | AMS - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | L. Carloni | Operations | Data Engineering | 112 | 0 | TO START | 0% | 2025 | 7 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 0.5 | 2.778% | 2.5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 4.167% | 4.762% | 4.348% | 4.762% | 2.273%
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25033 | ABS25033-18 | HR | AMS - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | M. Mannarino | Operations | Data Engineering | 112 | 0 | TO START | 0% | 2025 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.556% | 5% | 4.762% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25033 | ABS25033-18 | HR | AMS - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | M. Porcu | Operations | Technical Leader | 112 | 0 | TO START | 0% | 2025 | 14 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 8.696% | 8.333% | 9.524% | 8.696% | 9.524% | 4.545%
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25033 | ABS25033-18 | HR | AMS - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | M. Toci | Operations | Back End | 112 | 0 | TO START | 0% | 2025 | 12.5 | 2 | 2 | 1.5 | 1.5 | 2 | 1.5 | 2 | 1 | 1 | 2 | 2 | 1 | 11.11% | 10% | 7.143% | 6.818% | 10% | 7.5% | 8.696% | 8.333% | 4.762% | 8.696% | 9.524% | 4.545%
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25033 | ABS25033-18 | HR | AMS - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | N. GUERRERO | Delivery AMS | PM - Project Governance | 112 | 0 | TO START | 0% | 2025 | 10.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 1.5 | 1.5 | 1 | 8.333% | 7.5% | 7.143% | 6.818% | 7.5% | 7.5% | 6.522% | 4.167% | 7.143% | 6.522% | 7.143% | 4.545%
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25033 | ABS25033-18 | HR | AMS - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | R. Marasca | Delivery Projects | Analyst | 112 | 0 | TO START | 0% | 2025 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.778% | 2.5% | 2.381% | 2.273% | 2.5% | 2.5% | 2.174% | 4.167% | 2.381% | 2.174% | 2.381% | 2.273%
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25033 | ABS25033-18 | HR | AMS - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | S. Beltrami | Operations | Front End | 112 | 0 | TO START | 0% | 2025 | 11 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 2 | 1.5 | 0.5 | 1 | 1.5 | 1.5 | 1.5 | 5.556% | 7.5% | 7.143% | 6.818% | 7.5% | 10% | 6.522% | 4.167% | 4.762% | 6.522% | 7.143% | 6.818%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | A. Ferrari | Operations | Data Engineering | 200 | 0 | TO START | 0% | 2025 | 1.5 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 6.818% | 7.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | A. Nastasi | Operations | Data Management | 200 | 0 | TO START | 0% | 2025 | 8 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5.556% | 10% | 4.762% | 4.545% | 5% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | C. Di Lorenzo | Delivery Projects | Analyst | 200 | 0 | TO START | 0% | 2025 | 18.5 | 2 | 2 | 3 | 2.5 | 3 | 2.5 | 3 | 1 | 2.5 | 3 | 2.5 | 1 | 11.11% | 10% | 14.29% | 11.36% | 15% | 12.5% | 13.04% | 8.333% | 11.9% | 13.04% | 11.9% | 4.545%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | L. Cariglia | Operations | Technical Leader | 200 | 0 | TO START | 0% | 2025 | 8 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 11.11% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | L. Carloni | Operations | Data Engineering | 200 | 0 | TO START | 0% | 2025 | 14 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 0% | 0% | 0% | 9.091% | 10% | 10% | 8.696% | 8.333% | 9.524% | 8.696% | 9.524% | 4.545%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | M. Mannarino | Operations | Data Engineering | 200 | 0 | ON GOING | 0% | 2025 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.556% | 5% | 4.762% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | M. Porcu | Operations | Technical Leader | 200 | 0 | TO START | 0% | 2025 | 14 | 2 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 11.11% | 15% | 14.29% | 9.091% | 10% | 10% | 8.696% | 8.333% | 9.524% | 8.696% | 9.524% | 4.545%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | M. Toci | Operations | Back End | 200 | 0 | TO START | 0% | 2025 | 22.5 | 3 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 0.5 | 3.5 | 3.5 | 3.5 | 1 | 16.67% | 17.5% | 16.67% | 15.91% | 17.5% | 17.5% | 15.22% | 4.167% | 16.67% | 15.22% | 16.67% | 4.545%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | N. GUERRERO | Delivery AMS | PM - Project Governance | 200 | 0 | TO START | 0% | 2025 | 9.5 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 1.5 | 1 | 0.5 | 5.556% | 7.5% | 7.143% | 6.818% | 7.5% | 7.5% | 6.522% | 4.167% | 7.143% | 6.522% | 4.762% | 2.273%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | R. Marasca | Delivery Projects | Analyst | 200 | 0 | TO START | 0% | 2025 | 7 | 1 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 0.5 | 5.556% | 2.5% | 2.381% | 4.545% | 5% | 5% | 4.348% | 4.167% | 4.762% | 4.348% | 4.762% | 2.273%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | T. Wu | Not Available | Analyst | 200 | 0 | TO START | 0% | 2025 | 0 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.556% | 2.5% | 2.381% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | S. Beltrami | Operations | Front End | 200 | 0 | TO START | 0% | 2025 | 18.5 | 1 | 3 | 3 | 3 | 3 | 2.5 | 3 | 0.5 | 3 | 3 | 2.5 | 1 | 5.556% | 15% | 14.29% | 13.64% | 15% | 12.5% | 13.04% | 4.167% | 14.29% | 13.04% | 11.9% | 4.545%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | A. De Sanctis | Operations | Data Management | 0 | 0 | TO START | 0 | 2025 | 24 | 18 | 2 | 21 | 22 | 22 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 10% | 100% | 100% | 110% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | A. Nastasi | Operations | Data Management | 0 | 0 | TO START | 0 | 2025 | 17 | 12 | 13 | 9 | 9 | 9 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 66.67% | 65% | 42.86% | 40.91% | 45% | 40% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | D. De Pecol | #N/A | Data Management | 0 | 0 | ON GOING | 0% | 2025 | 0 | 0 | 0 | 9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 42.86% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | G. Cataldo | Operations | Data Management | 0 | 0 | TO START | 0 | 2025 | 4 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 5.556% | 10% | 9.524% | 9.091% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | G. Galati | Delivery AMS | Data Management | 0 | 0 | TO START | 0 | 2025 | 14 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 38.89% | 35% | 33.33% | 31.82% | 35% | 35% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | G. Mordà | Operations | Data Management | 0 | 0 | ON GOING | 0% | 2025 | 28 | 13 | 14 | 15 | 14 | 15 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 72.22% | 70% | 71.43% | 63.64% | 75% | 65% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | I. Bressan | Operations | Back End | 0 | 0 | TO START | 0 | 2025 | 0.5 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 1.389% | 1.25% | 1.19% | 1.136% | 1.25% | 1.25% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | L. Cariglia | Operations | Data Management | 0 | 0 | TO START | 0 | 2025 | 12 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 33.33% | 30% | 28.57% | 27.27% | 30% | 30% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | M. Migliorati | Operations | Front End | 0 | 0 | TO START | 0 | 2025 | 34 | 19 | 2 | 0 | 0 | 18 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 105.6% | 10% | 0% | 0% | 90% | 80% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | M. Vimercati | Operations | Data Management | 0 | 0 | TO START | 0 | 2025 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 11.11% | 10% | 9.524% | 9.091% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | N. GUERRERO | Delivery AMS | PM - Project Governance | 0 | 0 | TO START | 0 | 2025 | 36 | 18 | 19 | 20 | 19 | 19 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 95% | 95.24% | 86.36% | 95% | 85% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | R. Bondi | Operations | Data Management | 0 | 0 | ON GOING | 0% | 2025 | 4 | 0 | 0 | 9 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 42.86% | 4.545% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | R. Marasca | Delivery Projects | Data Integrator | 0 | 0 | TO START | 0% | 2025 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | T. Wu | Not Available | Analyst | 0 | 0 | TO START | 0% | 2025 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 10% | 9.524% | 9.091% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | L. Colombo | Not Available | Analyst | 0 | 0 | TO START | 0% | 2025 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 25% | 23.81% | 22.73% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | K. Dadaian | Delivery Projects | Analyst | 0 | 0 | TO START | 0% | 2025 | 38 | 0 | 0 | 0 | 0 | 18 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 90% | 100% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | A. De Sanctis | Operations | Data Management | 0 | 0 | TO START | 0 | 2025 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 8 | 21 | 23 | 21 | 17 | 0% | 0% | 0% | 0% | 0% | 0% | 95.65% | 66.67% | 100% | 100% | 100% | 77.27%
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | A. Nastasi | Operations | Data Management | 0 | 0 | TO START | 0 | 2025 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 2 | 12 | 12 | 11 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 52.17% | 16.67% | 57.14% | 52.17% | 52.38% | 13.64%
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | D. De Pecol | #N/A | Data Management | 0 | 0 | TO START | 0 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | G. Cataldo | Operations | Data Management | 0 | 0 | TO START | 0 | 2025 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 2 | 2 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 8.333% | 9.524% | 8.696% | 9.524% | 4.545%
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | G. Galati | Delivery AMS | Data Management | 0 | 0 | TO START | 0 | 2025 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 | 7 | 7 | 7 | 7 | 0% | 0% | 0% | 0% | 0% | 0% | 30.43% | 16.67% | 33.33% | 30.43% | 33.33% | 31.82%
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | G. Mordà | Operations | Data Management | 0 | 0 | TO START | 0% | 2025 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 3 | 16 | 17 | 14 | 11 | 0% | 0% | 0% | 0% | 0% | 0% | 73.91% | 25% | 76.19% | 73.91% | 66.67% | 50%
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | I. Bressan | Operations | Back End | 0 | 0 | TO START | 0 | 2025 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0% | 0% | 0% | 0% | 0% | 0% | 1.087% | 2.083% | 1.19% | 1.087% | 1.19% | 1.136%
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | L. Cariglia | Operations | Data Management | 0 | 0 | TO START | 0 | 2025 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 | 6 | 6 | 6 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 26.09% | 16.67% | 28.57% | 26.09% | 28.57% | 22.73%
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | M. Migliorati | Operations | Front End | 0 | 0 | TO START | 0 | 2025 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 17 | 19 | 17 | 18 | 0% | 0% | 0% | 0% | 0% | 0% | 82.61% | 8.333% | 80.95% | 82.61% | 80.95% | 81.82%
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | M. Vimercati | Operations | Data Management | 0 | 0 | TO START | 0 | 2025 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 0% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | N. GUERRERO | Delivery AMS | PM - Project Governance | 0 | 0 | TO START | 0 | 2025 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 7 | 20 | 21 | 19 | 16 | 0% | 0% | 0% | 0% | 0% | 0% | 86.96% | 58.33% | 95.24% | 91.3% | 90.48% | 72.73%
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | R. Bondi | Operations | Data Management | 0 | 0 | TO START | 0 | 2025 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 8.333% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | R. Marasca | Delivery Projects | Data Integrator | 0 | 0 | TO START | 0% | 2025 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1.5 | 1.5 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 8.333% | 9.524% | 6.522% | 7.143% | 4.545%
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | K. Dadaian | Delivery Projects | Analyst | 0 | 0 | TO START | 0% | 2025 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 10 | 22 | 22 | 21 | 18 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 83.33% | 104.8% | 95.65% | 100% | 81.82%
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | IAA | OTHER | CC - supporto CC Leader come Deputy |  | O. Sagazio | P. Anzellotti | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0% | 2025 | 17 | 3 | 3 | 3 |  |  | 3 | 3 | 1 | 3 | 3 | 3 | 1 | 16.67% | 15% | 14.29% | 0% | 0% | 15% | 13.04% | 8.333% | 14.29% | 13.04% | 14.29% | 4.545%
CONTRACT | AMS | Agile | 2025 | 2025-03-01 | 2025-04-11 | N/A | N/A | HR | A3198544L - BSD Integrazione gestione Buoni Nuance | EssilorLuxottica | P. Anzellotti | A. Lorena | Operations | Front End | 28 | 0 | To Start | 100% | 2025 | 0 |  |  | 5 | 1 | [8 empty] | 0% | 0% | 23.81% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Agile | 2025 | 2025-03-01 | 2025-04-11 | N/A | ABS0008-169 | HR | A3198544L - BSD Integrazione gestione Buoni Nuance | EssilorLuxottica | P. Anzellotti | G. De Feo | Operations | PMO - Project Management Officer | 28 | 0 | CLOSED | 100% | 2025 | 0 |  |  | 2 | 1 | [8 empty] | 0% | 0% | 9.524% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Agile | 2025 | 2025-03-01 | 2025-04-11 | N/A | N/A | HR | A3198544L - BSD Integrazione gestione Buoni Nuance | EssilorLuxottica | P. Anzellotti | G. TARTAGLIA | Operations | Back End | 28 | 0 | To Start | 100% | 2025 | 0 |  |  | 5 | 1 | [8 empty] | 0% | 0% | 23.81% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-03-01 | 2025-04-11 | N/A | N/A | HR | A3198544L - BSD Integrazione gestione Buoni Nuance | EssilorLuxottica | P. Anzellotti | P. Anzellotti | Operations | Technical Leader | 28 | 0 | To Start | 100% | 2025 | 0 |  |  | 3 | 1 | [8 empty] | 0% | 0% | 14.29% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Agile | 2025 | 2025-03-01 | 2025-04-11 | N/A | N/A | HR | A3198544L - BSD Integrazione gestione Buoni Nuance | EssilorLuxottica | P. Anzellotti | S. Delle Fave | Operations | Front End | 28 | 0 | To Start | 100% | 2025 | 2 |  |  |  | 1 | 2 | [7 empty] | 0% | 0% | 0% | 4.545% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | AMS | Agile | 2025 | 2025-03-01 | 2025-04-11 | N/A | N/A | HR | BSD - Blocco utilizzo stesso N. Ordine + Codice LSA su stesso Buono Sconto | EssilorLuxottica | P. Anzellotti | A. Lorena | Operations | Front End | 10 | 0 | To Start | 100% | 2025 | 2 |  |  |  | 1 | 2 | [7 empty] | 0% | 0% | 0% | 4.545% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | AMS | Agile | 2025 | 2025-03-01 | 2025-04-11 | N/A | N/A | HR | BSD - Blocco utilizzo stesso N. Ordine + Codice LSA su stesso Buono Sconto | EssilorLuxottica | P. Anzellotti | G. De Feo | Operations | PMO - Project Management Officer | 10 | 0 | To Start | 100% | 2025 | 1 | [5 empty] | 1 | 1 | [5 empty] | 0% | 0% | 0% | 4.545% | 5% | #REF! | #REF! | 0% | 0% | 0% | 0% | 0%
PROSPECT | AMS | Agile | 2025 | 2025-03-01 | 2025-04-11 | N/A | N/A | HR | BSD - Blocco utilizzo stesso N. Ordine + Codice LSA su stesso Buono Sconto | EssilorLuxottica | P. Anzellotti | G. TARTAGLIA | Operations | Back End | 10 | 0 | To Start | 100% | 2025 | 2 |  |  |  | 1 | 2 | [7 empty] | 0% | 0% | 0% | 4.545% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | AMS | Agile | 2025 | 2025-03-01 | 2025-04-11 | N/A | N/A | HR | BSD - Blocco utilizzo stesso N. Ordine + Codice LSA su stesso Buono Sconto | EssilorLuxottica | P. Anzellotti | P. Anzellotti | Operations | Technical Leader | 10 | 0 | To Start | 100% | 2025 | 2 |  |  |  | 1 | 2 | [7 empty] | 0% | 0% | 0% | 4.545% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-01-07 | 2025-02-15 | N/A | N/A | HR | Buoni Sconto Digitali - LSA CR | EssilorLuxottica | P. Anzellotti | A. Lorena | Operations | Front End | 20 | 0 | To Start | 100% | 2025 | 0 | 3 | 3 | 4 | [9 empty] | 16.67% | 15% | 19.05% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-01-07 | 2025-02-15 | N/A | ABS0008-59 | HR | Buoni Sconto Digitali - LSA CR | EssilorLuxottica | P. Anzellotti | G. De Feo | Operations | PM - Project Governance | 20 | 0 | CLOSED | 100% | 2025 | 0 | 1 | 1 | [10 empty] | 5.556% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-01-07 | 2025-02-15 | N/A | N/A | HR | Buoni Sconto Digitali - LSA CR | EssilorLuxottica | P. Anzellotti | G. TARTAGLIA | Operations | Back End | 20 | 0 | To Start | 100% | 2025 | 0 | 6 | 4 | 4 | [9 empty] | 33.33% | 20% | 19.05% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-01-07 | 2025-02-15 | N/A | N/A | HR | Buoni Sconto Digitali - LSA CR | EssilorLuxottica | P. Anzellotti | P. Anzellotti | Operations | Technical Leader | 20 | 0 | To Start | 100% | 2025 | 0 | 3 | 3 | 3 | [9 empty] | 16.67% | 15% | 14.29% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | ATD | OTHER | Carrier Manager Activities | Abstract | P. Pieroni | A. Di Pietro | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0% | 2025 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.778% | 2.5% | 2.381% | 2.273% | 2.5% | 2.5% | 2.174% | 4.167% | 2.381% | 2.174% | 2.381% | 2.273%
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | ATD | OTHER | Carrier Manager Activities | Abstract | P. Pieroni | I. Bressan | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0% | 2025 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.778% | 2.5% | 2.381% | 2.273% | 2.5% | 2.5% | 2.174% | 4.167% | 2.381% | 2.174% | 2.381% | 2.273%
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | ATD | OTHER | Carrier Manager Activities | Abstract | P. Pieroni | L. Franco | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0% | 2025 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.778% | 2.5% | 2.381% | 2.273% | 2.5% | 2.5% | 2.174% | 4.167% | 2.381% | 2.174% | 2.381% | 2.273%
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | ATD | OTHER | Carrier Manager Activities | Abstract | P. Pieroni | N. Fragale | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0% | 2025 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.778% | 2.5% | 2.381% | 2.273% | 2.5% | 2.5% | 2.174% | 4.167% | 2.381% | 2.174% | 2.381% | 2.273%
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | ATD | EPM | Carrier Manager Activities | Abstract | P. Pieroni | P. Pieroni | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0% | 2025 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | ABS0007 | PRACTICE DI | CDC/AREA MANAGEMENT | Abstract | P. Pieroni | P. Pieroni | Operations | PM - Project Governance | 55 | 0 | ON GOING | 100% | 2025 | 35 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  | 5 | 5 | 5 | 5 | 27.78% | 25% | 23.81% | 22.73% | 25% | 25% | 21.74% | 0% | 23.81% | 21.74% | 23.81% | 22.73%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25018 | ABS25018 | RETAIL | BULLSEYE AMS 2025 | EssilorLuxottica | T. Porzio | A. Nastasi | Operations | Data Management - SQL | 200 | 64 | ON GOING | 0% | 2025 | 27 | 0.5 | 0.5 | 1 | 4 | 4 | 4 | 4 | 1 | 4 | 4 | 4 | 2 | 2.778% | 2.5% | 4.762% | 18.18% | 20% | 20% | 17.39% | 8.333% | 19.05% | 17.39% | 19.05% | 9.091%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25018 | ABS25018 | RETAIL | BULLSEYE AMS 2025 | EssilorLuxottica | T. Porzio | A. PIROLA | Operations | Front End | 200 | 64 | ON GOING | 0% | 2025 | 8 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2.778% | 2.5% | 2.381% | 4.545% | 5% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25018 | ABS25018 | RETAIL | BULLSEYE AMS 2025 | EssilorLuxottica | T. Porzio | A. Vladi | Operations | Data Management | 200 | 64 | ON GOING | 0% | 2025 | 27 | 3 | 4 | 5 | 5 | 4 | 4 | 4 | 1 | 4 | 4 | 4 | 2 | 16.67% | 20% | 23.81% | 22.73% | 20% | 20% | 17.39% | 8.333% | 19.05% | 17.39% | 19.05% | 9.091%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25018 | ABS25018 | RETAIL | BULLSEYE AMS 2025 | EssilorLuxottica | T. Porzio | F. D'Alberto | Operations | Data Management - SQL | 200 | 64 | ON GOING | 0% | 2025 | 13 | 3 | 4 | 4 | 0 | 0 | 1 | 1 | 3 | 1 | 1 | 1 | 5 | 16.67% | 20% | 19.05% | 0% | 0% | 5% | 4.348% | 25% | 4.762% | 4.348% | 4.762% | 22.73%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25018 | ABS25018 | RETAIL | BULLSEYE AMS 2025 | EssilorLuxottica | T. Porzio | F. Spacagna | Operations | Back End | 200 | 64 | ON GOING | 0% | 2025 | 7 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 0.5 | 2.778% | 2.5% | 2.381% | 2.273% | 5% | 5% | 4.348% | 4.167% | 4.762% | 4.348% | 4.762% | 2.273%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25018 | ABS25018 | RETAIL | BULLSEYE AMS 2025 | EssilorLuxottica | T. Porzio | M. Vianelli | Delivery Projects | Analyst | 200 | 64 | ON GOING | 0% | 2025 | 17 | 1 | 2 | 2 | 2 | 4 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 5.556% | 10% | 9.524% | 9.091% | 20% | 10% | 8.696% | 8.333% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25018 | ABS25018 | RETAIL | BULLSEYE AMS 2025 | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 200 | 64 | ON GOING | 0% | 2025 | 15 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 16.67% | 10% | 9.524% | 9.091% | 10% | 10% | 8.696% | 8.333% | 9.524% | 8.696% | 9.524% | 9.091%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25019 | ABS25019 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 1H | EssilorLuxottica | T. Porzio | A. Ferrari | Operations | Back End | 100 | 0 | ON GOING | 0% | 2025 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25019 | ABS25019 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 1H | EssilorLuxottica | T. Porzio | A. Lorena | Operations | Front End | 100 | 0 | ON GOING | 0% | 2025 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | [6 empty] | 5.556% | 5% | 4.762% | 9.091% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25019 | ABS25019 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 1H | EssilorLuxottica | T. Porzio | A. PIROLA | Operations | Front End | 100 | 0 | ON GOING | 0% | 2025 | 4 | 1 | 1 | 1 | 2 | 2 | 2 | [6 empty] | 5.556% | 5% | 4.762% | 9.091% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25019 | ABS25019 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 1H | EssilorLuxottica | T. Porzio | A. Vladi | Operations | Team Leadership | 100 | 0 | ON GOING | 0% | 2025 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25019 | ABS25019 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 1H | EssilorLuxottica | T. Porzio | F. D'Alberto | Operations | Back End | 100 | 0 | ON GOING | 0% | 2025 | 10 | 5 | 7 | 5 |  | 5 | 5 | [6 empty] | 27.78% | 35% | 23.81% | 0% | 25% | 25% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25019 | ABS25019 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 1H | EssilorLuxottica | T. Porzio | F. Spacagna | Operations | Back End | 100 | 0 | ON GOING | 0% | 2025 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25019 | ABS25019 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 1H | EssilorLuxottica | T. Porzio | M. Vianelli | Delivery Projects | Analyst | 100 | 0 | ON GOING | 0% | 2025 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 11.11% | 10% | 9.524% | 9.091% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25019 | ABS25019 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 1H | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 100 | 0 | ON GOING | 0% | 2025 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | [6 empty] | 5.556% | 5% | 4.762% | 9.091% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 2H | EssilorLuxottica | T. Porzio | A. Ferrari | Operations | Back End | 100 | 0 | TO START | 0% | 2025 | 13 | [9 empty] | 5 | 5 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.74% | 23.81% | 13.64%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 2H | EssilorLuxottica | T. Porzio | A. Lorena | Operations | Front End | 100 | 0 | TO START | 0% | 2025 | 9 | [9 empty] | 3 | 3 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 14.29% | 13.64%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 2H | EssilorLuxottica | T. Porzio | A. PIROLA | Operations | Front End | 100 | 0 | TO START | 0% | 2025 | 1.5 | [9 empty] | 0.5 | 0.5 | 0.5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.174% | 2.381% | 2.273%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 2H | EssilorLuxottica | T. Porzio | A. Vladi | Operations | Team Leadership | 100 | 0 | TO START | 0% | 2025 | 6 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 2H | EssilorLuxottica | T. Porzio | F. D'Alberto | Operations | Back End | 100 | 0 | TO START | 0% | 2025 | 41 | [6 empty] | 8 | 4 | 8 | 8 | 8 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 34.78% | 33.33% | 38.1% | 34.78% | 38.1% | 22.73%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 2H | EssilorLuxottica | T. Porzio | F. Spacagna | Operations | Back End | 100 | 0 | TO START | 0% | 2025 | 12 | [6 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 16.67% | 9.524% | 8.696% | 9.524% | 9.091%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 2H | EssilorLuxottica | T. Porzio | M. Vianelli | Delivery Projects | Analyst | 100 | 0 | TO START | 0% | 2025 | 12 | [6 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 16.67% | 9.524% | 8.696% | 9.524% | 9.091%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 2H | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 100 | 0 | TO START | 0% | 2025 | 14 | [6 empty] | 2 | 2 | 3 | 3 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 16.67% | 14.29% | 13.04% | 9.524% | 9.091%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2025 | EssilorLuxottica | T. Porzio | E. Storti | Delivery Projects | Back End | 100 | 0 | TO START | 0% | 2025 | 10 | [6 empty] | 2 |  | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2025 | EssilorLuxottica | T. Porzio | N. Fragale | Operations | Back End | 100 | 0 | TO START | 0% | 2025 | 15 | [6 empty] | 3 |  | 3 | 3 | 3 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 0% | 14.29% | 13.04% | 14.29% | 13.64%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2025 | EssilorLuxottica | T. Porzio | O. BEN OTHMANE | Operations | Back End - Junior | 100 | 0 | TO START | 0% | 2025 | 14 | [6 empty] | 2 |  | 3 | 3 | 3 | 3 | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 0% | 14.29% | 13.04% | 14.29% | 13.64%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2025 | EssilorLuxottica | T. Porzio | P. Pieroni | Operations | Back End | 100 | 0 | TO START | 0% | 2025 | 12 | [6 empty] | 2 |  | 2 | 3 | 3 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 0% | 9.524% | 13.04% | 14.29% | 9.091%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2025 | EssilorLuxottica | T. Porzio | S. Preziosa | Delivery Projects | Analyst | 100 | 0 | TO START | 0% | 2025 | 18 | [6 empty] | 2 |  | 4 | 4 | 4 | 4 | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 0% | 19.05% | 17.39% | 19.05% | 18.18%
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 | N/A | N/A | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2025 | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 100 | 0 | TO START | 0% | 2025 | 11 | [6 empty] | 3 |  | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 13.04% | 0% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-01 | 2025-12-31 | N/A | N/A |  | Gara Leonardo | Regione Veneto | T. Porzio | A. Cuomo | Operations | Data Management | 2000 | 0 | TO START | 0% | 2025 | 120 | [7 empty] | 24 | 24 | 24 | 24 | 24 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 200% | 114.3% | 104.3% | 114.3% | 109.1%
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-01 | 2025-12-31 | N/A | N/A |  | Gara Leonardo | Regione Veneto | T. Porzio | A. Strada | Operations | Data Management | 2000 | 0 | TO START | 0% | 2025 | 120 | [7 empty] | 24 | 24 | 24 | 24 | 24 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 200% | 114.3% | 104.3% | 114.3% | 109.1%
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-01 | 2025-12-31 | N/A | N/A |  | Gara Leonardo | Regione Veneto | T. Porzio | C. Elia | Operations | Solution Architect | 2000 | 0 | TO START | 0% | 2025 | 10 | [7 empty] | 2 | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 16.67% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-01 | 2025-12-31 | N/A | N/A |  | Gara Leonardo | Regione Veneto | T. Porzio | F. SPACAGNA | Operations | Data Engineering | 2000 | 0 | TO START | 0% | 2025 | 90 | [7 empty] | 18 | 18 | 18 | 18 | 18 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 150% | 85.71% | 78.26% | 85.71% | 81.82%
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-01 | 2025-12-31 | N/A | N/A |  | Gara Leonardo | Regione Veneto | T. Porzio | M. Aristide | Operations | PM - Project Governance | 2000 | 0 | TO START | 0% | 2025 | 25 | [7 empty] | 5 | 5 | 5 | 5 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 41.67% | 23.81% | 21.74% | 23.81% | 22.73%
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-01 | 2025-12-31 | N/A | N/A |  | Gara Leonardo | Regione Veneto | T. Porzio | M. Gomitoni | Operations | Data Scientist | 2000 | 0 | TO START | 0% | 2025 | 40 | [7 empty] | 8 | 8 | 8 | 8 | 8 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 66.67% | 38.1% | 34.78% | 38.1% | 36.36%
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-01 | 2025-12-31 | N/A | N/A |  | Gara Leonardo | Regione Veneto | T. Porzio | M. Porcu | Operations | Solution Architect | 2000 | 0 | TO START | 0% | 2025 | 10 | [7 empty] | 2 | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 16.67% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-01 | 2025-12-31 | N/A | N/A |  | Gara Leonardo | Regione Veneto | T. Porzio | M. TOCI | Operations | Back End | 2000 | 0 | TO START | 0% | 2025 | 65 | [7 empty] | 13 | 13 | 13 | 13 | 13 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 108.3% | 61.9% | 56.52% | 61.9% | 59.09%
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-01 | 2025-12-31 | N/A | N/A |  | Gara Leonardo | Regione Veneto | T. Porzio | P. Anzellotti | Operations | Solution Architect | 2000 | 0 | TO START | 0% | 2025 | 80 | [7 empty] | 16 | 16 | 16 | 16 | 16 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 133.3% | 76.19% | 69.57% | 76.19% | 72.73%
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-01 | 2025-12-31 | N/A | N/A |  | Gara Leonardo | Regione Veneto | T. Porzio | S. DELLE FAVE | Operations | Front End | 2000 | 0 | TO START | 0% | 2025 | 65 | [7 empty] | 13 | 13 | 13 | 13 | 13 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 108.3% | 61.9% | 56.52% | 61.9% | 59.09%
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-01 | 2025-12-31 | N/A | N/A |  | Gara Leonardo | Regione Veneto | T. Porzio | T. Porzio | Operations | PM - Project Governance | 2000 | 0 | TO START | 0% | 2025 | 35 | [7 empty] | 7 | 7 | 7 | 7 | 7 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 58.33% | 33.33% | 30.43% | 33.33% | 31.82%
A CONSUMO | PRJ | Waterfall | 2024-2025 | 2025-01-01 | 2025-02-28 | N/A | N/A | EPM | Lux - Job Type - Wave2 | EssilorLuxottica | T. Porzio | A. Albanese | Delivery Projects | Back End | 24 | 0 | ON HOLD | 0% | 2025 | 0 | 1 | [11 empty] | 5.556% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | PRJ | Waterfall | 2024-2025 | 2025-01-01 | 2025-02-28 | N/A | N/A | EPM | Lux - Job Type - Wave2 | EssilorLuxottica | T. Porzio | L. Mangili | Operations | Back End | 24 | 0 | ON HOLD | 0% | 2025 | 0 | 2 | [11 empty] | 11.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | PRJ | Waterfall | 2024-2025 | 2025-01-01 | 2025-02-28 | N/A | N/A | EPM | Lux - Job Type - Wave2 | EssilorLuxottica | T. Porzio | P. Pieroni | Operations | Back End | 24 | 0 | ON HOLD | 0% | 2025 | 0 | 2 | [11 empty] | 11.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | PRJ | Waterfall | 2024-2025 | 2025-01-01 | 2025-02-28 | N/A | N/A | EPM | Lux - Job Type - Wave2 | EssilorLuxottica | T. Porzio | T. Baldi | Operations | Back End | 24 | 0 | ON HOLD | 0% | 2025 | 0 | 1 | [11 empty] | 5.556% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25063 | ABS25063 | EPM | LUX–DI-EPM–enhancements plus 10 Planning 2025_dismissioneWHSP | EssilorLuxottica | T. Porzio | G. Minervini | Operations | Analyst | 24 | 0 | TO START | 0% | 2025 | 0 |  |  | 5 | 5 | [8 empty] | 0% | 0% | 23.81% | 22.73% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25063 | ABS25063 | EPM | LUX–DI-EPM–enhancements plus 10 Planning 2025_dismissioneWHSP | EssilorLuxottica | T. Porzio | N. Fragale | Operations | Back End | 24 | 0 | TO START | 0% | 2025 | 0 |  |  | 5 | 5 | [8 empty] | 0% | 0% | 23.81% | 22.73% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25063 | ABS25063 | EPM | LUX–DI-EPM–enhancements plus 10 Planning 2025_dismissioneWHSP | EssilorLuxottica | T. Porzio | P. Pieroni | Operations | Analyst | 24 | 0 | TO START | 0% | 2025 | 0 |  |  | 1 | 1 | [8 empty] | 0% | 0% | 4.762% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25063 | ABS25063 | EPM | LUX–DI-EPM–enhancements plus 10 Planning 2025_dismissioneWHSP | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 24 | 0 | TO START | 0% | 2025 | 0 |  |  | 1 | 1 | [8 empty] | 0% | 0% | 4.762% | 4.545% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25013 | ABS25013 | EPM | Luxottica - DI - AMS EPM PLN 2025 | EssilorLuxottica | T. Porzio | A. Di Pietro | Operations | Back End | 1161 | 430 | ON GOING | 0% | 2025 | 0 | 2 | 2 | [10 empty] | 11.11% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25013 | ABS25013 | EPM | Luxottica - DI - AMS EPM PLN 2025 | EssilorLuxottica | T. Porzio | G. Minervini | Operations | Back End - Junior | 1161 | 430 | ON GOING | 0% | 2025 | 164 | 18 | 2 | 21 | 19 | 22 | 20 | 23 | 12 | 21 | 23 | 21 | 22 | 100% | 10% | 100% | 86.36% | 110% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25013 | ABS25013 | EPM | Luxottica - DI - AMS EPM PLN 2025 | EssilorLuxottica | T. Porzio | M. Favalli | Operations | Back End - Junior | 1161 | 430 | ON GOING | 0% | 2025 | 153 |  |  | 13 | 13 | 13 | 20 | 23 | 12 | 21 | 23 | 21 | 20 | 0% | 0% | 61.9% | 59.09% | 65% | 100% | 100% | 100% | 100% | 100% | 100% | 90.91%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25013 | ABS25013 | EPM | Luxottica - DI - AMS EPM PLN 2025 | EssilorLuxottica | T. Porzio | N. Fragale | Operations | Back End | 1161 | 430 | ON GOING | 0% | 2025 | 147 | 18 | 18 | 2 | 22 | 22 | 16 | 20 | 12 | 21 | 23 | 18 | 15 | 100% | 90% | 9.524% | 100% | 110% | 80% | 86.96% | 100% | 100% | 100% | 85.71% | 68.18%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25013 | ABS25013 | EPM | Luxottica - DI - AMS EPM PLN 2025 | EssilorLuxottica | T. Porzio | O. BEN OTHMANE | Operations | Back End - Junior | 1161 | 430 | ON GOING | 0% | 2025 | 155 | 17 | 17 | 18 | 17 | 18 | 20 | 23 | 12 | 21 | 23 | 21 | 17 | 94.44% | 85% | 85.71% | 77.27% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 77.27%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25013 | ABS25013 | EPM | Luxottica - DI - AMS EPM PLN 2025 | EssilorLuxottica | T. Porzio | P. Pieroni | Operations | Back End | 1161 | 430 | ON GOING | 0% | 2025 | 22 | 5 | 8 | 8 | 8 | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 27.78% | 40% | 38.1% | 36.36% | 40% | 10% | 8.696% | 16.67% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25013 | ABS25013 | EPM | Luxottica - DI - AMS EPM PLN 2025 | EssilorLuxottica | T. Porzio | S. Preziosa | Delivery Projects | Analyst | 1161 | 430 | ON GOING | 0% | 2025 | 13 | 1 | 13 | 13 | 9 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5.556% | 65% | 61.9% | 40.91% | 30% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25013 | ABS25013 | EPM | Luxottica - DI - AMS EPM PLN 2025 | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 1161 | 430 | ON GOING | 0% | 2025 | 61 | 7 | 7 | 7 | 7 | 8 | 8 | 9 | 5 | 8 | 8 | 8 | 7 | 38.89% | 35% | 33.33% | 31.82% | 40% | 40% | 39.13% | 41.67% | 38.1% | 34.78% | 38.1% | 31.82%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25013 | ABS25013 | EPM | Luxottica - DI - AMS EPM PLN 2025 | EssilorLuxottica | T. Porzio | V. Raso | Operations | Back End | 1161 | 430 | ON GOING | 0% | 2025 | 0 | 18 | 18 | [10 empty] | 100% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25013 | ABS25013 | EPM | Luxottica - DI - AMS EPM PLN 2025 | EssilorLuxottica | T. Porzio | A. Di Pietro | Operations | Back End | 1161 | 430 | ON GOING | 0% | 2025 | 39 |  |  |  |  | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0% | 0% | 0% | 0% | 20% | 25% | 21.74% | 41.67% | 23.81% | 21.74% | 23.81% | 22.73%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25016 | ABS25016 | EPM | Luxottica - DI - Enhancements plus 10 EPM PLN Q1 Q2 2025 | EssilorLuxottica | T. Porzio | A. Albanese | Delivery Projects | Back End | 150 | 0 | ON GOING | 0% | 2025 | 0 |  | 1 | [10 empty] | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25016 | ABS25016 | EPM | Luxottica - DI - Enhancements plus 10 EPM PLN Q1 Q2 2025 | EssilorLuxottica | T. Porzio | A. Di Pietro | Operations | Back End | 150 | 0 | ON GOING | 0% | 2025 | 2 | 3 | 3 | 3 | 2 | 1 | 1 | [6 empty] | 16.67% | 15% | 14.29% | 9.091% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25016 | ABS25016 | EPM | Luxottica - DI - Enhancements plus 10 EPM PLN Q1 Q2 2025 | EssilorLuxottica | T. Porzio | E. Storti | Delivery Projects | Back End | 150 | 0 | ON GOING | 0% | 2025 | 4 | 1 | 5 | 3 | 2 | 2 | 2 | [6 empty] | 5.556% | 25% | 14.29% | 9.091% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25016 | ABS25016 | EPM | Luxottica - DI - Enhancements plus 10 EPM PLN Q1 Q2 2025 | EssilorLuxottica | T. Porzio | L. Franco | Operations | Back End | 150 | 0 | ON GOING | 0% | 2025 | 0 | [12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25016 | ABS25016 | EPM | Luxottica - DI - Enhancements plus 10 EPM PLN Q1 Q2 2025 | EssilorLuxottica | T. Porzio | L. Mangili | Operations | Back End | 150 | 0 | ON GOING | 0% | 2025 | 0 |  | 4 | 4 | [9 empty] | 0% | 20% | 19.05% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25016 | ABS25016 | EPM | Luxottica - DI - Enhancements plus 10 EPM PLN Q1 Q2 2025 | EssilorLuxottica | T. Porzio | M. Favalli | Operations | Back End - Junior | 150 | 0 | ON GOING | 0% | 2025 | 0 |  |  | 3 | [9 empty] | 0% | 0% | 14.29% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25016 | ABS25016 | EPM | Luxottica - DI - Enhancements plus 10 EPM PLN Q1 Q2 2025 | EssilorLuxottica | T. Porzio | N. Fragale | Operations | Back End | 150 | 0 | ON GOING | 0% | 2025 | 0 |  | 2 | 2 | 2 | [8 empty] | 0% | 10% | 9.524% | 9.091% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25016 | ABS25016 | EPM | Luxottica - DI - Enhancements plus 10 EPM PLN Q1 Q2 2025 | EssilorLuxottica | T. Porzio | O. BEN OTHMANE | Operations | Back End - Junior | 150 | 0 | ON GOING | 0% | 2025 | 4 | 1 | 3 | 4 | 5 | 4 | 0 | [6 empty] | 5.556% | 15% | 19.05% | 22.73% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25016 | ABS25016 | EPM | Luxottica - DI - Enhancements plus 10 EPM PLN Q1 Q2 2025 | EssilorLuxottica | T. Porzio | P. Pieroni | Operations | Back End | 150 | 0 | ON GOING | 0% | 2025 | 5 | 2 | 6 | 2 | 3 | 3 | 2 | [6 empty] | 11.11% | 30% | 9.524% | 13.64% | 15% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25016 | ABS25016 | EPM | Luxottica - DI - Enhancements plus 10 EPM PLN Q1 Q2 2025 | EssilorLuxottica | T. Porzio | S. Preziosa | Delivery Projects | Analyst | 150 | 0 | ON GOING | 0% | 2025 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | [6 empty] | 22.22% | 20% | 9.524% | 9.091% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25016 | ABS25016 | EPM | Luxottica - DI - Enhancements plus 10 EPM PLN Q1 Q2 2025 | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 150 | 0 | ON GOING | 0% | 2025 | 4 | 3 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 16.67% | 10% | 9.524% | 9.091% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL TRAINING | FORMAZIONE |  | 2025 | 2025-01-01 | 2025-12-31 | N/A | ATD | OTHER | Training Luxottica - DI - AMS EPM PLN 2025 | Abstract | T. Porzio | M. Favalli | Operations | Back End - Junior | 0 | 0 | ON GOING | 0% | 2025 | 0 | 1 | 15 | [10 empty] | 5.556% | 75% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ | Waterfall | 2025 | 2025-05-04 | 2025-07-31 | N/A | ABS0008-99 | HR | Dashboard data quality | EssilorLuxottica | L. Roberto | R. Bondi | Delivery Projects | Front End | 0 | 0 | PROPOSAL | 0% | 2025 | 3 | [5 empty] | 1 | 1 | 1 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 5% | 4.348% | 8.333% | 0% | 0% | 0% | 0%
LEAD | PRESALES - DELIVERY |  | 2025 |  |  | N/A | ABS0008-159 |  | GEOX - Retail Community - Sales Assistant | GEOX | L. Roberto | L. Roberto | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0% | 2025 | 8 |  |  |  |  | 4 | 4 | [6 empty] | 0% | 0% | 0% | 0% | 20% | 20% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRESALES - DELIVERY |  | 2025 |  |  | N/A | ABS0008-159 |  | GEOX - Retail Community - Sales Assistant | GEOX | L. Roberto | F. Spacagna | Operations | Technical Leader | 0 | 0 | ON GOING | 0% | 2025 | 5 |  |  |  |  | 5 | [7 empty] | 0% | 0% | 0% | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRESALES - DELIVERY |  | 2025 |  |  | N/A | ABS0008-159 |  | GEOX - Retail Community - Sales Assistant | GEOX | L. Roberto | G. Sironi | Operations | Data Scientist | 0 | 0 | ON GOING | 0% | 2025 | 5 |  |  |  |  | 5 | [7 empty] | 0% | 0% | 0% | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRESALES - DELIVERY |  | 2025 |  |  | N/A | ABS0008-159 |  | GEOX - Retail Community - Sales Assistant | GEOX | L. Roberto | A. Imbimbo | Operations | Data Scientist | 0 | 0 | ON GOING | 0% | 2025 | 5 |  |  |  |  | 5 | [7 empty] | 0% | 0% | 0% | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRESALES - DELIVERY |  | 2025 |  |  | N/A | ABS0008-159 |  | GEOX - Retail Community - Sales Assistant | GEOX | L. Roberto | M. GOMITONI | Operations | Data Scientist | 0 | 0 | ON GOING | 0% | 2025 | 5 |  |  |  |  | 5 | [7 empty] | 0% | 0% | 0% | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 31/06/2025 | N/A | ABS0008-248 ABS0008-227 ABS0008-219 | HR | Evolutive Dashboard Maggio(post golive) | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer |  | 0 | ON GOING | 0% | 2025 | 2 |  |  |  |  | 2 | [7 empty] | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 31/06/2025 | N/A | ABS0008-248 ABS0008-227 ABS0008-219 | HR | Evolutive Dashboard Maggio(post golive) | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Front End |  | 0 | ON GOING | 0% | 2025 | 4 |  |  |  |  | 2 | 1 | 1 | [5 empty] | 0% | 0% | 0% | 0% | 10% | 5% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 31/06/2025 | N/A | ABS0008-248 ABS0008-227 ABS0008-219 | HR | Evolutive Dashboard Maggio(post golive) | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Business Analyst |  | 0 | ON GOING | 0% | 2025 | 3 |  |  |  |  | 3 | [7 empty] | 0% | 0% | 0% | 0% | 15% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-05-31 | N/A | IAA | HR | MY PLACE | Abstract | L. Roberto | G. De Feo | Operations | PMO - Project Management Officer | 0 | 0 | ON GOING | 0% | 2025 | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 10% | 10% | 8.696% | 16.67% | 9.524% | 8.696% | 9.524% | 9.091%
LEAD | PRJ | Waterfall | 2025 | 2025-05-04 | 2025-07-31 | N/A | ABS0008-99 | HR | Dashboard data quality | EssilorLuxottica | L. Roberto | L. Roberto | Delivery Projects | PM - Project Governance | 0 | 0 | PROPOSAL | 0% | 2025 | 2 | [6 empty] | 1 | 1 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 4.348% | 8.333% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 | N/A | ABS0008-140 | HR | Regole automatizzate - file hr controlling | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 18 | 0 | ON GOING | 95% | 2025 | 3 |  |  |  |  | 1 | 2 | [6 empty] | 0% | 0% | 0% | 0% | 5% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 | N/A | ABS0008-154 | HR | Talent Card BO | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer |  | 0 | ON GOING | 90% | 2025 | 3 |  |  |  |  | 1 | 1 | 1 | [5 empty] | 0% | 0% | 0% | 0% | 5% | 5% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 | N/A | ABS0008-154 | HR | Talent Card BO | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance |  | 0 | ON GOING | 90% | 2025 | 3 |  |  |  |  | 1 | 1 | 1 | [5 empty] | 0% | 0% | 0% | 0% | 5% | 5% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 | N/A | ABS0008-154 | HR | Talent Card BO | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Business Analyst |  | 0 | ON GOING | 90% | 2025 | 9 |  |  |  |  | 3 | 3 | 3 | [5 empty] | 0% | 0% | 0% | 0% | 15% | 15% | 13.04% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 | N/A | ABS0008-154 | HR | Talent Card BO | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Front End |  | 0 | ON GOING | 90% | 2025 | 13 |  |  |  |  | 3 | 5 | 5 | [5 empty] | 0% | 0% | 0% | 0% | 15% | 25% | 21.74% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 | N/A | ABS0008-154 | HR | Talent Card BO | EssilorLuxottica | L. Roberto | M. Porcu | Operations | Tech Lead |  | 0 | ON GOING | 90% | 2025 | 3 |  |  |  |  | 1 | 1 | 1 | [5 empty] | 0% | 0% | 0% | 0% | 5% | 5% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 | N/A | ABS0008-154 | HR | Talent Card BO | EssilorLuxottica | L. Roberto | M. Toci | Operations | Backend |  | 0 | ON GOING | 90% | 2025 | 4 |  |  |  |  | 2 | 1 | 1 | [5 empty] | 0% | 0% | 0% | 0% | 10% | 5% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 31/06/2025 | ABS24299 | ABS0008-138 | HR | Hypercare dismissione QLIK | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 570 | 567 | On Going | 95% | 2025 | 2 |  |  | 1 | 1 | 2 | [7 empty] | 0% | 0% | 4.762% | 4.545% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-257 | HR | HR - Banding | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management |  |  | ON GOING | 0% | 2025 | [5 empty] | 1 | 1 | [6 empty] | 0% | 0% | 0% | 0% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-257 | HR | HR - Banding | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Front End |  |  | ON GOING | 0% | 2025 | [5 empty] | 1 | 1 | [6 empty] | 0% | 0% | 0% | 0% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-257 | HR | HR - Banding | EssilorLuxottica | L. Roberto | S. Beltrami | Operations | Front End |  |  | ON GOING | 0% | 2025 | [5 empty] | 1 | [7 empty] | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-257 | HR | HR - Banding | EssilorLuxottica | L. Roberto | S. Toci | Operations | Back End |  |  | ON GOING | 0% | 2025 | [5 empty] | 1 | [7 empty] | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-257 | HR | HR - Banding | EssilorLuxottica | L. Roberto | L. Carloni | Operations | Back End |  |  | ON GOING | 0% | 2025 | [5 empty] | 1 | [7 empty] | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-257 | HR | HR - Banding | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer |  |  | ON GOING | 0% | 2025 | [5 empty] | 1 | [7 empty] | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-262 | HR | HR - Grade US | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer |  |  | ON GOING | 0% | 2025 | [5 empty] | 1 | 1 | [6 empty] | 0% | 0% | 0% | 0% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-262 | HR | HR - Grade US | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management |  |  | ON GOING | 0% | 2025 | [5 empty] | 1 | 8 | [6 empty] | 0% | 0% | 0% | 0% | 5% | 40% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-263 | HR | HR - HR Controlling - New Segment | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management |  |  | ON GOING | 0% | 2025 | [5 empty] | 2 | 3 | [6 empty] | 0% | 0% | 0% | 0% | 10% | 15% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-263 | HR | HR - HR Controlling - New Segment | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Business Analyst |  |  | ON GOING | 0% | 2025 | 6 |  |  |  |  | 2 | 3 | 1 | [5 empty] | 0% | 0% | 0% | 0% | 10% | 15% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-263 | HR | HR - HR Controlling - New Segment | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance |  |  | ON GOING | 0% | 2025 | [5 empty] | 1 | 1 | [6 empty] | 0% | 0% | 0% | 0% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-263 | HR | HR - HR Controlling - New Segment | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Front - End |  |  | ON GOING | 0% | 2025 | [6 empty] | 2 | 1 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 10% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-263 | HR | HR - HR Controlling - New Segment | EssilorLuxottica | L. Roberto | M. Toci | Operations | Back end |  |  | ON GOING | 0% | 2025 | [6 empty] | 1 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-263 | HR | HR - HR Controlling - New Segment | EssilorLuxottica | L. Roberto | M. Porcu | Operations | Tech Lead |  |  | ON GOING | 0% | 2025 | [6 empty] | 1 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-257 | HR | HR - Banding | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Business Analyst |  |  | ON GOING | 0% | 2025 | 4 |  |  |  |  | 1 | 2 | 1 | [5 empty] | 0% | 0% | 0% | 0% | 5% | 10% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 31/06/2025 | N/A | ABS0008-248 ABS0008-227 ABS0008-219 | HR | Evolutive Dashboard Maggio(post golive) | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Business Analyst |  | 0 | ON GOING | 0% | 2025 | 3 |  |  |  |  | 3 | [7 empty] | 0% | 0% | 0% | 0% | 15% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-262 | HR | HR - Grade US | EssilorLuxottica | L. Roberto | R. Marasca | Operations | Business Analyst |  |  | ON GOING | 0% | 2025 | 4 |  |  |  |  | 1 | 2 | 1 | [5 empty] | 0% | 0% | 0% | 0% | 5% | 10% | 4.348% | 0% | 0% | 0% | 0% | 0%
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 | N/A | IAA | HR | MY CAREER | Abstract | L. Roberto | D. Heba | Operations | Back end | 450 | 244 | ON GOING | 45% | 2025 | [5 empty] | 3 | 10 | 12 | [5 empty] | 0% | 0% | 0% | 0% | 15% | 50% | 52.17% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25089 | ABS25089 | FINANCE | AMS FDP - Fraud Detection Platform 2025 | EssilorLuxottica | A. Morterra | A. Crescimone | Operations |  |  |  | ONGOING |  | 2025 | 24 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5.556% | 5% | 4.762% | 4.545% | 15% | 15% | 13.04% | 25% | 14.29% | 13.04% | 14.29% | 13.64%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25089 | ABS25089 | FINANCE | AMS FDP - Fraud Detection Platform 2025 | EssilorLuxottica | A. Morterra | A. Saija | Operations |  |  |  | ONGOING |  | 2025 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.556% | 5% | 4.762% | 4.545% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25089 | ABS25089 | FINANCE | AMS FDP - Fraud Detection Platform 2025 | EssilorLuxottica | A. Morterra | G. Luongo | Delivery AMS |  |  |  | ONGOING |  | 2025 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5.556% | 5% | 4.762% | 4.545% | 5% | 5% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25089 | ABS25089 | FINANCE | AMS FDP - Fraud Detection Platform 2025 | EssilorLuxottica | A. Morterra | L. Gullotto | Operations |  |  |  | ONGOING |  | 2025 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2.778% | 2.5% | 2.381% | 2.273% | 2.5% | 2.5% | 2.174% | 4.167% | 2.381% | 2.174% | 2.381% | 2.273%
INTERNAL PRJ | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-05-31 | N/A | IAA | HR | MY PLACE | Abstract | L. Roberto | C. Elia | Operations | Backend | 0 | 0 | ON GOING | 0% | 2025 | [5 empty] | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 0% | 0% | 0% | 0% | 20% | 20% | 4.348% | 8.333% | 4.762% | 4.348% | 4.762% | 4.545%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | C. Elia | Operations | Data Management | 100 | 7 | ON GOING | 40% | 2025 | [5 empty] | 2 | 5 | [6 empty] | 0% | 0% | 0% | 0% | 10% | 25% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | M. Porcu | Operations | Tech Lead | 100 | 7 | ON GOING | 40% | 2025 | [5 empty] | 1 | 1 | [6 empty] | 0% | 0% | 0% | 0% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | M. Toci | Operations | Backend | 100 | 7 | ON GOING | 40% | 2025 | [5 empty] | 2 | [7 empty] | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
LEAD | PRJ | Waterfall | 2025 | 2025-05-04 | 2025-07-31 | N/A | N/A | HR | Dashboard Salary (dati vendite) | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Front End | 0 | 0 | PROPOSAL | 0% | 2025 | 3 | [5 empty] | 1 | 1 | 1 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 5% | 4.348% | 8.333% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo revisione | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analyst |  |  | PROPOSAL | 0% | 2025 | 4 | [5 empty] | 2 | 2 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 10% | 8.696% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo revisione | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer |  |  | PROPOSAL | 0% | 2025 | 4 | [5 empty] | 2 | 1 | 1 |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 10% | 4.348% | 8.333% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo revisione | EssilorLuxottica | L. Roberto | P. Flora | Delivery AMS | PM - Project Governance |  |  | PROPOSAL | 0% | 2025 | 2 | [5 empty] | 2 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo revisione | EssilorLuxottica | L. Roberto | A. De Sanctis | Operations | DataManagement |  |  | PROPOSAL | 0% | 2025 | 10 | [5 empty] | 5 | 5 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 25% | 21.74% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo revisione | EssilorLuxottica | L. Roberto | P. SINGH |  | DataManagement |  |  | PROPOSAL | 0% | 2025 | 10 | [5 empty] | 6 | 5 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 30% | 21.74% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo revisione | EssilorLuxottica | L. Roberto | L. Roberto | Delivery Projects | PM - Project Governance |  |  | PROPOSAL | 0% | 2025 | 1 | [5 empty] | 1 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo revisione | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | DataManagement |  |  | PROPOSAL | 0% | 2025 | 10 | [5 empty] | 4 | 5 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 20% | 21.74% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo revisione | EssilorLuxottica | L. Roberto | K. Dadaian | Consulting | Analisys |  |  | PROPOSAL | 0% | 2025 | 2 | [6 empty] | 2 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo revisione | EssilorLuxottica | L. Roberto | M. Migliorati | Operations | DataManagement |  |  | PROPOSAL | 0% | 2025 | 8 | [6 empty] | 8 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 34.78% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo AI | EssilorLuxottica | L. Roberto | G. Sironi | Operations |  |  |  | PROPOSAL | 0% | 2025 | 5 | [5 empty] | 5 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo AI | EssilorLuxottica | L. Roberto | M. Gomitoni | Operations |  |  |  | PROPOSAL | 0% | 2025 | 5 | [5 empty] | 5 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo AI | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | DataManagement |  |  | PROPOSAL | 0% | 2025 | 3 | [5 empty] | 3 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 15% | 0% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo AI | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analyst |  |  | PROPOSAL | 0% | 2025 | 5 | [5 empty] | 3 | 2 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 15% | 8.696% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo AI | EssilorLuxottica | L. Roberto | L. Roberto | Delivery Projects | PM - Project Governance |  |  | PROPOSAL | 0% | 2025 | 1 | [5 empty] | 1 | [6 empty] | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | R. Bondi | Operations | FrontEnd | 100 | 7 | ON GOING | 40% | 2025 | [5 empty] | 2 | [7 empty] | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 31/06/2025 | N/A | ABS0008-221 | HR | Evolutive Dashboard Maggio (post golive) | EssilorLuxottica | L. Roberto | M.Vimercati | Operations | Data Management | 6.5 | 0 | ON GOING | 80% | 2025 | 1 |  |  |  | 1 | 1 | [7 empty] | 0% | 0% | 0% | 4.545% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-06-23 | 2025-09-15 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 w4 - myEL integration | EssilorLuxottica | L. Roberto | C. Di Lorenzo | Delivery Projects | Analysis | 65 |  | To Be Start | 0% | 2025 | 3 | [5 empty] | 4 | 3 | 3 | 3 |  |  |  | 0% | 0% | 0% | 0% | 0% | 20% | 13.04% | 25% | 14.29% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-06-23 | 2025-09-15 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 w4 - myEL integration | EssilorLuxottica | L. Roberto | C. Elia | Operations | BackEnd | 65 |  | To Be Start | 0% | 2025 | 3 | [5 empty] | 5 | 4 | 3 | 3 |  |  |  | 0% | 0% | 0% | 0% | 0% | 25% | 17.39% | 25% | 14.29% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-06-23 | 2025-09-15 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 w4 - myEL integration | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 65 |  | To Be Start | 0% | 2025 | 1 | [5 empty] | 3 | 3 | 2 | 1 |  |  |  | 0% | 0% | 0% | 0% | 0% | 15% | 13.04% | 16.67% | 4.762% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-06-23 | 2025-09-15 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 w4 - myEL integration | EssilorLuxottica | L. Roberto | S. Beltrami | Operations | FrontEnd | 65 |  | To Be Start | 0% | 2025 | 3 | [5 empty] | 5 | 9 | 9 | 3 |  |  |  | 0% | 0% | 0% | 0% | 0% | 25% | 39.13% | 75% | 14.29% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-06-23 | 2025-09-15 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 w4 - myEL integration | EssilorLuxottica | L. Roberto | S. Delle Fave | Operations | FrontEnd | 65 |  | To Be Start | 0% | 2025 | 0 | [5 empty] | 1 | 1 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 5% | 4.348% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo AI | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer |  |  | PROPOSAL | 0% | 2025 | 11 | [5 empty] | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 0% | 0% | 0% | 0% | 0% | 5% | 4.348% | 8.333% | 9.524% | 8.696% | 9.524% | 9.091%
CONTRACT | PRJ | Waterfall | 2025 | 2025-06-23 | 2025-06-21 | N/A |  | HR | Flusso Automatico Utenze | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 7 |  | PROPOSAL | 0% | 2025 | 1 | [5 empty] | 0.5 | 0.5 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 2.5% | 2.174% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 |  |  | N/A |  | HR | Tracking HR Tools | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer |  |  | PROPOSAL | 0% | 2025 | [6 empty] | 1 | 1 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 5% | 4.348% | 0% | 0% | 0% | 0% | 0%
PROSPECT | PRJ | Waterfall | 2025 |  |  | N/A | ABS0008-67 | HR | One Org HR - geolocalizzazione puntuale in cartina | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer |  |  | PROPOSAL | 0% | 2025 | [6 empty] | 0.5 |  |  | 2 |  |  |  | 0% | 0% | 0% | 0% | 0% | 2.5% | 0% | 0% | 9.524% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Statutory | EssilorLuxottica | M. Cocchi | M. Cocchi | Consolidated & Tax | PM - Project Governance | 510 |  | ONGOING |  | 2025 | [6 empty] | 4 | 2.625 | 1.375 | 4 | 4.5 | 2.75 | 0.75 | 0% | 0% | 0% | 0% | 0% | 20% | 11.41% | 11.46% | 19.05% | 19.57% | 13.1% | 3.409%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Statutory | EssilorLuxottica | M. Cocchi | G. Campri | Operations | PM - Project Governance | 510 |  | ONGOING |  | 2025 | [6 empty] | 2.25 | 3.875 | 1.75 | 4.75 | 4.375 | 2.25 | 0.75 | 0% | 0% | 0% | 0% | 0% | 11.25% | 16.85% | 14.58% | 22.62% | 19.02% | 10.71% | 3.409%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Statutory | EssilorLuxottica | M. Cocchi | TBD | Operations | PM - Project Governance | 510 |  | ONGOING |  | 2025 | [6 empty] | 2.75 | 5.75 | 2.25 | 7.25 | 6.25 | 3.75 | 2 | 0% | 0% | 0% | 0% | 0% | 13.75% | 25% | 18.75% | 34.52% | 27.17% | 17.86% | 9.091%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Statutory | EssilorLuxottica | M. Cocchi | M. Salcini | Consolidated & Tax | Analisys | 510 |  | ONGOING |  | 2025 | [6 empty] | 19.5 | 11.125 | 5.5 | 14.5 | 13 | 4.375 | 2 | 0% | 0% | 0% | 0% | 0% | 97.5% | 48.37% | 45.83% | 69.05% | 56.52% | 20.83% | 9.091%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Statutory | EssilorLuxottica | M. Cocchi | G. Natili | Operations | Principal Consultant | 510 |  | ONGOING |  | 2025 | [6 empty] | 9 | 11.5 | 4.5 | 11 | 4 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 45% | 50% | 37.5% | 52.38% | 17.39% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Statutory | EssilorLuxottica | M. Cocchi | TBD | Operations | Senior Consultant | 510 |  | ONGOING |  | 2025 | [6 empty] | 11 | 23 | 7 | 22 | 17 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 55% | 100% | 58.33% | 104.8% | 73.91% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Statutory | EssilorLuxottica | M. Cocchi | TBD | Operations | Consultant | 510 |  | ONGOING |  | 2025 | [6 empty] | 11 | 23 | 8 | 22 | 16 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 55% | 100% | 66.67% | 104.8% | 69.57% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Statutory | EssilorLuxottica | M. Cocchi | P. Vernieri | Operations | Consultant | 510 |  | ONGOING |  | 2025 | [6 empty] | 0 | 19 | 16 | 22 | 23 | 5 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 82.61% | 133.3% | 104.8% | 100% | 23.81% | 22.73%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Statutory | EssilorLuxottica | M. Cocchi | A. Parisella | Operations | Consultant | 510 |  | ONGOING |  | 2025 | [6 empty] | 16 | 23 | 11 | 22 | 3 | 0 | 5 | 0% | 0% | 0% | 0% | 0% | 80% | 100% | 91.67% | 104.8% | 13.04% | 0% | 22.73%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Managerial | EssilorLuxottica | M. Cocchi | M. Cocchi | Consolidated & Tax | PM - Project Governance | 277 |  | ONGOING |  | 2025 | [6 empty] | 2.25 | 1.625 | 0.75 | 1.75 | 1.75 | 1.5 | 0.375 | 0% | 0% | 0% | 0% | 0% | 11.25% | 7.065% | 6.25% | 8.333% | 7.609% | 7.143% | 1.705%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Managerial | EssilorLuxottica | M. Cocchi | G. Campri | Operations | PM - Project Governance | 277 |  | ONGOING |  | 2025 | [6 empty] | 1.625 | 2.875 | 1 | 3 | 3.5 | 2.25 | 0.75 | 0% | 0% | 0% | 0% | 0% | 8.125% | 12.5% | 8.333% | 14.29% | 15.22% | 10.71% | 3.409%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Managerial | EssilorLuxottica | M. Cocchi | S. Preziosa | Consolidated & Tax | Team Leader | 277 |  | ONGOING |  | 2025 | [6 empty] | 10 | 10 | 4 | 9 | 9 | 7 | 2 | 0% | 0% | 0% | 0% | 0% | 50% | 43.48% | 33.33% | 42.86% | 39.13% | 33.33% | 9.091%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Managerial | EssilorLuxottica | M. Cocchi | P. Pieroni | Operations | Solution Architect | 277 |  | ONGOING |  | 2025 | [6 empty] | 10 | 9.5 | 4.5 | 8.5 | 9 | 7.5 | 2 | 0% | 0% | 0% | 0% | 0% | 50% | 41.3% | 37.5% | 40.48% | 39.13% | 35.71% | 9.091%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Managerial | EssilorLuxottica | M. Cocchi | TBD | Operations | Senior Consultant | 277 |  | ONGOING |  | 2025 | [6 empty] | 3 | 11.5 | 5.5 | 11.5 | 9 | 9.5 | 0 | 0% | 0% | 0% | 0% | 0% | 15% | 50% | 45.83% | 54.76% | 39.13% | 45.24% | 0%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Managerial | EssilorLuxottica | M. Cocchi | L. Mangilli | Operations | Consultant | 277 |  | ONGOING |  | 2025 | [6 empty] | 11 | 23 | 11 | 22 | 23 | 10 | 0 | 0% | 0% | 0% | 0% | 0% | 55% | 100% | 91.67% | 104.8% | 100% | 47.62% | 0%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - FDMEE | EssilorLuxottica | M. Cocchi | I. Bressan | Operations | TeamLeader | 90 |  | ONGOING |  | 2025 | [6 empty] | 7 | 6 | 5 | 11 | 6 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 35% | 26.09% | 41.67% | 52.38% | 26.09% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - FDMEE | EssilorLuxottica | M. Cocchi | E. Storti | Operations | Senior Consultant | 90 |  | ONGOING |  | 2025 | [6 empty] | 4 | 6 | 0 | 5 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 20% | 26.09% | 0% | 23.81% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - FDMEE | EssilorLuxottica | M. Cocchi | F. Atanasio | Operations | Senior Consultant | 90 |  | ONGOING |  | 2025 | [6 empty] | 6 | 18.5 | 3 | 11 | 1.5 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 30% | 80.43% | 25% | 52.38% | 6.522% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - APEX | EssilorLuxottica | M. Cocchi | F. De Pedis | Operations | TeamLeader | 90 |  | ONGOING |  | 2025 | [6 empty] | 5.5 | 10.5 | 4 | 11 | 4 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 27.5% | 45.65% | 33.33% | 52.38% | 17.39% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - APEX | EssilorLuxottica | M. Cocchi | F. Lombardini | Consolidated & Tax | Senior Consultant | 90 |  | ONGOING |  | 2025 | [6 empty] | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 23.81% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - APEX | EssilorLuxottica | M. Cocchi | TBD | Operations | Consultant | 90 |  | ONGOING |  | 2025 | [6 empty] | 1 | 23 | 6 | 20 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 5% | 100% | 50% | 95.24% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - CMFA STAT | EssilorLuxottica | M. Cocchi | F. De Pedis | Operations | Team Leader | 90 |  | ONGOING |  | 2025 | [6 empty] | 5 | 11 | 4 | 11 | 4 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 25% | 47.83% | 33.33% | 52.38% | 17.39% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - CMFA STAT | EssilorLuxottica | M. Cocchi | F. Lombardini | Consolidated & Tax | Senior Consultant | 90 |  | ONGOING |  | 2025 | [6 empty] | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 23.81% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - CMFA STAT | EssilorLuxottica | M. Cocchi | TBD | Operations | Consultant | 90 |  | ONGOING |  | 2025 | [6 empty] | 0 | 0 | 0 | 8.5 | 1.5 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40.48% | 6.522% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - CMFA STAT | EssilorLuxottica | M. Cocchi | I. Bressan | Operations | Solution Architect | 90 |  | ONGOING |  | 2025 | [6 empty] | 3 | 9.5 | 5 | 11 | 11.5 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 15% | 41.3% | 41.67% | 52.38% | 50% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - PMO | EssilorLuxottica | M. Cocchi | C. Paz | Delivery Projects | PMO - Project Management Officer |  |  | ONGOING |  | 2025 | [11 empty] | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - PMO | EssilorLuxottica | M. Cocchi | M. Vianelli | Delivery Projects | PMO - Project Management Officer |  |  | ONGOING |  | 2025 | [11 empty] | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-06-23 | 2025-06-21 | N/A |  | HR | Flusso Automatico Utenze | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 7 |  | PROPOSAL | 0% | 2025 | 2 | [5 empty] | 1 | 1 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 5% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-06-23 | 2025-06-21 | N/A |  | HR | Flusso Automatico Utenze | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 7 |  | PROPOSAL | 0% | 2025 | 1.5 | [5 empty] | 0.5 | 1 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 2.5% | 4.348% | 0% | 0% | 0% | 0% | 0%
CONTRACT | PRJ | Waterfall | 2025 | 2025-06-23 | 2025-06-21 | N/A |  | HR | Flusso Automatico Utenze | EssilorLuxottica | L. Roberto | M. Toci | Operations | Back End | 7 |  | PROPOSAL | 0% | 2025 | 2 | [6 empty] | 2 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 8.696% | 0% | 0% | 0% | 0% | 0%
[7 empty] | N/A | LOGISTIC | BIP - Caratteri speciali | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Engineering | 200 | 0 | TO START | 0% | 2025 | 40 |  |  |  | 0 | 0 | 7 | 7 | 5 | 7 | 7 | 7 |  | 0% | 0% | 0% | 0% | 0% | 35% | 30.43% | 41.67% | 33.33% | 30.43% | 33.33% | 0%
[7 empty] | N/A | LOGISTIC | BIP - Caratteri speciali | EssilorLuxottica | F. Taita | L. Altobelli | Operations | Data Engineering | 200 | 0 | TO START | 0% | 2025 | 75 |  |  |  |  | 0 | 10 | 15 | 5 | 15 | 15 | 15 |  | 0% | 0% | 0% | 0% | 0% | 50% | 65.22% | 41.67% | 71.43% | 65.22% | 71.43% | 0%
[7 empty] | N/A | LOGISTIC | BIP - Caratteri speciali | EssilorLuxottica | F. Taita | T. Baldi | Operations | Data Engineering | 200 | 0 | TO START | 0% | 2025 | 75 |  |  |  | 0 | 0 | 10 | 15 | 5 | 15 | 15 | 15 |  | 0% | 0% | 0% | 0% | 0% | 50% | 65.22% | 41.67% | 71.43% | 65% | 71.43% | 0%
Note on Q573: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consuntivazione parziale su Jira-chiedere a PM per resoconto ore registrate completo
Note on Q574: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consuntivazione parziale su Jira-chiedere a PM per resoconto ore registrate completo
Note on Q575: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consuntivazione parziale su Jira-chiedere a PM per resoconto ore registrate completo
Note on Q576: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consuntivazione parziale su Jira-chiedere a PM per resoconto ore registrate completo

## Foglio1
YEAR_OF_COMPETENCE | 2025
PROJECT_DESCR | MY CAREER
USER | Somma di gen | Somma di feb | Somma di mar | Somma di apr | Somma di mag | Somma di giu | Somma di lug
A. Brandizzi | 10 | 10 | 15 | 15 | 15 | 15 | 15
A. Lorena | 10 | 10 | 10 |  |  | 10 | 10
A. Pirola | 10 | 15 | 15 | 15 | 10 | 10 | 10
C. Di Lorenzo | 3 | 3 | 4 |  |  | 4 | 4
F. SCOGNAMIGLIO | 0 | 0 | 0 | 15 | 15 | 15 | 15
G. DE FEO | 4 | 3 | 3 | 3 | 3 | 3 | 5
G. Lopez | 15 | 15 | 15 |  |  | 15 | 15
G. Tartaglia | 15 | 15 | 15 |  |  | 15 | 15
M. Toci | 3 | 3 | 3 |  |  | 10 | 10
N. Pescione | 15 | 0 | 0 |  |  | 0 | 0
P. Anzellotti | 6 | 3 | 3 |  |  | 6 | 6
S. Beltrami | 3 | 3 | 3 |  |  | 3 | 3
S. Delle Fave | 3 | 3 | 3 |  |  | 15 | 15
Totale complessivo | 97 | 83 | 89 | 48 | 43 | 121 | 123

## Calendar (hidden)
KEY_CAL | Date | Year | Month_Num | Week | Num_Day_Week | Day_Num | Day_Descr | Month_Descr | Working_Day | Num_Day_Year | Progr_Working_Day
20240101 | 2024-01-01 | 2024 | 1 | 1 | 2 | 1 | lunedì | gennaio | 1 | 1 | 1
20240102 | 2024-01-02 | 2024 | 1 | 1 | 3 | 2 | martedì | gennaio | 1 | 2 | 2
20240103 | 2024-01-03 | 2024 | 1 | 1 | 4 | 3 | mercoledì | gennaio | 1 | 3 | 3
20240104 | 2024-01-04 | 2024 | 1 | 1 | 5 | 4 | giovedì | gennaio | 1 | 4 | 4
20240105 | 2024-01-05 | 2024 | 1 | 1 | 6 | 5 | venerdì | gennaio | 1 | 5 | 5
20240106 | 2024-01-06 | 2024 | 1 | 1 | 7 | 6 | sabato | gennaio | 0 | 6 | 5
20240107 | 2024-01-07 | 2024 | 1 | 2 | 1 | 7 | domenica | gennaio | 0 | 7 | 5
20240108 | 2024-01-08 | 2024 | 1 | 2 | 2 | 8 | lunedì | gennaio | 1 | 8 | 6
20240109 | 2024-01-09 | 2024 | 1 | 2 | 3 | 9 | martedì | gennaio | 1 | 9 | 7
20240110 | 2024-01-10 | 2024 | 1 | 2 | 4 | 10 | mercoledì | gennaio | 1 | 10 | 8
20240111 | 2024-01-11 | 2024 | 1 | 2 | 5 | 11 | giovedì | gennaio | 1 | 11 | 9
20240112 | 2024-01-12 | 2024 | 1 | 2 | 6 | 12 | venerdì | gennaio | 1 | 12 | 10
20240113 | 2024-01-13 | 2024 | 1 | 2 | 7 | 13 | sabato | gennaio | 0 | 13 | 10
20240114 | 2024-01-14 | 2024 | 1 | 3 | 1 | 14 | domenica | gennaio | 0 | 14 | 10
20240115 | 2024-01-15 | 2024 | 1 | 3 | 2 | 15 | lunedì | gennaio | 1 | 15 | 11
20240116 | 2024-01-16 | 2024 | 1 | 3 | 3 | 16 | martedì | gennaio | 1 | 16 | 12
20240117 | 2024-01-17 | 2024 | 1 | 3 | 4 | 17 | mercoledì | gennaio | 1 | 17 | 13
20240118 | 2024-01-18 | 2024 | 1 | 3 | 5 | 18 | giovedì | gennaio | 1 | 18 | 14
20240119 | 2024-01-19 | 2024 | 1 | 3 | 6 | 19 | venerdì | gennaio | 1 | 19 | 15
20240120 | 2024-01-20 | 2024 | 1 | 3 | 7 | 20 | sabato | gennaio | 0 | 20 | 15
20240121 | 2024-01-21 | 2024 | 1 | 4 | 1 | 21 | domenica | gennaio | 0 | 21 | 15
20240122 | 2024-01-22 | 2024 | 1 | 4 | 2 | 22 | lunedì | gennaio | 1 | 22 | 16
20240123 | 2024-01-23 | 2024 | 1 | 4 | 3 | 23 | martedì | gennaio | 1 | 23 | 17
20240124 | 2024-01-24 | 2024 | 1 | 4 | 4 | 24 | mercoledì | gennaio | 1 | 24 | 18
20240125 | 2024-01-25 | 2024 | 1 | 4 | 5 | 25 | giovedì | gennaio | 1 | 25 | 19
20240126 | 2024-01-26 | 2024 | 1 | 4 | 6 | 26 | venerdì | gennaio | 1 | 26 | 20
20240127 | 2024-01-27 | 2024 | 1 | 4 | 7 | 27 | sabato | gennaio | 0 | 27 | 20
20240128 | 2024-01-28 | 2024 | 1 | 5 | 1 | 28 | domenica | gennaio | 0 | 28 | 20
20240129 | 2024-01-29 | 2024 | 1 | 5 | 2 | 29 | lunedì | gennaio | 1 | 29 | 21
20240130 | 2024-01-30 | 2024 | 1 | 5 | 3 | 30 | martedì | gennaio | 1 | 30 | 22
20240131 | 2024-01-31 | 2024 | 1 | 5 | 4 | 31 | mercoledì | gennaio | 1 | 31 | 23
20240201 | 2024-02-01 | 2024 | 2 | 5 | 5 | 1 | giovedì | febbraio | 1 | 32 | 24
20240202 | 2024-02-02 | 2024 | 2 | 5 | 6 | 2 | venerdì | febbraio | 1 | 33 | 25
20240203 | 2024-02-03 | 2024 | 2 | 5 | 7 | 3 | sabato | febbraio | 0 | 34 | 25
20240204 | 2024-02-04 | 2024 | 2 | 6 | 1 | 4 | domenica | febbraio | 0 | 35 | 25
20240205 | 2024-02-05 | 2024 | 2 | 6 | 2 | 5 | lunedì | febbraio | 1 | 36 | 26
20240206 | 2024-02-06 | 2024 | 2 | 6 | 3 | 6 | martedì | febbraio | 1 | 37 | 27
20240207 | 2024-02-07 | 2024 | 2 | 6 | 4 | 7 | mercoledì | febbraio | 1 | 38 | 28
20240208 | 2024-02-08 | 2024 | 2 | 6 | 5 | 8 | giovedì | febbraio | 1 | 39 | 29
20240209 | 2024-02-09 | 2024 | 2 | 6 | 6 | 9 | venerdì | febbraio | 1 | 40 | 30
20240210 | 2024-02-10 | 2024 | 2 | 6 | 7 | 10 | sabato | febbraio | 0 | 41 | 30
20240211 | 2024-02-11 | 2024 | 2 | 7 | 1 | 11 | domenica | febbraio | 0 | 42 | 30
20240212 | 2024-02-12 | 2024 | 2 | 7 | 2 | 12 | lunedì | febbraio | 1 | 43 | 31
20240213 | 2024-02-13 | 2024 | 2 | 7 | 3 | 13 | martedì | febbraio | 1 | 44 | 32
20240214 | 2024-02-14 | 2024 | 2 | 7 | 4 | 14 | mercoledì | febbraio | 1 | 45 | 33
20240215 | 2024-02-15 | 2024 | 2 | 7 | 5 | 15 | giovedì | febbraio | 1 | 46 | 34
20240216 | 2024-02-16 | 2024 | 2 | 7 | 6 | 16 | venerdì | febbraio | 1 | 47 | 35
20240217 | 2024-02-17 | 2024 | 2 | 7 | 7 | 17 | sabato | febbraio | 0 | 48 | 35
20240218 | 2024-02-18 | 2024 | 2 | 8 | 1 | 18 | domenica | febbraio | 0 | 49 | 35
20240219 | 2024-02-19 | 2024 | 2 | 8 | 2 | 19 | lunedì | febbraio | 1 | 50 | 36
20240220 | 2024-02-20 | 2024 | 2 | 8 | 3 | 20 | martedì | febbraio | 1 | 51 | 37
20240221 | 2024-02-21 | 2024 | 2 | 8 | 4 | 21 | mercoledì | febbraio | 1 | 52 | 38
20240222 | 2024-02-22 | 2024 | 2 | 8 | 5 | 22 | giovedì | febbraio | 1 | 53 | 39
20240223 | 2024-02-23 | 2024 | 2 | 8 | 6 | 23 | venerdì | febbraio | 1 | 54 | 40
20240224 | 2024-02-24 | 2024 | 2 | 8 | 7 | 24 | sabato | febbraio | 0 | 55 | 40
20240225 | 2024-02-25 | 2024 | 2 | 9 | 1 | 25 | domenica | febbraio | 0 | 56 | 40
20240226 | 2024-02-26 | 2024 | 2 | 9 | 2 | 26 | lunedì | febbraio | 1 | 57 | 41
20240227 | 2024-02-27 | 2024 | 2 | 9 | 3 | 27 | martedì | febbraio | 1 | 58 | 42
20240228 | 2024-02-28 | 2024 | 2 | 9 | 4 | 28 | mercoledì | febbraio | 1 | 59 | 43
20240229 | 2024-02-29 | 2024 | 2 | 9 | 5 | 29 | giovedì | febbraio | 1 | 60 | 44
20240301 | 2024-03-01 | 2024 | 3 | 9 | 6 | 1 | venerdì | marzo | 1 | 61 | 45
20240302 | 2024-03-02 | 2024 | 3 | 9 | 7 | 2 | sabato | marzo | 0 | 62 | 45
20240303 | 2024-03-03 | 2024 | 3 | 10 | 1 | 3 | domenica | marzo | 0 | 63 | 45
20240304 | 2024-03-04 | 2024 | 3 | 10 | 2 | 4 | lunedì | marzo | 1 | 64 | 46
20240305 | 2024-03-05 | 2024 | 3 | 10 | 3 | 5 | martedì | marzo | 1 | 65 | 47
20240306 | 2024-03-06 | 2024 | 3 | 10 | 4 | 6 | mercoledì | marzo | 1 | 66 | 48
20240307 | 2024-03-07 | 2024 | 3 | 10 | 5 | 7 | giovedì | marzo | 1 | 67 | 49
20240308 | 2024-03-08 | 2024 | 3 | 10 | 6 | 8 | venerdì | marzo | 1 | 68 | 50
20240309 | 2024-03-09 | 2024 | 3 | 10 | 7 | 9 | sabato | marzo | 0 | 69 | 50
20240310 | 2024-03-10 | 2024 | 3 | 11 | 1 | 10 | domenica | marzo | 0 | 70 | 50
20240311 | 2024-03-11 | 2024 | 3 | 11 | 2 | 11 | lunedì | marzo | 1 | 71 | 51
20240312 | 2024-03-12 | 2024 | 3 | 11 | 3 | 12 | martedì | marzo | 1 | 72 | 52
20240313 | 2024-03-13 | 2024 | 3 | 11 | 4 | 13 | mercoledì | marzo | 1 | 73 | 53
20240314 | 2024-03-14 | 2024 | 3 | 11 | 5 | 14 | giovedì | marzo | 1 | 74 | 54
20240315 | 2024-03-15 | 2024 | 3 | 11 | 6 | 15 | venerdì | marzo | 1 | 75 | 55
20240316 | 2024-03-16 | 2024 | 3 | 11 | 7 | 16 | sabato | marzo | 0 | 76 | 55
20240317 | 2024-03-17 | 2024 | 3 | 12 | 1 | 17 | domenica | marzo | 0 | 77 | 55
20240318 | 2024-03-18 | 2024 | 3 | 12 | 2 | 18 | lunedì | marzo | 1 | 78 | 56
20240319 | 2024-03-19 | 2024 | 3 | 12 | 3 | 19 | martedì | marzo | 1 | 79 | 57
20240320 | 2024-03-20 | 2024 | 3 | 12 | 4 | 20 | mercoledì | marzo | 1 | 80 | 58
20240321 | 2024-03-21 | 2024 | 3 | 12 | 5 | 21 | giovedì | marzo | 1 | 81 | 59
20240322 | 2024-03-22 | 2024 | 3 | 12 | 6 | 22 | venerdì | marzo | 1 | 82 | 60
20240323 | 2024-03-23 | 2024 | 3 | 12 | 7 | 23 | sabato | marzo | 0 | 83 | 60
20240324 | 2024-03-24 | 2024 | 3 | 13 | 1 | 24 | domenica | marzo | 0 | 84 | 60
20240325 | 2024-03-25 | 2024 | 3 | 13 | 2 | 25 | lunedì | marzo | 1 | 85 | 61
20240326 | 2024-03-26 | 2024 | 3 | 13 | 3 | 26 | martedì | marzo | 1 | 86 | 62
20240327 | 2024-03-27 | 2024 | 3 | 13 | 4 | 27 | mercoledì | marzo | 1 | 87 | 63
20240328 | 2024-03-28 | 2024 | 3 | 13 | 5 | 28 | giovedì | marzo | 1 | 88 | 64
20240329 | 2024-03-29 | 2024 | 3 | 13 | 6 | 29 | venerdì | marzo | 1 | 89 | 65
20240330 | 2024-03-30 | 2024 | 3 | 13 | 7 | 30 | sabato | marzo | 0 | 90 | 65
20240331 | 2024-03-31 | 2024 | 3 | 14 | 1 | 31 | domenica | marzo | 0 | 91 | 65
20240401 | 2024-04-01 | 2024 | 4 | 14 | 2 | 1 | lunedì | aprile | 1 | 92 | 66
20240402 | 2024-04-02 | 2024 | 4 | 14 | 3 | 2 | martedì | aprile | 1 | 93 | 67
20240403 | 2024-04-03 | 2024 | 4 | 14 | 4 | 3 | mercoledì | aprile | 1 | 94 | 68
20240404 | 2024-04-04 | 2024 | 4 | 14 | 5 | 4 | giovedì | aprile | 1 | 95 | 69
20240405 | 2024-04-05 | 2024 | 4 | 14 | 6 | 5 | venerdì | aprile | 1 | 96 | 70
20240406 | 2024-04-06 | 2024 | 4 | 14 | 7 | 6 | sabato | aprile | 0 | 97 | 70
20240407 | 2024-04-07 | 2024 | 4 | 15 | 1 | 7 | domenica | aprile | 0 | 98 | 70
20240408 | 2024-04-08 | 2024 | 4 | 15 | 2 | 8 | lunedì | aprile | 1 | 99 | 71
20240409 | 2024-04-09 | 2024 | 4 | 15 | 3 | 9 | martedì | aprile | 1 | 100 | 72
20240410 | 2024-04-10 | 2024 | 4 | 15 | 4 | 10 | mercoledì | aprile | 1 | 101 | 73
20240411 | 2024-04-11 | 2024 | 4 | 15 | 5 | 11 | giovedì | aprile | 1 | 102 | 74
20240412 | 2024-04-12 | 2024 | 4 | 15 | 6 | 12 | venerdì | aprile | 1 | 103 | 75
20240413 | 2024-04-13 | 2024 | 4 | 15 | 7 | 13 | sabato | aprile | 0 | 104 | 75
20240414 | 2024-04-14 | 2024 | 4 | 16 | 1 | 14 | domenica | aprile | 0 | 105 | 75
20240415 | 2024-04-15 | 2024 | 4 | 16 | 2 | 15 | lunedì | aprile | 1 | 106 | 76
20240416 | 2024-04-16 | 2024 | 4 | 16 | 3 | 16 | martedì | aprile | 1 | 107 | 77
20240417 | 2024-04-17 | 2024 | 4 | 16 | 4 | 17 | mercoledì | aprile | 1 | 108 | 78
20240418 | 2024-04-18 | 2024 | 4 | 16 | 5 | 18 | giovedì | aprile | 1 | 109 | 79
20240419 | 2024-04-19 | 2024 | 4 | 16 | 6 | 19 | venerdì | aprile | 1 | 110 | 80
20240420 | 2024-04-20 | 2024 | 4 | 16 | 7 | 20 | sabato | aprile | 0 | 111 | 80
20240421 | 2024-04-21 | 2024 | 4 | 17 | 1 | 21 | domenica | aprile | 0 | 112 | 80
20240422 | 2024-04-22 | 2024 | 4 | 17 | 2 | 22 | lunedì | aprile | 1 | 113 | 81
20240423 | 2024-04-23 | 2024 | 4 | 17 | 3 | 23 | martedì | aprile | 1 | 114 | 82
20240424 | 2024-04-24 | 2024 | 4 | 17 | 4 | 24 | mercoledì | aprile | 1 | 115 | 83
20240425 | 2024-04-25 | 2024 | 4 | 17 | 5 | 25 | giovedì | aprile | 1 | 116 | 84
20240426 | 2024-04-26 | 2024 | 4 | 17 | 6 | 26 | venerdì | aprile | 1 | 117 | 85
20240427 | 2024-04-27 | 2024 | 4 | 17 | 7 | 27 | sabato | aprile | 0 | 118 | 85
20240428 | 2024-04-28 | 2024 | 4 | 18 | 1 | 28 | domenica | aprile | 0 | 119 | 85
20240429 | 2024-04-29 | 2024 | 4 | 18 | 2 | 29 | lunedì | aprile | 1 | 120 | 86
20240430 | 2024-04-30 | 2024 | 4 | 18 | 3 | 30 | martedì | aprile | 1 | 121 | 87
20240501 | 2024-05-01 | 2024 | 5 | 18 | 4 | 1 | mercoledì | maggio | 1 | 122 | 88
20240502 | 2024-05-02 | 2024 | 5 | 18 | 5 | 2 | giovedì | maggio | 1 | 123 | 89
20240503 | 2024-05-03 | 2024 | 5 | 18 | 6 | 3 | venerdì | maggio | 1 | 124 | 90
20240504 | 2024-05-04 | 2024 | 5 | 18 | 7 | 4 | sabato | maggio | 0 | 125 | 90
20240505 | 2024-05-05 | 2024 | 5 | 19 | 1 | 5 | domenica | maggio | 0 | 126 | 90
20240506 | 2024-05-06 | 2024 | 5 | 19 | 2 | 6 | lunedì | maggio | 1 | 127 | 91
20240507 | 2024-05-07 | 2024 | 5 | 19 | 3 | 7 | martedì | maggio | 1 | 128 | 92
20240508 | 2024-05-08 | 2024 | 5 | 19 | 4 | 8 | mercoledì | maggio | 1 | 129 | 93
20240509 | 2024-05-09 | 2024 | 5 | 19 | 5 | 9 | giovedì | maggio | 1 | 130 | 94
20240510 | 2024-05-10 | 2024 | 5 | 19 | 6 | 10 | venerdì | maggio | 1 | 131 | 95
20240511 | 2024-05-11 | 2024 | 5 | 19 | 7 | 11 | sabato | maggio | 0 | 132 | 95
20240512 | 2024-05-12 | 2024 | 5 | 20 | 1 | 12 | domenica | maggio | 0 | 133 | 95
20240513 | 2024-05-13 | 2024 | 5 | 20 | 2 | 13 | lunedì | maggio | 1 | 134 | 96
20240514 | 2024-05-14 | 2024 | 5 | 20 | 3 | 14 | martedì | maggio | 1 | 135 | 97
20240515 | 2024-05-15 | 2024 | 5 | 20 | 4 | 15 | mercoledì | maggio | 1 | 136 | 98
20240516 | 2024-05-16 | 2024 | 5 | 20 | 5 | 16 | giovedì | maggio | 1 | 137 | 99
20240517 | 2024-05-17 | 2024 | 5 | 20 | 6 | 17 | venerdì | maggio | 1 | 138 | 100
20240518 | 2024-05-18 | 2024 | 5 | 20 | 7 | 18 | sabato | maggio | 0 | 139 | 100
20240519 | 2024-05-19 | 2024 | 5 | 21 | 1 | 19 | domenica | maggio | 0 | 140 | 100
20240520 | 2024-05-20 | 2024 | 5 | 21 | 2 | 20 | lunedì | maggio | 1 | 141 | 101
20240521 | 2024-05-21 | 2024 | 5 | 21 | 3 | 21 | martedì | maggio | 1 | 142 | 102
20240522 | 2024-05-22 | 2024 | 5 | 21 | 4 | 22 | mercoledì | maggio | 1 | 143 | 103
20240523 | 2024-05-23 | 2024 | 5 | 21 | 5 | 23 | giovedì | maggio | 1 | 144 | 104
20240524 | 2024-05-24 | 2024 | 5 | 21 | 6 | 24 | venerdì | maggio | 1 | 145 | 105
20240525 | 2024-05-25 | 2024 | 5 | 21 | 7 | 25 | sabato | maggio | 0 | 146 | 105
20240526 | 2024-05-26 | 2024 | 5 | 22 | 1 | 26 | domenica | maggio | 0 | 147 | 105
20240527 | 2024-05-27 | 2024 | 5 | 22 | 2 | 27 | lunedì | maggio | 1 | 148 | 106
20240528 | 2024-05-28 | 2024 | 5 | 22 | 3 | 28 | martedì | maggio | 1 | 149 | 107
20240529 | 2024-05-29 | 2024 | 5 | 22 | 4 | 29 | mercoledì | maggio | 1 | 150 | 108
20240530 | 2024-05-30 | 2024 | 5 | 22 | 5 | 30 | giovedì | maggio | 1 | 151 | 109
20240531 | 2024-05-31 | 2024 | 5 | 22 | 6 | 31 | venerdì | maggio | 1 | 152 | 110
20240601 | 2024-06-01 | 2024 | 6 | 22 | 7 | 1 | sabato | giugno | 0 | 153 | 110
20240602 | 2024-06-02 | 2024 | 6 | 23 | 1 | 2 | domenica | giugno | 0 | 154 | 110
20240603 | 2024-06-03 | 2024 | 6 | 23 | 2 | 3 | lunedì | giugno | 1 | 155 | 111
20240604 | 2024-06-04 | 2024 | 6 | 23 | 3 | 4 | martedì | giugno | 1 | 156 | 112
20240605 | 2024-06-05 | 2024 | 6 | 23 | 4 | 5 | mercoledì | giugno | 1 | 157 | 113
20240606 | 2024-06-06 | 2024 | 6 | 23 | 5 | 6 | giovedì | giugno | 1 | 158 | 114
20240607 | 2024-06-07 | 2024 | 6 | 23 | 6 | 7 | venerdì | giugno | 1 | 159 | 115
20240608 | 2024-06-08 | 2024 | 6 | 23 | 7 | 8 | sabato | giugno | 0 | 160 | 115
20240609 | 2024-06-09 | 2024 | 6 | 24 | 1 | 9 | domenica | giugno | 0 | 161 | 115
20240610 | 2024-06-10 | 2024 | 6 | 24 | 2 | 10 | lunedì | giugno | 1 | 162 | 116
20240611 | 2024-06-11 | 2024 | 6 | 24 | 3 | 11 | martedì | giugno | 1 | 163 | 117
20240612 | 2024-06-12 | 2024 | 6 | 24 | 4 | 12 | mercoledì | giugno | 1 | 164 | 118
20240613 | 2024-06-13 | 2024 | 6 | 24 | 5 | 13 | giovedì | giugno | 1 | 165 | 119
20240614 | 2024-06-14 | 2024 | 6 | 24 | 6 | 14 | venerdì | giugno | 1 | 166 | 120
20240615 | 2024-06-15 | 2024 | 6 | 24 | 7 | 15 | sabato | giugno | 0 | 167 | 120
20240616 | 2024-06-16 | 2024 | 6 | 25 | 1 | 16 | domenica | giugno | 0 | 168 | 120
20240617 | 2024-06-17 | 2024 | 6 | 25 | 2 | 17 | lunedì | giugno | 1 | 169 | 121
20240618 | 2024-06-18 | 2024 | 6 | 25 | 3 | 18 | martedì | giugno | 1 | 170 | 122
20240619 | 2024-06-19 | 2024 | 6 | 25 | 4 | 19 | mercoledì | giugno | 1 | 171 | 123
20240620 | 2024-06-20 | 2024 | 6 | 25 | 5 | 20 | giovedì | giugno | 1 | 172 | 124
20240621 | 2024-06-21 | 2024 | 6 | 25 | 6 | 21 | venerdì | giugno | 1 | 173 | 125
20240622 | 2024-06-22 | 2024 | 6 | 25 | 7 | 22 | sabato | giugno | 0 | 174 | 125
20240623 | 2024-06-23 | 2024 | 6 | 26 | 1 | 23 | domenica | giugno | 0 | 175 | 125
20240624 | 2024-06-24 | 2024 | 6 | 26 | 2 | 24 | lunedì | giugno | 1 | 176 | 126
20240625 | 2024-06-25 | 2024 | 6 | 26 | 3 | 25 | martedì | giugno | 1 | 177 | 127
20240626 | 2024-06-26 | 2024 | 6 | 26 | 4 | 26 | mercoledì | giugno | 1 | 178 | 128
20240627 | 2024-06-27 | 2024 | 6 | 26 | 5 | 27 | giovedì | giugno | 1 | 179 | 129
20240628 | 2024-06-28 | 2024 | 6 | 26 | 6 | 28 | venerdì | giugno | 1 | 180 | 130
20240629 | 2024-06-29 | 2024 | 6 | 26 | 7 | 29 | sabato | giugno | 0 | 181 | 130
20240630 | 2024-06-30 | 2024 | 6 | 27 | 1 | 30 | domenica | giugno | 0 | 182 | 130
20240701 | 2024-07-01 | 2024 | 7 | 27 | 2 | 1 | lunedì | luglio | 1 | 183 | 131
20240702 | 2024-07-02 | 2024 | 7 | 27 | 3 | 2 | martedì | luglio | 1 | 184 | 132
20240703 | 2024-07-03 | 2024 | 7 | 27 | 4 | 3 | mercoledì | luglio | 1 | 185 | 133
20240704 | 2024-07-04 | 2024 | 7 | 27 | 5 | 4 | giovedì | luglio | 1 | 186 | 134
20240705 | 2024-07-05 | 2024 | 7 | 27 | 6 | 5 | venerdì | luglio | 1 | 187 | 135
20240706 | 2024-07-06 | 2024 | 7 | 27 | 7 | 6 | sabato | luglio | 0 | 188 | 135
20240707 | 2024-07-07 | 2024 | 7 | 28 | 1 | 7 | domenica | luglio | 0 | 189 | 135
20240708 | 2024-07-08 | 2024 | 7 | 28 | 2 | 8 | lunedì | luglio | 1 | 190 | 136
20240709 | 2024-07-09 | 2024 | 7 | 28 | 3 | 9 | martedì | luglio | 1 | 191 | 137
20240710 | 2024-07-10 | 2024 | 7 | 28 | 4 | 10 | mercoledì | luglio | 1 | 192 | 138
20240711 | 2024-07-11 | 2024 | 7 | 28 | 5 | 11 | giovedì | luglio | 1 | 193 | 139
20240712 | 2024-07-12 | 2024 | 7 | 28 | 6 | 12 | venerdì | luglio | 1 | 194 | 140
20240713 | 2024-07-13 | 2024 | 7 | 28 | 7 | 13 | sabato | luglio | 0 | 195 | 140
20240714 | 2024-07-14 | 2024 | 7 | 29 | 1 | 14 | domenica | luglio | 0 | 196 | 140
20240715 | 2024-07-15 | 2024 | 7 | 29 | 2 | 15 | lunedì | luglio | 1 | 197 | 141
20240716 | 2024-07-16 | 2024 | 7 | 29 | 3 | 16 | martedì | luglio | 1 | 198 | 142
20240717 | 2024-07-17 | 2024 | 7 | 29 | 4 | 17 | mercoledì | luglio | 1 | 199 | 143
20240718 | 2024-07-18 | 2024 | 7 | 29 | 5 | 18 | giovedì | luglio | 1 | 200 | 144
20240719 | 2024-07-19 | 2024 | 7 | 29 | 6 | 19 | venerdì | luglio | 1 | 201 | 145
20240720 | 2024-07-20 | 2024 | 7 | 29 | 7 | 20 | sabato | luglio | 0 | 202 | 145
20240721 | 2024-07-21 | 2024 | 7 | 30 | 1 | 21 | domenica | luglio | 0 | 203 | 145
20240722 | 2024-07-22 | 2024 | 7 | 30 | 2 | 22 | lunedì | luglio | 1 | 204 | 146
20240723 | 2024-07-23 | 2024 | 7 | 30 | 3 | 23 | martedì | luglio | 1 | 205 | 147
20240724 | 2024-07-24 | 2024 | 7 | 30 | 4 | 24 | mercoledì | luglio | 1 | 206 | 148
20240725 | 2024-07-25 | 2024 | 7 | 30 | 5 | 25 | giovedì | luglio | 1 | 207 | 149
20240726 | 2024-07-26 | 2024 | 7 | 30 | 6 | 26 | venerdì | luglio | 1 | 208 | 150
20240727 | 2024-07-27 | 2024 | 7 | 30 | 7 | 27 | sabato | luglio | 0 | 209 | 150
20240728 | 2024-07-28 | 2024 | 7 | 31 | 1 | 28 | domenica | luglio | 0 | 210 | 150
20240729 | 2024-07-29 | 2024 | 7 | 31 | 2 | 29 | lunedì | luglio | 1 | 211 | 151
20240730 | 2024-07-30 | 2024 | 7 | 31 | 3 | 30 | martedì | luglio | 1 | 212 | 152
20240731 | 2024-07-31 | 2024 | 7 | 31 | 4 | 31 | mercoledì | luglio | 1 | 213 | 153
20240801 | 2024-08-01 | 2024 | 8 | 31 | 5 | 1 | giovedì | agosto | 1 | 214 | 154
20240802 | 2024-08-02 | 2024 | 8 | 31 | 6 | 2 | venerdì | agosto | 1 | 215 | 155
20240803 | 2024-08-03 | 2024 | 8 | 31 | 7 | 3 | sabato | agosto | 0 | 216 | 155
20240804 | 2024-08-04 | 2024 | 8 | 32 | 1 | 4 | domenica | agosto | 0 | 217 | 155
20240805 | 2024-08-05 | 2024 | 8 | 32 | 2 | 5 | lunedì | agosto | 1 | 218 | 156
20240806 | 2024-08-06 | 2024 | 8 | 32 | 3 | 6 | martedì | agosto | 1 | 219 | 157
20240807 | 2024-08-07 | 2024 | 8 | 32 | 4 | 7 | mercoledì | agosto | 1 | 220 | 158
20240808 | 2024-08-08 | 2024 | 8 | 32 | 5 | 8 | giovedì | agosto | 1 | 221 | 159
20240809 | 2024-08-09 | 2024 | 8 | 32 | 6 | 9 | venerdì | agosto | 1 | 222 | 160
20240810 | 2024-08-10 | 2024 | 8 | 32 | 7 | 10 | sabato | agosto | 0 | 223 | 160
20240811 | 2024-08-11 | 2024 | 8 | 33 | 1 | 11 | domenica | agosto | 0 | 224 | 160
20240812 | 2024-08-12 | 2024 | 8 | 33 | 2 | 12 | lunedì | agosto | 0 | 225 | 160
20240813 | 2024-08-13 | 2024 | 8 | 33 | 3 | 13 | martedì | agosto | 0 | 226 | 160
20240814 | 2024-08-14 | 2024 | 8 | 33 | 4 | 14 | mercoledì | agosto | 0 | 227 | 160
20240815 | 2024-08-15 | 2024 | 8 | 33 | 5 | 15 | giovedì | agosto | 0 | 228 | 160
20240816 | 2024-08-16 | 2024 | 8 | 33 | 6 | 16 | venerdì | agosto | 0 | 229 | 160
20240817 | 2024-08-17 | 2024 | 8 | 33 | 7 | 17 | sabato | agosto | 0 | 230 | 160
20240818 | 2024-08-18 | 2024 | 8 | 34 | 1 | 18 | domenica | agosto | 0 | 231 | 160
20240819 | 2024-08-19 | 2024 | 8 | 34 | 2 | 19 | lunedì | agosto | 0 | 232 | 160
20240820 | 2024-08-20 | 2024 | 8 | 34 | 3 | 20 | martedì | agosto | 0 | 233 | 160
20240821 | 2024-08-21 | 2024 | 8 | 34 | 4 | 21 | mercoledì | agosto | 0 | 234 | 160
20240822 | 2024-08-22 | 2024 | 8 | 34 | 5 | 22 | giovedì | agosto | 0 | 235 | 160
20240823 | 2024-08-23 | 2024 | 8 | 34 | 6 | 23 | venerdì | agosto | 0 | 236 | 160
20240824 | 2024-08-24 | 2024 | 8 | 34 | 7 | 24 | sabato | agosto | 0 | 237 | 160
20240825 | 2024-08-25 | 2024 | 8 | 35 | 1 | 25 | domenica | agosto | 0 | 238 | 160
20240826 | 2024-08-26 | 2024 | 8 | 35 | 2 | 26 | lunedì | agosto | 1 | 239 | 161
20240827 | 2024-08-27 | 2024 | 8 | 35 | 3 | 27 | martedì | agosto | 1 | 240 | 162
20240828 | 2024-08-28 | 2024 | 8 | 35 | 4 | 28 | mercoledì | agosto | 1 | 241 | 163
20240829 | 2024-08-29 | 2024 | 8 | 35 | 5 | 29 | giovedì | agosto | 1 | 242 | 164
20240830 | 2024-08-30 | 2024 | 8 | 35 | 6 | 30 | venerdì | agosto | 1 | 243 | 165
20240831 | 2024-08-31 | 2024 | 8 | 35 | 7 | 31 | sabato | agosto | 0 | 244 | 165
20240901 | 2024-09-01 | 2024 | 9 | 36 | 1 | 1 | domenica | settembre | 0 | 245 | 165
20240902 | 2024-09-02 | 2024 | 9 | 36 | 2 | 2 | lunedì | settembre | 1 | 246 | 166
20240903 | 2024-09-03 | 2024 | 9 | 36 | 3 | 3 | martedì | settembre | 1 | 247 | 167
20240904 | 2024-09-04 | 2024 | 9 | 36 | 4 | 4 | mercoledì | settembre | 1 | 248 | 168
20240905 | 2024-09-05 | 2024 | 9 | 36 | 5 | 5 | giovedì | settembre | 1 | 249 | 169
20240906 | 2024-09-06 | 2024 | 9 | 36 | 6 | 6 | venerdì | settembre | 1 | 250 | 170
20240907 | 2024-09-07 | 2024 | 9 | 36 | 7 | 7 | sabato | settembre | 0 | 251 | 170
20240908 | 2024-09-08 | 2024 | 9 | 37 | 1 | 8 | domenica | settembre | 0 | 252 | 170
20240909 | 2024-09-09 | 2024 | 9 | 37 | 2 | 9 | lunedì | settembre | 1 | 253 | 171
20240910 | 2024-09-10 | 2024 | 9 | 37 | 3 | 10 | martedì | settembre | 1 | 254 | 172
20240911 | 2024-09-11 | 2024 | 9 | 37 | 4 | 11 | mercoledì | settembre | 1 | 255 | 173
20240912 | 2024-09-12 | 2024 | 9 | 37 | 5 | 12 | giovedì | settembre | 1 | 256 | 174
20240913 | 2024-09-13 | 2024 | 9 | 37 | 6 | 13 | venerdì | settembre | 1 | 257 | 175
20240914 | 2024-09-14 | 2024 | 9 | 37 | 7 | 14 | sabato | settembre | 0 | 258 | 175
20240915 | 2024-09-15 | 2024 | 9 | 38 | 1 | 15 | domenica | settembre | 0 | 259 | 175
20240916 | 2024-09-16 | 2024 | 9 | 38 | 2 | 16 | lunedì | settembre | 1 | 260 | 176
20240917 | 2024-09-17 | 2024 | 9 | 38 | 3 | 17 | martedì | settembre | 1 | 261 | 177
20240918 | 2024-09-18 | 2024 | 9 | 38 | 4 | 18 | mercoledì | settembre | 1 | 262 | 178
20240919 | 2024-09-19 | 2024 | 9 | 38 | 5 | 19 | giovedì | settembre | 1 | 263 | 179
20240920 | 2024-09-20 | 2024 | 9 | 38 | 6 | 20 | venerdì | settembre | 1 | 264 | 180
20240921 | 2024-09-21 | 2024 | 9 | 38 | 7 | 21 | sabato | settembre | 0 | 265 | 180
20240922 | 2024-09-22 | 2024 | 9 | 39 | 1 | 22 | domenica | settembre | 0 | 266 | 180
20240923 | 2024-09-23 | 2024 | 9 | 39 | 2 | 23 | lunedì | settembre | 1 | 267 | 181
20240924 | 2024-09-24 | 2024 | 9 | 39 | 3 | 24 | martedì | settembre | 1 | 268 | 182
20240925 | 2024-09-25 | 2024 | 9 | 39 | 4 | 25 | mercoledì | settembre | 1 | 269 | 183
20240926 | 2024-09-26 | 2024 | 9 | 39 | 5 | 26 | giovedì | settembre | 1 | 270 | 184
20240927 | 2024-09-27 | 2024 | 9 | 39 | 6 | 27 | venerdì | settembre | 1 | 271 | 185
20240928 | 2024-09-28 | 2024 | 9 | 39 | 7 | 28 | sabato | settembre | 0 | 272 | 185
20240929 | 2024-09-29 | 2024 | 9 | 40 | 1 | 29 | domenica | settembre | 0 | 273 | 185
20240930 | 2024-09-30 | 2024 | 9 | 40 | 2 | 30 | lunedì | settembre | 1 | 274 | 186
20241001 | 2024-10-01 | 2024 | 10 | 40 | 3 | 1 | martedì | ottobre | 1 | 275 | 187
20241002 | 2024-10-02 | 2024 | 10 | 40 | 4 | 2 | mercoledì | ottobre | 1 | 276 | 188
20241003 | 2024-10-03 | 2024 | 10 | 40 | 5 | 3 | giovedì | ottobre | 1 | 277 | 189
20241004 | 2024-10-04 | 2024 | 10 | 40 | 6 | 4 | venerdì | ottobre | 1 | 278 | 190
20241005 | 2024-10-05 | 2024 | 10 | 40 | 7 | 5 | sabato | ottobre | 0 | 279 | 190
20241006 | 2024-10-06 | 2024 | 10 | 41 | 1 | 6 | domenica | ottobre | 0 | 280 | 190
20241007 | 2024-10-07 | 2024 | 10 | 41 | 2 | 7 | lunedì | ottobre | 1 | 281 | 191
20241008 | 2024-10-08 | 2024 | 10 | 41 | 3 | 8 | martedì | ottobre | 1 | 282 | 192
20241009 | 2024-10-09 | 2024 | 10 | 41 | 4 | 9 | mercoledì | ottobre | 1 | 283 | 193
20241010 | 2024-10-10 | 2024 | 10 | 41 | 5 | 10 | giovedì | ottobre | 1 | 284 | 194
20241011 | 2024-10-11 | 2024 | 10 | 41 | 6 | 11 | venerdì | ottobre | 1 | 285 | 195
20241012 | 2024-10-12 | 2024 | 10 | 41 | 7 | 12 | sabato | ottobre | 0 | 286 | 195
20241013 | 2024-10-13 | 2024 | 10 | 42 | 1 | 13 | domenica | ottobre | 0 | 287 | 195
20241014 | 2024-10-14 | 2024 | 10 | 42 | 2 | 14 | lunedì | ottobre | 1 | 288 | 196
20241015 | 2024-10-15 | 2024 | 10 | 42 | 3 | 15 | martedì | ottobre | 1 | 289 | 197
20241016 | 2024-10-16 | 2024 | 10 | 42 | 4 | 16 | mercoledì | ottobre | 1 | 290 | 198
20241017 | 2024-10-17 | 2024 | 10 | 42 | 5 | 17 | giovedì | ottobre | 1 | 291 | 199
20241018 | 2024-10-18 | 2024 | 10 | 42 | 6 | 18 | venerdì | ottobre | 1 | 292 | 200
20241019 | 2024-10-19 | 2024 | 10 | 42 | 7 | 19 | sabato | ottobre | 0 | 293 | 200
20241020 | 2024-10-20 | 2024 | 10 | 43 | 1 | 20 | domenica | ottobre | 0 | 294 | 200
20241021 | 2024-10-21 | 2024 | 10 | 43 | 2 | 21 | lunedì | ottobre | 1 | 295 | 201
20241022 | 2024-10-22 | 2024 | 10 | 43 | 3 | 22 | martedì | ottobre | 1 | 296 | 202
20241023 | 2024-10-23 | 2024 | 10 | 43 | 4 | 23 | mercoledì | ottobre | 1 | 297 | 203
20241024 | 2024-10-24 | 2024 | 10 | 43 | 5 | 24 | giovedì | ottobre | 1 | 298 | 204
20241025 | 2024-10-25 | 2024 | 10 | 43 | 6 | 25 | venerdì | ottobre | 1 | 299 | 205
20241026 | 2024-10-26 | 2024 | 10 | 43 | 7 | 26 | sabato | ottobre | 0 | 300 | 205
20241027 | 2024-10-27 | 2024 | 10 | 44 | 1 | 27 | domenica | ottobre | 0 | 301 | 205
20241028 | 2024-10-28 | 2024 | 10 | 44 | 2 | 28 | lunedì | ottobre | 1 | 302 | 206
20241029 | 2024-10-29 | 2024 | 10 | 44 | 3 | 29 | martedì | ottobre | 1 | 303 | 207
20241030 | 2024-10-30 | 2024 | 10 | 44 | 4 | 30 | mercoledì | ottobre | 1 | 304 | 208
20241031 | 2024-10-31 | 2024 | 10 | 44 | 5 | 31 | giovedì | ottobre | 1 | 305 | 209
20241101 | 2024-11-01 | 2024 | 11 | 44 | 6 | 1 | venerdì | novembre | 1 | 306 | 210
20241102 | 2024-11-02 | 2024 | 11 | 44 | 7 | 2 | sabato | novembre | 0 | 307 | 210
20241103 | 2024-11-03 | 2024 | 11 | 45 | 1 | 3 | domenica | novembre | 0 | 308 | 210
20241104 | 2024-11-04 | 2024 | 11 | 45 | 2 | 4 | lunedì | novembre | 1 | 309 | 211
20241105 | 2024-11-05 | 2024 | 11 | 45 | 3 | 5 | martedì | novembre | 1 | 310 | 212
20241106 | 2024-11-06 | 2024 | 11 | 45 | 4 | 6 | mercoledì | novembre | 1 | 311 | 213
20241107 | 2024-11-07 | 2024 | 11 | 45 | 5 | 7 | giovedì | novembre | 1 | 312 | 214
20241108 | 2024-11-08 | 2024 | 11 | 45 | 6 | 8 | venerdì | novembre | 1 | 313 | 215
20241109 | 2024-11-09 | 2024 | 11 | 45 | 7 | 9 | sabato | novembre | 0 | 314 | 215
20241110 | 2024-11-10 | 2024 | 11 | 46 | 1 | 10 | domenica | novembre | 0 | 315 | 215
20241111 | 2024-11-11 | 2024 | 11 | 46 | 2 | 11 | lunedì | novembre | 1 | 316 | 216
20241112 | 2024-11-12 | 2024 | 11 | 46 | 3 | 12 | martedì | novembre | 1 | 317 | 217
20241113 | 2024-11-13 | 2024 | 11 | 46 | 4 | 13 | mercoledì | novembre | 1 | 318 | 218
20241114 | 2024-11-14 | 2024 | 11 | 46 | 5 | 14 | giovedì | novembre | 1 | 319 | 219
20241115 | 2024-11-15 | 2024 | 11 | 46 | 6 | 15 | venerdì | novembre | 1 | 320 | 220
20241116 | 2024-11-16 | 2024 | 11 | 46 | 7 | 16 | sabato | novembre | 0 | 321 | 220
20241117 | 2024-11-17 | 2024 | 11 | 47 | 1 | 17 | domenica | novembre | 0 | 322 | 220
20241118 | 2024-11-18 | 2024 | 11 | 47 | 2 | 18 | lunedì | novembre | 1 | 323 | 221
20241119 | 2024-11-19 | 2024 | 11 | 47 | 3 | 19 | martedì | novembre | 1 | 324 | 222
20241120 | 2024-11-20 | 2024 | 11 | 47 | 4 | 20 | mercoledì | novembre | 1 | 325 | 223
20241121 | 2024-11-21 | 2024 | 11 | 47 | 5 | 21 | giovedì | novembre | 1 | 326 | 224
20241122 | 2024-11-22 | 2024 | 11 | 47 | 6 | 22 | venerdì | novembre | 1 | 327 | 225
20241123 | 2024-11-23 | 2024 | 11 | 47 | 7 | 23 | sabato | novembre | 0 | 328 | 225
20241124 | 2024-11-24 | 2024 | 11 | 48 | 1 | 24 | domenica | novembre | 0 | 329 | 225
20241125 | 2024-11-25 | 2024 | 11 | 48 | 2 | 25 | lunedì | novembre | 1 | 330 | 226
20241126 | 2024-11-26 | 2024 | 11 | 48 | 3 | 26 | martedì | novembre | 1 | 331 | 227
20241127 | 2024-11-27 | 2024 | 11 | 48 | 4 | 27 | mercoledì | novembre | 1 | 332 | 228
20241128 | 2024-11-28 | 2024 | 11 | 48 | 5 | 28 | giovedì | novembre | 1 | 333 | 229
20241129 | 2024-11-29 | 2024 | 11 | 48 | 6 | 29 | venerdì | novembre | 1 | 334 | 230
20241130 | 2024-11-30 | 2024 | 11 | 48 | 7 | 30 | sabato | novembre | 0 | 335 | 230
20241201 | 2024-12-01 | 2024 | 12 | 49 | 1 | 1 | domenica | dicembre | 0 | 336 | 230
20241202 | 2024-12-02 | 2024 | 12 | 49 | 2 | 2 | lunedì | dicembre | 1 | 337 | 231
20241203 | 2024-12-03 | 2024 | 12 | 49 | 3 | 3 | martedì | dicembre | 1 | 338 | 232
20241204 | 2024-12-04 | 2024 | 12 | 49 | 4 | 4 | mercoledì | dicembre | 1 | 339 | 233
20241205 | 2024-12-05 | 2024 | 12 | 49 | 5 | 5 | giovedì | dicembre | 1 | 340 | 234
20241206 | 2024-12-06 | 2024 | 12 | 49 | 6 | 6 | venerdì | dicembre | 1 | 341 | 235
20241207 | 2024-12-07 | 2024 | 12 | 49 | 7 | 7 | sabato | dicembre | 0 | 342 | 235
20241208 | 2024-12-08 | 2024 | 12 | 50 | 1 | 8 | domenica | dicembre | 0 | 343 | 235
20241209 | 2024-12-09 | 2024 | 12 | 50 | 2 | 9 | lunedì | dicembre | 1 | 344 | 236
20241210 | 2024-12-10 | 2024 | 12 | 50 | 3 | 10 | martedì | dicembre | 1 | 345 | 237
20241211 | 2024-12-11 | 2024 | 12 | 50 | 4 | 11 | mercoledì | dicembre | 1 | 346 | 238
20241212 | 2024-12-12 | 2024 | 12 | 50 | 5 | 12 | giovedì | dicembre | 1 | 347 | 239
20241213 | 2024-12-13 | 2024 | 12 | 50 | 6 | 13 | venerdì | dicembre | 1 | 348 | 240
20241214 | 2024-12-14 | 2024 | 12 | 50 | 7 | 14 | sabato | dicembre | 0 | 349 | 240
20241215 | 2024-12-15 | 2024 | 12 | 51 | 1 | 15 | domenica | dicembre | 0 | 350 | 240
20241216 | 2024-12-16 | 2024 | 12 | 51 | 2 | 16 | lunedì | dicembre | 1 | 351 | 241
20241217 | 2024-12-17 | 2024 | 12 | 51 | 3 | 17 | martedì | dicembre | 1 | 352 | 242
20241218 | 2024-12-18 | 2024 | 12 | 51 | 4 | 18 | mercoledì | dicembre | 1 | 353 | 243
20241219 | 2024-12-19 | 2024 | 12 | 51 | 5 | 19 | giovedì | dicembre | 1 | 354 | 244
20241220 | 2024-12-20 | 2024 | 12 | 51 | 6 | 20 | venerdì | dicembre | 1 | 355 | 245
20241221 | 2024-12-21 | 2024 | 12 | 51 | 7 | 21 | sabato | dicembre | 0 | 356 | 245
20241222 | 2024-12-22 | 2024 | 12 | 52 | 1 | 22 | domenica | dicembre | 0 | 357 | 245
20241223 | 2024-12-23 | 2024 | 12 | 52 | 2 | 23 | lunedì | dicembre | 1 | 358 | 246
20241224 | 2024-12-24 | 2024 | 12 | 52 | 3 | 24 | martedì | dicembre | 1 | 359 | 247
20241225 | 2024-12-25 | 2024 | 12 | 52 | 4 | 25 | mercoledì | dicembre | 1 | 360 | 248
20241226 | 2024-12-26 | 2024 | 12 | 52 | 5 | 26 | giovedì | dicembre | 1 | 361 | 249
20241227 | 2024-12-27 | 2024 | 12 | 52 | 6 | 27 | venerdì | dicembre | 1 | 362 | 250
20241228 | 2024-12-28 | 2024 | 12 | 52 | 7 | 28 | sabato | dicembre | 0 | 363 | 250
20241229 | 2024-12-29 | 2024 | 12 | 53 | 1 | 29 | domenica | dicembre | 0 | 364 | 250
20241230 | 2024-12-30 | 2024 | 12 | 53 | 2 | 30 | lunedì | dicembre | 1 | 365 | 251
20241231 | 2024-12-31 | 2024 | 12 | 53 | 3 | 31 | martedì | dicembre | 1 | 366 | 252
20250101 | 2025-01-01 | 2025 | 1 | 1 | 4 | 1 | mercoledì | gennaio | 0 | 1 | 252
20250102 | 2025-01-02 | 2025 | 1 | 1 | 5 | 2 | giovedì | gennaio | 1 | 2 | 253
20250103 | 2025-01-03 | 2025 | 1 | 1 | 6 | 3 | venerdì | gennaio | 1 | 3 | 254
20250104 | 2025-01-04 | 2025 | 1 | 1 | 7 | 4 | sabato | gennaio | 0 | 4 | 254
20250105 | 2025-01-05 | 2025 | 1 | 2 | 1 | 5 | domenica | gennaio | 0 | 5 | 254
20250106 | 2025-01-06 | 2025 | 1 | 2 | 2 | 6 | lunedì | gennaio | 0 | 6 | 254
20250107 | 2025-01-07 | 2025 | 1 | 2 | 3 | 7 | martedì | gennaio | 1 | 7 | 255
20250108 | 2025-01-08 | 2025 | 1 | 2 | 4 | 8 | mercoledì | gennaio | 1 | 8 | 256
20250109 | 2025-01-09 | 2025 | 1 | 2 | 5 | 9 | giovedì | gennaio | 1 | 9 | 257
20250110 | 2025-01-10 | 2025 | 1 | 2 | 6 | 10 | venerdì | gennaio | 1 | 10 | 258
20250111 | 2025-01-11 | 2025 | 1 | 2 | 7 | 11 | sabato | gennaio | 0 | 11 | 258
20250112 | 2025-01-12 | 2025 | 1 | 3 | 1 | 12 | domenica | gennaio | 0 | 12 | 258
20250113 | 2025-01-13 | 2025 | 1 | 3 | 2 | 13 | lunedì | gennaio | 1 | 13 | 259
20250114 | 2025-01-14 | 2025 | 1 | 3 | 3 | 14 | martedì | gennaio | 1 | 14 | 260
20250115 | 2025-01-15 | 2025 | 1 | 3 | 4 | 15 | mercoledì | gennaio | 1 | 15 | 261
20250116 | 2025-01-16 | 2025 | 1 | 3 | 5 | 16 | giovedì | gennaio | 1 | 16 | 262
20250117 | 2025-01-17 | 2025 | 1 | 3 | 6 | 17 | venerdì | gennaio | 1 | 17 | 263
20250118 | 2025-01-18 | 2025 | 1 | 3 | 7 | 18 | sabato | gennaio | 0 | 18 | 263
20250119 | 2025-01-19 | 2025 | 1 | 4 | 1 | 19 | domenica | gennaio | 0 | 19 | 263
20250120 | 2025-01-20 | 2025 | 1 | 4 | 2 | 20 | lunedì | gennaio | 1 | 20 | 264
20250121 | 2025-01-21 | 2025 | 1 | 4 | 3 | 21 | martedì | gennaio | 1 | 21 | 265
20250122 | 2025-01-22 | 2025 | 1 | 4 | 4 | 22 | mercoledì | gennaio | 1 | 22 | 266
20250123 | 2025-01-23 | 2025 | 1 | 4 | 5 | 23 | giovedì | gennaio | 1 | 23 | 267
20250124 | 2025-01-24 | 2025 | 1 | 4 | 6 | 24 | venerdì | gennaio | 1 | 24 | 268
20250125 | 2025-01-25 | 2025 | 1 | 4 | 7 | 25 | sabato | gennaio | 0 | 25 | 268
20250126 | 2025-01-26 | 2025 | 1 | 5 | 1 | 26 | domenica | gennaio | 0 | 26 | 268
20250127 | 2025-01-27 | 2025 | 1 | 5 | 2 | 27 | lunedì | gennaio | 1 | 27 | 269
20250128 | 2025-01-28 | 2025 | 1 | 5 | 3 | 28 | martedì | gennaio | 1 | 28 | 270
20250129 | 2025-01-29 | 2025 | 1 | 5 | 4 | 29 | mercoledì | gennaio | 1 | 29 | 271
20250130 | 2025-01-30 | 2025 | 1 | 5 | 5 | 30 | giovedì | gennaio | 1 | 30 | 272
20250131 | 2025-01-31 | 2025 | 1 | 5 | 6 | 31 | venerdì | gennaio | 1 | 31 | 273
20250201 | 2025-02-01 | 2025 | 2 | 5 | 7 | 1 | sabato | febbraio | 0 | 32 | 273
20250202 | 2025-02-02 | 2025 | 2 | 6 | 1 | 2 | domenica | febbraio | 0 | 33 | 273
20250203 | 2025-02-03 | 2025 | 2 | 6 | 2 | 3 | lunedì | febbraio | 1 | 34 | 274
20250204 | 2025-02-04 | 2025 | 2 | 6 | 3 | 4 | martedì | febbraio | 1 | 35 | 275
20250205 | 2025-02-05 | 2025 | 2 | 6 | 4 | 5 | mercoledì | febbraio | 1 | 36 | 276
20250206 | 2025-02-06 | 2025 | 2 | 6 | 5 | 6 | giovedì | febbraio | 1 | 37 | 277
20250207 | 2025-02-07 | 2025 | 2 | 6 | 6 | 7 | venerdì | febbraio | 1 | 38 | 278
20250208 | 2025-02-08 | 2025 | 2 | 6 | 7 | 8 | sabato | febbraio | 0 | 39 | 278
20250209 | 2025-02-09 | 2025 | 2 | 7 | 1 | 9 | domenica | febbraio | 0 | 40 | 278
20250210 | 2025-02-10 | 2025 | 2 | 7 | 2 | 10 | lunedì | febbraio | 1 | 41 | 279
20250211 | 2025-02-11 | 2025 | 2 | 7 | 3 | 11 | martedì | febbraio | 1 | 42 | 280
20250212 | 2025-02-12 | 2025 | 2 | 7 | 4 | 12 | mercoledì | febbraio | 1 | 43 | 281
20250213 | 2025-02-13 | 2025 | 2 | 7 | 5 | 13 | giovedì | febbraio | 1 | 44 | 282
20250214 | 2025-02-14 | 2025 | 2 | 7 | 6 | 14 | venerdì | febbraio | 1 | 45 | 283
20250215 | 2025-02-15 | 2025 | 2 | 7 | 7 | 15 | sabato | febbraio | 0 | 46 | 283
20250216 | 2025-02-16 | 2025 | 2 | 8 | 1 | 16 | domenica | febbraio | 0 | 47 | 283
20250217 | 2025-02-17 | 2025 | 2 | 8 | 2 | 17 | lunedì | febbraio | 1 | 48 | 284
20250218 | 2025-02-18 | 2025 | 2 | 8 | 3 | 18 | martedì | febbraio | 1 | 49 | 285
20250219 | 2025-02-19 | 2025 | 2 | 8 | 4 | 19 | mercoledì | febbraio | 1 | 50 | 286
20250220 | 2025-02-20 | 2025 | 2 | 8 | 5 | 20 | giovedì | febbraio | 1 | 51 | 287
20250221 | 2025-02-21 | 2025 | 2 | 8 | 6 | 21 | venerdì | febbraio | 1 | 52 | 288
Formulas:
Week = WEEKNUM([Date])

## Competence Center (hidden)
KEY_CC | RESPONSIBLE | SHORT_DESCR_CC | LONG_DESCR_CC | KEY_CC | SHORT_DESCR_CC | LONG_DESCR_CC | RESPONSIBLE
CC01 | M. PORCU | WEBAPP | WEB APPLICATIONS | CC01 | WebApp | Web Applications | M. Porcu
CC02 | A. STRADA | DM | DATA MANAGEMENT | CC02 | DM | Data Management | A. Strada
CC03 | A. ALBANESE | EPM | EPM | CC03 | EPM | EPM | M. Baragioli
CC04 | G. SIRONI | DS | DATA SCIENCE | CC04 | DS | Data Science | G. Sironi
CC06 | O. SAGAZIO | OPERATION | OPERATIONS | CC05 | AI | Artificial Intelligence | E. Carena
CC07 | M. CALABRESE | DELIVERY - PRJ | DELIVERY PROJECTS | CC06 | Operation | Operations | O. Sagazio
CC08 | F. PINNELLI | DELIVERY - AMS | DELIVERY MAINTENANCE | CC07 | Delivery - Prj | Delivery Projects | M. Calabrese
CC09 | M. COCCHI | CONSULTING | CONSULTING | CC08 | Delivery - AMS | Delivery Maintenance | F. Pinnelli
CC10 | A. MICALI | CONTROLLING | CONTROLLING | CC09 | Consulting | Consulting | M. Cocchi
CC11 | L. ROBERTO | HYBRIDAPP | HYBRID APPLICATIONS | CC10 | Outside DI | Outside DI | Not Available
XX01 | R. RUGGERI | R&D | RICERCA E SVILUPPO | CC11 | HybridApp | Hybrid Applications | L. Roberto
XX02 | M. BARAGIOLI | DI | DATA INTELLIGENCE | CC12 | t.b.d. | t.b.d. | t.b.d.
XX03 | G. LAROCCA | LAB MOBILE | LAB MOBILE
XX04 | A. OLIVO | ALTRA PRACTICE | ALTRA PRACTICE
XX05 | A. DE FILIPPO | ALTRA PRACTICE | ALTRA PRACTICE
XX06 | t.b.d. | t.b.d. | t.b.d.

## FerieDI (2024) (hidden)
FERIE 2024 | time axis 2024-01-01 to 2025-01-31
User | Practice | Area | CdC | FLAG CHIUSURA AGOSTO | time axis 2024-01-01 to 2025-01-31
A. ALBANESE | Data Intelligence | Delivery Projects | Delivery Projects | 10 | bar: 2024-01-02 to 2024-01-05; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-08-26 to 2024-08-30
A. BRANDIZZI | Data Intelligence | Operations | Hybrid Applications | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
A. CALDANA | Data Intelligence | Operations | Data Management | 5 | bar: 2024-08-12 to 2024-08-16
A. CAMARA | SAP ECC | SAP ECC | Outside DI | 0
A. Cerrato | Data Intelligence | Operations | Data Management | 10 | bar: 2024-08-05 to 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
A. CRESCIMONE | Data Intelligence | Operations | Data Management | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
A. CUOMO | Data Intelligence | Operations | Data Management | 10 | bar: 2024-08-05 to 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-10-03 to 2024-10-04; 2024-11-21 to 2024-11-22; 2024-11-25 to 2024-11-29
A. DE SANCTIS | Data Intelligence | Operations | Data Management | 6 | bar: 2024-08-15; 2024-08-19 to 2024-08-23
A. DI PIETRO | Data Intelligence | Operations | EPM | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-08-30; 2024-09-06; 2024-09-13; 2024-09-20; 2024-09-27; 2024-10-04; 2024-10-11; 2024-10-18; 2024-10-25; 2024-11-08; 2024-11-15; 2024-11-22; 2025-01-02 to 2025-01-03
A. ELIA | UX/UI | UX/UI | Outside DI | 10 | bar: 2024-01-10; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
A. FERRARI | Data Intelligence | Operations | Web Applications | 10 | bar: 2024-08-05 to 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
A. GERMINARIO | SAP ECC | SAP ECC | Outside DI | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
A. IEMBO | Data Intelligence | Controlling | Outside DI | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
A. IMBIMBO | Data Intelligence | Operations | Data Science | 7 | bar: 2024-08-15 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-09-09
A. LORENA | Data Intelligence | Operations | Web Applications | 10 | bar: 2024-08-05 to 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
A. MICALI | Data Intelligence | Controlling | Outside DI | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
A. NASTASI | Data Intelligence | Operations | Web Applications | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
A. PIROLA | Data Intelligence | Operations | Web Applications | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-08-26
A. SAIJA | Data Intelligence | Operations | Data Management | 2 | bar: 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-15 to 2024-08-16; 2024-12-25 to 2024-12-27; 2024-12-30 to 2025-01-02; 2025-01-13 to 2025-01-17; 2025-01-20 to 2025-01-24; 2025-01-27 to 2025-01-29
A. SANTORO | Data Intelligence | Consulting | Consulting | 10 | bar: 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
A. SIMONE | Data Intelligence | Controlling | Outside DI | 10 | bar: 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
A. STRADA | Data Intelligence | Operations | Data Management | 10 | bar: 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
A. Torone | Data Intelligence | Delivery Projects | Delivery Projects | 10 | bar: 2024-01-02 to 2024-01-05; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-08-26 to 2024-08-30
A. VLADI | Data Intelligence | Operations | Web Applications | 0 | bar: 2024-01-02 to 2024-01-05; 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-26 to 2024-08-30; 2024-09-02 to 2024-09-06; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
B. CAPOTORTO | Data Intelligence | Operations | Data Management | 0 | bar: 2024-01-02 to 2024-01-05; 2025-01-01 to 2025-01-02
C. DI LORENZO | Data Intelligence | Consulting | Consulting | 10 | bar: 2024-01-02 to 2024-01-05; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
C. ELIA | Data Intelligence | Operations | Hybrid Applications | 10 | bar: 2024-01-02 to 2024-01-05; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-08-26 to 2024-08-28
C. ESPOSITO | Data Intelligence | Operations | EPM | 10 | bar: 2024-01-02 to 2024-01-05; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
C. PAZ | Data Intelligence | Delivery Projects | Delivery Projects | 10 | 2024-01-02: x; 2024-01-03: x; 2024-01-04: x; 2024-01-05: x; 2024-07-22: x; 2024-07-23: x; 2024-07-24: x; 2024-07-25: x; 2024-07-26: x; 2024-08-12: x; 2024-08-13: x; 2024-08-14: x; 2024-08-15: x; 2024-08-16: x; 2024-08-19: x; 2024-08-20: x; 2024-08-21: x; 2024-08-22: x; 2024-08-23: x; 2024-09-11: 1/2 X (P); 2024-09-12: X; 2024-09-13: X; 2024-10-09: 1/2 X (P); 2024-10-10: X; 2024-10-11: X; 2024-11-13: 1/2 X (P); 2024-11-14: X; 2024-11-15: X; 2024-12-11: 1/2 X (P); 2024-12-12: X; 2024-12-13: X; 2025-01-29: 1/2 X (P); 2025-01-30: X; 2025-01-31: X
C. Piraccini | Data Intelligence | Operations | Data Management | 10 | bar: 2024-01-02 to 2024-01-05; 2024-08-02; 2024-08-05 to 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
C. TIBERTI | Data Intelligence | Operations | EPM | 10 | bar: 2024-01-02 to 2024-01-05; 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-09-16 to 2024-09-20; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
D. MILANI | CRM | CRM | Outside DI | 10 | bar: 2024-01-02 to 2024-01-05; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
E. STORTI | Data Intelligence | Consulting | Consulting | 10 | bar: 2024-01-02 to 2024-01-05; 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
E. TOSETTO | Data Intelligence | Operations | EPM | 10 | bar: 2024-01-02 to 2024-01-05; 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-05 to 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
F. ATANASIO | Data Intelligence | Operations | EPM | 10 | bar: 2024-01-02 to 2024-01-05; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-08-26 to 2024-08-28
F. D'ALBERTO | Data Intelligence | Operations | Web Applications | 10 | bar: 2024-01-02 to 2024-01-05; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
F. DE PEDIS | Data Intelligence | Operations | EPM | 10 | bar: 2024-01-02 to 2024-01-05; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-08-26 to 2024-08-30
F. Delogu | Data Intelligence | Operations | Web Applications | 10 | bar: 2024-01-02 to 2024-01-05; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
F. IANNI | SAP FIORI | SAP FIORI | Outside DI | 10 | bar: 2024-01-02 to 2024-01-05; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
F. LOMBARDINI | Data Intelligence | Consulting | Consulting | 10 | bar: 2024-01-02 to 2024-01-05; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
F. MALVEZZI | Data Intelligence | Operations | Data Science | 10 | bar: 2024-01-02 to 2024-01-05; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
F. PINNELLI | Data Intelligence | Delivery AMS | Delivery Maintenance | 0 | bar: 2024-01-02 to 2024-01-05; 2024-09-09 to 2024-09-13; 2024-09-16 to 2024-09-20
F. Plebani | Data Intelligence | Operations | Data Management | 10 | bar: 2024-01-02 to 2024-01-05; 2024-07-19; 2024-07-22; 2024-07-29 to 2024-08-02; 2024-08-05 to 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
F. REALE | Data Intelligence | Operations | Data Management | 10 | bar: 2024-01-02 to 2024-01-05; 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
F. SPACAGNA | Data Intelligence | Operations | Hybrid Applications | 10 | bar: 2024-01-02 to 2024-01-05; 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
F. Taita | Data Intelligence | Delivery Projects | Delivery Projects | 10 | bar: 2024-01-02 to 2024-01-05; 2024-05-10; 2024-05-23; 2024-06-10; 2024-07-18 to 2024-07-19; 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-12-25 to 2025-01-21
F. TARQUINI | SAP ECC | SAP ECC | Outside DI | 10 | bar: 2024-01-02 to 2024-01-05; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
F. VASSALLO | Data Intelligence | Delivery AMS | Delivery Maintenance | 10 | bar: 2024-01-02 to 2024-01-05; 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
G. Cataldo | Data Intelligence | Operations | Data Management | 10 | bar: 2024-01-02 to 2024-01-05; 2024-06-06 to 2024-06-07; 2024-06-20; 2024-06-27; 2024-07-25; 2024-07-31; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-08-26 to 2024-08-30
G. D'AMANTI | Data Intelligence | Operations | Data Management | 10 | bar: 2024-01-02 to 2024-01-05; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
G. DE FEO | Data Intelligence | Delivery Projects | Delivery Projects | 10 | bar: 2024-01-02 to 2024-01-05; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
G. ESPOSITO | R&D | R&D | Outside DI | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
G. FIORENTINI | Data Intelligence | Operations | Data Management | 10 | bar: 2024-06-07; 2024-06-17 to 2024-06-21; 2024-07-25; 2024-08-05 to 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
G. FRANCHI | Data Intelligence | Operations | Web Applications | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
G. GALATI | Data Intelligence | Delivery AMS | Delivery Maintenance | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
G. LOPEZ | Data Intelligence | Operations | Web Applications | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
G. LUONGO | Data Intelligence | Delivery AMS | Delivery Maintenance | 1 | bar: 2024-04-26; 2024-04-30 to 2024-05-03; 2024-07-03; 2024-07-29 to 2024-08-02; 2024-08-05 to 2024-08-09; 2024-08-15; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
G. MINERVINI | Data Intelligence | Operations | EPM | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-08-26; 2024-09-09; 2024-12-24; 2024-12-27; 2024-12-30 to 2024-12-31; 2025-01-02 to 2025-01-03
G. PAOLO | Data Intelligence | Consulting | Outside DI | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
G. PICERNO | Data Intelligence | Consulting | Consulting | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
G. Sabbatini | Data Intelligence | Operations | Data Science | 10 | bar: 2024-04-26; 2024-05-01 to 2024-05-03; 2024-07-01 to 2024-07-05; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
G. SIRONI | Data Intelligence | Operations | Data Science | 10 | bar: 2024-04-26; 2024-05-01 to 2024-05-03; 2024-07-22; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-08-26 to 2024-08-30; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
G. TARTAGLIA | Data Intelligence | Operations | Web Applications | 10 | bar: 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
I. BRESSAN | Data Intelligence | Operations | EPM | 10 | bar: 2024-07-22 to 2024-07-26; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
J. DACI | Data Intelligence | Operations | Data Management | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
L. BARIANI | Data Intelligence | Delivery Projects | Delivery Projects | bar: 2024-01-02 to 2024-01-05; 2024-01-08 to 2024-01-12; 2024-01-15 to 2024-01-19; 2024-01-22 to 2024-01-26; 2024-01-29 to 2024-02-02; 2024-02-05 to 2024-02-09; 2024-02-12 to 2024-02-16; 2024-02-19 to 2024-02-23; 2024-02-26 to 2024-03-01; 2024-03-04 to 2024-03-08; 2024-03-11 to 2024-03-15; 2024-03-18 to 2024-03-22; 2024-03-25 to 2024-03-29; 2024-04-01 to 2024-04-05; 2024-04-08 to 2024-04-12; 2024-04-15 to 2024-04-19; 2024-04-22 to 2024-04-26; 2024-04-29 to 2024-05-03; 2024-05-06 to 2024-05-10; 2024-05-13 to 2024-05-17; 2024-05-20 to 2024-05-24; 2024-05-27 to 2024-05-31; 2024-06-03 to 2024-06-07; 2024-06-10 to 2024-06-14; 2024-06-17 to 2024-06-21; 2024-06-24 to 2024-06-28; 2024-07-01 to 2024-07-05; 2024-07-08 to 2024-07-12; 2024-07-15 to 2024-07-19; 2024-07-22 to 2024-07-26; 2024-07-29 to 2024-08-02; 2024-08-05 to 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-08-26 to 2024-08-30
L. CARIGLIA | Data Intelligence | Operations | Data Management | 10 | bar: 2024-08-05 to 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
L. Franceschini | Data Intelligence | Delivery Projects | Delivery Projects | 5 | bar: 2024-01-02 to 2024-01-05; 2024-04-22 to 2024-04-23; 2024-08-19 to 2024-08-23; 2024-08-26 to 2024-08-30
L. FRANCO | Data Intelligence | Operations | EPM | 10 | bar: 2024-01-02 to 2024-01-05; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-08-26 to 2024-08-30; 2024-09-02 to 2024-09-04
L. GULLOTTO | Data Intelligence | Operations | Data Management | 10 | bar: 2024-01-02 to 2024-01-05; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2025-01-01 to 2025-01-02
L. MANGILI | Data Intelligence | Operations | EPM | 10 | bar: 2024-01-02 to 2024-01-05; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
L. PIGAZZINI | Data Intelligence | Operations | EPM | 7 | bar: 2024-01-02 to 2024-01-05; 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-20; 2024-08-28 to 2024-08-29
L. ROBERTO | Data Intelligence | Operations | Hybrid Applications | 10 | bar: 2024-01-02 to 2024-01-05; 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
L. Stroppa | Data Intelligence | Operations | Data Management | 10 | bar: 2024-01-02 to 2024-01-05; 2024-08-05 to 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-08-26 to 2024-08-30; 2024-12-23 to 2025-01-07
M. ATTANASIO | R&D | R&D | Outside DI | 5 | bar: 2024-01-02 to 2024-01-05; 2024-08-12 to 2024-08-16
M. CALABRESE | Data Intelligence | Delivery Projects | Delivery Projects | 10 | bar: 2024-01-02 to 2024-01-05; 2024-06-24; 2024-06-28; 2024-06-30; 2024-07-12; 2024-08-05 to 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
M. COCCHI | Data Intelligence | Consulting | Consulting | 5 | bar: 2024-08-12 to 2024-08-16
M. FAVALLI | Data Intelligence | Operations | EPM | 10 | bar: 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
M. GOMITONI | Data Intelligence | Operations | Data Science | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
M. MANNARINO | Data Intelligence | Operations | Web Applications | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
M. MIGLIORATI | Data Intelligence | Operations | Data Management | 1 | bar: 2024-07-01 to 2024-07-05; 2024-08-15
M. Piazza | SAP ECC | SAP ECC | Outside DI | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
M. PORCU | Data Intelligence | Operations | Web Applications | 5 | bar: 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-15 to 2024-08-16; 2024-08-21 to 2024-08-23; 2024-09-09 to 2024-09-13; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
M. Regini | Data Intelligence | Operations | Data Management | 10 | bar: 2024-08-05 to 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
M. Sabarese | DIGITAL | SAP FIORI | Outside DI | 10 | bar: 2024-04-26; 2024-05-01 to 2024-05-03; 2024-05-23 to 2024-06-07; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
M. SALCINI | Data Intelligence | Consulting | Consulting | 8 | bar: 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-12 to 2024-08-16; 2024-08-21 to 2024-08-23; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
M. SIMEONE | Data Intelligence | Operations | Hybrid Applications | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
M. SORRENTINO | Data Intelligence | Operations | EPM | 10 | bar: 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-05 to 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
M. TOCI | Data Intelligence | Operations | Web Applications | 10 | bar: 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
M. VIANELLI | Data Intelligence | Consulting | Consulting | 10 | bar: 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
M. VIMERCATI | Data Intelligence | Operations | Data Management | 10 | bar: 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
N. FRAGALE | Data Intelligence | Operations | EPM | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2025-01-01 to 2025-01-03
N. GUERRERO | Data Intelligence | Delivery AMS | Delivery Maintenance | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
N. PESCIONE | Data Intelligence | Operations | Web Applications | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
O. BEN OTHMANE | Data Intelligence | Operations | EPM | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-12-23 to 2024-12-24; 2024-12-27; 2024-12-30 to 2024-12-31
O. SAGAZIO | Data Intelligence | Operations | Operations | 5 | bar: 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-15 to 2024-08-16; 2024-08-21 to 2024-08-23; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
P. Anzelotti | Data Intelligence | Operations | Web Applications | 10 | bar: 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-09-02 to 2024-09-06; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
P. ASSIRELLI | Data Intelligence | Operations | Data Management | 10 | bar: 2024-08-02; 2024-08-05 to 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2025-01-01 to 2025-01-02
P. BUONASORTE | Data Intelligence | Operations | EPM | 10 | bar: 2024-08-07 to 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-09-16 to 2024-09-20; 2024-12-23 to 2024-12-24; 2024-12-27
P. DOLZANI | SAP ECC | SAP ECC | Outside DI | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
P. GALVAGNI | Data Intelligence | Consulting | Consulting | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
P. PIERONI | Data Intelligence | Operations | EPM | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
P. SINGH | R&D | R&D | Outside DI | 10 | bar: 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
R. Bondi | Data Intelligence | Operations | Data Management | 10 | bar: 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
R. FREDDI | Data Intelligence | Operations | EPM | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
R. GRANDI | Data Intelligence | Operations | Data Management | 10 | bar: 2024-08-01 to 2024-08-02; 2024-08-05 to 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
R. Grienti | Data Intelligence | Operations | Data Management | 10 | bar: 2024-08-05 to 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
R. MARASCA | Data Intelligence | Delivery Projects | Consulting | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
R. Nunziata | SAP ECC | SAP ECC | Outside DI | 10 | bar: 2024-04-11 to 2024-04-12; 2024-04-26; 2024-05-01 to 2024-05-03; 2024-05-08 to 2024-05-10; 2024-05-13 to 2024-05-17; 2024-05-20 to 2024-05-24; 2024-05-27 to 2024-05-31; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
R. TORTORA | Data Intelligence | Operations | Data Management | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
S. BELTRAMI | Data Intelligence | Operations | Web Applications | 10 | bar: 2024-08-05 to 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
S. DELLE FAVE | Data Intelligence | Operations | Web Applications | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
S. GUASTAVIGNA | SAP ECC | SAP ECC | Outside DI | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
L. STEFANELLI | Data Intelligence | Delivery AMS | Delivery Maintenance | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
M. STRADA | Data Intelligence | Delivery AMS | Delivery Maintenance | 0 | bar: 2024-07-29 to 2024-08-02; 2024-08-05 to 2024-08-09
S. PREZIOSA | Data Intelligence | Consulting | Consulting | 7 | bar: 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-20; 2024-09-02 to 2024-09-06; 2024-12-23 to 2024-12-27; 2024-12-30 to 2024-12-31; 2025-01-02 to 2025-01-03
T. Baldi | Data Intelligence | Operations | Data Management | 10 | bar: 2024-08-05 to 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-08-26 to 2024-08-30
T. Lazzari | SAP ECC | SAP ECC | Outside DI | 10 | bar: 2024-04-22 to 2024-05-03; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31
T. PORZIO | Data Intelligence | Delivery AMS | Delivery Maintenance | 10 | bar: 2024-04-26; 2024-05-01 to 2024-05-03; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23; 2024-12-02; 2024-12-25 to 2024-12-27; 2024-12-30 to 2024-12-31; 2025-01-02 to 2025-01-03
t.b.d. | t.b.d. | t.b.d. | t.b.d. | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
V. ECHARRY | Data Intelligence | Operations | Data Science | 10 | bar: 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
V. RASO | Data Intelligence | Operations | EPM | 12 | bar: 2024-03-01 to 2024-10-31; 2024-12-23 to 2024-12-27; 2024-12-30 to 2024-12-31
W. MORANDELLI | Data Intelligence | Operations | Data Management | 2 | bar: 2024-06-20 to 2024-06-21; 2024-06-24 to 2024-06-27; 2024-08-15 to 2024-08-16; 2024-09-05 to 2024-09-06
Y. BEN | Data Intelligence | Operations | Data Management | 8 | bar: 2024-08-12 to 2024-08-14; 2024-08-19 to 2024-08-23
M. STORICO | Digital QA | Delivery AMS | Outside DI | 10 | bar: 2024-08-05 to 2024-08-09; 2024-08-12 to 2024-08-16; 2024-08-19 to 2024-08-23
D. HEBA | Data Intelligence | Operations | Web Applications | 0
A. SEIRA | Data Intelligence | Operations | Data Intelligence | bar: 2024-12-25 to 2025-01-06

## FerieDI (2025)
FERIE 2024 | time axis 2025-01-01 to 2026-01-31
User | Practice | Area | CdC | FLAG CHIUSURA AGOSTO | [396 empty] | sab | time axis 2025-01-01 to 2026-01-31
A. ALBANESE | Data Intelligence | Delivery Projects | Delivery Projects | 0
A. BRANDIZZI | Data Intelligence | Operations | Hybrid Applications | 0
A. CALDANA | Data Intelligence | Operations | Data Management | 0
A. CAMARA | SAP ECC | SAP ECC | Outside DI | 0
A. Cerrato | Data Intelligence | Operations | Data Management | 0
A. CRESCIMONE | Data Intelligence | Operations | Data Management | 0
A. CUOMO | Data Intelligence | Operations | Data Management | 0 | bar: 2025-05-16; 2025-07-07 to 2025-07-11
A. DE SANCTIS | Data Intelligence | Operations | Data Management | 0
A. DI PIETRO | Data Intelligence | Operations | EPM | 0
A. ELIA | UX/UI | UX/UI | Outside DI | 0
A. FERRARI | Data Intelligence | Operations | Web Applications | 0
A. GERMINARIO | SAP ECC | SAP ECC | Outside DI | 0
A. IEMBO | Data Intelligence | Controlling | Outside DI | 0
A. IMBIMBO | Data Intelligence | Operations | Data Science | 0
A. LORENA | Data Intelligence | Operations | Web Applications | 0
A. MICALI | Data Intelligence | Controlling | Outside DI | 0
A. NASTASI | Data Intelligence | Operations | Web Applications | 0
A. PIROLA | Data Intelligence | Operations | Web Applications | 0 | bar: 2025-08-25 to 2025-08-28
A. SAIJA | Data Intelligence | Operations | Data Management | 0
A. SANTORO | Data Intelligence | Consulting | Consulting | 0
A. SIMONE | Data Intelligence | Controlling | Outside DI | 0
A. STRADA | Data Intelligence | Operations | Data Management | 0
A. Torone | Data Intelligence | Delivery Projects | Delivery Projects | 0
A. VLADI | Data Intelligence | Operations | Web Applications | 0
B. CAPOTORTO | Data Intelligence | Operations | Data Management | 0
C. DI LORENZO | Data Intelligence | Consulting | Consulting | 0
C. ELIA | Data Intelligence | Operations | Hybrid Applications | 0
C. ESPOSITO | Data Intelligence | Operations | EPM | 0
C. PAZ | Data Intelligence | Delivery Projects | Delivery Projects | 0
C. Piraccini | Data Intelligence | Operations | Data Management | 0
C. TIBERTI | Data Intelligence | Operations | EPM | 0
D. MILANI | CRM | CRM | Outside DI | 0
E. STORTI | Data Intelligence | Consulting | Consulting | 0
E. TOSETTO | Data Intelligence | Operations | EPM | 0
F. ATANASIO | Data Intelligence | Operations | EPM | 0
F. D'ALBERTO | Data Intelligence | Operations | Web Applications | 0
F. DE PEDIS | Data Intelligence | Operations | EPM | 0
F. Delogu | Data Intelligence | Operations | Web Applications | 0
F. IANNI | SAP FIORI | SAP FIORI | Outside DI | 0
F. LOMBARDINI | Data Intelligence | Consulting | Consulting | 0
F. MALVEZZI | Data Intelligence | Operations | Data Science | 0
F. PINNELLI | Data Intelligence | Delivery AMS | Delivery Maintenance | 0
F. Plebani | Data Intelligence | Operations | Data Management | 0
F. REALE | Data Intelligence | Operations | Data Management | 0
F. SPACAGNA | Data Intelligence | Operations | Hybrid Applications | 0
F. Taita | Data Intelligence | Delivery Projects | Delivery Projects | 0
F. TARQUINI | SAP ECC | SAP ECC | Outside DI | 0
F. VASSALLO | Data Intelligence | Delivery AMS | Delivery Maintenance | 0
G. Cataldo | Data Intelligence | Operations | Data Management | 0
G. D'AMANTI | Data Intelligence | Operations | Data Management | 0
G. DE FEO | Data Intelligence | Delivery Projects | Delivery Projects | 0
G. ESPOSITO | R&D | R&D | Outside DI | 0
G. FIORENTINI | Data Intelligence | Operations | Data Management | 0
G. FRANCHI | Data Intelligence | Operations | Web Applications | 0
G. GALATI | Data Intelligence | Delivery AMS | Delivery Maintenance | 0
G. LOPEZ | Data Intelligence | Operations | Web Applications | 0
G. LUONGO | Data Intelligence | Delivery AMS | Delivery Maintenance | 0
G. MINERVINI | Data Intelligence | Operations | EPM | 0
G. PAOLO | Data Intelligence | Consulting | Outside DI | 0
G. PICERNO | Data Intelligence | Consulting | Consulting | 0
G. Sabbatini | Data Intelligence | Operations | Data Science | 0
G. SIRONI | Data Intelligence | Operations | Data Science | 0
G. TARTAGLIA | Data Intelligence | Operations | Web Applications | 0 | bar: 2025-08-04 to 2025-08-08
I. BRESSAN | Data Intelligence | Operations | EPM | 0
J. DACI | Data Intelligence | Operations | Data Management | 0
L. BARIANI | Data Intelligence | Delivery Projects | Delivery Projects
L. CARIGLIA | Data Intelligence | Operations | Data Management | 0
L. Franceschini | Data Intelligence | Delivery Projects | Delivery Projects | 0
L. FRANCO | Data Intelligence | Operations | EPM | 0
L. GULLOTTO | Data Intelligence | Operations | Data Management | 0
L. MANGILI | Data Intelligence | Operations | EPM | 0
L. PIGAZZINI | Data Intelligence | Operations | EPM | 0
L. ROBERTO | Data Intelligence | Operations | Hybrid Applications | 1 | bar: 2025-06-17
L. Stroppa | Data Intelligence | Operations | Data Management | 0
M. ATTANASIO | R&D | R&D | Outside DI | 0
M. CALABRESE | Data Intelligence | Delivery Projects | Delivery Projects | 0
M. FAVALLI | Data Intelligence | Operations | EPM | 0
M. GOMITONI | Data Intelligence | Operations | Data Science | 0
M. MANNARINO | Data Intelligence | Operations | Web Applications | 0
M. MIGLIORATI | Data Intelligence | Operations | Data Management | 0
M. Piazza | SAP ECC | SAP ECC | Outside DI | 0
M. PORCU | Data Intelligence | Operations | Web Applications | 0 | bar: 2025-07-11; 2025-07-25; 2025-09-08 to 2025-09-12
M. Regini | Data Intelligence | Operations | Data Management | 0
M. Sabarese | DIGITAL | SAP FIORI | Outside DI | 0
M. SALCINI | Data Intelligence | Consulting | Consulting | 0
M. SIMEONE | Data Intelligence | Operations | Hybrid Applications | 0
M. SORRENTINO | Data Intelligence | Operations | EPM | 0
M. TOCI | Data Intelligence | Operations | Web Applications | 0
M. VIANELLI | Data Intelligence | Consulting | Consulting | 0
M. VIMERCATI | Data Intelligence | Operations | Data Management | 0
N. FRAGALE | Data Intelligence | Operations | EPM | 0
N. GUERRERO | Data Intelligence | Delivery AMS | Delivery Maintenance | 0
N. PESCIONE | Data Intelligence | Operations | Web Applications | 0
O. BEN OTHMANE | Data Intelligence | Operations | EPM | 0
O. SAGAZIO | Data Intelligence | Operations | Operations | 0
P. Anzelotti | Data Intelligence | Operations | Web Applications | 0 | bar: 2025-05-30; 2025-08-25 to 2025-08-29
P. ASSIRELLI | Data Intelligence | Operations | Data Management | 0
P. BUONASORTE | Data Intelligence | Operations | EPM | 0
P. DOLZANI | SAP ECC | SAP ECC | Outside DI | 0
P. GALVAGNI | Data Intelligence | Consulting | Consulting | 0
P. PIERONI | Data Intelligence | Operations | EPM | 0
P. SINGH | R&D | R&D | Outside DI | 0
R. Bondi | Data Intelligence | Operations | Data Management | 0
R. FREDDI | Data Intelligence | Operations | EPM | 0
R. GRANDI | Data Intelligence | Operations | Data Management | 0
R. Grienti | Data Intelligence | Operations | Data Management | 0
R. MARASCA | Data Intelligence | Delivery Projects | Consulting | 0
R. Nunziata | SAP ECC | SAP ECC | Outside DI | 0
R. TORTORA | Data Intelligence | Operations | Data Management | 0
S. BELTRAMI | Data Intelligence | Operations | Web Applications | 0 | bar: 2025-08-04 to 2025-08-08
S. DELLE FAVE | Data Intelligence | Operations | Web Applications | 0 | bar: 2025-07-28 to 2025-08-01
S. GUASTAVIGNA | SAP ECC | SAP ECC | Outside DI | 0
L. STEFANELLI | Data Intelligence | Delivery AMS | Delivery Maintenance | 0
M. STRADA | Data Intelligence | Delivery AMS | Delivery Maintenance | 0
S. PREZIOSA | Data Intelligence | Consulting | Consulting | 0
T. Baldi | Data Intelligence | Operations | Data Management | 0
T. Lazzari | SAP ECC | SAP ECC | Outside DI | 0
T. PORZIO | Data Intelligence | Delivery AMS | Delivery Maintenance | 0
t.b.d. | t.b.d. | t.b.d. | t.b.d. | 0
V. ECHARRY | Data Intelligence | Operations | Data Science | 0
V. RASO | Data Intelligence | Operations | EPM | 0
W. MORANDELLI | Data Intelligence | Operations | Data Management | 0
Y. BEN | Data Intelligence | Operations | Data Management | 0
M. STORICO | Digital QA | Delivery AMS | Outside DI | 0
D. HEBA | Data Intelligence | Operations | Web Applications | 0
A. SEIRA | Data Intelligence | Operations | Data Intelligence

## LoVs
ITEM_TYPE | DELIVERY_TYPE | WORKSTREAM | PROJECT_STREAM | JOB | STATUS | USER
CONTRACT | PRJ | Agile | HR | BackEnd | PROPOSAL | A. VLADI
LEAD | AMS | Waterfall | RETAIL | FrontEnd | TO START | M. VIMERCATI
PROSPECT | PreSales - GO TO MARKET | Scrum | WHOLESALE | DataManagement | STARTED | M. VIANELLI
INTERNAL PRJ | PreSales - GARE | Kanban | LOGISTIC | Analisys | ON GOING | F. VASSALLO
INTERNAL TRAINING | PreSales - DELIVERY | Scrumban | BIP | Data Engineering | ON HOLD | E. TOSETTO
PRE-SALES | TRAINING | PRINCE2 | FINANCE | Graphic Interface | CLOSED | A. TORONE
SALES |  | Six Sigma | CRM/CS | PM - Project Governance | POST-GO LIVE | M. TOCI
INTERNAL ACTIVITES |  | CPM | ALTRO | Architecture Analysis |  | C. TIBERTI
|  | CCPM | EPM | PMO - Project Management Officer |  | G. TARTAGLIA
|  | Lean management | CS | ECC Developer |  | F. TAITA
|  | PMBOK | CONSOLIDATO | ECC Analyst |  | A. STRADA
|  | XP |  | SM - Service Manager |  | E. STORTI
|  | Time&Materials |  | Tech Lead |  | F. SPACAGNA
M. SORRENTINO
G. SIRONI
P. SINGH
H. SINGH
A. SIMONE
A. SANTORO
M. SALCINI
A. SAIJA
O. SAGAZIO
L. ROBERTO
F. REALE
V. RASO
S. PREZIOSA
T. PORZIO
M. PORCU
A. PIROLA
F. PINNELLI
L. PIGAZZINI
P. PIERONI
G. PICERNO
N. PESCIONE
C. PAZ
G. PAOLO
F. ORIGLIA
A. NASTASI
G. MINERVINI
D. MILANI
M. MIGLIORATI
A. MICALI
M. SIMEONE
M. ATTANASIO
R. MARASCA
L. MANGILI
F. MALVEZZI
G. LUONGO
A. LORENA
F. LOMBARDINI
A. IMBIMBO
A. IEMBO
L. GULLOTTO
N. GUERRERO
R. GRANDI
M. GOMITONI
G. GALATI
R. FREDDI
L. FRANCO
L. FRANCESCHINI
N. FRAGALE
A. FERRARI
M. FAVALLI
G. ESPOSITO
C. ESPOSITO
C. ELIA
A. ELIA
V. ECHARRY
A. DI PIETRO
C. DI LORENZO
S. DELLE FAVE
A. DE SANCTIS
F. DE PEDIS
G. DE FEO
G. D'AMANTI
F. D'ALBERTO
J. DACI
A. CUOMO
A. CRESCIMONE
M. COCCHI
L. CARIGLIA
G. LOPEZ
M. CALABRESE
P. BUONASORTE
I. BRESSAN
A. BRANDIZZI
R. BONDI
Y. BEN
O. BEN OTHMANE
S. BELTRAMI
L. BARIANI
F. ATANASIO
P. ANZELLOTTI
R. ALVES
A. ALBANESE
S. LUCA
S. MATTEO
P. GALVAGNI
L. TIRONESE
D. SCALIA
L. CARLONI
E. ULIU
D. SCARCI
E. SOLDONI
M. VERGANI
G. LA FRANCA
A. CERRATO
R. GRIENTI
R. NUNZIATA
L. STROPPA
T. BALDI
G. SABBATINI
F. ORIGLIA
S. BORIASHOV
G. CATALDO
F. PLEBANI
C. PIRACCINI
M. REGINI
M. BARAGIOLI
M. MANNARINO
O. BEN OTHMANE
G.F. Fiorentini
O. BEN OTHMANE
A. Caldana
B. Capotorto
G.F. Fiorentini
A. Caldana
B. Capotorto
G.F. Fiorentini

## EMPLOYEE
USER_KEY | NAME | SURNAME | SHORT_DESCR | LONG_DESCR | PRACTICE | AREA | AREA_REF | COMPETENCE_CENTER_REF | ROLE | FLAG_INT | COMPANY | START_DATE | END_DATE | COMPETENCE_CENTER | FLAG_JUNIOR
E001 | ARCANGELO | ALBANESE | A. ALBANESE | ARCANGELO ALBANESE | Data Intelligence | Delivery Projects | Monica Calabrese | M. CALABRESE |  | I | ABSTRACT | 2018-03-19 00:00:00.000 | 2025-03-31 00:00:00.001 | Delivery Projects
E002 | LUCA | ALTOBELLI | L. ALTOBELLI | LUCA ALTOBELLI | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | I | ABSTRACT |  |  | Data Management
E003 | RAYLA | ALVES | R. ALVES | RAYLA ALVES | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | I | ABSTRACT | 2023-10-02 00:00:00.000 | 2024-07-30 | Data Management
E004 | PIERLUIGI | ANZELLOTTI | P. ANZELLOTTI | PIERLUIGI ANZELLOTTI | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | I | ABSTRACT | 2023-05-21 00:00:00.000 |  | Web Applications
E005 | PATRICK | ASSIRELLI | P. ASSIRELLI | PATRICK ASSIRELLI | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | E | MBO |  |  | Data Management
E006 | FEDERICO | ATANASIO | F. ATANASIO | FEDERICO ATANASIO | Data Intelligence | Operations | Omar Sagazio | M. BARAGIOLI |  | I | ABSTRACT | 2022-10-17 00:00:00.000 |  | EPM | X
E007 | MARCO | ATTANASIO | M. ATTANASIO | MARCO ATTANASIO | R&D | R&D | Renato Ruggeri | Not Available |  | I | ABSTRACT | 2024-01-10 00:00:00.000 |  | Outside DI | x
E008 | TIMOTY | BALDI | T. Baldi | TIMOTY BALDI | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | E | MBO |  |  | Data Management
E009 | MARIA GRAZIA | BARAGIOLI | M. BARAGIOLI | MARIA GRAZIA BARAGIOLI | Data Intelligence | Practice Data Intelligence | Maria Grazia Baragioli | M. BARAGIOLI |  | I | ABSTRACT |  |  | Practice Data Intelligence
E010 | LISA ADELE | BARIANI | L. BARIANI | LISA ADELE BARIANI | Data Intelligence | Delivery Projects | Monica Calabrese | M. CALABRESE |  | I | ABSTRACT | 2022-05-02 00:00:00.000 |  | Delivery Projects
E011 | STEFANO | BELTRAMI | S. BELTRAMI | STEFANO BELTRAMI | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | I | ABSTRACT | 2022-09-12 00:00:00.000 |  | Web Applications
E012 | OMAR | BEN OTHMANE | O. BEN OTHMANE | OMAR BEN OTHMANE | Data Intelligence | Operations | Omar Sagazio | M. BARAGIOLI |  | I | ABSTRACT | 2023-11-20 00:00:00.000 |  | EPM | X
E013 | SENDA | BEN YOUNES | S. BEN YOUNES | SENDA BEN YOUNES | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | I | Abstract |  |  | Data Management
E014 | RICCARDO | BONDI | R. BONDI | RICCARDO BONDI | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | I | ABSTRACT | 2022-04-11 00:00:00.000 |  | Data Management
E015 | SERGEI | BORIASHOV | S. Boriashov | SERGEI BORIASHOV | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | E | EPAM |  |  | Data Management
E016 | ALINA | BRANDIZZI | A. BRANDIZZI | ALINA BRANDIZZI | Data Intelligence | Operations | Omar Sagazio | L. ROBERTO |  | I | ABSTRACT | 2023-12-04 00:00:00.000 |  | Hybrid Applications | x
E017 | IVAN | BRESSAN | I. BRESSAN | IVAN BRESSAN | Data Intelligence | Operations | Omar Sagazio | M. BARAGIOLI |  | I | ABSTRACT | 2007-11-19 00:00:00.000 |  | EPM
E018 | SALVATORE | BRUNO | S. BRUNO | SALVATORE BRUNO | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | E | Ulixe |  | 2024-07-05 | Web Applications
E019 | PAOLO | BUONASORTE | P. BUONASORTE | PAOLO BUONASORTE | Data Intelligence | Operations | Omar Sagazio | M. BARAGIOLI |  | I | ABSTRACT | 2023-02-01 00:00:00.000 |  | EPM | X
E020 | MONICA | CALABRESE | M. CALABRESE | MONICA CALABRESE | Data Intelligence | Delivery Projects | Monica Calabrese | M. CALABRESE |  | I | ABSTRACT | 2019-10-07 00:00:00.000 |  | Delivery Projects
E021 | ALESSANDRO | CALDANA | A. CALDANA | ALESSANDRO CALDANA | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | E | MBO |  |  | Data Management
E022 | STEFANO | CALVI | S. CALVI | STEFANO CALVI | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | E | P. IVA |  |  | Data Management
E023 | ABDOULAYE | CAMARA | A. CAMARA | ABDOULAYE CAMARA | SAP ECC | SAP ECC | Not Available | Not Available |  | I | ABSTRACT |  |  | Outside DI
E024 | BEPPE | CAPOTORTO | B. CAPOTORTO | BEPPE CAPOTORTO | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | E | MBO |  |  | Data Management
E025 | Valerio | Carcaterra | V. Carcaterra | Valerio Carcaterra | DIGITAL | Not Available | DIGITAL | Not Available |  | E | Ulixe Nova |  |  | Outside DI
E026 | LUCA | CARIGLIA | L. CARIGLIA | LUCA CARIGLIA | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | I | ABSTRACT | 2018-10-15 00:00:00.000 |  | Data Management
E027 | LUCA | CARLONI | L. Carloni | LUCA CARLONI | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | E | ThinkOpen |  | 2024-04-29 | Web Applications
E028 | ANDREA | CARMISCIANO | A. CARMISCIANO | CARMISCIANO ANDREA | DIGITAL | Not Available | Not Available | Not Available |  | I | ABSTRACT |  |  | Outside DI
E029 | Andrea | Carmisciano | A. Carmisciano | Andrea Carmisciano | DIGITAL | Not Available | DIGITAL | Not Available |  | I | ABSTRACT |  |  | Outside DI
E030 | GIUSEPPE | CATALDO | G. Cataldo | GIUSEPPE CATALDO | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | E | Derga |  |  | Data Management
E031 | LUCA | CATTANEO | L. CATTANEO | LUCA CATTANEO | SAP ECC | SAP ECC | Not Available | Not Available |  | I | ABSTRACT |  |  | Outside DI
E032 | ARMANDO | CERRATO | A. Cerrato | ARMANDO CERRATO | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | E | KPMG |  | 2024-09-30 | Data Management
E033 | Yehor | Cherednychenko | Y. Cherednychenko | Yehor Cherednychenko | DIGITAL | Not Available | DIGITAL | Not Available |  | I | ABSTRACT |  |  | Outside DI
E034 | Piermichele | Cielo | P. Cielo | PIERMICHELE CIELO | SAP ECC | SAP ECC | Not Available | Not Available |  | I | ABSTRACT |  |  | Outside DI
E035 | Pierfrancesco | Cimino | P. Cimino | Pierfrancesco Cimino | DIGITAL | Not Available | DIGITAL | Not Available |  | I | ABSTRACT |  |  | Outside DI
E036 | MAURIZIO | COCCHI | M. COCCHI | MAURIZIO COCCHI | Finance | Consolidated & Tax | Antonio De Vivo | M. Cocchi |  | I | ABSTRACT | 2016-12-30 00:00:00.000 |  | Outside DI
E037 | Laura | Colombo | L. Colombo | Laura Colombo | DIGITAL | Not Available | DIGITAL | Not Available |  | I | ABSTRACT |  |  | Outside DI
E038 | ALESSIO | CRESCIMONE | A. CRESCIMONE | ALESSIO CRESCIMONE | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | I | ABSTRACT | 2022-02-14 00:00:00.000 |  | Data Management | x
E039 | ALFONSO | CUOMO | A. CUOMO | ALFONSO CUOMO | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | I | ABSTRACT | 2018-06-11 00:00:00.000 |  | Data Management
E040 | JULIANA | DACI | J. DACI | JULIANA DACI | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | I | ABSTRACT | 2022-07-06 00:00:00.000 |  | Data Management
E041 | Kristina | Dadaian | K. Dadaian | Kristina Dadaian | Data Intelligence | Delivery Projects | Monica Calabrese | M. CALABRESE |  | I | ABSTRACT |  |  | Delivery Projects
E042 | FIORENZO | D'ALBERTO | F. D'ALBERTO | FIORENZO D'ALBERTO | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | I | ABSTRACT | 2018-04-23 00:00:00.000 |  | Web Applications
E043 | GUIDO | D'AMANTI | G. D'AMANTI | GUIDO D'AMANTI | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | I | ABSTRACT | 2023-03-06 00:00:00.000 | 2024-11-15 00:00:00.000 | Data Management | x
E044 | GIACOMO | DE FEO | G. DE FEO | GIACOMO DE FEO | Data Intelligence | Delivery Projects | Monica Calabrese | M. CALABRESE |  | I | ABSTRACT | 2023-09-25 00:00:00.000 |  | Delivery Projects | x
E045 | DIEGO | DE PECOL | D. DE PECOL | DIEGO DE PECOL | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | I | ABSTRACT |  |  | Data Management
E046 | FLAVIO | DE PEDIS | F. DE PEDIS | FLAVIO DE PEDIS | Data Intelligence | Operations | Omar Sagazio | M. BARAGIOLI |  | I | ABSTRACT | 2021-03-01 00:00:00.000 |  | EPM
E047 | ANDREA | DE SANCTIS | A. DE SANCTIS | ANDREA DE SANCTIS | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | I | ABSTRACT | 2023-10-02 00:00:00.000 |  | Data Management | x
E048 | SIMONE | DELLE FAVE | S. DELLE FAVE | SIMONE DELLE FAVE | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | I | ABSTRACT | 2023-11-22 00:00:00.000 |  | Web Applications
E049 | FEDERICA | DELOGU | F. Delogu | FEDERICA DELOGU | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | I | ABSTRACT |  | 2024-06-30 | Web Applications
E050 | CARMEN | DI LORENZO | C. DI LORENZO | CARMEN DI LORENZO | Data Intelligence | Delivery Projects | Monica Calabrese | M. CALABRESE |  | I | ABSTRACT | 2023-11-06 00:00:00.000 |  | Delivery Projects | X
E051 | ANDREA | DI PIETRO | A. DI PIETRO | ANDREA DI PIETRO | Data Intelligence | Operations | Omar Sagazio | M. BARAGIOLI |  | I | ABSTRACT | 2018-08-01 00:00:00.000 |  | EPM
E052 | PAOLO | DOLZANI | P. DOLZANI | PAOLO DOLZANI | SAP ECC | SAP ECC | Not Available | Not Available |  | I | ABSTRACT |  |  | Outside DI
E053 | VALERIA | ECHARRY | V. ECHARRY | VALERIA ECHARRY | Data Intelligence | Operations | Omar Sagazio | G. SIRONI |  | I | ABSTRACT | 2022-03-21 00:00:00.000 |  | Data Science
E054 | CARMINE | ELIA | C. ELIA | CARMINE ELIA | Data Intelligence | Operations | Omar Sagazio | L. ROBERTO |  | I | ABSTRACT | 2021-04-19 00:00:00.000 |  | Hybrid Applications
E055 | ALESSANDRO | ELIA | A. ELIA | ALESSANDRO ELIA | UX/UI | UX/UI | Fabrizio Luri | Not Available |  | I | ABSTRACT | 2021-09-19 00:00:00.000 |  | Outside DI
E056 | GIANLUCA | ESPOSITO | G. ESPOSITO | GIANLUCA ESPOSITO | AREA TECH | AREA TECH | Renato Ruggeri | PAOLO ROMANO |  | I | ABSTRACT | 2021-11-15 00:00:00.000 |  | Outside DI
E057 | CHIARA | ESPOSITO | C. ESPOSITO | CHIARA ESPOSITO | Finance | Consolidated & Tax | Maurizio Cocchi | Antonio De Vivo |  | I | ABSTRACT | 2022-04-11 00:00:00.000 |  | Outside DI
E058 | MATTEO | FAVALLI | M. FAVALLI | MATTEO FAVALLI | Data Intelligence | Operations | Omar Sagazio | M. BARAGIOLI |  | I | ABSTRACT | 2023-04-17 00:00:00.000 |  | EPM | X
E059 | ANDREA | FERRARI | A. FERRARI | ANDREA FERRARI | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | I | ABSTRACT | 2022-05-23 00:00:00.000 |  | Web Applications | X
E060 | GIANFRANCO | FIORENTINI | G. FIORENTINI | GIANFRANCO FIORENTINI | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | E | MBO |  |  | Data Management
E061 | NORA | FRAGALE | N. FRAGALE | NORA FRAGALE | Data Intelligence | Operations | Omar Sagazio | M. BARAGIOLI |  | I | ABSTRACT | 2019-12-02 00:00:00.000 |  | EPM
E062 | LAURA | FRANCESCHINI | L. FRANCESCHINI | LAURA FRANCESCHINI | Data Intelligence | Delivery Projects | Monica Calabrese | M. CALABRESE |  | I | ABSTRACT | 2019-03-01 00:00:00.000 |  | Delivery Projects
E063 | GUALTIERO | FRANCHI | G. FRANCHI | GUALTIERO FRANCHI | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | I | Abstract |  |  | Web Applications
E064 | LEONARDO | FRANCO | L. FRANCO | LEONARDO FRANCO | Data Intelligence | Operations | Omar Sagazio | M. BARAGIOLI |  | I | ABSTRACT | 2020-11-02 00:00:00.000 |  | EPM
E065 | RICCARDO | FREDDI | R. FREDDI | RICCARDO FREDDI | Data Intelligence | Operations | Omar Sagazio | M. BARAGIOLI |  | I | ABSTRACT | 2022-10-03 00:00:00.000 | 2024-03-30 | EPM
E066 | GENATO | GALATI | G. GALATI | GENATO GALATI | Data Intelligence | Delivery AMS | Flora Pinnelli | F. PINNELLI |  | I | ABSTRACT | 2006-10-06 00:00:00.000 |  | Delivery Maintenance
E067 | PAOLO | GALVAGNI | P. GALVAGNI | PAOLO GALVAGNI | Finance | Consolidated & Tax | Maurizio Cocchi | Antonio De Vivo |  | I | ABSTRACT |  |  | Outside DI | x
E068 | PAOLO | GAMBONI | P. GAMBONI | PAOLO GAMBONI | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | I | ABSTRACT | 2025-02-03 00:00:00.000 |  | Data Management
E069 | ANNALISA | GERMINARIO | A. GERMINARIO | ANNALISA GERMINARIO | SAP ECC | SAP ECC | Not Available | Not Available |  | I | ABSTRACT |  |  | Outside DI
E070 | MARCELLO PAOLO | GOMITONI | M. GOMITONI | MARCELLO PAOLO GOMITONI | Data Intelligence | Operations | Omar Sagazio | G. SIRONI |  | I | ABSTRACT | 2023-09-18 00:00:00.000 |  | Data Science
E071 | RICCARDO | GRANDI | R. GRANDI | RICCARDO GRANDI | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | I | ABSTRACT |  |  | Data Management | x
E072 | ANDREA | GRAZIANI | A. GRAZIANI | ANDREA GRAZIANI | Go To Market |  |  |  |  | I | Abstract |  |  | Outside DI
E073 | ROBERTA | GRIENTI | R. Grienti | ROBERTA GRIENTI | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | E | KPMG |  | 2024-09-30 | Data Management
E074 | STEFANO | GUASTAVIGNA | S. GUASTAVIGNA | STEFANO GUASTAVIGNA | SAP ECC | SAP ECC | Not Available | Not Available |  | I | ABSTRACT |  |  | Outside DI
E075 | NIMZAY PAOLA | GUERRERO | N. GUERRERO | NIMZAY PAOLA GUERRERO MORA | Data Intelligence | Delivery AMS | Flora Pinnelli | F. PINNELLI |  | I | ABSTRACT | 2018-10-15 00:00:00.000 |  | Delivery Maintenance
E076 | LUCA | GULLOTTO | L. GULLOTTO | LUCA GULLOTTO | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | I | ABSTRACT | 2023-03-06 00:00:00.000 |  | Data Management | x
E077 | DENYS | HEBA | D. HEBA | DENYS HEBA | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | I | ABSTRACT | 2023-03-13 00:00:00.000 |  | Web Applications
E078 | FRANCESCO | IANNI | F. IANNI | FRANCESCO IANNI | SAP FIORI | SAP FIORI | Not Available | Not Available |  | I | ABSTRACT |  |  | Outside DI
E079 | ALESSANDRO | IEMBO | A. IEMBO | ALESSANDRO IEMBO | Process and Risk Delivery | Controlling | Aristide Micali | A. MICALI |  | I | ABSTRACT | 2018-04-03 00:00:00.000 |  | Outside DI | x
E080 | ALESSIO | IMBIMBO | A. IMBIMBO | ALESSIO IMBIMBO | Data Intelligence | Operations | Omar Sagazio | G. SIRONI |  | I | ABSTRACT | 2023-06-05 00:00:00.000 |  | Data Science
E081 | Giuseppe | Izzo | G. Izzo | Giuseppe Izzo | DIGITAL | Not Available | DIGITAL | Not Available |  | I | ABSTRACT |  |  | Outside DI
E082 | GIUSEPPE | LA FRANCA | G. La Franca | GIUSEPPE LA FRANCA | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | E | ThinkOpen |  | 2024-04-29 | Web Applications
E083 | GIUSEPPE | LAPIETRA | G. LAPIETRA | GIUSEPPE LAPIETRA | DIGITAL | Not Available | Not Available | Not Available |  | I | ABSTRACT |  |  | Outside DI
E084 | THOMAS | LAZZARI | T. LAZZARI | THOMAS LAZZARI | SAP ECC | SAP ECC | Not Available | Not Available |  | I | ABSTRACT |  |  | Outside DI
E085 | LINDA | LAZZARI | L. LAZZARI | LINDA LAZZARI | SAP ECC | SAP ECC | Not Available | Not Available |  | I | ABSTRACT |  |  | Outside DI
E086 | FRANCO | LOMBARDINI | F. LOMBARDINI | FRANCO LOMBARDINI | Finance | Consolidated & Tax | Maurizio Cocchi | Antonio De Vivo |  | I | ABSTRACT | 2015-12-15 00:00:00.000 |  | Outside DI
E087 | GERALDINE | LOPEZ | G. LOPEZ | GERALDINE LOPEZ | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | I | ABSTRACT | 2022-05-23 00:00:00.000 |  | Web Applications
E088 | Irish | Lopez | I. Lopez | Irish Lopez | DIGITAL | Not Available | DIGITAL | Not Available |  | I | ABSTRACT |  |  | Outside DI
E089 | ALBERTO | LORENA | A. LORENA | ALBERTO LORENA | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | I | ABSTRACT | 2022-06-21 00:00:00.000 |  | Web Applications | x
E090 | GIOVANNA | LUONGO | G. LUONGO | GIOVANNA LUONGO | Data Intelligence | Delivery AMS | Flora Pinnelli | F. PINNELLI |  | I | ABSTRACT | 2022-06-23 00:00:00.000 |  | Delivery Maintenance
E091 | Gian Renato | MAFFINI | G. Maffini | GIAN RENATO MAFFINI | DIGITAL |  | Andrea Olivo | G. MAFFINI |  | I | ABSTRACT |  |  | t.b.d.
E092 | FRANCESCO | MALVEZZI | F. MALVEZZI | FRANCESCO MALVEZZI | Data Intelligence | Operations | Omar Sagazio | G. SIRONI |  | I | ABSTRACT | 2023-02-06 00:00:00.000 |  | Data Science
E093 | Giacomo | Mandrioli | G. Mandrioli | Giacomo Mandrioli | DIGITAL | Not Available | DIGITAL | Not Available |  | I | ABSTRACT |  |  | Outside DI
E094 | LUCA | MANGILI | L. MANGILI | LUCA MANGILI | Data Intelligence | Operations | Omar Sagazio | M. BARAGIOLI |  | I | ABSTRACT | 2021-06-09 00:00:00.000 |  | EPM
E095 | MARCO | MANNARINO | M. MANNARINO | MARCO MANNARINO | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | E |  |  |  | Web Applications
E096 | RICCARDO | MARASCA | R. MARASCA | RICCARDO MARASCA | Data Intelligence | Delivery Projects | Monica Calabrese | M. CALABRESE |  | I | ABSTRACT | 2021-01-18 00:00:00.000 |  | Delivery Projects
E097 | Alex | Mattucci | A. Mattucci | Alex Mattucci | DIGITAL | Not Available | DIGITAL | Not Available |  | I | ABSTRACT |  |  | Outside DI
E098 | ARISTIDE | MICALI | A. MICALI | ARISTIDE MICALI | Process and Risk Delivery | Controlling | Aristide Micali | A. MICALI |  | I | ABSTRACT |  |  | Outside DI
E099 | MASSIMO | MIGLIORATI | M. MIGLIORATI | MASSIMO MIGLIORATI | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | I | ABSTRACT |  |  | Data Management
E100 | DARIO | MILANI | D. MILANI | DARIO MILANI | CRM | CRM | Andrea Olivo | Not Available |  | I | ABSTRACT | 2022-09-05 00:00:00.000 |  | Outside DI
E101 | GIUSEPPE | MINERVINI | G. MINERVINI | GIUSEPPE MINERVINI | Data Intelligence | Operations | Omar Sagazio | M. BARAGIOLI |  | I | ABSTRACT | 2022-12-12 00:00:00.000 |  | EPM | X
E102 | WALTER | MORANDELLI | W. MORANDELLI | WALTER MORANDELLI | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | E | Derga |  |  | Data Management
E103 | GIOVANNI | MORDÀ | G. MORDÀ | GIOVANNI MORDÀ | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | I | ABSTRACT | 2024-07-01 00:00:00:00 |  | Data Management | X
E104 | ANTONELLO | NASTASI | A. NASTASI | ANTONELLO NASTASI | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | I | ABSTRACT | 2023-04-03 00:00:00.000 |  | Web Applications
E105 | ROSALINDA | NUNZIATA | R. Nunziata | ROSALINDA NUNZIATA | SAP ECC | SAP ECC | SAP ECC | Not Available |  | E | Syscons |  |  | Outside DI
E106 | FABIO | ORIGLIA | F. ORIGLIA | FABIO ORIGLIA | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | E | ABSTRACT |  | 2024-06-14 | Web Applications
E107 | IVAN | OSTYMCHUCK | I. OSTYMCHUCK | IVAN OSTYMCHUCK | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | I | ABSTRACT | 2023-03-13 00:00:00.000 |  | Web Applications
E108 | CRYSELL | PAZ | C. PAZ | CRYSELL PAZ | Data Intelligence | Delivery Projects | Monica Calabrese | M. CALABRESE |  | I | ABSTRACT | 2019-06-04 00:00:00.000 |  | Delivery Projects
E109 | NICHOLAS | PESCIONE | N. PESCIONE | NICHOLAS PESCIONE | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | I | ABSTRACT | 2021-07-05 00:00:00.000 |  | Web Applications
E110 | MIRIAM | PIAZZA | M. Piazza | MIRIAM PIAZZA | SAP ECC | SAP ECC | SAP ECC | Not Available |  | E | Syscons |  |  | Outside DI
E111 | GABRIELE | PICERNO | G. PICERNO | GABRIELE PICERNO | Finance | Consolidated & Tax | Maurizio Cocchi | Antonio De Vivo |  | I | ABSTRACT | 2022-10-03 00:00:00.000 |  | Outside DI | X
E112 | PIETRO PAOLO | PIERONI | P. PIERONI | PIETRO PAOLO PIERONI | Data Intelligence | Operations | Omar Sagazio | M. BARAGIOLI |  | I | ABSTRACT | 2008-08-09 00:00:00.000 |  | EPM
E113 | LORENZO | PIGAZZINI | L. PIGAZZINI | LORENZO PIGAZZINI | Finance | Consolidated & Tax | Maurizio Cocchi | Antonio De Vivo |  | I | ABSTRACT | 2014-07-09 00:00:00.000 |  | Outside DI | X
E114 | FLORA | PINNELLI | F. PINNELLI | FLORA PINNELLI | Data Intelligence | Delivery AMS | Flora Pinnelli | F. PINNELLI |  | I | ABSTRACT | 2021-10-04 00:00:00.000 |  | Delivery Maintenance
E115 | CHRISTIAN | PIRACCINI | C. Piraccini | CHRISTIAN PIRACCINI | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | E | MBO |  |  | Data Management
E116 | ANDREA | PIROLA | A. PIROLA | ANDREA PIROLA | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | I | ABSTRACT | 2020-06-22 00:00:00.000 |  | Web Applications
E117 | FEDERICO | PLEBANI | F. Plebani | FEDERICO PLEBANI | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | E | Derga |  |  | Data Management
E118 | MIRKO | PORCU | M. PORCU | MIRKO PORCU | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | I | ABSTRACT | 2023-03-13 00:00:00.000 |  | Web Applications
E119 | TATIANA | PORZIO | T. PORZIO | TATIANA PORZIO | Data Intelligence | Delivery AMS | Flora Pinnelli | F. PINNELLI |  | I | ABSTRACT | 2023-05-02 00:00:00.000 |  | Delivery Maintenance
E120 | SALVATORE | PREZIOSA | S. PREZIOSA | SALVATORE PREZIOSA | Data Intelligence | Delivery Projects | Monica Calabrese | M. CALABRESE |  | I | ABSTRACT | 2023-04-17 00:00:00.000 |  | Delivery Projects
E121 | VERONICA | RASO | V. RASO | VERONICA RASO | Data Intelligence | Operations | Omar Sagazio | M. BARAGIOLI |  | I | ABSTRACT | 2015-12-15 00:00:00.000 |  | EPM
E122 | FLAVIO | REALE | F. REALE | FLAVIO REALE | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | I | ABSTRACT | 2022-01-19 00:00:00.000 |  | Data Management
E123 | MATTEO | REGINI | M. Regini | MATTEO REGINI | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | E | MBO |  |  | Data Management
E124 | Davide | Reich | D. Reich | Davide Reich | DIGITAL | Not Available | DIGITAL | Not Available |  | I | ABSTRACT |  |  | Outside DI
E125 | LUCA | ROBERTO | L. ROBERTO | LUCA ROBERTO | Data Intelligence | Operations | Omar Sagazio | L. ROBERTO |  | I | ABSTRACT | 2021-10-18 00:00:00.000 |  | Hybrid Applications
E126 | MICHELE | SABARESE | M. SABARESE | MICHELE SABARESE | SAP FIORI | SAP FIORI | Not Available | Not Available |  | I | ABSTRACT |  |  | Outside DI
E127 | GIULIANO | SABBATINI | G. Sabbatini | GIULIANO SABBATINI | Data Intelligence | Operations | Omar Sagazio | G. SIRONI |  | E |  |  | END | Data Science
E128 | OMAR | SAGAZIO | O. SAGAZIO | OMAR SAGAZIO | Data Intelligence | Operations | Omar Sagazio | O. SAGAZIO |  | I | ABSTRACT | 2022-05-02 00:00:00.000 |  | Operations
E129 | ANTONINO | SAIJA | A. SAIJA | ANTONINO SAIJA | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | I | ABSTRACT | 2021-11-02 00:00:00.000 |  | Data Management | x
E130 | MARIO | SALCINI | M. SALCINI | MARIO SALCINI | Finance | Consolidated & Tax | Maurizio Cocchi | Antonio De Vivo |  | I | ABSTRACT | 2014-04-01 00:00:00.000 |  | Outside DI
E131 | ALMA CHIARA | SANTORO | A. SANTORO | ALMA CHIARA SANTORO | Data Intelligence |  |  |  |  | I | ABSTRACT | 2022-01-10 00:00:00.000 | 2025-12-31
E132 | Dorotea | Scala | D. Scala | Dorotea Scala | DIGITAL | Not Available | DIGITAL | Not Available |  | I | ABSTRACT |  |  | Outside DI
E133 | DARIO | SCALIA | D. Scalia | DARIO SCALIA | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | E | ThinkOpen |  | 2024-04-29 | Web Applications
E134 | DANILO | SCARCI | D. Scarci | DANILO SCARCI | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | E | ThinkOpen |  | 2024-04-29 | Web Applications
E135 | FABIO | SCOGNAMILGIO | F. SCOGNAMIGLIO | FABIO SCOGNAMIGLIO | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | I | ABSTRACT | 2023-03-13 00:00:00.000 |  | Web Applications
E136 | ALBERTO | SEIRA OZINO | A. SEIRA | ALBERTO SEIRA OZINO | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | I | ABSTRACT | 2024-12-09 00:00:00:00 |  | Data Management | X
E137 | MATTIA | SIMEONE | M. SIMEONE | MATTIA SIMEONE | Data Intelligence | Operations | Omar Sagazio | L. ROBERTO |  | I | ABSTRACT |  |  | Hybrid Applications | x
E138 | ARIANNA | SIMONE | A. SIMONE | ARIANNA SIMONE | Process and Risk Delivery | Controlling | Aristide Micali | A. MICALI |  | I | ABSTRACT | 2023-04-03 00:00:00.000 |  | Outside DI | x
E139 | PARMRAJ | SINGH | P. SINGH | PARMRAJ SINGH | AREA TECH | AREA TECH | Renato Ruggeri | PAOLO ROMANO |  | I | ABSTRACT | 2019-01-21 00:00:00.000 |  | Outside DI
E140 | HARASHMAN | SINGH | H. SINGH | HARASHMAN SINGH | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | I | ABSTRACT | 2022-07-14 00:00:00.000 | 2024-04-30 | Data Management
E141 | GIANLUCA | SIRONI | G. SIRONI | GIANLUCA SIRONI | Data Intelligence | Operations | Omar Sagazio | G. SIRONI |  | I | ABSTRACT | 2018-10-15 00:00:00.000 |  | Data Science
E142 | ELENA | SOLDONI | E. Soldoni | ELENA SOLDONI | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | E | ThinkOpen |  | 2024-04-29 | Web Applications
E143 | JENNYFER | SORGATO | J. SORGATO | JENNYFER SORGATO | SAP ECC | SAP ECC | Not Available | Not Available |  | I | ABSTRACT |  |  | Outside DI
E144 | MARIA CHIARA | SORRENTINO | M. SORRENTINO | MARIA CHIARA SORRENTINO | Finance | Consolidated & Tax | Maurizio Cocchi | Antonio De Vivo |  | I | ABSTRACT | 2014-04-01 00:00:00.000 |  | Outside DI
E145 | FABIO | SPACAGNA | F. SPACAGNA | FABIO SPACAGNA | Data Intelligence | Operations | Omar Sagazio | L. ROBERTO |  | I | ABSTRACT | 2021-07-01 00:00:00.000 |  | Hybrid Applications
E146 | LUCA | STEFANELLI | L. STEFANELLI | LUCA STEFANELLI | Data Intelligence | Delivery AMS | Flora Pinnelli | F. PINNELLI |  | I | ABSTRACT |  |  | Delivery Maintenance
E147 | ELENA | STORTI | E. STORTI | ELENA STORTI | Data Intelligence | Delivery Projects | Monica Calabrese | M. CALABRESE |  | I | ABSTRACT | 2022-06-06 00:00:00.000 |  | Delivery Projects
E148 | ALBERTO | STRADA | A. STRADA | ALBERTO STRADA | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | I | ABSTRACT | 2020-11-02 00:00:00.000 |  | Data Management
E149 | MATTEO | STRADA | M. STRADA | MATTEO STRADA | Data Intelligence | Delivery AMS | Flora Pinnelli | F. PINNELLI |  | I | ABSTRACT |  |  | Delivery Maintenance
E150 | LOREDANA | STROPPA | L. Stroppa | LOREDANA STROPPA | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | E | Metisoft |  |  | Data Management
E151 | RAMIREZ FRANCESCA MICHELLE | TAITA | F. TAITA | RAMIREZ FRANCESCA MICHELLE TAITA | Data Intelligence | Delivery Projects | Monica Calabrese | M. CALABRESE |  | I | ABSTRACT | 2022-07-06 00:00:00.000 |  | Delivery Projects
E152 | FABIO | TARQUINI | F. TARQUINI | FABIO TARQUINI | SAP ECC | SAP ECC | Not Available | Not Available |  | I | ABSTRACT |  |  | Outside DI
E153 | GABRIELE | TARTAGLIA | G. TARTAGLIA | GABRIELE TARTAGLIA | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | I | ABSTRACT | 2022-05-03 00:00:00.000 |  | Web Applications | x
E154 | CLAUDIA | TIBERTI | C. TIBERTI | CLAUDIA TIBERTI | Data Intelligence | Operations | Omar Sagazio | M. BARAGIOLI |  | I | ABSTRACT | 2023-03-27 00:00:00.000 |  | EPM | X
E155 | LUIGI | TIRONESE | L. Tironese | LUIGI TIRONESE | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | E | ThinkOpen |  | 2024-04-29 | Web Applications
E156 | MIRJAN | TOCI | M. TOCI | MIRJAN TOCI | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | I | ABSTRACT | 2023-03-01 00:00:00.000 |  | Web Applications
E157 | ALBERTO | TORONE | A. TORONE | ALBERTO TORONE | Data Intelligence | Delivery AMS | Flora Pinnelli | F. Pinnelli | Service Manager | I | ABSTRACT | 2019-01-21 00:00:00.000 |  | Delivery AMS
E158 | Alessandro | Torri | A. Torri | Alessandro Torri | DIGITAL | Not Available | DIGITAL | Not Available |  | I | ABSTRACT |  |  | Outside DI
E159 | RENATO | TORTORA | R. TORTORA | RENATO TORTORA | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | I | Abstract |  |  | Data Management
E160 | ERNESTO | TOSETTO | E. TOSETTO | ERNESTO TOSETTO | Finance | Consolidated & Tax | Maurizio Cocchi | Antonio De Vivo |  | I | ABSTRACT | 2021-03-21 00:00:00.000 |  | Outside DI
E161 | Giulia | Tuninetti | G. Tuninetti | Giulia Tuninetti | DIGITAL | Not Available | DIGITAL | Not Available |  | I | ABSTRACT |  |  | Outside DI
E162 | ENDAR | ULIU | E. Uliu | ENDAR ULIU | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | E | ThinkOpen |  | 2024-04-29 | Web Applications
E163 | FABRIZIO | VASSALLO | F. VASSALLO | FABRIZIO VASSALLO | Data Intelligence | Delivery AMS | Flora Pinnelli | F. PINNELLI |  | I | ABSTRACT | 2023-03-01 00:00:00.000 |  | Delivery Maintenance
E164 | MAURO | VERGANI | M. Vergani | MAURO VERGANI | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | E | ThinkOpen |  | 2024-04-29 | Web Applications
E165 | MILO | VIANELLI | M. VIANELLI | MILO VIANELLI | Data Intelligence | Delivery Projects | Monica Calabrese | M. CALABRESE |  | I | ABSTRACT | 2022-07-06 00:00:00.000 |  | Delivery Projects
E166 | MANUEL | VIMERCATI | M. VIMERCATI | MANUEL VIMERCATI | Data Intelligence | Operations | Omar Sagazio | A. STRADA |  | I | ABSTRACT | 2020-09-01 00:00:00.000 |  | Data Management
E167 | ANDRI | VLADI | A. VLADI | ANDRI VLADI | Data Intelligence | Operations | Omar Sagazio | M. PORCU |  | I | ABSTRACT | 2021-03-15 00:00:00.000 |  | Web Applications
E168 | Ting Ting | Wu | T. Wu | Ting Ting Wu | DIGITAL | Not Available | DIGITAL | Not Available |  | I | ABSTRACT |  |  | Outside DI

## Foglio2
PM 2025
A. Cuomo
F. Taita
G. SIRONI
L. BARIANI
L. Franceschini
L. Roberto
M. Calabrese
O. Sagazio
P. Anzellotti

## Festività&Chiusure
ClosurePeriodFrom | ClosurePeriodTo | ReasonDescr | ReasonType | year | 2025 | gennaio | febbraio | marzo | aprile | maggio | giugno | luglio | agosto | settembre | ottobre | novembre | dicembre
2025-01-01 | 2025-01-01 | Capodanno | Festivity |  |  | 18 | 20 | 21 | 22 | 20 | 20 | 23 | 12 | 21 | 23 | 21 | 22
2025-01-06 | 2025-01-06 | Epifania | Festivity
2025-04-25 | 2024-04-26 | Festa della Liberazione (1945) | Festivity
2025-04-21 | 2025-04-21 | Lunedì dell'Angelo | Festivity
2025-05-01 | 2024-05-03 | Festa del lavoro | Festivity
2025-06-02 | 2025-06-02 | Festa della Repubblica | Festivity
2025-08-15 | 2025-08-15 | Assunzione di Maria | Festivity
2025-11-01 | 2025-11-01 | Ognissanti | Festivity
2025-12-07 | 2025-12-07 | Milano - Santo Patrono | Festivity
2025-12-08 | 2025-12-08 | Immacolata Concezione | Festivity
2025-12-25 | 2025-12-25 | Natale di Gesù | Festivity
2025-12-26 | 2025-12-26 | Santo Stefano | Festivity
2025-01-02 | 2024-01-05 | Cristmas' Holidays | Abstract Closure
2024-08-12 | 2024-08-23 | Summer's Holidays | Abstract Closure
2025-12-29 | 2025-01-03 | Cristmas' Holidays | Abstract Closure
2025-12-30 | 2025-01-03 | Cristmas' Holidays | Abstract Closure
2025-12-29 | 2025-01-03 | Cristmas' Holidays | Abstract Closure
Formulas:
ClosurePeriodTo = [ClosurePeriodFrom]