## Scheduling
ITEM_TYPE | DELIVERY_TYPE | WORKSTREAM | YEAR_OF_COMPETENCE | START_DATE | END_DATE | SOW_ID | JIRA_KEY | PROJECT_STREAM | PROJECT_DESCR | CLIENT | PM_SM | USER | AREA_CC | JOB | PLANNED_FTE | ACTUAL_FTE | STATUS | PROGRESS_% | YEAR | Tot_sched_next | gen | feb | mar | apr | mag | giu | lug | ago | set | ott | nov | dic | gen1 | feb1 | mar1 | apr1 | mag1 | giu1 | lug1 | ago1 | set1 | ott1 | nov1 | dic1 | PM | DELETE
CONTRACT | PRJ |  | 2023-2024 | 2024-11-01 | 2025-02-28 | ABS23459 | AEACUGIW | EPM | Essilor Adj Conso Upstream group Integration_Wave1 | EssilorLuxottica | A. Albanese | A. Di Pietro | Operations | BackEnd | 60 | 60 | CLOSED | 1 | 2024 | 0 | 8 | 8 | [10 empty] | 0.44444 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2023-2024 | 2024-11-01 | 2025-02-28 | ABS23459 | AEACUGIW | EPM | Essilor Adj Conso Upstream group Integration_Wave1 | EssilorLuxottica | A. Albanese | E. Storti | Delivery Projects | BackEnd | 60 | 60 | CLOSED | 1 | 2024 | 0 | 8 | 8 | [10 empty] | 0.44444 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Formazione Apex | Abstract | A. Albanese | L. Mangili | Operations | BackEnd | 0 | 0 |  | 0 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Formazione FCCS | Abstract | A. Albanese | C. Esposito | Consolidated & Tax | BackEnd | 0 | 0 |  | 0 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Formazione FCCS | Abstract | A. Albanese | M. Sorrentino | Consolidated & Tax | Analysis | 0 | 0 |  | 0 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Formazione HFM | Abstract | A. Albanese | L. Pigazzini | Consolidated & Tax | BackEnd | 0 | 0 |  | 0 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Formazione nuovo assunto |  | A. Albanese | L. Pigazzini | Consolidated & Tax | BackEnd | 0 | 0 |  | 0 | 2024 | 27 | 12.6 | 21 | 21 | 19 | 2 | 2 | 23 | [5 empty] | 0.7 | 1.05 | 1 | 0.86364 | 0.1 | 0.1 | 1 | 0 | 0 | 0 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Formazione Talentia | Abstract | A. Albanese | C. Tiberti | Operations | BackEnd | 0 | 0 |  | 1 | 2024 | 0 | 1.8 | 3.15 | 4.2 | 2.85 | [8 empty] | 0.1 | 0.1575 | 0.2 | 0.12955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Formazione Tax | Abstract | A. Albanese | C. Tiberti | Operations | BackEnd | 0 | 0 |  | 1 | 2024 | 0 | 5.4 | 6.3 | 5.25 | 3.8 | [8 empty] | 0.3 | 0.315 | 0.25 | 0.17273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - NRT | FERRERO | A. Albanese | F. Atanasio | Operations | BackEnd | 52 | 0 | PROPOSAL | 0 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - NRT | FERRERO | A. Albanese | F. Lombardini | Consolidated & Tax | Analysis | 52 | 0 | PROPOSAL | 0 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - NRT | FERRERO | A. Albanese | I. Bressan | Operations | Tech Lead | 52 | 0 | PROPOSAL | 0 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - NRT | FERRERO | A. Albanese | P. Galvagni | Consolidated & Tax | Analysis | 52 | 0 | PROPOSAL | 0 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato FCCS | Vision Group | A. Albanese | A. Albanese | Delivery Projects | PM - Project Governance | 210 | 220 | ON GOING | 0 | 2024 | 10 | [6 empty] | 2 |  | 3 | 3 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0 | 0.14286 | 0.13043 | 0.095238 | 0
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato FCCS | Vision Group | A. Albanese | Esterno |  | Analysis | 210 | 220 | ON GOING | 0 | 2024 | 10 | [8 empty] | 4 | 6 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19048 | 0.26087 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato FCCS | Vision Group | A. Albanese | F. Atanasio | Operations | BackEnd - Junior | 210 | 220 | ON GOING | 0 | 2024 | 32 | [8 empty] | 3 | 12 | 12 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.52174 | 0.57143 | 0.22727
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato FCCS | Vision Group | A. Albanese | F. De Pedis | Operations | BackEnd | 210 | 220 | ON GOING | 0 | 2024 | 23 | [8 empty] | 4 | 7 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19048 | 0.30435 | 0.33333 | 0.22727
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato FCCS | Vision Group | A. Albanese | M. Salcini | Consolidated & Tax | Analysis | 210 | 220 | ON GOING | 0 | 2024 | 15 | [8 empty] | 1 | 7 | 7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0.30435 | 0.33333 | 0
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato FCCS | Vision Group | A. Albanese | M. Sorrentino | Consolidated & Tax | Analysis | 210 | 220 | ON GOING | 0 | 2024 | 14 | [6 empty] | 1 |  | 1 | 7 | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0 | 0.047619 | 0.30435 | 0.2381 | 0
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato FCCS | Vision Group | A. Albanese | P. Galvagni | Consolidated & Tax | Tech Lead | 210 | 220 | ON GOING | 0 | 2024 | 19 | [6 empty] | 1 |  | 1 | 7 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0 | 0.047619 | 0.30435 | 0.2381 | 0.22727
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato Managerial / Store P&L | Vision Group | A. Albanese | C. DI LORENZO | Delivery Projects | Analysis | 210 | 220 | ON GOING | 0 | 2024 | 4 | [6 empty] | 1 |  | 1 | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0 | 0.047619 | 0.043478 | 0.047619 | 0
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato Managerial / Store P&L | Vision Group | A. Albanese | L. Franco | Operations | Tech Lead | 210 | 220 | ON GOING | 0 | 2024 | 37 | [6 empty] | 3 | 2 | 13 | 9 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0.16667 | 0.61905 | 0.3913 | 0.2381 | 0.22727
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato Managerial / Store P&L | Vision Group | A. Albanese | L. Mangili | Operations | BackEnd | 210 | 220 | ON GOING | 0 | 2024 | 12 | [7 empty] | 3 | 1 | 1 | 7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.047619 | 0.043478 | 0.33333 | 0
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato Managerial / Store P&L | Vision Group | A. Albanese | M. Favalli | Operations | BackEnd - Junior | 210 | 220 | ON GOING | 0 | 2024 | 35 | [7 empty] | 3 | 12 | 1 | 14 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.57143 | 0.043478 | 0.66667 | 0.22727
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato Managerial / Store P&L | Vision Group | A. Albanese | P. Galvagni | Consolidated & Tax | Analysis | 210 | 220 | ON GOING | 0 | 2024 | 28 | [6 empty] | 3 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0.41667 | 0.2381 | 0.21739 | 0.2381 | 0.22727
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-30 | ABS24349 | ABS24349 | EPM | KPMG - Vision Group - Consolidato Managerial / Store P&L | Vision Group | A. Albanese | S. Preziosa | Delivery Projects | Analysis | 210 | 220 | ON GOING | 0 | 2024 | 23 | [6 empty] | 3 | 5 | 5 | 5 | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0.41667 | 0.2381 | 0.21739 | 0.2381 | 0
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-05-31 | ABS24494 | ABS24494 | EPM | Lux - Job Type - Wave1 | EssilorLuxottica | A. Albanese | A. Albanese | Delivery Projects | BackEnd | 35 | 15 | CLOSED | 1 | 2024 | 2 | [9 empty] | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.047619 | 0
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-05-31 | ABS24494 | ABS24494 | EPM | Lux - Job Type - Wave1 | EssilorLuxottica | A. Albanese | T. Baldi | Operations | BackEnd | 35 | 15 | CLOSED | 1 | 2024 | 1 | [9 empty] | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-01-01 | 2024-06-30 | ABS23458 | APLTENCR | EPM | Push Lux to ESSTECH + New CMFA Region | EssilorLuxottica | A. Albanese | F. Atanasio | Operations | BackEnd | 50 | 66 | CLOSED | 1 | 2024 | 0 | 9 | 5.4 | 2.7 | [9 empty] | 0.5 | 0.27 | 0.12857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-01-01 | 2024-06-30 | ABS23458 | APLTENCR | EPM | Push Lux to ESSTECH + New CMFA Region | EssilorLuxottica | A. Albanese | M. Favalli | Operations | BackEnd | 50 | 66 | CLOSED | 1 | 2024 | 0 | 9 | 5.4 | 2.7 | [9 empty] | 0.5 | 0.27 | 0.12857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-01-01 | 2024-06-30 | ABS23458 | APLTENCR | EPM | Push Lux to ESSTECH + New CMFA Region | EssilorLuxottica | A. Albanese | P. Buonasorte | Operations | BackEnd | 50 | 66 | CLOSED | 1 | 2024 | 0 | 9 | 5.4 | 2.7 | [9 empty] | 0.5 | 0.27 | 0.12857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-06-30 | ABS23496 | AERSSDVF | EPM | Reply Supporto specialistico DM vs FCCS | Reply | A. Albanese | F. Atanasio | Operations | BackEnd | 160 | 123 | CLOSED | 1 | 2024 | 0 | 9 | 1.5 | 11.55 | [9 empty] | 0.5 | 0.075 | 0.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-06-30 | ABS23496 | AERSSDVF | EPM | Reply Supporto specialistico DM vs FCCS | Reply | A. Albanese | F. De Pedis | Operations | BackEnd | 160 | 123 | CLOSED | 1 | 2024 | 16 |  |  |  |  | 1 | 15 | [6 empty] | 0 | 0 | 0 | 0 | 0.05 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Time&Materials | 2024 | 2024-07-01 | 2024-12-31 | ABS24230 | ABS24230 | EPM | Reply Supporto specialistico DM vs FCCS | Reply | A. Albanese | F. De Pedis | Operations | BackEnd | 160 | 130 | ON GOING | 0 | 2024 | 16 | [6 empty] | 5 |  | 6 | 5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0 | 0.28571 | 0.21739 | 0 | 0
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-06-30 | ABS23496 | AERSSDVF | EPM | Reply Supporto specialistico DM vs FCCS | Reply | A. Albanese | M. Favalli | Operations | BackEnd | 160 | 123 | CLOSED | 1 | 2024 | 1 |  |  |  | 19 | 1 | [7 empty] | 0 | 0 | 0 | 0.86364 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Time&Materials | 2024 | 2024-07-01 | 2024-12-31 | ABS24230 | ABS24230 | EPM | Reply Supporto specialistico DM vs FCCS | Reply | A. Albanese | M. Favalli | Operations | BackEnd | 160 | 130 | ON GOING | 0 | 2024 | 9 |  |  |  |  | 1 | 2 | 5 |  | 1 |  |  |  | 0 | 0 | 0 | 0 | 0.05 | 0.1 | 0.21739 | 0 | 0.047619 | 0 | 0 | 0
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-06-30 | ABS23496 | AERSSDVF | EPM | Reply Supporto specialistico DM vs FCCS | Reply | A. Albanese | P. Buonasorte | Operations | BackEnd | 160 | 123 | CLOSED | 1 | 2024 | 27 |  |  |  | 19 | 22 | 5 | [6 empty] | 0 | 0 | 0 | 0.86364 | 1.1 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-09-01 | 2024-11-30 | ABS24384 | ABS24384 | EPM | Tax Normalization | EssilorLuxottica | A. Albanese | A. Albanese | Delivery Projects | PM - Project Governance | 46 | 25 | ON GOING | 0 | 2024 | 4 | [8 empty] | 2 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.086957 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-09-01 | 2024-11-30 | ABS24384 | ABS24384 | EPM | Tax Normalization | EssilorLuxottica | A. Albanese | F. Atanasio | Operations | BackEnd | 46 | 25 | ON GOING | 0 | 2024 | 13 | [9 empty] | 8 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.34783 | 0 | 0.22727
CONTRACT | PRJ |  | 2024 | 2024-09-01 | 2024-11-30 | ABS24384 | ABS24384 | EPM | Tax Normalization | EssilorLuxottica | A. Albanese | F. Lombardini | Consolidated & Tax | Analysis | 46 | 25 | ON GOING | 0 | 2024 | 8 | [8 empty] | 3 | 3 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.13043 | 0.095238 | 0
CONTRACT | PRJ |  | 2024 | 2024-09-01 | 2024-11-30 | ABS24384 | ABS24384 | EPM | Tax Normalization | EssilorLuxottica | A. Albanese | L. Mangili | Operations | BackEnd | 46 | 25 | ON GOING | 0 | 2024 | 6 | [11 empty] | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27273
CONTRACT | PRJ |  | 2024 | 2024-09-01 | 2024-11-30 | ABS24384 | ABS24384 | EPM | Tax Normalization | EssilorLuxottica | A. Albanese | M. Salcini | Consolidated & Tax | Analysis | 46 | 25 | ON GOING | 0 | 2024 | 4 | [9 empty] | 2 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.095238 | 0
CONTRACT | PRJ |  | 2024 | 2024-09-01 | 2024-11-30 | ABS24384 | ABS24384 | EPM | Tax Normalization | EssilorLuxottica | A. Albanese | P. Galvagni | Consolidated & Tax | Analysis | 46 | 25 | ON GOING | 0 | 2024 | 8 | [8 empty] | 3 | 3 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.13043 | 0.095238 | 0
CONTRACT | PRJ |  | 2024 | 2024-09-01 | 2024-11-30 | ABS24384 | ABS24384 | EPM | Tax Normalization | EssilorLuxottica | A. Albanese | P. Pieroni | Operations | Solution Architect | 46 | 25 | ON GOING | 0 | 2024 | 3 | [9 empty] | 2 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.047619 | 0
CONTRACT | PRJ | WATERFALL | 2024 | 2024-09-01 | 2025-12-31 | ABS24401 | ABS24401 | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - EVOLUTIVA DI 2024 | AO FERRARA | A. Coletti | L. Lazzari | SAP ECC | Account Manager | 100 | 258 | ON GOING | 0 | 2024 | 5 | [9 empty] | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.095238 | 0.045455
CONTRACT | PRJ | WATERFALL | 2024 | 2024-09-01 | 2025-12-31 | ABS24401 | ABS24401 | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - EVOLUTIVA DI 2024 | AO FERRARA | A. Coletti | M. Calabrese | Delivery Projects | PM - Project Governance | 100 | 258 | ON GOING | 0 | 2024 | 45 | [9 empty] | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65217 | 0.71429 | 0.68182
CONTRACT | PRJ | WATERFALL | 2024 | 2024-09-01 | 2025-12-31 | ABS24401 | ABS24401 | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - EVOLUTIVA DI 2024 | AO FERRARA | A. Coletti | P. Singh | AREA TECH | BackEnd | 100 | 258 | ON GOING | 0 | 2024 | 2 | [9 empty] | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0 | 0
CONTRACT | PRJ | WATERFALL | 2024 | 2024-09-01 | 2025-12-31 | ABS24401 | ABS24401 | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - EVOLUTIVA DI 2024 | AO FERRARA | A. Coletti | R. Bondi | Operations | FrontEnd | 100 | 258 | ON GOING | 0 | 2024 | 4 | [10 empty] | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.090909
CONTRACT | PRJ | WATERFALL | 2024 | 2024-09-01 | 2025-12-31 | ABS24401 | ABS24401 | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - EVOLUTIVA DI 2024 | AO FERRARA | A. Coletti | R. Tortora | Operations | FrontEnd | 100 | 258 | ON GOING | 0 | 2024 | 25 | [9 empty] | 8 | 2 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.34783 | 0.095238 | 0.68182
CONTRACT | PRJ |  | 2022-2023 | 2023-01-01 | 2023-12-31 | ABS24305 | CT | LOGISTIC | CONTROL TOWER | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | Data Management | 1376 | 911 | CLOSED | 1 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-12-01 | 2024-12-24 | ABS24565 | ABS24565 | LOGISTIC | CONTROL TOWER - Grand Vision Italy and Poland plant integration | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | Data Engineering | 30 | 29 | CLOSED | 1 | 2024 | 8 | [11 empty] | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36364
CONTRACT | PRJ |  | 2024-2025 | 2024-12-01 | 2024-12-24 | ABS24565 | ABS24565 | LOGISTIC | CONTROL TOWER - Grand Vision Italy and Poland plant integration | EssilorLuxottica | A. Cuomo | J. Daci | Operations | BackEnd | 30 | 29 | CLOSED | 1 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-12-01 | 2024-12-24 | ABS24565 | ABS24565 | LOGISTIC | CONTROL TOWER - Grand Vision Italy and Poland plant integration | EssilorLuxottica | A. Cuomo | T. Lazzari | SAP ECC | ECC Developer | 30 | 29 | CLOSED | 1 | 2024 | 2 | [11 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.090909
CONTRACT | PRJ |  | 2024 | 2024-10-01 | 2024-11-30 | ABS24471 | ABS24471 | LOGISTIC | CONTROL TOWER - CONTACT LENSES ENHANCEMENT & NEW BRANDsINTEGRATION | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | Data Engineering | 125 | 120 | CLOSED | 1 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-10-01 | 2024-11-30 | ABS24471 | ABS24471 | LOGISTIC | CONTROL TOWER - CONTACT LENSES ENHANCEMENT & NEW BRANDsINTEGRATION | EssilorLuxottica | A. Cuomo | J. Daci | Operations | BackEnd | 125 | 120 | CLOSED | 1 | 2024 | 8 | [11 empty] | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36364
CONTRACT | PRJ |  | 2024 | 2024-10-01 | 2024-11-30 | ABS24471 | ABS24471 | LOGISTIC | CONTROL TOWER - CONTACT LENSES ENHANCEMENT & NEW BRANDsINTEGRATION | EssilorLuxottica | A. Cuomo | S. Ben Younes | Operations | DataManagement | 125 | 120 | CLOSED | 1 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-10-01 | 2024-11-30 | ABS24471 | ABS24471 | LOGISTIC | CONTROL TOWER - CONTACT LENSES ENHANCEMENT & NEW BRANDsINTEGRATION | EssilorLuxottica | A. Cuomo | T. Lazzari | SAP ECC | ECC Developer | 125 | 120 | CLOSED | 1 | 2024 | 2 | [11 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.090909
CONTRACT | PRJ |  | 2024 | 2024-05-01 | 2024-09-30 | ABS24348 | ABS24348 | LOGISTIC | CONTROL TOWER - ROLLOUT- NEW BRANDsINTEGRATION-CRs | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | Data Engineering | 310 | 271 | CLOSED | 1 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-05-01 | 2024-09-30 | ABS24348 | ABS24348 | LOGISTIC | CONTROL TOWER - ROLLOUT- NEW BRANDsINTEGRATION-CRs | EssilorLuxottica | A. Cuomo | F. Ianni | SAP FIORI | FrontEnd | 310 | 271 | CLOSED | 1 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-05-01 | 2024-09-30 | ABS24348 | ABS24348 | LOGISTIC | CONTROL TOWER - ROLLOUT- NEW BRANDsINTEGRATION-CRs | EssilorLuxottica | A. Cuomo | F. Tarquini | SAP ECC | ECC Analyst | 310 | 271 | CLOSED | 1 | 2024 | 3 | [11 empty] | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13636
CONTRACT | PRJ |  | 2024 | 2024-05-01 | 2024-09-30 | ABS24348 | ABS24348 | LOGISTIC | CONTROL TOWER - ROLLOUT- NEW BRANDsINTEGRATION-CRs | EssilorLuxottica | A. Cuomo | J. Daci | Operations | BackEnd | 310 | 271 | CLOSED | 1 | 2024 | 3 | [11 empty] | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13636
CONTRACT | PRJ |  | 2024 | 2024-05-01 | 2024-09-30 | ABS24348 | ABS24348 | LOGISTIC | CONTROL TOWER - ROLLOUT- NEW BRANDsINTEGRATION-CRs | EssilorLuxottica | A. Cuomo | L. Cariglia | Operations | DataManagement | 310 | 271 | CLOSED | 1 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-05-01 | 2024-09-30 | ABS24348 | ABS24348 | LOGISTIC | CONTROL TOWER - ROLLOUT- NEW BRANDsINTEGRATION-CRs | EssilorLuxottica | A. Cuomo | M. Sabarese | SAP FIORI | FrontEnd | 310 | 271 | CLOSED | 1 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-05-01 | 2024-09-30 | ABS24348 | ABS24348 | LOGISTIC | CONTROL TOWER - ROLLOUT- NEW BRANDsINTEGRATION-CRs | EssilorLuxottica | A. Cuomo | T. Lazzari | SAP ECC | ECC Developer | 310 | 271 | CLOSED | 1 | 2024 | 3 | [11 empty] | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13636
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-04-30 | ABS24204 | ACTW567 | LOGISTIC | Control Tower Wave 5-6-7 | EssilorLuxottica | A. Cuomo | A. Camara | SAP ECC | ECC Analyst | 553 | 519 | CLOSED | 1 | 2024 | 0 | 17 | 21 | 2 | 11 | [8 empty] | 0.94444 | 1.05 | 0.095238 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-04-30 | ABS24204 | ACTW567 | LOGISTIC | Control Tower Wave 5-6-7 | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | Data Engineering | 553 | 519 | CLOSED | 1 | 2024 | 0 | 18 | 2 | 2 | 19 | [8 empty] | 1 | 0.1 | 0.095238 | 0.86364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-04-30 | ABS24204 | ACTW567 | LOGISTIC | Control Tower Wave 5-6-7 | EssilorLuxottica | A. Cuomo | A. Germinario | SAP ECC | ECC Developer | 553 | 519 | CLOSED | 1 | 2024 | 0 |  | 2.5 | 1 | 1 | [8 empty] | 0 | 0.125 | 0.047619 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-04-30 | ABS24204 | ACTW567 | LOGISTIC | Control Tower Wave 5-6-7 | EssilorLuxottica | A. Cuomo | F. Ianni | SAP FIORI | FrontEnd | 553 | 519 | CLOSED | 1 | 2024 | 0 | 2 | 5 | 2 | 1 | [8 empty] | 0.11111 | 0.25 | 0.095238 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-04-30 | ABS24204 | ACTW567 | LOGISTIC | Control Tower Wave 5-6-7 | EssilorLuxottica | A. Cuomo | F. Tarquini | SAP ECC | ECC Analyst | 553 | 519 | CLOSED | 1 | 2024 | 0 | 17 | 19 | 2 | 12 | [8 empty] | 0.94444 | 0.95 | 0.095238 | 0.54545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-04-30 | ABS24204 | ACTW567 | LOGISTIC | Control Tower Wave 5-6-7 | EssilorLuxottica | A. Cuomo | J. Daci | Operations | DataManagement | 553 | 519 | CLOSED | 1 | 2024 | 0 | 6.5 | 13 | 2 | 16 | [8 empty] | 0.36111 | 0.65 | 0.095238 | 0.72727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-04-30 | ABS24204 | ACTW567 | LOGISTIC | Control Tower Wave 5-6-7 | EssilorLuxottica | A. Cuomo | L. Cariglia | Operations | DataManagement | 553 | 519 | CLOSED | 1 | 2024 | 0 | 15 | 16 | 11 | 12 | [8 empty] | 0.83333 | 0.8 | 0.52381 | 0.54545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-04-30 | ABS24204 | ACTW567 | LOGISTIC | Control Tower Wave 5-6-7 | EssilorLuxottica | A. Cuomo | M. Sabarese | SAP FIORI | FrontEnd | 553 | 519 | CLOSED | 1 | 2024 | 0 |  | 3 | 2 | 3 | [8 empty] | 0 | 0.15 | 0.095238 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-04-30 | ABS24204 | ACTW567 | LOGISTIC | Control Tower Wave 5-6-7 | EssilorLuxottica | A. Cuomo | P. Dolzani | SAP ECC | ECC Developer | 553 | 519 | CLOSED | 1 | 2024 | 0 | 18 | 2 | 11 | 11 | [8 empty] | 1 | 0.1 | 0.52381 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-04-30 | ABS24204 | ACTW567 | LOGISTIC | Control Tower Wave 5-6-7 | EssilorLuxottica | A. Cuomo | S. Boriashov | Operations | DataManagement | 553 | 519 | CLOSED | 1 | 2024 | 0 | 18 | 21 | [10 empty] | 1 | 1.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-04-30 | ABS24204 | ACTW567 | LOGISTIC | Control Tower Wave 5-6-7 | EssilorLuxottica | A. Cuomo | T. Lazzari | SAP ECC | ECC Developer | 553 | 519 | CLOSED | 1 | 2024 | 0 | 9 | 21 | 16 | 14 | [8 empty] | 0.5 | 1.05 | 0.7619 | 0.63636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-12-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | A. Cerrato | Operations | BackEnd | 190 | 177 | CLOSED | 1 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-12-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | Data Engineering | 190 | 177 | CLOSED | 1 | 2024 | 3 | [11 empty] | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13636
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-12-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | BackEnd | 190 | 177 | CLOSED | 1 | 2024 | 4 | [11 empty] | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18182
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-12-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | A. Strada | Operations | BackEnd | 190 | 177 | CLOSED | 1 | 2024 | 1 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.045455
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-12-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | A. Torone | Delivery AMS | Data Management | 190 | 177 | CLOSED | 1 | 2024 | 3 | [11 empty] | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13636
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-12-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | C. Paz | Delivery Projects | PMO - Project Management Officer | 190 | 177 | CLOSED | 1 | 2024 | 1 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.045455
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-12-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | F. Reale | Operations | FrontEnd | 190 | 177 | CLOSED | 1 | 2024 | 17 | [11 empty] | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77273
CONTRACT | PRJ |  | 2024 |  |  | ABS24403 | LUCY | Lucy | Lucy PTP AI: Invoices Classification Suggestion | EssilorLuxottica | A. Graziani | A. Imbimbo | Operations | Data Scientist | 150 | 70 | ON GOING | 0 | 2024 | 73 | [5 empty] | 6 | 5 |  | 14 | 17 | 17 | 14 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.21739 | 0 | 0.66667 | 0.73913 | 0.80952 | 0.63636
CONTRACT | PRJ |  | 2024 |  |  | ABS24403 | LUCY | Lucy | Lucy PTP AI: Invoices Classification Suggestion | EssilorLuxottica | A. Graziani | F. Malvezzi | Operations | Data Scientist | 150 | 70 | ON GOING | 0 | 2024 | 13 | [8 empty] | 4 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19048 | 0.17391 | 0.19048 | 0.045455
CONTRACT | PRJ |  | 2024 |  |  | ABS24403 | LUCY | Lucy | Lucy PTP AI: Invoices Classification Suggestion | EssilorLuxottica | A. Graziani | G. Sabbatini | Operations | Data Engineering | 150 | 70 | ON GOING | 0 | 2024 | 5 | [6 empty] | 1 |  | 3 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0 | 0.14286 | 0.043478 | 0 | 0
CONTRACT | PRJ |  | 2024 |  |  | ABS24403 | LUCY | Lucy | Lucy PTP AI: Invoices Classification Suggestion | EssilorLuxottica | A. Graziani | G. Sironi | Operations | Team Leadership | 150 | 70 | ON GOING | 0 | 2024 | 22 | [5 empty] | 3 | 4 |  | 4 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.17391 | 0 | 0.19048 | 0.21739 | 0.14286 | 0.13636
CONTRACT | PRJ |  | 2024 |  |  | ABS24403 | LUCY | Lucy | Lucy PTP AI: Invoices Classification Suggestion | EssilorLuxottica | A. Graziani | M. Gomitoni | Operations | Tech Lead | 150 | 70 | ON GOING | 0 | 2024 | 14 | [5 empty] | 5 | 5 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.21739 | 0 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | PRJ |  | 2024 |  |  | ABS24403 | LUCY | Lucy | Lucy PTP AI: Invoices Classification Suggestion | EssilorLuxottica | A. Graziani | V. Echarry | Operations | Data Scientist | 150 | 70 | ON GOING | 0 | 2024 | 23 | [8 empty] | 4 | 7 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19048 | 0.30435 | 0.33333 | 0.22727
CONTRACT | PRJ |  | 2024 |  |  |  |  | Lucy | Lucy Vendor Matching ML | EssilorLuxottica | A. Graziani | A. Imbimbo | Operations | Data Scientist | 0 | 0 | PROPOSAL | 0 | 2024 | 9 | [9 empty] | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0.14286 | 0.13636
CONTRACT | PRJ |  | 2024 |  |  |  |  | Lucy | Lucy Vendor Matching ML | EssilorLuxottica | A. Graziani | F. Malvezzi | Operations | Data Scientist | 0 | 0 | PROPOSAL | 0 | 2024 | 15 | [9 empty] | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.2381 | 0.22727
CONTRACT | PRJ |  | 2024 |  |  |  |  | Lucy | Lucy Vendor Matching ML | EssilorLuxottica | A. Graziani | G. Sironi | Operations | Team Leadership | 0 | 0 | PROPOSAL | 0 | 2024 | 6 | [9 empty] | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.095238 | 0.090909
CONTRACT | PRJ |  | 2024 |  |  |  |  | Lucy | Lucy Vendor Matching ML | EssilorLuxottica | A. Graziani | M. Gomitoni | Operations | Tech Lead | 0 | 0 | PROPOSAL | 0 | 2024 | 9 | [9 empty] | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0.14286 | 0.13636
CONTRACT | PRJ |  | 2024 |  |  |  |  | Lucy | Lucy Vendor Matching ML | EssilorLuxottica | A. Graziani | V. Echarry | Operations | Data Scientist | 0 | 0 | PROPOSAL | 0 | 2024 | 15 | [9 empty] | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.2381 | 0.22727
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24049 | ALAFDP2 | FINANCE | AMS FRAUD Detection Platform 2024 | EssilorLuxottica | A. Morterra | A. Crescimone | Operations | BackEnd | 0 | 0 | CLOSED | 0 | 2024 | 24 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.15 | 0.15 | 0.13043 | 0.25 | 0.14286 | 0.13043 | 0.14286 | 0.13636
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24049 | ALAFDP2 | FINANCE | AMS FRAUD Detection Platform 2024 | EssilorLuxottica | A. Morterra | A. SAIJA | Operations | BackEnd | 0 | 0 | CLOSED | 0 | 2024 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24049 | ALAFDP2 | FINANCE | AMS FRAUD Detection Platform 2024 | EssilorLuxottica | A. Morterra | G. D'Amanti | Operations | BackEnd | 0 | 0 | ON GOING | 0 | 2024 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 |  | 0.027778 | 0.025 | 0.02381 | 0.022727 | 0.025 | 0.025 | 0.021739 | 0.041667 | 0.02381 | 0.021739 | 0.047619 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24049 | ALAFDP2 | FINANCE | AMS FRAUD Detection Platform 2024 | EssilorLuxottica | A. Morterra | G. Luongo | Delivery AMS | PM - Project Governance | 0 | 0 | CLOSED | 0 | 2024 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24049 | ALAFDP2 | FINANCE | AMS FRAUD Detection Platform 2024 | EssilorLuxottica | A. Morterra | L. Gullotto | Operations | BackEnd | 0 | 0 | CLOSED | 0 | 2024 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.027778 | 0.025 | 0.02381 | 0.022727 | 0.025 | 0.025 | 0.021739 | 0.041667 | 0.02381 | 0.021739 | 0.02381 | 0.022727
CONTRACT | AMS |  | 2024 |  |  | ABS24089 | ABS24089 | FINANCE | FDP - Fraud Detection Plathform 2024 | EssilorLuxottica | A. Morterra | A. Imbimbo | Operations | Data Scientist | 110 | 0 | ON GOING | 0 | 2024 | 19 |  |  | 4 | 4 | 4 | 4 | 2 | 1 | 3 | 1 | 1 | 3 | 0 | 0 | 0.19048 | 0.18182 | 0.2 | 0.2 | 0.086957 | 0.083333 | 0.14286 | 0.043478 | 0.047619 | 0.13636
CONTRACT | AMS |  | 2024 |  |  | ABS24089 | ABS24089 | FINANCE | FDP - Fraud Detection Plathform 2024 | EssilorLuxottica | A. Morterra | G. Sabbatini | Operations | Data Engineering | 110 | 0 | ON GOING | 0 | 2024 | 21 |  |  | 2 | 2 | 2 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 0 | 0 | 0.095238 | 0.090909 | 0.1 | 0.15 | 0.086957 | 0.16667 | 0.14286 | 0.13043 | 0.14286 | 0.13636
CONTRACT | AMS |  | 2024 |  |  | ABS24089 | ABS24089 | FINANCE | FDP - Fraud Detection Plathform 2024 | EssilorLuxottica | A. Morterra | G. Sironi | Operations | PM - Project Governance Support | 110 | 0 | ON GOING | 0 | 2024 | 20 |  |  | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 0 | 0 | 0.047619 | 0.045455 | 0.1 | 0.1 | 0.086957 | 0.16667 | 0.14286 | 0.13043 | 0.14286 | 0.13636
CONTRACT | AMS |  | 2024 |  |  | ABS24089 | ABS24089 | FINANCE | FDP - Fraud Detection Plathform 2024 | EssilorLuxottica | A. Morterra | L. Cariglia | Operations | DataManagement | 110 | 0 | ON GOING | 0 | 2024 | 29 |  |  | 4 | 4 | 5 | 8 | 9 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | 0.19048 | 0.18182 | 0.25 | 0.4 | 0.3913 | 0.25 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS |  | 2024 |  |  | ABS24089 | ABS24089 | FINANCE | FDP - Fraud Detection Plathform 2024 | EssilorLuxottica | A. Morterra | M. Gomitoni | Operations | Tech Lead | 110 | 0 | ON GOING | 0 | 2024 | 6 | [5 empty] | 1 | 1 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.043478 | 0 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS |  | 2024 |  |  | ABS24089 | ABS24089 | FINANCE | FDP - Fraud Detection Plathform 2024 | EssilorLuxottica | A. Morterra | V. Echarry | Operations | Data Scientist | 110 | 0 | ON GOING | 0 | 2024 | 19 |  |  | 4 | 4 | 4 | 4 | 2 | 3 | 2 | 1 | 1 | 2 | 0 | 0 | 0.19048 | 0.18182 | 0.2 | 0.2 | 0.086957 | 0.25 | 0.095238 | 0.043478 | 0.047619 | 0.090909
PROSPECT | PRESALES - DELIVERY |  | 2024 |  |  |  |  | FINANCE/DS | Outlier Detection - PO & I | EssilorLuxottica | A. Morterra | A. Imbimbo | Operations | Data Scientist | 0 | 0 | PROPOSAL | 0 | 2024 | 7 |  |  |  |  | 2 | 3 | 2 | [5 empty] | 0 | 0 | 0 | 0 | 0.1 | 0.15 | 0.086957 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRESALES - DELIVERY |  | 2024 |  |  |  |  | FINANCE/DS | Outlier Detection - PO & I | EssilorLuxottica | A. Morterra | G. Sabbatini | Operations | Data Engineering | 0 | 0 | PROPOSAL | 0 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRESALES - DELIVERY |  | 2024 |  |  |  |  | FINANCE/DS | Outlier Detection - PO & I | EssilorLuxottica | A. Morterra | G. Sironi | Operations | PM - Project Governance | 0 | 0 | PROPOSAL | 0 | 2024 | 3 |  |  |  |  | 1 | 1 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0.05 | 0.05 | 0.043478 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRESALES - DELIVERY |  | 2024 |  |  |  |  | FINANCE/DS | Outlier Detection - PO & I | EssilorLuxottica | A. Morterra | L. Cariglia | Operations | DataManagement | 0 | 0 | PROPOSAL | 0 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRESALES - DELIVERY |  | 2024 |  |  |  |  | FINANCE/DS | Outlier Detection - PO & I | EssilorLuxottica | A. Morterra | M. Gomitoni | Operations | Tech Lead | 0 | 0 | PROPOSAL | 0 | 2024 | 2 | [5 empty] | 1 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.043478 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRESALES - DELIVERY |  | 2024 |  |  |  |  | FINANCE/DS | Outlier Detection - PO & I | EssilorLuxottica | A. Morterra | V. Echarry | Operations | Data Scientist | 0 | 0 | PROPOSAL | 0 | 2024 | 7 |  |  |  |  | 4 | 2 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0.2 | 0.1 | 0.043478 | 0 | 0 | 0 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  |  | ATD | OTHER | Formazione | Abstract | A. Strada | A. Crescimone | Operations | PM - Project Governance | 0 | 0 |  | 0 | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  |  | ATD | OTHER | Formazione | Abstract | A. Strada | A. Cuomo | Operations | PM - Project Governance | 0 | 0 |  | 0 | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  |  | ATD | OTHER | Formazione | Abstract | A. Strada | A. Saija | Operations | PM - Project Governance | 0 | 0 |  | 0 | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  |  | ATD | OTHER | Formazione | Abstract | A. Strada | A. Strada | Operations | PM - Project Governance | 0 | 0 |  | 0 | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  |  | ATD | OTHER | Formazione | Abstract | A. Strada | F. Reale | Operations | PM - Project Governance | 0 | 0 |  | 0 | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  |  | ATD | OTHER | Formazione | Abstract | A. Strada | F. Reale | Operations | backEnd | 0 | 0 |  | 0 | 2024 | 4 | [5 empty] | 2 | 2 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0 | 0 | 0 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  |  | ATD | OTHER | Formazione | Abstract | A. Strada | G. D'Amanti | Operations | PM - Project Governance | 0 | 0 |  | 0 | 2024 | 8 | [5 empty] | 2 | 2 |  | 2 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0 | 0.095238 | 0.086957 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  |  | ATD | OTHER | Formazione | Abstract | A. Strada | J. Daci | Operations | PM - Project Governance | 0 | 0 |  | 0 | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  |  | ATD | OTHER | Formazione | Abstract | A. Strada | L. Cariglia | Operations | PM - Project Governance | 0 | 0 |  | 0 | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  |  | ATD | OTHER | Formazione | Abstract | A. Strada | L. Gullotto | Operations | PM - Project Governance | 0 | 0 |  | 0 | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  |  | ATD | OTHER | Formazione | Abstract | A. Strada | M. Migliorati | Operations | PM - Project Governance | 0 | 0 |  | 0 | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  |  | ATD | OTHER | Formazione | Abstract | A. Strada | M. Vimercati | Operations | PM - Project Governance | 0 | 0 |  | 0 | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  |  | ATD | OTHER | Formazione | Abstract | A. Strada | R. Alves | Operations | PM - Project Governance | 0 | 0 |  | 0 | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  |  | ATD | OTHER | Formazione | Abstract | A. Strada | R. Bondi | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  |  | ATD | OTHER | Formazione | Abstract | A. Strada | R. Grandi | Operations | Data Management | 0 | 0 |  | 0 | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  |  | ATD | OTHER | Formazione | Abstract | A. Strada | S. Ben Younes | Operations | PM - Project Governance | 0 | 0 |  | 0 | 2024 | 12 | [5 empty] | 2 | 2 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | PRJ |  | 2024 | 2024-02-01 | 2024-02-29 | ABS24110 | AGCBSUB | CRM/CS | Global CS - BI Streaming-UK Brands | EssilorLuxottica | A. Torone | A. Strada | Operations | DataManagement | 35 | 30 | CLOSED | 1 | 2024 | 0 |  | 12 |  | 5 | [8 empty] | 0 | 0.6 | 0 | 0.22727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-02-01 | 2024-02-29 | ABS24110 | AGCBSUB | CRM/CS | Global CS - BI Streaming-UK Brands | EssilorLuxottica | A. Torone | A. Torone | Delivery AMS | PM - Project Governance | 35 | 30 | CLOSED | 1 | 2024 | 0 |  | 0.25 | 0.25 | 0.25 | [8 empty] | 0 | 0.0125 | 0.011905 | 0.011364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-02-01 | 2024-02-29 | ABS24110 | AGCBSUB | CRM/CS | Global CS - BI Streaming-UK Brands | EssilorLuxottica | A. Torone | M. Porcu | Operations | BackEnd | 35 | 30 | CLOSED | 1 | 2024 | 0 |  | 1.5 | 8 | [9 empty] | 0 | 0.075 | 0.38095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-02-01 | 2024-02-29 | ABS24110 | AGCBSUB | CRM/CS | Global CS - BI Streaming-UK Brands | EssilorLuxottica | A. Torone | P. Anzellotti | Operations | BackEnd | 35 | 30 | CLOSED | 1 | 2024 | 0 |  |  | 2.75 | [9 empty] | 0 | 0 | 0.13095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-12-31 | ABS24347 | BS24163 | CRM/CS | Global CS Enhancements 2024 | EssilorLuxottica | A. Torone | A. Strada | Operations | BackEnd | 48 | 38 | CLOSED | 1 | 2024 | 0 | 1 | [11 empty] | 0.055556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-04-30 | ABS24347 | BS24163 | CRM/CS | Global CS Enhancements 2024 | EssilorLuxottica | A. Torone | A. Torone | Delivery AMS | PM - Project Governance | 48 | 38 | CLOSED | 1 | 2024 | 0 | 1 | 1.5 | 1.5 | 0.5 | [8 empty] | 0.055556 | 0.075 | 0.071429 | 0.022727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-12-31 | ABS24347 | BS24163 | CRM/CS | Global CS Enhancements 2024 | EssilorLuxottica | A. Torone | D. Scalia | Operations | BackEnd | 48 | 38 | CLOSED | 1 | 2024 | 0 | 5.5 | 4.625 | 3.25 | [9 empty] | 0.30556 | 0.23125 | 0.15476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-12-31 | ABS24347 | BS24163 | CRM/CS | Global CS Enhancements 2024 | EssilorLuxottica | A. Torone | G. Esposito | AREA TECH | BackEnd | 48 | 38 | CLOSED | 1 | 2024 | 0 |  |  | 2.875 | [9 empty] | 0 | 0 | 0.1369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-12-31 | ABS24347 | BS24163 | CRM/CS | Global CS Enhancements 2024 | EssilorLuxottica | A. Torone | M. Porcu | Operations | BackEnd | 48 | 38 | CLOSED | 1 | 2024 | 0 | 0.5 |  |  | 1.3125 | [8 empty] | 0.027778 | 0 | 0 | 0.059659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-12-31 | ABS24347 | BS24163 | CRM/CS | Global CS Enhancements 2024 | EssilorLuxottica | A. Torone | M. Toci | Operations | BackEnd | 48 | 38 | CLOSED | 1 | 2024 | 0 |  |  | 9.625 | 3.5 | [8 empty] | 0 | 0 | 0.45833 | 0.15909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-12-31 | ABS24347 | BS24163 | CRM/CS | Global CS Enhancements 2024 | EssilorLuxottica | A. Torone | P. Anzellotti | Operations | BackEnd | 48 | 38 | CLOSED | 1 | 2024 | 0 |  |  |  | 1.25 | [8 empty] | 0 | 0 | 0 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-01-31 | 2024-03-31 | ABS24104 | ABS24104 | CRM/CS | Global CS-B2B | EssilorLuxottica | A. Torone | A. Torone | Delivery AMS | PM - Project Governance | 24 | 46 | CLOSED | 1 | 2024 | 0 | 0.25 | 0.25 | 0.25 | 0.25 | [8 empty] | 0.013889 | 0.0125 | 0.011905 | 0.011364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-01-31 | 2024-03-31 | ABS24104 | ABS24104 | CRM/CS | Global CS-B2B | EssilorLuxottica | A. Torone | D. Scalia | Operations | BackEnd | 24 | 46 | CLOSED | 1 | 2024 | 0 | 0.875 | 8.75 | 4.375 | [9 empty] | 0.048611 | 0.4375 | 0.20833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-01-31 | 2024-03-31 | ABS24104 | ABS24104 | CRM/CS | Global CS-B2B | EssilorLuxottica | A. Torone | M. Porcu | Operations | BackEnd | 24 | 46 | CLOSED | 1 | 2024 | 0 | 1.8125 | 1.5625 | 4.9375 | 0.9375 | [8 empty] | 0.10069 | 0.078125 | 0.23512 | 0.042614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-01-31 | 2024-03-31 | ABS24104 | ABS24104 | CRM/CS | Global CS-B2B | EssilorLuxottica | A. Torone | M. Toci | Operations | BackEnd | 24 | 46 | CLOSED | 1 | 2024 | 0 |  |  | 3.5 | 11.125 | [8 empty] | 0 | 0 | 0.16667 | 0.50568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-01-31 | 2024-03-31 | ABS24104 | ABS24104 | CRM/CS | Global CS-B2B | EssilorLuxottica | A. Torone | P. Anzellotti | Operations | Technical Leader | 24 | 46 | CLOSED | 1 | 2024 | 0 |  |  |  | 3.5 | [8 empty] | 0 | 0 | 0 | 0.15909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2023-11-27 | 2024-03-31 | ABS23340 | LMD2 | OTHER | LUX_Marginality_Discounts_CMD_WF_2023 | EssilorLuxottica | A. Torone | A. Torone | Delivery AMS | PM - Project Governance | 45 | 65 | CLOSED | 1 | 2024 | 1.25 | 0.3125 | 1.4375 | 1 | 0.25 | 0.25 | 0.5 | 0.5 | [5 empty] | 0.017361 | 0.071875 | 0.047619 | 0.011364 | 0.0125 | 0.025 | 0.021739 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2023-11-27 | 2024-03-31 | ABS23340 | LMD2 | OTHER | LUX_Marginality_Discounts_CMD_WF_2023 | EssilorLuxottica | A. Torone | P. Singh | AREA TECH | DataManagement | 45 | 65 | CLOSED | 1 | 2024 | 0 | 13.875 | 14.125 | 8 | 7 | [8 empty] | 0.77083 | 0.70625 | 0.38095 | 0.31818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2023-11-27 | 2024-03-31 | ABS23340 | LMD2 | OTHER | LUX_Marginality_Discounts_CMD_WF_2023 | EssilorLuxottica | A. Torone | R. Alves | Operations | FrontEnd | 45 | 65 | CLOSED | 1 | 2024 | 2.125 | 0.625 | 3.6875 | 3.5938 | 3.3963 | 1.625 |  | 0.5 | [5 empty] | 0.034722 | 0.18438 | 0.17113 | 0.15438 | 0.08125 | 0 | 0.021739 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2023-11-27 | 2024-03-31 | ABS23340 | LMD2 | OTHER | LUX_Marginality_Discounts_CMD_WF_2023 | EssilorLuxottica | A. Torone | S. Guastavigna | SAP ECC | Analysis | 45 | 65 | CLOSED | 1 | 2024 | 0 | 2.7 | 3.15 | [10 empty] | 0.15 | 0.1575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Out per Permesso MBA |  | C. Paz | C. Paz | Delivery Projects |  | 50 | 0 |  | 0 | 2024 | 31 | 3.6 | 4.2 | 4.2 | 3.8 | 4 | 6 | 5 |  | 4 | 4 | 4 | 4 | 0.2 | 0.21 | 0.2 | 0.17273 | 0.2 | 0.3 | 0.21739 | 0 | 0.19048 | 0.17391 | 0.19048 | 0.18182
CONTRACT | PRJ |  |  |  |  | ABS23334 | ALESCP | BIP | Eliot Short Trip | EssilorLuxottica | C. Piraccini | C. Piraccini | Operations | BackEnd | 0 | 0 | CLOSED | 1 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  |  |  |  | ABS23334 | ALESCP | BIP | Eliot Short Trip | EssilorLuxottica | C. Piraccini | M. Regini | Operations | BackEnd | 0 | 0 | CLOSED | 1 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRESALES - DELIVERY |  | 2024 | 2024-07-01 | 2024-11-01 |  |  | CRM/DS | CRM-User Scoring Model | EDISON | F. Ferri | G. Sironi | Operations | PM - Project Governance | 8 | 8 | PROPOSAL | 0 | 2024 | 5 | [6 empty] | 1 | 1 | 2 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.083333 | 0.095238 | 0.043478 | 0 | 0
PROSPECT | PRESALES - DELIVERY |  | 2024 | 2024-07-01 | 2024-11-01 |  |  | CRM/DS | CRM-User Scoring Model | EDISON | F. Ferri | M. Gomitoni | Operations | Tech Lead | 8 | 8 | PROPOSAL | 0 | 2024 | 5 | [6 empty] | 1 | 1 | 2 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.083333 | 0.095238 | 0.043478 | 0 | 0
CONTRACT | AMS |  | 2024 | 2024-07-01 | 2024-12-31 | ABS24060 | ABS24060 | EPM | RDM - AMS Talentia | RDM | F. Lombardini | F. Lombardini | Consolidated & Tax | PM - Project Governance | 40 | 8 | ON GOING | 0 | 2024 | 11 | [6 empty] | 2 | 1 | 1 | 4 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.083333 | 0.047619 | 0.17391 | 0.047619 | 0.090909
CONTRACT | AMS |  | 2024 | 2024-07-01 | 2024-12-31 | ABS24060 | ABS24060 | EPM | RDM - AMS Talentia | RDM | F. Lombardini | G. Picerno | Consolidated & Tax | BackEnd | 40 | 8 | ON GOING | 0 | 2024 | 11 | [6 empty] | 2 | 1 | 1 | 4 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.083333 | 0.047619 | 0.17391 | 0.047619 | 0.090909
CONTRACT | AMS |  | 2024 | 2023-07-01 | 2024-06-30 | ABS24334 | ABS24334 | EPM | Thom Browne | Thom Browne | F. Lombardini | F. Lombardini | Consolidated & Tax | Analysis | 16 | 0 | ON GOING | 0 | 2024 | 4 | 1 | 1 | 1 | 1 | 2 | 2 | [6 empty] | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024-2025 | 2024-07-01 | 2025-06-30 | ABS24334 | ABS24334 | EPM | Thom Browne | Thom Browne | F. Lombardini | F. Lombardini | Consolidated & Tax | Analysis | 20 | 0 | ON GOING | 0 | 2024 | 5 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS |  | 2024 | 2023-07-01 | 2024-06-30 | ABS24334 | ABS24334 | EPM | Thom Browne | Thom Browne | F. Lombardini | G. Picerno | Consolidated & Tax | Analysis | 16 | 0 | ON GOING | 0 | 2024 | 4 | 1 | 1 | 1 | 1 | 2 | 2 | [6 empty] | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024-2025 | 2024-07-01 | 2025-06-30 | ABS24334 | ABS24334 | EPM | Thom Browne | Thom Browne | F. Lombardini | G. Picerno | Consolidated & Tax | Analysis | 20 | 0 | ON GOING | 0 | 2024 | 5 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24325 | BS24108 | Retail | DMV AMS 2024 | EssilorLuxottica | F. Pinnelli | A. Torone | Delivery AMS | Project Governance | 164 | 0 | ON GOING | 0 | 2024 | 24.5 | [8 empty] | 0.5 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02381 | 0.34783 | 0.38095 | 0.36364
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24325 | BS24108 | Retail | DMV AMS 2024 | EssilorLuxottica | F. Pinnelli | S. Calvi | Operations | Data Management | 164 | 0 | ON GOING | 0 | 2024 | 9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 1 |  |  |  | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.41667 | 0.047619 | 0 | 0 | 0
INTERNAL PRJ | AMS | Waterfall | 2024 | 2024-08-01 | 2024-12-31 |  | IAA | QA | Quality Assurance | EssilorLuxottica | F. Pinnelli | G. Picerno | Consolidated & Tax | Analysis | 220 | 0 | ON GOING | 0 | 2024 | 38 | [8 empty] | 4 | 4 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19048 | 0.17391 | 0.71429 | 0.68182
INTERNAL PRJ | AMS | Waterfall | 2024 | 2024-08-01 | 2024-12-31 |  | IAA | QA | Quality Assurance | EssilorLuxottica | F. Pinnelli | L. Stefanelli | Delivery Maintenance | Tester | 220 | 0 | ON GOING | 0 | 2024 | 19 | [10 empty] | 2 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.77273
INTERNAL PRJ | AMS | Waterfall | 2024 | 2024-08-01 | 2024-12-31 |  | IAA | QA | Quality Assurance | EssilorLuxottica | F. Pinnelli | M. Strada | Delivery Maintenance | Tester | 220 | 0 | ON GOING | 0 | 2024 | 19 | [10 empty] | 2 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.77273
INTERNAL PRJ | AMS | Waterfall | 2024 | 2024-08-01 | 2024-12-31 |  | IAA | QA | Quality Assurance | EssilorLuxottica | F. Pinnelli | M. Vianelli | Delivery Projects | Analysis | 220 | 0 | ON GOING | 0 | 2024 | 16 | [8 empty] | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19048 | 0.17391 | 0.19048 | 0.18182
PROSPECT | AMS |  | 2025 | 2025-01-01 | 2025-12-31 |  |  | BIP | BIP Projects 2025 | EssilorLuxottica | F. Taita | A. Seira | Operations | Backend | 620 | 0 | PROPOSAL | 0 | 2024 | 7 | [11 empty] | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.31818
PROSPECT | AMS |  | 2025 | 2025-01-01 | 2025-12-31 |  |  | BIP | BIP Projects 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | DataManagement | 620 | 0 | PROPOSAL | 0 | 2024 | 4 | [11 empty] | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18182
PROSPECT | AMS |  | 2025 | 2025-01-01 | 2025-12-31 |  |  | BIP | BIP Projects 2025 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | Backend | 620 | 0 | PROPOSAL | 0 | 2024 | 9 | [11 empty] | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.40909
PROSPECT | AMS |  | 2025 | 2025-01-01 | 2025-12-31 |  |  | BIP | BIP Projects 2025 | EssilorLuxottica | F. Taita | T. Baldi | Operations | Backend | 620 | 0 | PROPOSAL | 0 | 2024 | 6 | [11 empty] | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27273
CONTRACT | AMS |  | 2024 | 2024-05-01 | 2024-12-31 | ABS24219 | ABS24219 | BIP | Ecommerce Rollout support 2 quater 2024 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | DataManagement | 70 | 36 | CLOSED | 1 | 2024 | 16 |  |  |  |  | 8 | 8 | [6 empty] | 0 | 0 | 0 | 0 | 0.4 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2024-05-01 | 2024-12-31 | ABS24219 | ABS24219 | BIP | Ecommerce Rollout support 2 quater 2024 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | DataManagement | 70 | 36 | CLOSED | 1 | 2024 | 19 |  |  |  |  | 18 | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0.9 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2024-05-01 | 2024-12-31 | ABS24219 | ABS24219 | BIP | Ecommerce Rollout support 2 quater 2024 | EssilorLuxottica | F. Taita | R. Grienti | Operations | DataManagement | 70 | 36 | CLOSED | 1 | 2024 | 3 |  |  |  |  | 1 | 2 | [6 empty] | 0 | 0 | 0 | 0 | 0.05 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2024-05-01 | 2024-12-31 | ABS24219 | ABS24219 | BIP | Ecommerce Rollout support 2 quater 2024 | EssilorLuxottica | F. Taita | T. Baldi | Operations | DataManagement | 70 | 36 | CLOSED | 1 | 2024 | 17 |  |  |  |  | 9 | 8 | [6 empty] | 0 | 0 | 0 | 0 | 0.45 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2024-06-17 | 2024-08-31 | ABS24323 | ABS24323 | BIP | Ecommerce Rollout support 3rd quarter 2024 | EssilorLuxottica | F. Taita | A. Cerrato | Operations | DataManagement | 55 | 55 | CLOSED | 1 | 2024 | 5 | [5 empty] | 3 | 2 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.086957 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2024-06-17 | 2024-08-31 | ABS24323 | ABS24323 | BIP | Ecommerce Rollout support 3rd quarter 2024 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | DataManagement | 55 | 55 | CLOSED | 1 | 2024 | 5 | [5 empty] | 4 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2024-06-17 | 2024-08-31 | ABS24323 | ABS24323 | BIP | Ecommerce Rollout support 3rd quarter 2024 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | DataManagement | 55 | 55 | CLOSED | 1 | 2024 | 23 | [5 empty] | 8 | 15 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.65217 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2024-06-17 | 2024-08-31 | ABS24323 | ABS24323 | BIP | Ecommerce Rollout support 3rd quarter 2024 | EssilorLuxottica | F. Taita | R. Grienti | Operations | DataManagement | 55 | 55 | CLOSED | 1 | 2024 | 5 | [5 empty] | 3 | 2 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.086957 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2024-06-17 | 2024-08-31 | ABS24323 | ABS24323 | BIP | Ecommerce Rollout support 3rd quarter 2024 | EssilorLuxottica | F. Taita | T. Baldi | Operations | DataManagement | 55 | 55 | CLOSED | 1 | 2024 | 24 | [5 empty] | 8 | 16 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.69565 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2024-09-01 | 2024-12-31 | ABS24371 | ABS24371 | BIP | Ecommerce Rollout support 4Q 2024 | EssilorLuxottica | F. Taita | A. Seira | Operations | Backend | 56 | 47 | CLOSED | 1 | 2024 | 19 | [7 empty] | 1 | 18 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.083333 | 0.85714 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2024-09-01 | 2024-12-31 | ABS24371 | ABS24371 | BIP | Ecommerce Rollout support 4Q 2024 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | DataManagement | 56 | 47 | CLOSED | 1 | 2024 | 2 | [7 empty] | 1 | 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.083333 | 0.047619 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2024-09-01 | 2024-12-31 | ABS24371 | ABS24371 | BIP | Ecommerce Rollout support 4Q 2024 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | Backend | 56 | 47 | CLOSED | 1 | 2024 | 18 | [7 empty] | 3 | 15 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.71429 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2024-09-01 | 2024-12-31 | ABS24371 | ABS24371 | BIP | Ecommerce Rollout support 4Q 2024 | EssilorLuxottica | F. Taita | T. Baldi | Operations | Backend | 56 | 47 | CLOSED | 1 | 2024 | 18 | [7 empty] | 1 | 17 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.083333 | 0.80952 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2023-12-01 | 2024-12-31 | ABS24053 | ALDDRES2 | BIP | Ecommerce Rollout Supporto 2024 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | DataManagement | 200 | 200 | CLOSED | 1 | 2024 | 0 | 2 | 2 | 2 | 16.15 | [8 empty] | 0.11111 | 0.1 | 0.095238 | 0.73409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2023-12-01 | 2024-12-31 | ABS24053 | ALDDRES2 | BIP | Ecommerce Rollout Supporto 2024 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | DataManagement | 200 | 200 | CLOSED | 1 | 2024 | 0 | 19 | 19 | 19 | 17 | [8 empty] | 1.0556 | 0.95 | 0.90476 | 0.77273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2023-12-01 | 2024-12-31 | ABS24053 | ALDDRES2 | BIP | Ecommerce Rollout Supporto 2024 | EssilorLuxottica | F. Taita | R. Grienti | Operations | DataManagement | 200 | 200 | CLOSED | 1 | 2024 | 5 |  |  |  | 5 | 5 | [7 empty] | 0 | 0 | 0 | 0.22727 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2023-12-01 | 2024-12-31 | ABS24053 | ALDDRES2 | BIP | Ecommerce Rollout Supporto 2024 | EssilorLuxottica | F. Taita | T. Baldi | Operations | DataManagement | 200 | 200 | CLOSED | 1 | 2024 | 9 | 5 |  | 17 | 17 | 9 | [7 empty] | 0.27778 | 0 | 0.80952 | 0.77273 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2022-01-01 | 2024-05-31 | ABS24292 | ALB | LOGISTIC | LMS BRASILE - LIGHT | EssilorLuxottica | F. Taita | C. Piraccini | Operations | Data Engineering | 188 | 180 | CLOSED | 0 | 2024 | 56.5 | 1.8 | 8.5 | 16 | 14.3 | 17 | 9 | 8 | 3.5 | 5 | 6 | 4 | 4 | 0.1 | 0.425 | 0.7619 | 0.65 | 0.85 | 0.45 | 0.34783 | 0.29167 | 0.2381 | 0.26087 | 0.19048 | 0.18182
CONTRACT | PRJ | Waterfall | 2024 | 2022-01-01 | 2024-05-31 | ABS24292 | ALB | LOGISTIC | LMS BRASILE - LIGHT | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | DataManagement | 188 | 180 | CLOSED | 0 | 2024 | 9 | [8 empty] | 2 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.13043 | 0.095238 | 0.090909
CONTRACT | PRJ | Waterfall | 2024 | 2022-01-01 | 2024-05-31 | ABS24292 | ALB | LOGISTIC | LMS BRASILE - LIGHT | EssilorLuxottica | F. Taita | M. Regini | Operations | BackEnd | 188 | 180 | CLOSED | 0 | 2024 | 49.5 |  | 6.4 | 17 | 11 | 13.5 | 15 | 6 |  | 4 | 4 | 3 | 4 | 0 | 0.32 | 0.80952 | 0.5 | 0.675 | 0.75 | 0.26087 | 0 | 0.19048 | 0.17391 | 0.14286 | 0.18182
CONTRACT | PRJ | Waterfall | 2024 | 2022-01-01 | 2024-05-31 | ABS24292 | ALB | LOGISTIC | LMS BRASILE - LIGHT | EssilorLuxottica | F. Taita | R. Bondi | Operations | Data Engineering | 188 | 180 | CLOSED | 0 | 2024 | 10 | [5 empty] | 7 | 3 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.35 | 0.13043 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2024 | 2024-10-15 | 2024-12-31 |  |  | LOGISTIC | LMS GIRONA- LIGHT | EssilorLuxottica | F. Taita | C. Piraccini | Operations | Data Engineering | 20 | 12 | CLOSED | 0 | 2024 | 8 | [9 empty] | 4 | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17391 | 0.19048 | 0
PROSPECT | PRJ | Waterfall | 2024 | 2024-10-15 | 2024-12-31 |  |  | LOGISTIC | LMS GIRONA- LIGHT | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | DataManagement | 20 | 12 | CLOSED | 0 | 2024 | 2 | [9 empty] | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.047619 | 0
PROSPECT | PRJ | Waterfall | 2024 | 2024-10-15 | 2024-12-31 |  |  | LOGISTIC | LMS GIRONA- LIGHT | EssilorLuxottica | F. Taita | M. Regini | Operations | BackEnd | 20 | 12 | CLOSED | 0 | 2024 | 9 | [9 empty] | 5 | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.19048 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-04-01 | 2024-12-31 | ABS24164 | ALT | LOGISTIC | LMS TIJUANA | EssilorLuxottica | F. Taita | C. Piraccini | Operations | Data Engineering | 133 | 88 | ON GOING | 0 | 2024 | 50.45 |  |  | 1.125 |  | 1.4 | 3 | 11 | 1.3 | 12.75 | 7 | 7 | 7 | 0 | 0 | 0.053571 | 0 | 0.07 | 0.15 | 0.47826 | 0.10833 | 0.60714 | 0.30435 | 0.33333 | 0.31818
CONTRACT | PRJ | Waterfall | 2024 | 2024-04-01 | 2024-12-31 | ABS24164 | ALT | LOGISTIC | LMS TIJUANA | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Engineering | 133 | 88 | ON GOING | 0 | 2024 | 8 | [8 empty] | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | PRJ | Waterfall | 2024 | 2024-04-01 | 2024-12-31 | ABS24164 | ALT | LOGISTIC | LMS TIJUANA | EssilorLuxottica | F. Taita | M. Regini | Operations | BackEnd | 133 | 88 | ON GOING | 0 | 2024 | 31.6 | [6 empty] | 7 | 1.3 | 7.3 | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30435 | 0.10833 | 0.34762 | 0.26087 | 0.2381 | 0.22727
CONTRACT | PRJ | Waterfall | 2024 | 2022-01-01 | 2024-05-31 | ABS24208 | ALDSE2ER | LOGISTIC | LUX DM Supporto ELECTRA 2024 - anhancement & Rollout | EssilorLuxottica | F. Taita | C. Piraccini | Operations | Data Engineering | 50 | 43 | ON GOING | 0 | 2024 | 13.8 |  |  |  | 1 | 0.25 | 0.5 | 2 | 0.25 | 1.8 | 3 | 3 | 3 | 0 | 0 | 0 | 0.045455 | 0.0125 | 0.025 | 0.086957 | 0.020833 | 0.085714 | 0.13043 | 0.14286 | 0.13636
CONTRACT | PRJ | Waterfall | 2024 | 2022-01-01 | 2024-05-31 | ABS24208 | ALDSE2ER | LOGISTIC | LUX DM Supporto ELECTRA 2024 - anhancement & Rollout | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | DataManagement | 50 | 43 | ON GOING | 0 | 2024 | 3 | [9 empty] | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.047619 | 0.045455
CONTRACT | PRJ | Waterfall | 2024 | 2022-01-01 | 2024-05-31 | ABS24208 | ALDSE2ER | LOGISTIC | LUX DM Supporto ELECTRA 2024 - anhancement & Rollout | EssilorLuxottica | F. Taita | M. Regini | Operations | BackEnd | 50 | 43 | ON GOING | 0 | 2024 | 29 |  |  |  | 3 | 3 | 2.5 | 5 | 1.5 | 5 | 6 | 3 | 3 | 0 | 0 | 0 | 0.13636 | 0.15 | 0.125 | 0.21739 | 0.125 | 0.2381 | 0.26087 | 0.14286 | 0.13636
CONTRACT | AMS | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS24450 | ABS24450 | BIP | LUX-DI-DM – fifth ecommerce support- rollout 2024 | EssilorLuxottica | F. Taita | A. Seira | Operations | BackEnd | 55 | 50 | ON GOING | 0 | 2024 | 21 | [9 empty] | 21 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.91304 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS24450 | ABS24450 | BIP | LUX-DI-DM – fifth ecommerce support- rollout 2024 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | PM - Project Governance | 55 | 53 | CLOSED | 0 | 2024 | 4 | [9 empty] | 4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17391 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS24450 | ABS24450 | BIP | LUX-DI-DM – fifth ecommerce support- rollout 2024 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | BackEnd | 55 | 53 | CLOSED | 0 | 2024 | 1 | [9 empty] | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS24450 | ABS24450 | BIP | LUX-DI-DM – fifth ecommerce support- rollout 2024 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | BackEnd | 55 | 53 | CLOSED | 0 | 2024 | 16 | [9 empty] | 16 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.69565 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS24450 | ABS24450 | BIP | LUX-DI-DM – fifth ecommerce support- rollout 2024 | EssilorLuxottica | F. Taita | T. Baldi | Operations | BackEnd | 55 | 53 | CLOSED | 0 | 2024 | 1 | [9 empty] | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-11-01 | 2024-12-31 | ABS24526 | ABS24526 | BIP | LUX-DI-DM – Sixth ecommerce support- rollout 2024 | EssilorLuxottica | F. Taita | A. Seira | Operations | BackEnd | 60 | 44 | ON GOING | 0 | 2024 | 3 | [10 empty] | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.045455
CONTRACT | AMS | Waterfall | 2024 | 2024-11-01 | 2024-12-31 | ABS24526 | ABS24526 | BIP | LUX-DI-DM – Sixth ecommerce support- rollout 2024 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | PM - Project Governance | 60 | 44 | ON GOING | 0 | 2024 | 6 | [10 empty] | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19048 | 0.090909
CONTRACT | AMS | Waterfall | 2024 | 2024-11-01 | 2024-12-31 | ABS24526 | ABS24526 | BIP | LUX-DI-DM – Sixth ecommerce support- rollout 2024 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | BackEnd | 60 | 44 | ON GOING | 0 | 2024 | 4 | [10 empty] | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0.13636
CONTRACT | AMS | Waterfall | 2024 | 2024-11-01 | 2024-12-31 | ABS24526 | ABS24526 | BIP | LUX-DI-DM – Sixth ecommerce support- rollout 2024 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | BackEnd | 60 | 44 | ON GOING | 0 | 2024 | 20 | [10 empty] | 14 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66667 | 0.27273
CONTRACT | AMS | Waterfall | 2024 | 2024-11-01 | 2024-12-31 | ABS24526 | ABS24526 | BIP | LUX-DI-DM – Sixth ecommerce support- rollout 2024 | EssilorLuxottica | F. Taita | T. Baldi | Operations | BackEnd | 60 | 44 | ON GOING | 0 | 2024 | 20 | [10 empty] | 14 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66667 | 0.27273
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-12-31 | ABS24163 | BS24163 | LOGISTIC | RTTF support 2024 | EssilorLuxottica | F. Taita | A. Cerrato | Operations | BackEnd | 100 | 100 | CLOSED | 1 | 2024 | 22 |  |  |  |  | 8 | 1 | 13 | [5 empty] | 0 | 0 | 0 | 0 | 0.4 | 0.05 | 0.56522 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-12-31 | ABS24163 | BS24163 | LOGISTIC | RTTF support 2024 | EssilorLuxottica | F. Taita | A. Strada | Operations | DataManagement | 100 | 100 | CLOSED | 1 | 2024 | 4 |  |  |  |  | 2 | 1 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0.1 | 0.05 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-12-31 | ABS24163 | BS24163 | LOGISTIC | RTTF support 2024 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | PM - Project Governance | 100 | 100 | CLOSED | 1 | 2024 | 16 |  |  |  | 4 | 5 | 4 | 4 |  | 3 |  |  |  | 0 | 0 | 0 | 0.18182 | 0.25 | 0.2 | 0.17391 | 0 | 0.14286 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-12-31 | ABS24163 | BS24163 | LOGISTIC | RTTF support 2024 | EssilorLuxottica | F. Taita | M. Calabrese | Delivery Projects | Analysis | 100 | 100 | CLOSED | 1 | 2024 | 1 |  |  |  |  | 1 | [7 empty] | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-12-31 | ABS24163 | BS24163 | LOGISTIC | RTTF support 2024 | EssilorLuxottica | F. Taita | M. Vimercati | Operations | FrontEnd | 100 | 100 | CLOSED | 1 | 2024 | 1 |  |  |  |  | 1 | [7 empty] | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-12-31 | ABS24163 | BS24163 | LOGISTIC | RTTF support 2024 | EssilorLuxottica | F. Taita | R. Bondi | Operations | FrontEnd | 100 | 100 | CLOSED | 1 | 2024 | 12.5 |  |  |  | 0.5 | 4.5 | 2 | 5 |  | 1 |  |  |  | 0 | 0 | 0 | 0.022727 | 0.225 | 0.1 | 0.21739 | 0 | 0.047619 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-12-31 | ABS24163 | BS24163 | LOGISTIC | RTTF support 2024 | EssilorLuxottica | F. Taita | R. Grienti | Operations | BackEnd | 100 | 100 | CLOSED | 1 | 2024 | 11 |  |  |  |  | 7 | 1 | 1 |  | 2 |  |  |  | 0 | 0 | 0 | 0 | 0.35 | 0.05 | 0.043478 | 0 | 0.095238 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24593 | ABS24593 | RETAIL | LUX-DI-VAPP GRA Wave1 + Wave2 | EssilorLuxottica | F. Vassallo | F. Vassallo | Delivery AMS | PM - Project Governance | 75 | 10 | ON GOING | 0 | 2024 | 15 | [8 empty] | 5 | 5 | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2381 | 0.21739 | 0.2381 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24593 | ABS24593 | RETAIL | LUX-DI-VAPP GRA Wave1 + Wave2 | EssilorLuxottica | F. Vassallo | I. OSTYMCHUCK | Operations | BackEnd | 75 | 10 | ON GOING | 0 | 2024 | 15 | [8 empty] | 5 | 5 | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2381 | 0.21739 | 0.2381 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24593 | ABS24593 | RETAIL | LUX-DI-VAPP GRA Wave1 + Wave2 | EssilorLuxottica | F. Vassallo | M. Porcu | Operations | Technical Leader | 75 | 10 | ON GOING | 0 | 2024 | 2 | [8 empty] | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0.043478 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24593 | ABS24593 | RETAIL | LUX-DI-VAPP GRA Wave1 + Wave2 | EssilorLuxottica | F. Vassallo | S. Beltrami | Operations | FrontEnd | 75 | 10 | ON GOING | 0 | 2024 | 15 | [8 empty] | 5 | 5 | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2381 | 0.21739 | 0.2381 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24592 | ABS24592 | RETAIL | LUX-DI-VAPP GRSD Top Brand Wave 1 | EssilorLuxottica | F. Vassallo | A. Pirola | Operations | BackEnd | 60 | 50 | ON GOING | 0 | 2024 | 1 | [6 empty] | 0.5 | 0.5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.021739 | 0.041667 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24592 | ABS24592 | RETAIL | LUX-DI-VAPP GRSD Top Brand Wave 1 | EssilorLuxottica | F. Vassallo | D. Heba | Operations | BackEnd | 60 | 50 | ON GOING | 0 | 2024 | 21 | [7 empty] | 6 | 15 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.71429 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24592 | ABS24592 | RETAIL | LUX-DI-VAPP GRSD Top Brand Wave 1 | EssilorLuxottica | F. Vassallo | F. Vassallo | Delivery AMS | PM - Project Governance | 60 | 50 | ON GOING | 0 | 2024 | 1 | [6 empty] | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24592 | ABS24592 | RETAIL | LUX-DI-VAPP GRSD Top Brand Wave 1 | EssilorLuxottica | F. Vassallo | M. Mannarino | Operations | BackEnd | 60 | 50 | ON GOING | 0 | 2024 | 18 | [6 empty] | 1 | 5 | 12 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.41667 | 0.57143 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24592 | ABS24592 | RETAIL | LUX-DI-VAPP GRSD Top Brand Wave 1 | EssilorLuxottica | F. Vassallo | M. Vianelli | Delivery Projects | Analysis | 60 | 50 | ON GOING | 0 | 2024 | 3 | [6 empty] | 3 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24592 | ABS24592 | RETAIL | LUX-DI-VAPP GRSD Top Brand Wave 1 | EssilorLuxottica | F. Vassallo | R. Grandi | Operations | Data Management | 60 | 50 | ON GOING | 0 | 2024 | 2.5 | [6 empty] | 2 | 0.5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.041667 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24592 | ABS24592 | RETAIL | LUX-DI-VAPP GRSD Top Brand Wave 1 | EssilorLuxottica | F. Vassallo | R. Tortora | Operations | Data Management | 60 | 50 | ON GOING | 0 | 2024 | 2 | [7 empty] | 2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16667 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-09-01 | 2024-12-31 | ABS24592 | ABS24592 | RETAIL | LUX-DI-VAPP GRSD Top Brand Wave 1 | EssilorLuxottica | F. Vassallo | S. Delle Fave | Operations | BackEnd | 60 | 50 | ON GOING | 0 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2023 | 2024-09-01 | 2024-12-31 | ABS24592 | ABS24592 | RETAIL | LUX-DI-VAPP GRSD Top Brand Wave 1 | EssilorLuxottica | F. Vassallo | T. Porzio | Delivery AMS | PM - Project Governance | 60 | 50 | ON GOING | 0 | 2024 | 4 | [6 empty] | 1 | 3 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.25 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | A. Ferrari | Operations | Monitoraggio WE | 1210 | 755 | ON GOING | 0 | 2024 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0.16667 | 0.095238 | 0.086957 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | A. Pirola | Operations | FrontEnd | 1210 | 755 | ON GOING | 0 | 2024 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | A. Pirola | Operations | FrontEnd | 1210 | 755 | ON GOING | 0 | 2024 | 6 |  |  |  | 1 | 1 | 5 | [6 empty] | 0 | 0 | 0 | 0.045455 | 0.05 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | A. Vladi | Operations | Reperibilità | 1210 | 755 | ON GOING | 0 | 2024 | 15 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 2 | 2 |  |  | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0.41667 | 0.095238 | 0.086957 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | C. Piraccini | Operations | Data Management | 1210 | 755 | ON GOING | 0 | 2024 | 10 | [10 empty] | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2381 | 0.22727
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | D. Heba | Operations | BackEnd | 1210 | 755 | ON GOING | 0 | 2024 | 37 | [8 empty] | 5 | 15 | 2 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2381 | 0.65217 | 0.095238 | 0.68182
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | D. HEBA | Operations | Reperibilità | 1210 | 755 | ON GOING | 0 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | F. D'ALBERTO | Operations | BackEnd | 1210 | 755 | ON GOING | 0 | 2024 | 2 | [11 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.090909
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | F. Malvezzi | Operations | Data Engineer | 1210 | 755 | ON GOING | 0 | 2024 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | F. Origlia | Operations | Technical Leader | 1210 | 755 | ON GOING | 0 | 2024 | 3 |  |  |  | 2 | 3 | [7 empty] | 0 | 0 | 0 | 0.090909 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | F. Vassallo | Delivery AMS | PM - Project Governance | 1210 | 755 | ON GOING | 0 | 2024 | 200 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 1.3889 | 1.25 | 1.1905 | 1.1364 | 1.25 | 1.25 | 1.087 | 2.0833 | 1.1905 | 1.087 | 1.1905 | 1.1364
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | F. Vassallo | Delivery AMS | Reperibilità | 1210 | 755 | ON GOING | 0 | 2024 | 32 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 4 | 4 | 4 |  |  | 0.44444 | 0.4 | 0.38095 | 0.36364 | 0.4 | 0.4 | 0.17391 | 0.33333 | 0.19048 | 0.17391 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | G. Mordà | Operations | Data Management | 1210 | 755 | ON GOING | 0 | 2024 | 2 | [8 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02381 | 0.021739 | 0.02381 | 0.022727
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | G. Sabbatini | Operations | Synapse | 1210 | 755 | ON GOING | 0 | 2024 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [5 empty] | 0.027778 | 0.025 | 0.02381 | 0.022727 | 0.025 | 0.025 | 0.021739 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | G. Tartaglia | Operations | Monitoraggio WE | 1210 | 755 | ON GOING | 0 | 2024 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0.16667 | 0.095238 | 0.086957 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | M. Mannarino | Operations | BackEnd | 1210 | 755 | ON GOING | 0 | 2024 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | M. Mannarino | Operations | BackEnd | 1210 | 755 | ON GOING | 0 | 2024 | 60 | 12 | 12 | 12 | 5 | 5 | 5 | 5 | 5 | 1 | 15 | 12 | 12 | 0.66667 | 0.6 | 0.57143 | 0.22727 | 0.25 | 0.25 | 0.21739 | 0.41667 | 0.047619 | 0.65217 | 0.57143 | 0.54545
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | M. Mannarino | Operations | Reperibilità | 1210 | 755 | ON GOING | 0 | 2024 | 15 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 2 | 2 |  |  | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0.41667 | 0.095238 | 0.086957 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | M. Vianelli | Delivery Projects | Analysis | 1210 | 755 | ON GOING | 0 | 2024 | 41 | 5 | 6 | 6 | 5 | 6 | 6 | 6 | 5 | 3 | 5 | 5 | 5 | 0.27778 | 0.3 | 0.28571 | 0.22727 | 0.3 | 0.3 | 0.26087 | 0.41667 | 0.14286 | 0.21739 | 0.2381 | 0.22727
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | N. GUERRERO | Delivery AMS | PM - Project Governance | 1210 | 755 | ON GOING | 0 | 2024 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.027778 | 0.025 | 0.02381 | 0.022727 | 0.025 | 0.025 | 0.021739 | 0.041667 | 0.02381 | 0.021739 | 0.02381 | 0.022727
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | N. GUERRERO | Delivery AMS | Monitoraggio WE | 1210 | 755 | ON GOING | 0 | 2024 | 11 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 |  |  | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0.083333 | 0.095238 | 0.086957 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | N. Pescione | Operations | Monitoraggio WE | 1210 | 755 | ON GOING | 0 | 2024 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0.16667 | 0.095238 | 0.086957 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | P. Anzellotti | Operations | Technical Leader | 1210 | 755 | ON GOING | 0 | 2024 | 4.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 0.027778 | 0.025 | 0.02381 | 0.022727 | 0.025 | 0.025 | 0.021739 | 0.041667 | 0.02381 | 0.021739 | 0.02381 | 0.045455
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | P. Anzellotti | Operations | Monitoraggio WE | 1210 | 755 | ON GOING | 0 | 2024 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0.16667 | 0.095238 | 0.086957 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | P. SINGH | AREA TECH | Data Management | 1210 | 755 | ON GOING | 0 | 2024 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [7 empty] | 0.027778 | 0.025 | 0.02381 | 0.022727 | 0.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | R. Grandi | Operations | Data Management | 1210 | 755 | ON GOING | 0 | 2024 | 42 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 5 | 15 | 15 | 2 | 2 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.41667 | 0.71429 | 0.65217 | 0.095238 | 0.090909
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | R. Marasca | Delivery Projects | Analysis | 1210 | 755 | ON GOING | 0 | 2024 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [7 empty] | 0.027778 | 0.025 | 0.02381 | 0.022727 | 0.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | R. Tortora | Operations | Data Management | 1210 | 755 | ON GOING | 0 | 2024 | 71 | [5 empty] | 5 | 1 | 5 | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.043478 | 0.41667 | 0.71429 | 0.65217 | 0.71429 | 0.68182
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24010 | ALDAV2 | RETAIL | VAPP AMS 7 App 2024 | EssilorLuxottica | F. Vassallo | T. Porzio | Delivery AMS | Data Management | 1210 | 755 | ON GOING | 0 | 2024 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 2 | 4 |  |  | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.25 | 0.095238 | 0.17391 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24377 | ABS24377 | RETAIL | VAPP CR Plus Q3Q4 2024 | EssilorLuxottica | F. Vassallo | D. Heba | Operations | BackEnd | 50 | 0 | ON GOING | 0 | 2024 | 25 | [6 empty] | 5 |  | 15 | 5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0 | 0.71429 | 0.21739 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24377 | ABS24377 | RETAIL | VAPP CR Plus Q3Q4 2024 | EssilorLuxottica | F. Vassallo | F. Vassallo | Delivery AMS | PM - Project Governance | 50 | 0 | ON GOING | 0 | 2024 | 15 | [6 empty] | 5 |  | 5 | 5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0 | 0.2381 | 0.21739 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24377 | ABS24377 | RETAIL | VAPP CR Plus Q3Q4 2024 | EssilorLuxottica | F. Vassallo | M. Mannarino | Operations | Data Engineer | 50 | 0 | ON GOING | 0 | 2024 | 20 | [6 empty] | 5 |  | 15 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0 | 0.71429 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24377 | ABS24377 | RETAIL | VAPP CR Plus Q3Q4 2024 | EssilorLuxottica | F. Vassallo | M. Vianelli | Delivery Projects | Analysis | 50 | 0 | ON GOING | 0 | 2024 | 19 | [8 empty] | 5 | 5 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2381 | 0.21739 | 0.2381 | 0.18182
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24377 | ABS24377 | RETAIL | VAPP CR Plus Q3Q4 2024 | EssilorLuxottica | F. Vassallo | R. Grandi | Operations | Data Management | 50 | 0 | ON GOING | 0 | 2024 | 11 | [6 empty] | 5 |  | 1 | 5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0 | 0.047619 | 0.21739 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24377 | ABS24377 | RETAIL | VAPP CR Plus Q3Q4 2024 | EssilorLuxottica | F. Vassallo | R. Tortora | Operations | Data Management | 50 | 0 | ON GOING | 0 | 2024 | 11 | [6 empty] | 5 |  | 1 | 5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0 | 0.047619 | 0.21739 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24377 | ABS24377 | RETAIL | VAPP CR Plus Q3Q4 2024 | EssilorLuxottica | F. Vassallo | S. Beltrami | Operations | FrontEnd | 50 | 0 | ON GOING | 0 | 2024 | 40 | [6 empty] | 5 |  | 21 | 14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0 | 1 | 0.6087 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24377 | ABS24377 | RETAIL | VAPP CR Plus Q3Q4 2024 | EssilorLuxottica | F. Vassallo | S. Delle Fave | Operations | FrontEnd | 50 | 0 | ON GOING | 0 | 2024 | 6 | [6 empty] | 5 |  | 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0 | 0.047619 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24377 | ABS24377 | RETAIL | VAPP CR Plus Q3Q4 2024 | EssilorLuxottica | F. Vassallo | T. Porzio | Delivery AMS | Data Management | 50 | 0 | ON GOING | 0 | 2024 | 9 | [6 empty] | 2 |  | 5 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0 | 0.2381 | 0.086957 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | A. PIROLA | Operations | FrontEnd | 75 | 14 | ON GOING | 0 | 2024 | 8 | [10 empty] | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.22727
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | C. Piraccini | Operations | Data Management | 75 | 14 | ON GOING | 0 | 2024 | 6 | [10 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.13636
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | D. Heba | Operations | BackEnd | 75 | 14 | ON GOING | 0 | 2024 | 4 | [10 empty] | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.045455
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | F. Vassallo | Delivery AMS | PM - Project Governance | 75 | 14 | ON GOING | 0 | 2024 | 7 | [10 empty] | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.22727
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | M. Mannarino | Operations | Data Engineer | 75 | 14 | ON GOING | 0 | 2024 | 4 | [10 empty] | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.045455
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | M. Vianelli | Consulting | Analysis | 75 | 14 | ON GOING | 0 | 2024 | 5 | [10 empty] | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.090909
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | R. Grandi | Operations | Data Management | 75 | 14 | ON GOING | 0 | 2024 | 6 | [10 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.13636
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | A. Caldana | Operations | BackEnd | 188 | 170 | CLOSED | 0 | 2024 | 7 | 5 | 4 | 5 | 5 | 5 | 2 | [6 empty] | 0.27778 | 0.2 | 0.2381 | 0.22727 | 0.25 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | A. Pirola | Operations | FrontEnd | 188 | 170 | CLOSED | 0 | 2024 | 19 |  |  |  | 5 | 5 | 6 | 1 | 2 | 5 |  |  |  | 0 | 0 | 0 | 0.22727 | 0.25 | 0.3 | 0.043478 | 0.16667 | 0.2381 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | B. Capotorto | Operations | BackEnd | 188 | 170 | CLOSED | 0 | 2024 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | [6 empty] | 0.27778 | 0.25 | 0.2381 | 0.22727 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | D. Heba | Operations | BackEnd | 188 | 170 | CLOSED | 0 | 2024 | 0 |  | 2 | 1 | [9 empty] | 0 | 0.1 | 0.047619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | F. Origlia | Operations | Architecture Analysis | 188 | 170 | CLOSED | 0 | 2024 | 1 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [6 empty] | 0 | 0.025 | 0.02381 | 0.022727 | 0.025 | 0.025 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | F. Vassallo | Delivery AMS | PM - Project Governance | 188 | 170 | CLOSED | 0 | 2024 | 3 |  | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 0 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | G. Fiorentini | Operations | BackEnd | 188 | 170 | CLOSED | 0 | 2024 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | G. Luongo | Delivery AMS | PM - Project Governance | 188 | 170 | CLOSED | 0 | 2024 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | M. Mannarino | Operations | BackEnd | 188 | 170 | CLOSED | 0 | 2024 | 3 |  | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 0 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | M. Vianelli | Delivery Projects | Analysis | 188 | 170 | CLOSED | 0 | 2024 | 0 |  | 5 | 5 | 5 | [8 empty] | 0 | 0.25 | 0.2381 | 0.22727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | P. Anzellotti | Operations | Technical Leader | 188 | 170 | CLOSED | 0 | 2024 | 0.6 |  |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | [5 empty] | 0 | 0 | 0.0095238 | 0.0090909 | 0.01 | 0.01 | 0.0086957 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | P. Assirelli | Operations | Technical Leader | 188 | 170 | CLOSED | 0 | 2024 | 12 | 6 | 6 | 6 | 6 | 6 | 6 | [6 empty] | 0.33333 | 0.3 | 0.28571 | 0.27273 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | R. Grandi | Operations | Data Management | 188 | 170 | CLOSED | 0 | 2024 | 3 |  | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 0 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | S. Delle Fave | Operations | FrontEnd | 188 | 170 | CLOSED | 0 | 2024 | 2 |  | 2 | 2 |  | 2 | [7 empty] | 0 | 0.1 | 0.095238 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24043 | ALDVEPQ2 | RETAIL | VAPP OneLRA CR Plus Q1Q2 2024 | EssilorLuxottica | F. Vassallo | T. Porzio | Delivery AMS | Data Management | 188 | 170 | CLOSED | 0 | 2024 | 11 |  | 3 | 3 | 3 | 3 | 3 | 3 |  | 1 | 1 |  |  | 0 | 0.15 | 0.14286 | 0.13636 | 0.15 | 0.15 | 0.13043 | 0 | 0.047619 | 0.043478 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-12-31 |  |  | ECC | ECC LOGISTIC PROJECTS GOVERNANCE | EssilorLuxottica | G. D'alesio | A. Torone | Delivery AMS | PM - Project Governance | 154 | 143 | ON GOING | 0 | 2024 | 83.5 | 12 | 14 | 15 | 13.5 | 15 | 14 | 16 | 8 | 15 | 11.5 | 2 | 2 | 0.66667 | 0.7 | 0.71429 | 0.61364 | 0.75 | 0.7 | 0.69565 | 0.66667 | 0.71429 | 0.5 | 0.095238 | 0.090909
CONTRACT | AMS | Watefall | 2024 | 2024-05-01 | 2024-08-31 | ABS24216 | ABS24216 | CRM | Global CS B2C AMS 2024 | EssilorLuxottica | G. Galati | A. De Sanctis | Operations | Data Management | 21 | 6 | CLOSED | 0 | 2024 | 13 |  |  | 2 | 2 | 4 | 5 | 4 | [5 empty] | 0 | 0 | 0.095238 | 0.090909 | 0.2 | 0.25 | 0.17391 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Watefall | 2024 | 2024-05-01 | 2024-08-31 | ABS24216 | ABS24216 | CRM | Global CS B2C AMS 2024 | EssilorLuxottica | G. Galati | G. Galati | Delivery AMS | PM - Project Governance | 21 | 6 | CLOSED | 0 | 2024 | 4 |  |  |  |  | 1.5 | 1.5 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0.075 | 0.075 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2023-11-01 | 2024-12-31 | ABS24087 | ACTAA | Logistic | CTRL-Tower Atlanta AMS 2024 | EssilorLuxottica | G. Luongo | A. Crescimone | Operations | BackEnd | 212 | 56 | ON GOING | 0 | 2024 | 16 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0.027778 | 0.025 | 0.02381 | 0.022727 | 0.1 | 0.1 | 0.086957 | 0.16667 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | AMS | Waterfall | 2024 | 2023-11-01 | 2024-12-31 | ABS24087 | ACTAA | Logistic | CTRL-Tower Atlanta AMS 2024 | EssilorLuxottica | G. Luongo | A. Saija | Operations | BackEnd | 212 | 56 | ON GOING | 0 | 2024 | 16 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0.16667 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | AMS | Waterfall | 2024 | 2023-11-01 | 2024-12-31 | ABS24087 | ACTAA | Logistic | CTRL-Tower Atlanta AMS 2024 | EssilorLuxottica | G. Luongo | G. D'Amanti | Operations | BackEnd | 212 | 56 | ON GOING | 0 | 2024 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 |  | 0.027778 | 0.025 | 0.02381 | 0.022727 | 0.025 | 0.025 | 0.021739 | 0.041667 | 0.02381 | 0.021739 | 0.047619 | 0
CONTRACT | AMS | Waterfall | 2024 | 2023-11-01 | 2024-12-31 | ABS24087 | ACTAA | Logistic | CTRL-Tower Atlanta AMS 2024 | EssilorLuxottica | G. Luongo | G. Luongo | Delivery AMS | PM - Project Governance | 212 | 56 | ON GOING | 0 | 2024 | 8 | 1 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.055556 | 0.025 | 0.02381 | 0.022727 | 0.05 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS | Waterfall | 2024 | 2023-11-01 | 2024-12-31 | ABS24087 | ACTAA | Logistic | CTRL-Tower Atlanta AMS 2024 | EssilorLuxottica | G. Luongo | L. Gullotto | Operations | BackEnd | 212 | 56 | ON GOING | 0 | 2024 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.027778 | 0.025 | 0.02381 | 0.022727 | 0.025 | 0.025 | 0.021739 | 0.041667 | 0.02381 | 0.021739 | 0.02381 | 0.022727
CONTRACT | AMS | Waterfall | 2024 | 2023-11-01 | 2024-12-31 | ABS24087 | ACTAA | Logistic | CTRL-Tower Atlanta AMS 2024 | EssilorLuxottica | G. Luongo | P. Assirelli | Operations | Technical Leader | 212 | 56 | ON GOING | 0 | 2024 | 16 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0.16667 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-01 | ABS24318 | ADATLS | RETAIL | Digital Platform LENS Transition Simulator | EssilorLuxottica | G. Luongo | G. D'Amanti | Operations | BackEnd | 9 | 1 | ON GOING | 0 | 2024 | 8 | [9 empty] | 6 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26087 | 0.095238 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-01 | ABS24318 | ADATLS | RETAIL | Digital Platform LENS Transition Simulator | EssilorLuxottica | G. Luongo | P. Assirelli | Operations | Technical Leader | 9 | 1 | ON GOING | 0 | 2024 | 1 | [6 empty] | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | A. Caldana | Operations | BackEnd | 1610 | 1067 | ON GOING | 0 | 2024 | 63 | 13 | 16 | 16 | 14 | 17 | 12 | 18 |  | 16 |  |  |  | 0.72222 | 0.8 | 0.7619 | 0.63636 | 0.85 | 0.6 | 0.78261 | 0 | 0.7619 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | A. Crescimone | Operations | BackEnd | 1610 | 1067 | ON GOING | 0 | 2024 | 113 | 19 | 21 | 21 | 19 | 19 | 15 | 18 |  | 16 | 18 | 15 | 12 | 1.0556 | 1.05 | 1 | 0.86364 | 0.95 | 0.75 | 0.78261 | 0 | 0.7619 | 0.78261 | 0.71429 | 0.54545
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | A. Saija | Operations | BackEnd | 1610 | 1067 | ON GOING | 0 | 2024 | 110 | 16 | 18 | 19 | 17 | 2 | 16 | 19 |  | 19 | 21 | 18 | 15 | 0.88889 | 0.9 | 0.90476 | 0.77273 | 0.1 | 0.8 | 0.82609 | 0 | 0.90476 | 0.91304 | 0.85714 | 0.68182
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | B. Capotorto | Operations | Analysis | 1610 | 1067 | ON GOING | 0 | 2024 | 102 | 13 | 15 | 16 | 14 | 17 | 15 | 18 |  | 7 | 18 | 15 | 12 | 0.72222 | 0.75 | 0.7619 | 0.63636 | 0.85 | 0.75 | 0.78261 | 0 | 0.33333 | 0.78261 | 0.71429 | 0.54545
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | C. Piraccini | Operations | Backend | 1610 | 1067 | ON GOING | 0 | 2024 | 15 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | [5 empty] | 0.27778 | 0.25 | 0.2381 | 0.22727 | 0.25 | 0.25 | 0.21739 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | G. D'Amanti | Operations | BackEnd | 1610 | 1067 | ON GOING | 0 | 2024 | 83 | 17 | 19 | 21 | 19 | 21 | 17 | 2 |  | 21 | 14 | 8 |  | 0.94444 | 0.95 | 1 | 0.86364 | 1.05 | 0.85 | 0.086957 | 0 | 1 | 0.6087 | 0.38095 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | G. Fiorentini | Operations | BackEnd | 1610 | 1067 | ON GOING | 0 | 2024 | 32 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  | 8 |  |  |  | 0.44444 | 0.4 | 0.38095 | 0.36364 | 0.4 | 0.4 | 0.34783 | 0 | 0.38095 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | G. Luongo | Delivery AMS | PM - Project Governance | 1610 | 1067 | ON GOING | 0 | 2024 | 202 | 17 | 2 | 2 | 18 | 19 | 19 | 19 |  | 19 | 48 | 42 | 36 | 0.94444 | 0.1 | 0.095238 | 0.81818 | 0.95 | 0.95 | 0.82609 | 0 | 0.90476 | 2.087 | 2 | 1.6364
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | L. Gullotto | Operations | BackEnd | 1610 | 1067 | ON GOING | 0 | 2024 | 101 | 17 | 19 | 21 | 19 | 21 | 17 | 2 |  | 19 | 23 | 2 | 17 | 0.94444 | 0.95 | 1 | 0.86364 | 1.05 | 0.85 | 0.086957 | 0 | 0.90476 | 1 | 0.095238 | 0.77273
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | M. Regini | Operations | Backend | 1610 | 1067 | ON GOING | 0 | 2024 | 23 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  | 2 | 2 | 2 | 2 | 0.27778 | 0.25 | 0.2381 | 0.22727 | 0.25 | 0.25 | 0.21739 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | P. Assirelli | Operations | Technical Leader/Analista | 1610 | 1067 | ON GOING | 0 | 2024 | 82 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 1 | 15 | 15 | 15 | 0.66667 | 0.6 | 0.57143 | 0.54545 | 0.6 | 0.6 | 0.52174 | 0 | 0.047619 | 0.65217 | 0.71429 | 0.68182
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24039 | ALDDAO2 | Retail | OneLRA AMS 2024 | EssilorLuxottica | G. Luongo | T. Baldi | Operations | Backend | 1610 | 1067 | ON GOING | 0 | 2024 | 7 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 1 |  |  |  | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0 | 0.047619 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24568 |  | RETAIL | OneLRA CR Plus Q3Q4 2024 | EssilorLuxottica | G. Luongo | A. Caldana | Operations | BackEnd | 250 | 79 | ON GOING | 0 | 2024 | 17 | 5 | 4 | 5 | 5 | 5 | 2 | 5 |  | 5 |  |  |  | 0.27778 | 0.2 | 0.2381 | 0.22727 | 0.25 | 0.1 | 0.21739 | 0 | 0.2381 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24568 |  | RETAIL | OneLRA CR Plus Q3Q4 2024 | EssilorLuxottica | G. Luongo | B. Capotorto | Operations | BackEnd | 250 | 79 | ON GOING | 0 | 2024 | 19 | [6 empty] | 5 |  | 5 | 1 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0 | 0.2381 | 0.043478 | 0.33333 | 0.045455
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24568 |  | RETAIL | OneLRA CR Plus Q3Q4 2024 | EssilorLuxottica | G. Luongo | G. Fiorentini | Operations | BackEnd | 250 | 79 | ON GOING | 0 | 2024 | 4 | [6 empty] | 2 |  | 2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0 | 0.095238 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24568 |  | RETAIL | OneLRA CR Plus Q3Q4 2024 | EssilorLuxottica | G. Luongo | G. Luongo | Delivery AMS | PM - Project Governance | 250 | 79 | ON GOING | 0 | 2024 | 5 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24568 |  | RETAIL | OneLRA CR Plus Q3Q4 2024 | EssilorLuxottica | G. Luongo | P. Assirelli | Operations | Technical Leader | 250 | 79 | ON GOING | 0 | 2024 | 31 | [6 empty] | 5 |  | 5 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0 | 0.2381 | 0.30435 | 0.33333 | 0.31818
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-01 | ABS24115 | ALDDDC | RETAIL | S&V Dashboard Changes | EssilorLuxottica | G. Luongo | A. Caldana | Operations | BackEnd | 31 | 30 | CLOSED | 0 | 2024 | 0 |  |  | 1 | 5 | [8 empty] | 0 | 0 | 0.047619 | 0.22727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-01 | ABS24115 | ALDDDC | RETAIL | S&V Dashboard Changes | EssilorLuxottica | G. Luongo | P. Assirelli | Operations | Technical Leader | 31 | 30 | CLOSED | 0 | 2024 | 0 |  |  | 1 | 5 | [8 empty] | 0 | 0 | 0.047619 | 0.22727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2023-09-01 | 2024-11-30 |  |  | OTHER | EyeMed | Abstract | G. Maffini | M. Simeone | Operations | FrontEnd | 0 | 0 | ON GOING | 0 | 2024 | 3 | [6 empty] | 3 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ |  | 2024 | 2024-07-01 | 2024-12-31 |  |  | HR | AI for HR Recruiting and Absenteeism | EssilorLuxottica | G. Sironi | G. Sironi | Operations | PM - Project Governance | 0 | 0 | ON HOLD | 0 | 2024 | 1 | [5 empty] | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ |  | 2024 | 2024-07-01 | 2024-12-31 |  |  | HR | AI for HR Recruiting and Absenteeism | EssilorLuxottica | G. Sironi | M. Gomitoni | Operations | Tech Lead | 0 | 0 | ON HOLD | 0 | 2024 | 1 | [5 empty] | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | ABS0019 | RETAIL | Edison Targeting & Churn - Presale | Edison | G. Sironi | G. Sironi | Operations | Tech Lead Support | 110 | 0 | PROPOSAL | 0 | 2024 | 4 | [6 empty] | 1 | 1 | 2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.083333 | 0.095238 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | ABS0019 | RETAIL | Edison Targeting & Churn - Presale | Edison | G. Sironi | M. Gomitoni | Operations | Tech Lead | 110 | 0 | PROPOSAL | 0 | 2024 | 4 | [6 empty] | 1 | 1 | 2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.083333 | 0.095238 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | A. Imbimbo | Operations | Data Scientist | 105 | 177 | ON GOING | 0 | 2024 | 5 | [6 empty] | 1 | 1 | 1 | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | A. Pirola | Operations | FrontEnd | 105 | 177 | ON GOING | 0 | 2024 | 45 | [5 empty] | 7 | 1 | 7 | 8 | 8 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0.35 | 0.043478 | 0.58333 | 0.38095 | 0.34783 | 0.42857 | 0.22727
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | F. Origlia | Operations | Architecture Analysis | 105 | 177 | ON GOING | 0 | 2024 | 2 | [5 empty] | 2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | G. Lopez | Operations | FrontEnd | 105 | 177 | ON GOING | 0 | 2024 | 38 | [5 empty] | 1 | 15 | 5 | 13 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.65217 | 0.41667 | 0.61905 | 0.086957 | 0.047619 | 0.045455
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | G. Mordà | Operations | DataManagement | 105 | 177 | ON GOING | 0 | 2024 | 20 | [7 empty] | 5 | 5 | 5 | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41667 | 0.2381 | 0.21739 | 0.2381 | 0
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | G. Sabbatini | Operations | Data Engineering | 105 | 177 | ON GOING | 0 | 2024 | 28 | [5 empty] | 5 | 5 | 5 | 5 | 6 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.21739 | 0.41667 | 0.2381 | 0.26087 | 0.047619 | 0.045455
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | G. Sironi | Operations | PM - Project Governance | 105 | 177 | ON GOING | 0 | 2024 | 17 | [5 empty] | 3 | 3 | 3 | 3 | 3 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.13043 | 0.25 | 0.14286 | 0.13043 | 0.095238 | 0
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | M. MANNARINO | Operations | BackEnd | 105 | 177 | ON GOING | 0 | 2024 | 12 | [5 empty] | 1 | 3 | 2 | 1 | 3 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.13043 | 0.16667 | 0.047619 | 0.13043 | 0.095238 | 0
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | M. Vianelli | Delivery Projects | Analysis | 105 | 177 | ON GOING | 0 | 2024 | 24 | [5 empty] | 5 | 8 | 2 | 3 | 3 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.34783 | 0.16667 | 0.14286 | 0.13043 | 0.14286 | 0
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | N. Pescione | Operations | BackEnd | 105 | 177 | ON GOING | 0 | 2024 | 57 | [5 empty] | 1 | 15 | 8 | 13 | 16 | 4 |  | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.65217 | 0.66667 | 0.61905 | 0.69565 | 0.19048 | 0
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | P. Anzellotti | Operations | Solution Architect | 105 | 177 | ON GOING | 0 | 2024 | 40 | [5 empty] | 4 | 8 | 3 | 4 | 8 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.34783 | 0.25 | 0.19048 | 0.34783 | 0.38095 | 0.22727
CONTRACT | PRJ |  | 2024 | 2024-04-15 | 2024-11-30 | ABS24088 | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 | EssilorLuxottica | G. Sironi | P. Singh | AREA TECH | DataManagement | 105 | 177 | ON GOING | 0 | 2024 | 4 | [5 empty] | 3 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.043478 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-03-31 |  | DSL | FINANCE | Laboratorio AI per Lux | EssilorLuxottica | G. Sironi | I. Bressan | Operations | Data Engineering | 0 | 0 | CLOSED | 0 | 2024 | 0 | 9 | 1.5 | 1.5 | [9 empty] | 0.5 | 0.075 | 0.071429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | A. BRANDIZZI | Operations | FRONT END | 220 | 190 | CLOSED | 0 | 2024 | 24 | [9 empty] | 5 | 2 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.095238 | 0.77273
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | A. SANTORO | Delivery Projects | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 13.4375 | [8 empty] | 8.4375 | 5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.40179 | 0.21739 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | A. STRADA | Operations | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 2 | [9 empty] | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | A. TORONE | Delivery AMS | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 16.5 | [8 empty] | 1 | 5 | 5.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0.21739 | 0.2619 | 0.22727
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | C. DI LORENZO | Delivery Projects | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 15 | [9 empty] | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.2381 | 0.22727
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | C. TIBERTI | Operations | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 42 | [9 empty] | 23 | 2 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.095238 | 0.77273
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | F. SCOGNAMIGLIO | Operations | BACK END | 220 | 190 | CLOSED | 0 | 2024 | 42 | [9 empty] | 23 | 2 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.095238 | 0.77273
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | F. SPACAGNA | Operations | BACK END | 220 | 190 | CLOSED | 0 | 2024 | 14.25 | [9 empty] | 5 | 5 | 4.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.2381 | 0.19318
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | F. VASSALLO | Delivery AMS | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 1 | [8 empty] | 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | G. DE FEO | Delivery Projects | PM - Project Governance | 220 | 190 | CLOSED | 0 | 2024 | 8.375 | [8 empty] | 2.375 | 3 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1131 | 0.13043 | 0.14286 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | G. TARTAGLIA | Operations | BACK END | 220 | 190 | CLOSED | 0 | 2024 | 24 | [9 empty] | 5 | 2 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.095238 | 0.77273
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | I. OSTYMCHUCK | Operations | BACK END | 220 | 190 | CLOSED | 0 | 2024 | 20 | [9 empty] | 1 | 2 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.095238 | 0.77273
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | J. SORGATO |  | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 15 | [8 empty] | 6 | 1 | 1 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28571 | 0.043478 | 0.047619 | 0.31818
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | L. BARIANI | Delivery Projects | PM - Project Governance | 220 | 190 | CLOSED | 0 | 2024 | 7 | [8 empty] | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0.086957 | 0.095238 | 0.090909
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | L. BARIANI | Delivery Projects | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 54 | [9 empty] | 21 | 18 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.91304 | 0.85714 | 0.68182
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | L. CATTANEO |  | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 10 | [8 empty] | 1 | 1 | 1 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0.043478 | 0.047619 | 0.31818
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | M. Porcu | Operations | BACK END | 220 | 190 | CLOSED | 0 | 2024 | 48 | [8 empty] | 2 | 18 | 16 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.78261 | 0.7619 | 0.54545
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | M. TOCI | Operations | BACK END | 220 | 190 | CLOSED | 0 | 2024 | 20 | [9 empty] | 1 | 2 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.095238 | 0.77273
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | M. VIANELLI | Delivery Projects | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 1 | [8 empty] | 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | M. VIMERCATI | Operations | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 1 | [8 empty] | 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | O. SAGAZIO | Operations | BACK END | 220 | 190 | CLOSED | 0 | 2024 | 17 | [9 empty] | 6 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26087 | 0.28571 | 0.22727
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | P. ANZELLOTTI | Operations | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 1 | [8 empty] | 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | S. Beltrami | Operations | BACK END | 220 | 190 | CLOSED | 0 | 2024 | 27 | [9 empty] | 8 | 2 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.34783 | 0.095238 | 0.77273
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | S. BEN YOUNES | Operations | Analysis | 220 | 190 | CLOSED | 0 | 2024 | 3 | [9 empty] | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.047619 | 0.045455
CONTRACT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-08-01 | 2024-12-31 | ABS24375 | ABS24375 | RETAIL | POC - FFD - Field Force Dashboard | EssilorLuxottica | L. BARIANI | S. DELLE FAVE | Operations | FRONT END | 220 | 190 | CLOSED | 0 | 2024 | 49.6 | [8 empty] | 1 | 19 | 16 | 13.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0.82609 | 0.7619 | 0.61818
LEAD | PRESALES - DELIVERY |  | 2024-2025 | 2024-09-01 | 2025-01-31 | ABS24523 | ABS24523 | EPM | Tax Cube | EssilorLuxottica | L. Bariani | A. Di Pietro | Operations | BackEnd | 180 | 0 | ON HOLD | 0 | 2024 | 2 | [9 empty] | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0 | 0
LEAD | PRESALES - DELIVERY |  | 2024-2025 | 2024-09-01 | 2025-01-31 | ABS24523 | ABS24523 | EPM | Tax Cube | EssilorLuxottica | L. Bariani | E. Storti | Delivery Projects | Analisys | 180 | 0 | ON HOLD | 0 | 2024 | 3 | [8 empty] | 1 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0.086957 | 0 | 0
LEAD | PRESALES - DELIVERY |  | 2024-2025 | 2024-09-01 | 2025-01-31 | ABS24523 | ABS24523 | EPM | Tax Cube | EssilorLuxottica | L. Bariani | F. Atanasio | Operations | BackEnd | 180 | 0 | ON HOLD | 0 | 2024 | 2 | [9 empty] | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0 | 0
LEAD | PRESALES - DELIVERY |  | 2024-2025 | 2024-09-01 | 2025-01-31 | ABS24523 | ABS24523 | EPM | Tax Cube | EssilorLuxottica | L. Bariani | I. Bressan | Operations | Architecture Analysis | 180 | 0 | ON HOLD | 0 | 2024 | 3 | [8 empty] | 1 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0.086957 | 0 | 0
LEAD | PRESALES - DELIVERY |  | 2024-2025 | 2024-09-01 | 2025-01-31 | ABS24523 | ABS24523 | EPM | Tax Cube | EssilorLuxottica | L. Bariani | L. BARIANI | Delivery Projects | PM - Project Governance | 180 | 0 | ON HOLD | 0 | 2024 | 4 | [8 empty] | 2 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.086957 | 0 | 0
LEAD | PRESALES - DELIVERY |  | 2024-2025 | 2024-09-01 | 2025-01-31 | ABS24523 | ABS24523 | EPM | Tax Cube | EssilorLuxottica | L. Bariani | S. Preziosa | Delivery Projects | Analisys | 180 | 0 | ON HOLD | 0 | 2024 | 6 | [8 empty] | 4 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19048 | 0.086957 | 0 | 0
PROSPECT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-03-15 | 2024-12-31 |  | ABS0015 | RETAIL | BullsEye POC Data Science | EssilorLuxottica | L. Franceschini | A. Imbimbo | Operations | Data Scientist | 35 | 14 | ON GOING | 0 | 2024 | 1 |  |  |  | 1 | 1 | [7 empty] | 0 | 0 | 0 | 0.045455 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-03-15 | 2024-12-31 |  | ABS0015 | RETAIL | BullsEye POC Data Science | EssilorLuxottica | L. Franceschini | F. Malvezzi | Operations | Data Scientist | 35 | 14 | ON GOING | 0 | 2024 | 2 |  |  |  | 1 | 1 | 1 | [6 empty] | 0 | 0 | 0 | 0.045455 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-03-15 | 2024-12-31 |  | ABS0015 | RETAIL | BullsEye POC Data Science | EssilorLuxottica | L. Franceschini | G. Sabbatini | Operations | Data Engineering | 35 | 14 | ON GOING | 0 | 2024 | 2 |  |  |  | 1 | 1 | 1 | [6 empty] | 0 | 0 | 0 | 0.045455 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-03-15 | 2024-12-31 |  | ABS0015 | RETAIL | BullsEye POC Data Science | EssilorLuxottica | L. Franceschini | G. Sironi | Operations | Team Leadership | 35 | 14 | ON GOING | 0 | 2024 | 2 |  |  |  | 1 | 1 | 1 | [6 empty] | 0 | 0 | 0 | 0.045455 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-03-15 | 2024-12-31 |  | ABS0015 | RETAIL | BullsEye POC Data Science | EssilorLuxottica | L. Franceschini | M. Gomitoni | Operations | Tech Lead | 35 | 14 | ON GOING | 0 | 2024 | 3 |  |  |  | 1 | 2 | 1 | [6 empty] | 0 | 0 | 0 | 0.045455 | 0.1 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRESALES - DELIVERY | Waterfall | 2024 | 2024-03-15 | 2024-12-31 |  | ABS0015 | RETAIL | BullsEye POC Data Science | EssilorLuxottica | L. Franceschini | V. Echarry | Operations | Data Scientist | 35 | 14 | ON GOING | 0 | 2024 | 2 |  |  |  | 1 | 1 | 1 | [6 empty] | 0 | 0 | 0 | 0.045455 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | A. Ferrari | Operations | DataManagement | 780 | 735 | ON HOLD | 0 | 2024 | 31 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 8 | 1 | 1 | 1 | 5 | 0.11111 | 0.25 | 0.2381 | 0.22727 | 0.25 | 0.25 | 0.21739 | 0.66667 | 0.047619 | 0.043478 | 0.047619 | 0.22727
CONTRACT | PRJ | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | A. Lorena | Operations | FrontEnd | 780 | 735 | ON HOLD | 0 | 2024 | 41 |  | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 15 |  |  | 0 | 0.1 | 0.2381 | 0.22727 | 0.25 | 0.25 | 0.21739 | 0.41667 | 0.28571 | 0.65217 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | A. Pirola | Operations | FrontEnd | 780 | 735 | ON HOLD | 0 | 2024 | 18 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 4 | 4 | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.043478 | 0.083333 | 0.095238 | 0.086957 | 0.19048 | 0.18182
CONTRACT | PRJ | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | A. Vladi | Operations | TL - DataManagement | 780 | 735 | ON HOLD | 0 | 2024 | 139 | 8 | 1 | 1 | 1 | 18 | 18 | 18 | 15 | 18 | 18 | 18 | 16 | 0.44444 | 0.05 | 0.047619 | 0.045455 | 0.9 | 0.9 | 0.78261 | 1.25 | 0.85714 | 0.78261 | 0.85714 | 0.72727
CONTRACT | PRJ | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | C. Elia | Operations | DataManagement | 780 | 735 | ON HOLD | 0 | 2024 | 36 | [6 empty] | 5 | 5 | 5 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.41667 | 0.2381 | 0.30435 | 0.33333 | 0.31818
CONTRACT | PRJ | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | F. D'Alberto | Operations | DataManagement | 780 | 735 | ON HOLD | 0 | 2024 | 72 | 4 | 4 | 4 | 4 | 5 | 1 | 2 | 1 | 21 | 23 | 2 | 17 | 0.22222 | 0.2 | 0.19048 | 0.18182 | 0.25 | 0.05 | 0.086957 | 0.083333 | 1 | 1 | 0.095238 | 0.77273
CONTRACT | PRJ | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | F. Origlia | Operations | Solution Architect | 780 | 735 | ON HOLD | 0 | 2024 | 17 | 8 | 8 | 8 | 9 | 9 | 8 | [6 empty] | 0.44444 | 0.4 | 0.38095 | 0.40909 | 0.45 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | F. Spacagna | Operations | Solution Architect | 780 | 735 | ON HOLD | 0 | 2024 | 71 | [6 empty] | 8 | 7 | 13 | 15 | 15 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0.34783 | 0.58333 | 0.61905 | 0.65217 | 0.71429 | 0.59091
CONTRACT | PRJ | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | G. Franchi | Operations | BackEnd | 780 | 735 | ON HOLD | 0 | 2024 | 66 | [5 empty] | 1 | 15 | 1 | 15 | 15 | 2 | 17 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.65217 | 0.083333 | 0.71429 | 0.65217 | 0.095238 | 0.77273
CONTRACT | PRJ | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | L. Franceschini | Delivery Projects | PM - Project Governance | 780 | 735 | ON HOLD | 0 | 2024 | 34 | 9 | 9 | 9 | 3 | 3 | 3 | 3 | 2 | 6 | 6 | 6 | 5 | 0.5 | 0.45 | 0.42857 | 0.13636 | 0.15 | 0.15 | 0.13043 | 0.16667 | 0.28571 | 0.26087 | 0.28571 | 0.22727
CONTRACT | PRJ | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | M. Vianelli | Delivery Projects | Analysis | 780 | 735 | ON HOLD | 0 | 2024 | 31 | 4 | 5 | 5 | 5 | 5 | 5 | 5 |  |  | 6 | 5 | 5 | 0.22222 | 0.25 | 0.2381 | 0.22727 | 0.25 | 0.25 | 0.21739 | 0 | 0 | 0.26087 | 0.2381 | 0.22727
CONTRACT | PRJ | Waterfall | 2024 | 2023-12-01 | 2024-08-01 | ABS23409 | AE | FINANCE | EDEN ESSILOR FRANCIA | EssilorLuxottica | L. Franceschini | A. De Sanctis | Operations | FrontEnd | 125 | 66 | CLOSED | 0 | 2024 | 23 | 7 | 1 | 1 | 8 | 9 | 9 | 1 | 4 |  |  |  |  | 0.38889 | 0.05 | 0.047619 | 0.36364 | 0.45 | 0.45 | 0.043478 | 0.33333 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2023-12-01 | 2024-08-01 | ABS23409 | AE | FINANCE | EDEN ESSILOR FRANCIA | EssilorLuxottica | L. Franceschini | A. Strada | Operations | DataManagement | 125 | 66 | CLOSED | 0 | 2024 | 20 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 0.27778 | 0.25 | 0.2381 | 0.22727 | 0.25 | 0.25 | 0.21739 | 0.41667 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2023-12-01 | 2024-08-01 | ABS23409 | AE | FINANCE | EDEN ESSILOR FRANCIA | EssilorLuxottica | L. Franceschini | F. Taita | Delivery Projects | DataManagement | 125 | 66 | CLOSED | 0 | 2024 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | [6 empty] | 0.11111 | 0.1 | 0.095238 | 0.045455 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2023-12-01 | 2024-08-01 | ABS23409 | AE | FINANCE | EDEN ESSILOR FRANCIA | EssilorLuxottica | L. Franceschini | L. Franceschini | Delivery Projects | PM - Project Governance | 125 | 66 | CLOSED | 0 | 2024 | 12 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 2 |  |  |  |  | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.2 | 0.17391 | 0.16667 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2023-12-01 | 2024-08-01 | ABS23409 | AE | FINANCE | EDEN ESSILOR FRANCIA | EssilorLuxottica | L. Franceschini | R. Bondi | Operations | FrontEnd | 125 | 66 | CLOSED | 0 | 2024 | 17 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 2 |  |  |  |  | 0.22222 | 0.25 | 0.2381 | 0.22727 | 0.25 | 0.25 | 0.21739 | 0.16667 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2023-12-01 | 2024-04-01 | ABS24369 | ABS24336 | FINANCE | EDEN W2 | EssilorLuxottica | L. Franceschini | A. De Sanctis | Operations | FrontEnd | 100 | 124 | CLOSED | 0 | 2024 | 8 | [8 empty] | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | PRJ | Waterfall | 2024 | 2023-12-01 | 2024-04-01 | ABS24369 | ABS24336 | FINANCE | EDEN W2 | EssilorLuxottica | L. Franceschini | A. Strada | Operations | DataManagement | 100 | 124 | CLOSED | 0 | 2024 | 8 | [8 empty] | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | PRJ | Waterfall | 2024 | 2023-12-01 | 2024-04-01 | ABS24369 | ABS24336 | FINANCE | EDEN W2 | EssilorLuxottica | L. Franceschini | L. Franceschini | Delivery Projects | PM - Project Governance | 100 | 124 | CLOSED | 0 | 2024 | 11 | [5 empty] | 2 | 1 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.043478 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | PRJ | Waterfall | 2024 | 2023-12-01 | 2024-04-01 | ABS24369 | ABS24336 | FINANCE | EDEN W2 | EssilorLuxottica | L. Franceschini | R. Bondi | Operations | FrontEnd | 100 | 124 | CLOSED | 0 | 2024 | 28 | [8 empty] | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33333 | 0.30435 | 0.33333 | 0.31818
CONTRACT | PRJ | Waterfall | 2024 | 2023-12-01 | 2024-04-01 | ABS24369 | ABS24336 | FINANCE | EDEN W2 | EssilorLuxottica | L. Franceschini | S. Ben Younes | Operations | DataManagement | 100 | 124 | CLOSED | 0 | 2024 | 44 | [8 empty] | 7 | 7 | 13 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33333 | 0.30435 | 0.61905 | 0.77273
CONTRACT | PRJ | Waterfall | 2024 | 2023-01-01 | 2024-12-31 |  | LXT | FINANCE | EEFR | EssilorLuxottica | L. Franceschini | L. Franceschini | Delivery Projects | PM - Project Governance | 50 | 34 | ON GOING | 0 | 2024 | 9 |  |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 3 | 1 | 1 | 0 | 0 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0 | 0.047619 | 0.13043 | 0.047619 | 0.045455
CONTRACT | PRJ | Waterfall | 2024 | 2024-05-01 | 2024-12-31 |  | U20R | ERP | UNIEURO | UNIEURO | L. Franceschini | L. Franceschini | Delivery Projects | PM - Project Governance | 100 | 55 | ON GOING | 0 | 2024 | 47 |  |  |  | 7 | 7 | 7 | 7 |  | 7 | 7 | 7 | 5 | 0 | 0 | 0 | 0.31818 | 0.35 | 0.35 | 0.30435 | 0 | 0.33333 | 0.30435 | 0.33333 | 0.22727
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-06-01 | 2024-12-31 |  | ATD | OTHER | Formazione | Abstract | L. Franco | G. Minervini | Operations | BackEnd | 0 | 0 |  | 0 | 2024 | 6 | [5 empty] | 3 | 3 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.13043 | 0 | 0 | 0 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-06-01 | 2024-12-31 |  | ATD | OTHER | Formazione | Abstract | L. Franco | L. Franco | Operations | PM - Project Governance | 0 | 0 |  | 0 | 2024 | 6 | [5 empty] | 3 | 3 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.13043 | 0 | 0 | 0 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-06-01 | 2024-12-31 |  | ATD | OTHER | Formazione | Abstract | L. Franco | O. BEN OTHMANE | Operations | BackEnd | 0 | 0 |  | 0 | 2024 | 6 | [5 empty] | 3 | 3 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.13043 | 0 | 0 | 0 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-06-01 | 2024-12-31 |  | ATD | OTHER | Formazione | Abstract | L. Franco | P. Buonasorte | Operations | BackEnd | 0 | 0 |  | 0 | 2024 | 6 | [5 empty] | 3 | 3 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.13043 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ |  | 2024 |  |  |  |  | HR | Assessment Logiche DWH | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 0 | 0 | CLOSED | 0 | 2024 | 3 | [5 empty] | 3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | ABS23148 | ABS0008-33 | HR | Attività progettuali Salary 2025 | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Management | 30 | 0 | CLOSED | 1 | 2024 | 5 | [9 empty] | 2 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.14286 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | ABS23148 | ABS0008-33 | HR | Attività progettuali Salary 2025 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | Project Governance | 30 | 0 | CLOSED | 1 | 2024 | 0.5 | [10 empty] | 0.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02381 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | ABS23148 | ABS0008-33 | HR | Attività progettuali Salary 2025 | EssilorLuxottica | L. Roberto | M. VIMERCATI | Operations | Data Management | 30 | 0 | CLOSED | 1 | 2024 | 5 | [9 empty] | 2 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.14286 | 0
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-12-31 |  | IAA | OTHER | CC - Attività |  | L. ROBERTO | C. Elia | Operations | BackEnd | 0 | 0 | CLOSED | 0 | 2024 | 8 | [5 empty] | 2 | 2 | 2 | 2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0.16667 | 0.095238 | 0 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  |  | ATD | OTHER | Formazione | Abstract | L. Roberto | A. Brandizzi | Operations | FrontEnd | 0 | 0 | CLOSED | 0 | 2024 | 19 |  |  |  |  | 2 | 3 | 3 |  | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0.1 | 0.15 | 0.13043 | 0 | 0.14286 | 0.13043 | 0.14286 | 0.090909
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  |  | ATD | OTHER | Formazione | Abstract | L. Roberto | C. Elia | Operations | BackEnd | 0 | 0 | CLOSED | 0 | 2024 | 21 |  |  |  |  | 3 | 3 | 3 |  | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0.15 | 0.15 | 0.13043 | 0 | 0.14286 | 0.13043 | 0.14286 | 0.13636
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  |  | ATD | OTHER | Formazione | Abstract | L. Roberto | F. Spacagna | Operations | BackEnd | 0 | 0 | CLOSED | 0 | 2024 | 21 |  |  |  |  | 3 | 3 | 3 |  | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0.15 | 0.15 | 0.13043 | 0 | 0.14286 | 0.13043 | 0.14286 | 0.13636
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  |  | ATD | OTHER | Formazione | Abstract | L. Roberto | L. Roberto | Operations | PM - Project Governance | 0 | 0 | CLOSED | 0 | 2024 | 17 |  |  |  | 2 | 3 | 3 | 3 |  | 3 | 3 | 2 |  | 0 | 0 | 0 | 0.090909 | 0.15 | 0.15 | 0.13043 | 0 | 0.14286 | 0.13043 | 0.095238 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  |  | ATD | OTHER | Formazione | Abstract | L. Roberto | M. Simeone | Operations | FrontEnd | 0 | 0 | CLOSED | 0 | 2024 | 16 |  |  |  |  | 2 | 3 | 3 |  |  | 3 | 2 | 3 | 0 | 0 | 0 | 0 | 0.1 | 0.15 | 0.13043 | 0 | 0 | 0.13043 | 0.095238 | 0.13636
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-05-31 |  | ATD |  | Formazione Scala | Abstract | L. Roberto | F. Spacagna | Operations | BackEnd | 0 | 0 | CLOSED | 1 | 2024 | 5 |  |  | 5 | 5 | 5 | [7 empty] | 0 | 0 | 0.2381 | 0.22727 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRESALES - GO TO MARKET |  | 2024 |  |  |  | ABS0007 | CRM/DS | Gara Mediamarket | MediaMarket | L. Roberto | G. Sabbatini | Operations | Data Engineering | 20 | 20 | CLOSED | 1 | 2024 | 3 | [5 empty] | 3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRESALES - GO TO MARKET |  | 2024 |  |  |  | ABS0007 | CRM/DS | Gara Mediamarket | MediaMarket | L. Roberto | G. Sironi | Operations | Team Leadership | 20 | 20 | CLOSED | 1 | 2024 | 2 | [5 empty] | 2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRESALES - GO TO MARKET |  | 2024 |  |  |  | ABS0007 | CRM/DS | Gara Mediamarket | MediaMarket | L. Roberto | L. Roberto | Operations | PM - Project Governance | 20 | 20 | CLOSED | 1 | 2024 | 4 | [5 empty] | 4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRESALES - GO TO MARKET |  | 2024 |  |  |  | ABS0007 | CRM/DS | Gara Mediamarket | MediaMarket | L. Roberto | M. Gomitoni | Operations | Tech Lead | 20 | 20 | CLOSED | 1 | 2024 | 3 | [5 empty] | 3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRESALES - GO TO MARKET |  | 2024 |  |  |  | ABS0007 | CRM/DS | Gara Mediamarket | MediaMarket | L. ROBERTO | V. Echarry | Operations | Data Scientist | 20 | 20 | CLOSED | 1 | 2024 | 3 |  |  |  |  | 2 | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0.1 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-12-31 |  | ABS24299 | ABS24299 | HR - BPO CROSS ACTIVITIES | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 570 | 567 | CLOSED | 0 | 2024 | 18 |  |  |  |  | 2 | 5 | 6 |  | 5 |  |  |  | 0 | 0 | 0 | 0 | 0.1 | 0.25 | 0.26087 | 0 | 0.2381 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-01-30 | ABS23135 | AHW5 | HR | HR - Coni di Visibilità - Wave 5 | EssilorLuxottica | L. Roberto | A. Nastasi | Operations | DataManagement | 275 | 0 | CLOSED | 1 | 2024 | 2 |  |  |  |  | 1 | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-01-30 | ABS23135 | AHW5 | HR | HR - Coni di Visibilità - Wave 5 | EssilorLuxottica | L. Roberto | C. Elia | Operations | Architecture Analysis | 275 | 0 | CLOSED | 1 | 2024 | 13 |  |  |  |  | 8 | 1 | 4 | [5 empty] | 0 | 0 | 0 | 0 | 0.4 | 0.05 | 0.17391 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-01-30 | ABS23135 | AHW5 | HR | HR - Coni di Visibilità - Wave 5 | EssilorLuxottica | L. Roberto | F. D'Alberto | Operations | DataManagement | 275 | 0 | CLOSED | 1 | 2024 | 2 |  |  |  |  | 1 | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-01-30 | ABS23135 | AHW5 | HR | HR - Coni di Visibilità - Wave 5 | EssilorLuxottica | L. Roberto | F. Plebani | Operations | Data Management | 275 | 0 | CLOSED | 1 | 2024 | 24 |  |  |  |  | 8 | 8 | 5 |  | 3 |  |  |  | 0 | 0 | 0 | 0 | 0.4 | 0.4 | 0.21739 | 0 | 0.14286 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-01-30 | ABS23135 | AHW5 | HR | HR - Coni di Visibilità - Wave 5 | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 275 | 0 | CLOSED | 1 | 2024 | 8 |  |  |  |  | 4 | 4 | [6 empty] | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-01-30 | ABS23135 | AHW5 | HR | HR - Coni di Visibilità - Wave 5 | EssilorLuxottica | L. Roberto | M. Porcu | Operations | BackEnd | 275 | 0 | CLOSED | 1 | 2024 | 22 |  |  |  |  | 9 | 9 | 4 | [5 empty] | 0 | 0 | 0 | 0 | 0.45 | 0.45 | 0.17391 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-01-30 | ABS23135 | AHW5 | HR | HR - Coni di Visibilità - Wave 5 | EssilorLuxottica | L. Roberto | M. Toci | Operations | BackEnd | 275 | 0 | CLOSED | 1 | 2024 | 28 |  |  |  |  | 9 | 14 | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0.45 | 0.7 | 0.21739 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-01-01 | 2024-12-31 | ABS23135 | AHW5 | HR | HR - Coni di Visibilità - Wave 5 | EssilorLuxottica | L. Roberto | P. Anzellotti | Operations | PM - Project Governance | 275 | 0 | CLOSED | 1 | 2024 | 3 |  |  |  |  | 1 | 1 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0.05 | 0.05 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-01-30 | ABS23135 | AHW5 | HR | HR - Coni di Visibilità - Wave 5 | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects |  | 275 | 0 | CLOSED | 1 | 2024 | 15 | [5 empty] | 5 | 5 |  | 3 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.21739 | 0 | 0.14286 | 0.086957 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-03-01 | 2024-01-30 | ABS23135 | AHW5 | HR | HR - Coni di Visibilità - Wave 5 | EssilorLuxottica | L. Roberto | S. Beltrami | Operations | FrontEnd | 275 | 0 | CLOSED | 1 | 2024 | 12 | [5 empty] | 7 | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.35 | 0.21739 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2024 | 2024-08-01 | 2024-05-31 | ABS24107 | AABGCV | HR | HR - Coni visibilità BO | EssilorLuxottica | L. Roberto | F. Plebani | Operations | BackEnd | 61 | 10 | CLOSED | 0 | 2024 | 1 |  | 2.1 | 2.1 | 3.8 | [5 empty] | 1 |  |  | 0 | 0.105 | 0.1 | 0.17273 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0 | 0
CONTRACT | PRJ | Agile | 2024 | 2024-08-01 | 2024-05-31 | ABS24107 | AABGCV | HR | HR - Coni visibilità BO | EssilorLuxottica | L. Roberto | M. Vimercati | Operations | PM - Project Governance | 61 | 10 | CLOSED | 0 | 2024 | 11 |  | 2.1 | 2.1 | 3.8 | 8 |  |  |  |  | 3 |  |  | 0 | 0.105 | 0.1 | 0.17273 | 0.4 | 0 | 0 | 0 | 0 | 0.13043 | 0 | 0
CONTRACT | PRJ | Agile | 2024 | 2024-08-01 | 2024-05-31 | ABS24107 | AABGCV | HR | HR - Coni visibilità BO | EssilorLuxottica | L. Roberto | R. Alves | Operations | FrontEnd | 61 | 10 | CLOSED | 0 | 2024 | 1 |  |  |  | 9.5 | 1 | [7 empty] | 0 | 0 | 0 | 0.43182 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-12-31 | ABS24048 | ABS24048 | HR | HR - DATAFLOW- ROLLOUT | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | BackEnd | 25 | 0 | CLOSED | 0 | 2024 | 14.4 | 1.8 | 2.1 | 2.1 | 1.9 | 2 | 2 | 2.3 |  | 2.1 | 2.3 | 2 | 1.7 | 0.1 | 0.105 | 0.1 | 0.086364 | 0.1 | 0.1 | 0.1 | 0 | 0.1 | 0.1 | 0.095238 | 0.077273
CONTRACT | PRJ | Agile | 2024 | 2024-02-01 | 2024-04-30 |  |  | HR | HR - ECP MD/TM/PY - ROLLOUT | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | BackEnd | 15 | 0 | ON GOING | 0 | 2024 | 0 |  | 2.5 | 2 | 8 | [8 empty] | 0 | 0.125 | 0.095238 | 0.36364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2024 | 2024-02-01 | 2024-04-30 |  |  | HR | HR - ECP MD/TM/PY - ROLLOUT | EssilorLuxottica | L. Roberto | M. Vimercati | Operations | PM - Project Governance | 15 | 0 | ON GOING | 0 | 2024 | 0 |  | 2.5 | 1 | 4 | [8 empty] | 0 | 0.125 | 0.047619 | 0.18182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-09-18 | 2024-10-03 |  | ABS0008-3 | HR | HR - Gestione permessi Talent V1 | EssilorLuxottica | L. Roberto | C. Elia | Operations | BackEnd | 16 | 14 | CLOSED | 0 | 2024 | 2 | [8 empty] | 2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-09-18 | 2024-10-03 |  | ABS0008-3 | HR | HR - Gestione permessi Talent V1 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | BackEnd | 16 | 14 | CLOSED | 0 | 2024 | 2 | [8 empty] | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0.043478 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-09-18 | 2024-10-03 |  | ABS0008-3 | HR | HR - Gestione permessi Talent V1 | EssilorLuxottica | L. Roberto | M. PORCU | Operations | BackEnd | 16 | 14 | CLOSED | 0 | 2024 | 3 | [8 empty] | 2 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.043478 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-09-18 | 2024-10-03 |  | ABS0008-3 | HR | HR - Gestione permessi Talent V1 | EssilorLuxottica | L. Roberto | M. Toci | Operations | BackEnd | 16 | 14 | CLOSED | 0 | 2024 | 5 | [8 empty] | 3 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.086957 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-09-18 | 2024-10-03 |  | ABS0008-3 | HR | HR - Gestione permessi Talent V1 | EssilorLuxottica | L. Roberto | S. Beltrami | Operations | BackEnd | 16 | 14 | CLOSED | 0 | 2024 | 5 | [8 empty] | 3 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.086957 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-09-18 | 2024-11-18 |  | ABS0008-9 | HR | HR - Gestione permessi Talent v2 | EssilorLuxottica | L. Roberto | A. De Sanctis | Operations | Data Management | 34 | 3 | ON GOING | 0 | 2024 | 4 | [9 empty] | 3 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0.047619 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-09-18 | 2024-11-18 |  | ABS0008-9 | HR | HR - Gestione permessi Talent v2 | EssilorLuxottica | L. Roberto | C. Elia | Operations | Data Engineer | 34 | 3 | ON GOING | 0 | 2024 | 3 | [9 empty] | 1 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.095238 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-09-18 | 2024-11-18 |  | ABS0008-9 | HR | HR - Gestione permessi Talent v2 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 34 | 3 | ON GOING | 0 | 2024 | 3 | [9 empty] | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.047619 | 0.045455
CONTRACT | PRJ | Waterfall | 2024 | 2024-09-18 | 2024-11-18 |  | ABS0008-9 | HR | HR - Gestione permessi Talent v2 | EssilorLuxottica | L. Roberto | M. Porcu | Operations | BackEnd | 34 | 3 | ON GOING | 0 | 2024 | 4 | [9 empty] | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.095238 | 0.045455
CONTRACT | PRJ | Waterfall | 2024 | 2024-09-18 | 2024-11-18 |  | ABS0008-9 | HR | HR - Gestione permessi Talent v2 | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 34 | 0 | ON GOING | 0 | 2024 | 4 | [9 empty] | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.095238 | 0.045455
CONTRACT | PRJ | Waterfall | 2024 | 2024-09-18 | 2024-11-18 |  | ABS0008-9 | HR | HR - Gestione permessi Talent v2 | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 34 | 3 | ON GOING | 0 | 2024 | 5 | [9 empty] | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0.047619 | 0.045455
CONTRACT | PRJ | Time&Materials |  | 2024-01-01 | 2024-09-01 | ABS24027 | LGRAVISION | HR | HR - GV Light | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | BackEnd | 35 | 24 | CLOSED | 1 | 2024 | 4 |  | 6.3 | 1.5 | 1.9 |  |  | 2 |  | 2 |  |  |  | 0 | 0.315 | 0.071429 | 0.086364 | 0 | 0 | 0.086957 | 0 | 0.095238 | 0 | 0 | 0
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-12-31 |  |  | HR | HR - INTEGRAZIONE INFOTYPE 9906 | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | BackEnd | 10 | 0 | CLOSED | 1 | 2024 | 0 |  |  | 5.25 | [9 empty] | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Time&Materials | 2024 | 2024-01-01 | 2024-12-31 |  |  | HR | HR - INTEGRAZIONE INFOTYPE 9906 | EssilorLuxottica | L. Roberto | M. Vimercati | Operations | FrontEnd | 10 | 0 | CLOSED | 1 | 2024 | 0 |  |  | 5.25 | [9 empty] | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 |  | ABS0008-29 | HR | HR - Job Architecture | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Management | 0 | 0 | ON GOING | 0 | 2024 | 10 | [10 empty] | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2381 | 0.22727
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 |  | ABS0008-29 | HR | HR - Job Architecture | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 0 | 0 | ON GOING | 0 | 2024 | 3 | [10 empty] | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0.090909
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 |  | ABS0008-29 | HR | HR - Job Architecture | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 0 | 0 | ON GOING | 0 | 2024 | 6 | [10 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.13636
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 |  | ABS0008-29 | HR | HR - Job Architecture | EssilorLuxottica | L. Roberto | L. Roberto | Operations | Project Governance | 0 | 0 | ON GOING | 0 | 2024 | 3 | [9 empty] | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.047619 | 0.045455
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 |  | ABS0008-29 | HR | HR - Job Architecture | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 0 | 0 | ON GOING | 0 | 2024 | 5 | [9 empty] | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.095238 | 0.045455
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | ABS25085 | ABS25085 | HR | HR - LandingPage wave1 | EssilorLuxottica | L. Roberto | C. Elia | Operations | BackEnd | 65 | 60 | ON HOLD | 0 | 2024 | 17 | [9 empty] | 6 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26087 | 0.28571 | 0.22727
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | ABS25085 | ABS25085 | HR | HR - LandingPage wave1 | EssilorLuxottica | L. Roberto | C. Paz | Delivery Projects | PMO - Project Management Officer | 65 | 60 | ON HOLD | 0 | 2024 | 3 | [9 empty] | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.047619 | 0.045455
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | ABS25085 | ABS25085 | HR | HR - LandingPage wave1 | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 65 | 60 | ON HOLD | 0 | 2024 | 5 | [9 empty] | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.095238 | 0.090909
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | ABS25085 | ABS25085 | HR | HR - LandingPage wave1 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 65 | 60 | ON HOLD | 0 | 2024 | 5 | [9 empty] | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.095238 | 0.045455
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | ABS25085 | ABS25085 | HR | HR - LandingPage wave1 | EssilorLuxottica | L. Roberto | M. Porcu | Operations | BackEnd | 65 | 60 | ON HOLD | 0 | 2024 | 12 | [9 empty] | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.19048 | 0.13636
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | ABS25085 | ABS25085 | HR | HR - LandingPage wave1 | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 65 | 60 | ON HOLD | 0 | 2024 | 7 | [9 empty] | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.095238 | 0.13636
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 | ABS25085 | ABS25085 | HR | HR - LandingPage wave1 | EssilorLuxottica | L. Roberto | S. Delle Fave | Operations | FrontEnd | 65 | 60 | ON HOLD | 0 | 2024 | 6 | [9 empty] | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.095238 | 0.090909
CONTRACT | PRJ | Scrum | 2024 | 2024-01-22 | 2024-05-31 | ABS24059 | DQAW1 | HR | HR - QLIK ASSESSMENT | EssilorLuxottica | L. ROBERTO | E. Storti | Delivery Projects | Analysis | 146 | 151 | CLOSED | 1 | 2024 | 11 |  |  |  |  | 11 | [7 empty] | 0 | 0 | 0 | 0 | 0.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-01-22 | 2024-05-31 | ABS24059 | DQAW1 | HR | HR - QLIK ASSESSMENT | EssilorLuxottica | L. ROBERTO | F. Reale | Operations | FrontEnd | 146 | 151 | CLOSED | 1 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-01-22 | 2024-05-31 | ABS24059 | DQAW1 | HR | HR - QLIK ASSESSMENT | EssilorLuxottica | L. ROBERTO | G. De Feo | Delivery Projects | PMO - Project Management Officer | 146 | 151 | CLOSED | 1 | 2024 | 14 | 2.7 | 14.7 | 14.7 | 13.3 | 14 | [7 empty] | 0.15 | 0.735 | 0.7 | 0.60455 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-01-22 | 2024-05-31 | ABS24059 | DQAW1 | HR | HR - QLIK ASSESSMENT | EssilorLuxottica | L. ROBERTO | M. Porcu | Operations | PM - Project Governance | 146 | 151 | CLOSED | 1 | 2024 | 2 | 2.7 | 2.1 | 2.1 | 1.9 | 2 | [7 empty] | 0.15 | 0.105 | 0.1 | 0.086364 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-01-22 | 2024-05-31 | ABS24059 | DQAW1 | HR | HR - QLIK ASSESSMENT | EssilorLuxottica | L. ROBERTO | M. Vimercati | Operations | FrontEnd | 146 | 151 | CLOSED | 1 | 2024 | 4 | 2.7 | 5.25 | 4.75 | 4.75 | 4 | [7 empty] | 0.15 | 0.2625 | 0.22619 | 0.21591 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-01-22 | 2024-05-31 | ABS24059 | DQAW1 | HR | HR - QLIK ASSESSMENT | EssilorLuxottica | L. ROBERTO | R. Marasca | Delivery Projects | Analysis | 146 | 151 | CLOSED | 1 | 2024 | 11 | 9 | 9 | 9 | 9 | 11 | [7 empty] | 0.5 | 0.45 | 0.42857 | 0.40909 | 0.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile |  | 2024-01-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | HR - Reporting Projects management | EssilorLuxottica | L. Roberto | M. Vimercati | Operations | PM - Project Governance | 570 | 567 | CLOSED | 1 | 2024 | 25 | 14.4 | 12.6 | 5.25 | 3.8 | 5 | 8 | 3 |  | 3 | 2 | 2 | 2 | 0.8 | 0.63 | 0.25 | 0.17273 | 0.25 | 0.4 | 0.13043 | 0 | 0.14286 | 0.086957 | 0.095238 | 0.090909
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-12-02 | 2025-03-18 | ABS25085 | ABS25085 | HR | HR - Revisione DMGLOBAL | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Management | 109 | 60 | ON GOING | 0 | 2024 | 5 | [11 empty] | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22727
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-12-02 | 2025-03-18 | ABS25085 | ABS25085 | HR | HR - Revisione DMGLOBAL | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 109 | 60 | ON GOING | 0 | 2024 | 5 | [11 empty] | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22727
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-12-02 | 2025-03-18 | ABS25085 | ABS25085 | HR | HR - Revisione DMGLOBAL | EssilorLuxottica | L. Roberto | L. Roberto | Operations | Project Governance | 109 | 60 | ON GOING | 0 | 2024 | 3 | [11 empty] | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13636
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-12-02 | 2025-03-18 | ABS25085 | ABS25085 | HR | HR - Revisione DMGLOBAL | EssilorLuxottica | L. Roberto | M. VIMERCATI | Operations | Data Management | 109 | 60 | ON GOING | 0 | 2024 | 5 | [11 empty] | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22727
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-12-02 | 2025-03-18 | ABS25085 | ABS25085 | HR | HR - Revisione DMGLOBAL | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 109 | 60 | ON GOING | 0 | 2024 | 2 | [11 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.090909
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 |  | ABS0008-16 | HR | HR - Revisione PA0002 | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Management | 29 | 12 | CLOSED | 0 | 2024 | 8 | [9 empty] | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0.14286 | 0.090909
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 |  | ABS0008-16 | HR | HR - Revisione PA0002 | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 29 | 12 | CLOSED | 0 | 2024 | 7 | [9 empty] | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0.095238 | 0.090909
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 |  | ABS0008-16 | HR | HR - Revisione PA0002 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | Project Governance | 29 | 12 | CLOSED | 0 | 2024 | 3 | [9 empty] | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.047619 | 0.045455
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 |  | ABS0008-16 | HR | HR - Revisione PA0002 | EssilorLuxottica | L. Roberto | M. VIMERCATI | Operations | Data Management | 29 | 12 | CLOSED | 0 | 2024 | 8 | [9 empty] | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0.14286 | 0.090909
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 |  | ABS0008-16 | HR | HR - Revisione PA0002 | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 29 | 12 | CLOSED | 0 | 2024 | 3 | [9 empty] | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.047619 | 0.045455
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 |  | ABS0008-17 | HR | HR - Revisione PA0709 | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Management | 13 | 0 | CLOSED | 0 | 2024 | 4 | [9 empty] | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.095238 | 0.045455
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 |  | ABS0008-17 | HR | HR - Revisione PA0709 | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 13 | 0 | CLOSED | 0 | 2024 | 4 | [9 empty] | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.047619 | 0.045455
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 |  | ABS0008-17 | HR | HR - Revisione PA0709 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | Project Governance | 13 | 0 | CLOSED | 0 | 2024 | 2 | [9 empty] | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.047619 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 |  | ABS0008-17 | HR | HR - Revisione PA0709 | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 13 | 0 | CLOSED | 0 | 2024 | 3 | [9 empty] | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.047619 | 0.045455
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-01-30 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | A. Brandizzi | Operations | FrontEnd | 450 | 244 | ON GOING | 0 | 2024 | 64 |  |  |  |  | 4 | 12 | 14 |  | 16 | 18 |  |  | 0 | 0 | 0 | 0 | 0.2 | 0.6 | 0.6087 | 0 | 0.7619 | 0.78261 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | A. Lorena | Operations | FrontEnd | 450 | 244 | ON GOING | 0 | 2024 | 3 | [10 empty] | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.045455
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | A. Pirola | Operations | BackEnd | 450 | 244 | ON GOING | 0 | 2024 | 31 | [6 empty] | 1 |  | 15 | 15 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0 | 0.71429 | 0.65217 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | C. Di Lorenzo | Delivery Projects | Analysis | 450 | 244 | ON GOING | 0 | 2024 | 24 | 5 | 5 | 5 | 4 | 4 | 5 | 5 |  | 3 | 3 | 1 | 3 | 0.27778 | 0.25 | 0.2381 | 0.18182 | 0.2 | 0.25 | 0.21739 | 0 | 0.14286 | 0.13043 | 0.047619 | 0.13636
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | C. Elia | Operations | Architecture Analysis | 450 | 244 | ON GOING | 0 | 2024 | 19 | [5 empty] | 4 | 5 |  | 5 | 5 |  |  | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.21739 | 0 | 0.2381 | 0.21739 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | F. Delogu | Operations | BackEnd | 450 | 244 | ON GOING | 0 | 2024 | 45 | [6 empty] | 15 |  | 15 | 15 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.65217 | 0 | 0.71429 | 0.65217 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | F. Spacagna | Operations | BackEnd | 450 | 244 | ON GOING | 0 | 2024 | 4 |  |  |  |  | 2 | 2 | [6 empty] | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | G. De Feo | Delivery Projects | BackEnd | 450 | 244 | ON GOING | 0 | 2024 | 19 | [6 empty] | 5 |  | 4 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0 | 0.19048 | 0.17391 | 0.14286 | 0.13636
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | G. Lopez | Operations | FrontEnd | 450 | 244 | ON GOING | 0 | 2024 | 12 | [10 empty] | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19048 | 0.36364
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | G. Tartaglia | Operations | BackEnd | 450 | 244 | ON GOING | 0 | 2024 | 46 | [6 empty] | 15 |  | 15 | 15 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.65217 | 0 | 0.71429 | 0.65217 | 0.047619 | 0
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | L. Roberto | Operations | PM - Project Governance | 450 | 244 | ON GOING | 0 | 2024 | 21 | 1 | 1 | 1 | 3 | 4 | 4 | 5 |  | 3 | 3 | 1 | 1 | 0.055556 | 0.05 | 0.047619 | 0.13636 | 0.2 | 0.2 | 0.21739 | 0 | 0.14286 | 0.13043 | 0.047619 | 0.045455
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | M. Porcu | Operations | BackEnd | 450 | 244 | ON GOING | 0 | 2024 | 14 | [6 empty] | 5 |  | 4 | 5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0 | 0.19048 | 0.21739 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | M. Toci | Operations | BackEnd | 450 | 244 | ON GOING | 0 | 2024 | 36 | [6 empty] | 1 |  | 17 | 18 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0 | 0.80952 | 0.78261 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | N. Pescione | Operations | BackEnd | 450 | 244 | ON GOING | 0 | 2024 | 3 | [10 empty] | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.045455
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | P. Anzellotti | Operations | BackEnd | 450 | 244 | ON GOING | 0 | 2024 | 11 | [5 empty] | 4 |  |  |  |  | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0 | 0.047619 | 0.27273
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | S. Beltrami | Operations | FrontEnd | 450 | 244 | ON GOING | 0 | 2024 | 46 | [6 empty] | 12 |  | 17 | 17 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.52174 | 0 | 0.80952 | 0.73913 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 | 2024-03-01 | 2024-11-30 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | S. Delle Fave | Operations | FrontEnd | 450 | 244 | ON GOING | 0 | 2024 | 26 | [6 empty] | 6 |  | 9 | 9 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26087 | 0 | 0.42857 | 0.3913 | 0.047619 | 0.045455
INTERNAL PRJ | PRJ |  |  | 2023-09-01 | 2024-05-31 |  | IAA | HR | MY PLACE | Abstract | L. Roberto | A. Brandizzi | Operations | FrontEnd | 0 | 0 | ON GOING | 0 | 2024 | 37 | 18 | 21 | 18 | 19 | 15 | 1 | 7 |  | 5 | 3 | 3 | 3 | 1 | 1.05 | 0.85714 | 0.86364 | 0.75 | 0.05 | 0.30435 | 0 | 0.2381 | 0.13043 | 0.14286 | 0.13636
INTERNAL PRJ | PRJ |  |  | 2023-09-01 | 2024-05-31 |  | IAA | HR | MY PLACE | Abstract | L. Roberto | A. Elia | UX/UI | Graphic Interface | 0 | 0 | ON GOING | 0 | 2024 | 0 |  |  |  | 4.75 | [8 empty] | 0 | 0 | 0 | 0.21591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 | 2023-09-01 | 2024-05-31 |  | IAA | HR | MY PLACE | Abstract | L. Roberto | C. Di Lorenzo | Delivery Projects | Analysis | 0 | 0 | ON GOING | 0 | 2024 | 23 |  |  | 5 | 4 | 4 | 4 | 5 |  | 3 | 3 | 2 | 2 | 0 | 0 | 0.2381 | 0.18182 | 0.2 | 0.2 | 0.21739 | 0 | 0.14286 | 0.13043 | 0.095238 | 0.090909
INTERNAL PRJ | PRJ |  |  | 2023-09-01 | 2024-05-31 |  | IAA | HR | MY PLACE | Abstract | L. Roberto | C. Elia | Operations | BackEnd | 0 | 0 | ON GOING | 0 | 2024 | 14 | 4 | 4 | 4 | 3 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 0.22222 | 0.2 | 0.19048 | 0.13636 | 0.1 | 0.1 | 0.086957 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
INTERNAL PRJ | PRJ |  |  | 2023-09-01 | 2024-05-31 |  | IAA | HR | MY PLACE | Abstract | L. Roberto | F. Spacagna | Operations | BackEnd | 0 | 0 | ON GOING | 0 | 2024 | 14 | 14.4 | 16.8 |  | 2 | 6 | 2 | 2 |  | 2 | 2 |  |  | 0.8 | 0.84 | 0 | 0.090909 | 0.3 | 0.1 | 0.086957 | 0 | 0.095238 | 0.086957 | 0 | 0
INTERNAL PRJ | PRJ |  |  | 2023-09-01 | 2024-05-31 |  | IAA | HR | MY PLACE | Abstract | L. Roberto | G. Esposito | AREA TECH | FrontEnd | 0 | 0 | ON GOING | 0 | 2024 | 4 |  |  |  | 3 | 2 | 2 | [6 empty] | 0 | 0 | 0 | 0.13636 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  |  | 2023-09-01 | 2024-05-31 |  | IAA | HR | MY PLACE | Abstract | L. Roberto | L. Roberto | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2024 | 25 | 4 | 4 | 4 | 5 | 5 | 4 | 4 |  | 4 | 4 | 2 | 2 | 0.22222 | 0.2 | 0.19048 | 0.22727 | 0.25 | 0.2 | 0.17391 | 0 | 0.19048 | 0.17391 | 0.095238 | 0.090909
INTERNAL PRJ | PRJ |  |  | 2023-09-01 | 2024-05-31 |  | IAA | HR | MY PLACE | Abstract | L. Roberto | M. Attanasio | R&D | FrontEnd | 0 | 0 | ON GOING | 0 | 2024 | 1 | 18 | 21 | 18 | 19 | 1 | [7 empty] | 1 | 1.05 | 0.85714 | 0.86364 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  |  | 2023-09-01 | 2024-05-31 |  | IAA | HR | MY PLACE | Abstract | L. Roberto | M. Simeone | Operations | FrontEnd | 0 | 0 | ON GOING | 0 | 2024 | 119 | 18 | 21 | 13 | 15 | 19 | 19 | 18 |  | 18 | 15 | 15 | 15 | 1 | 1.05 | 0.61905 | 0.68182 | 0.95 | 0.95 | 0.78261 | 0 | 0.85714 | 0.65217 | 0.71429 | 0.68182
CONTRACT | PRJ |  | 2024 | 2024-03-15 | 2024-04-30 | ABS24176 | AEPP | OTHER | POC PODCAST | EssilorLuxottica | L. Roberto | A. Elia | UX/UI | Graphic Interface | 18 | 20 | CLOSED | 1 | 2024 | 0 |  |  |  | 1 | [8 empty] | 0 | 0 | 0 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-03-15 | 2024-04-30 | ABS24176 | AEPP | OTHER | POC PODCAST | EssilorLuxottica | L. Roberto | F. Spacagna | Operations | BackEnd | 18 | 20 | CLOSED | 1 | 2024 | 0 |  |  | 1 | 5 | [8 empty] | 0 | 0 | 0.047619 | 0.22727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-03-15 | 2024-04-30 | ABS24176 | AEPP | OTHER | POC PODCAST | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 18 | 20 | CLOSED | 1 | 2024 | 0 |  |  | 1 | 1 | [8 empty] | 0 | 0 | 0.047619 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-03-15 | 2024-04-30 | ABS24176 | AEPP | OTHER | POC PODCAST | EssilorLuxottica | L. Roberto | M. Simeone | Operations | FrontEnd | 18 | 20 | CLOSED | 1 | 2024 | 0 |  |  | 6 | [9 empty] | 0 | 0 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione | EssilorLuxottica | L. Roberto | C. Paz | Delivery Projects | PMO - Project Management Officer | 570 | 567 | CLOSED | 1 | 2024 | 29 | [5 empty] | 3 | 6 |  | 7 | 5 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.26087 | 0 | 0.33333 | 0.21739 | 0.14286 | 0.22727
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 570 | 567 | CLOSED | 1 | 2024 | 36 | [5 empty] | 8 | 8 |  | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.34783 | 0 | 0.2381 | 0.21739 | 0.2381 | 0.22727
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Management | 570 | 567 | CLOSED | 1 | 2024 | 28 | [5 empty] | 3 | 9 |  | 6 | 6 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.3913 | 0 | 0.28571 | 0.26087 | 0.14286 | 0.045455
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione | EssilorLuxottica | L. Roberto | M. Calabrese | Delivery Projects | Analysis | 570 | 567 | CLOSED | 1 | 2024 | 15 | [5 empty] | 3 | 3 |  | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.13043 | 0 | 0.14286 | 0.13043 | 0.095238 | 0.045455
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS25085 | ABS25085 | HR | Qlik - Project Dismissione - DE&I phase 1 | EssilorLuxottica | L. Roberto | C. Paz | Delivery Projects | Project Governance | 80 | 60 | CLOSED | 1 | 2024 | 7 | [9 empty] | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.14286 | 0.13636
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS25085 | ABS25085 | HR | Qlik - Project Dismissione - DE&I phase 1 | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analysis | 80 | 60 | CLOSED | 1 | 2024 | 12 | [8 empty] | 3 | 3 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.13043 | 0.095238 | 0.18182
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS25085 | ABS25085 | HR | Qlik - Project Dismissione - DE&I phase 1 | EssilorLuxottica | L. Roberto | F. Reale | Operations | FrontEnd | 80 | 60 | CLOSED | 1 | 2024 | 9 | [9 empty] | 5 | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.19048 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS25085 | ABS25085 | HR | Qlik - Project Dismissione - DE&I phase 1 | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | Project Governance | 80 | 60 | CLOSED | 1 | 2024 | 9 | [9 empty] | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0.14286 | 0.13636
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS25085 | ABS25085 | HR | Qlik - Project Dismissione - DE&I phase 1 | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 80 | 60 | CLOSED | 1 | 2024 | 10 | [9 empty] | 5 | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.2381 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS25085 | ABS25085 | HR | Qlik - Project Dismissione - DE&I phase 1 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | Project Governance | 80 | 60 | CLOSED | 1 | 2024 | 7 | [8 empty] | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.045455
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS25085 | ABS25085 | HR | Qlik - Project Dismissione - DE&I phase 1 | EssilorLuxottica | L. Roberto | R. Bondi | Operations | FrontEnd | 80 | 60 | CLOSED | 1 | 2024 | 12 | [9 empty] | 6 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26087 | 0.047619 | 0.22727
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-01 | 2024-12-31 | ABS25085 | ABS25085 | HR | Qlik - Project Dismissione - DE&I phase 1 | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 80 | 60 | CLOSED | 1 | 2024 | 9 | [8 empty] | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.13043 | 0.095238 | 0.045455
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - Eye Resumè (Hana Cloud) | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 570 | 567 | CLOSED | 1 | 2024 | 22 | [5 empty] | 3 | 3 |  | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.13043 | 0 | 0.19048 | 0.17391 | 0.19048 | 0.18182
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - POC | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analysis | 570 | 567 | CLOSED | 1 | 2024 | 11 | [8 empty] | 3 | 4 | 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.17391 | 0.19048 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - POC | EssilorLuxottica | L. Roberto | R. Bondi | Operations | FrontEnd | 570 | 567 | CLOSED | 1 | 2024 | 3 | [6 empty] | 1 |  | 2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0 | 0.095238 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - POC | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 570 | 567 | CLOSED | 1 | 2024 | 7 | [8 empty] | 3 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.043478 | 0.047619 | 0.090909
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analysis | 570 | 567 | CLOSED | 1 | 2024 | 27 | [5 empty] | 3 | 1 |  | 6 | 6 | 5 | 6 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.043478 | 0 | 0.28571 | 0.26087 | 0.2381 | 0.27273
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye | EssilorLuxottica | L. Roberto | F. Plebani | Operations | Data Management | 570 | 567 | CLOSED | 1 | 2024 | 11.5 | [6 empty] | 7.5 |  |  | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32609 | 0 | 0 | 0.043478 | 0.095238 | 0.045455
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye | EssilorLuxottica | L. Roberto | F. Reale | Operations | FrontEnd | 570 | 567 | CLOSED | 1 | 2024 | 13 | [8 empty] | 3 | 5 | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.21739 | 0.2381 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Management | 570 | 567 | CLOSED | 1 | 2024 | 29.5 | [6 empty] | 2.5 |  | 2 | 15 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1087 | 0 | 0.095238 | 0.65217 | 0.28571 | 0.18182
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 570 | 567 | CLOSED | 1 | 2024 | 21 | [5 empty] | 3.5 | 3.5 |  | 3.5 | 3.5 | 3.5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0.175 | 0.15217 | 0 | 0.16667 | 0.15217 | 0.16667 | 0.15909
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye | EssilorLuxottica | L. Roberto | L. Roberto | Operations | Project Governance | 570 | 567 | CLOSED | 1 | 2024 | 16 | [8 empty] | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19048 | 0.17391 | 0.19048 | 0.18182
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye | EssilorLuxottica | L. Roberto | M. Vimercati | Operations | Data Management | 570 | 567 | CLOSED | 1 | 2024 | 42 | [5 empty] | 4 | 4 |  | 8 | 14 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.17391 | 0 | 0.38095 | 0.6087 | 0.33333 | 0.22727
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye | EssilorLuxottica | L. Roberto | R. Bondi | Operations | FrontEnd | 570 | 567 | CLOSED | 1 | 2024 | 24 | [5 empty] | 5 | 5 |  | 3 | 3 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.21739 | 0 | 0.14286 | 0.13043 | 0.14286 | 0.22727
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 570 | 567 | CLOSED | 1 | 2024 | 16 | [5 empty] | 2 | 4 |  | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.17391 | 0 | 0.14286 | 0.13043 | 0.14286 | 0.045455
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | C. Di Lorenzo | Delivery Projects | Analysis | 570 | 567 | CLOSED | 1 | 2024 | 8 | [10 empty] | 1 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0.31818
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | C. Elia | Operations | Data Engineering | 570 | 567 | CLOSED | 1 | 2024 | 17 | [6 empty] | 12 |  | 2 |  | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52174 | 0 | 0.095238 | 0 | 0.047619 | 0.090909
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analysis | 570 | 567 | CLOSED | 1 | 2024 | 16 | [5 empty] | 3 | 1 |  | 4 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.043478 | 0 | 0.19048 | 0.17391 | 0.14286 | 0.045455
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | F. Plebani | Operations | Data Management | 570 | 567 | CLOSED | 1 | 2024 | 19.5 | [6 empty] | 7.5 |  | 8 | 2 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.32609 | 0 | 0.38095 | 0.086957 | 0.095238 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Management | 570 | 567 | CLOSED | 1 | 2024 | 31.5 | [6 empty] | 2.5 |  | 18 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1087 | 0 | 0.85714 | 0.21739 | 0.19048 | 0.090909
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 570 | 567 | CLOSED | 1 | 2024 | 4 | [10 empty] | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0.13636
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | G. Tuninetti |  | UX/UI | 570 | 567 | CLOSED | 1 | 2024 | 12 | [6 empty] | 12 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0.52174 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 570 | 567 | CLOSED | 1 | 2024 | 21 | [5 empty] | 3.5 | 3.5 |  | 3.5 | 3.5 | 3.5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0.175 | 0.15217 | 0 | 0.16667 | 0.15217 | 0.16667 | 0.15909
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 570 | 567 | CLOSED | 1 | 2024 | 13 | [8 empty] | 4 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19048 | 0.13043 | 0.14286 | 0.13636
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | M. Porcu | Operations | BackEnd | 570 | 567 | CLOSED | 1 | 2024 | 24 | [5 empty] | 2 | 8 |  | 8 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.34783 | 0 | 0.38095 | 0.17391 | 0.047619 | 0.045455
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | M. Toci | Operations | BackEnd | 570 | 567 | CLOSED | 1 | 2024 | 4 | [6 empty] | 1 |  | 3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0 | 0.14286 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | M. Vimercati | Operations | Data Management | 570 | 567 | CLOSED | 1 | 2024 | 16 | [8 empty] | 7 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33333 | 0.17391 | 0.14286 | 0.090909
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 570 | 567 | CLOSED | 1 | 2024 | 18 | [5 empty] | 2 | 4 |  | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.17391 | 0 | 0.19048 | 0.17391 | 0.095238 | 0.090909
CONTRACT | PRJ | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | S. Beltrami | Operations | FrontEnd | 570 | 567 | CLOSED | 1 | 2024 | 14 | [6 empty] | 12 |  | 2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.52174 | 0 | 0.095238 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2023-10-01 | 2024-03-31 | ABS23397 | AR | CRM/CS | REWARD HUB - AMS | EssilorLuxottica | L. Roberto | C. Di Lorenzo | Delivery Projects | Analysis | 51 | 47 | CLOSED | 1 | 2024 | 0 | 4 | 6 | 6 | [9 empty] | 0.22222 | 0.3 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2023-10-01 | 2024-03-31 | ABS23397 | AR | CRM/CS | REWARD HUB - AMS | EssilorLuxottica | L. Roberto | C. Elia | Operations | BackEnd | 51 | 47 | CLOSED | 1 | 2024 | 0 | 5 | 5 | 5 | [9 empty] | 0.27778 | 0.25 | 0.2381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2023-10-01 | 2024-03-31 | ABS23397 | AR | CRM/CS | REWARD HUB - AMS | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 51 | 47 | CLOSED | 1 | 2024 | 0 | 2.7 | 3.15 | 3 | [9 empty] | 0.15 | 0.1575 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-03-15 | 2024-05-31 | ABS24158 | AER30E | CRM/CS | REWARD HUB w3 | EssilorLuxottica | L. Roberto | A. Elia | UX/UI | Graphic Interface | 192 | 155 | CLOSED | 1 | 2024 | 0 |  |  |  | 7.6 | [8 empty] | 0 | 0 | 0 | 0.34545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-03-15 | 2024-05-31 | ABS24158 | AER30E | CRM/CS | REWARD HUB w3 | EssilorLuxottica | L. Roberto | C. Di Lorenzo | Delivery Projects | Analysis | 192 | 155 | CLOSED | 1 | 2024 | 24 | 9 | 1 | 5 | 11 | 12 | 12 | [6 empty] | 0.5 | 0.05 | 0.2381 | 0.5 | 0.6 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-03-15 | 2024-05-31 | ABS24158 | AER30E | CRM/CS | REWARD HUB w3 | EssilorLuxottica | L. Roberto | C. Elia | Operations | BackEnd | 192 | 155 | CLOSED | 1 | 2024 | 19 |  |  | 5 | 19 | 14 | 5 | [6 empty] | 0 | 0 | 0.2381 | 0.86364 | 0.7 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-03-15 | 2024-05-31 | ABS24158 | AER30E | CRM/CS | REWARD HUB w3 | EssilorLuxottica | L. Roberto | G. Esposito | AREA TECH | FrontEnd | 192 | 155 | CLOSED | 1 | 2024 | 9 |  |  | 1 | 19 | 2 | 7 | [6 empty] | 0 | 0 | 0.047619 | 0.86364 | 0.1 | 0.35 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-03-15 | 2024-05-31 | ABS24158 | AER30E | CRM/CS | REWARD HUB w3 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 192 | 155 | CLOSED | 1 | 2024 | 6 |  |  | 5 | 9.5 | 1 | 5 | [6 empty] | 0 | 0 | 0.2381 | 0.43182 | 0.05 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-03-15 | 2024-05-31 | ABS24158 | AER30E | CRM/CS | REWARD HUB w3 | EssilorLuxottica | L. Roberto | L. Tironese | Operations | FrontEnd | 192 | 155 | CLOSED | 1 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2024 | 2024-04-01 | 2024-07-31 | ABS23342 | ATAW2 | HR | Talent Acquisition W2 - SF fields through API to DWH | EssilorLuxottica | L. Roberto | F. Reale | Operations | FrontEnd | 0 | 0 | CLOSED | 0 | 2024 | 3 | [5 empty] | 3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2024 | 2024-04-01 | 2024-07-31 | ABS23342 | ATAW2 | HR | Talent Acquisition W2 - SF fields through API to DWH | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Engineering | 0 | 0 | CLOSED | 0 | 2024 | 3 | [5 empty] | 3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2024 | 2024-04-01 | 2024-07-31 | ABS23342 | ATAW2 | HR | Talent Acquisition W2 - SF fields through API to DWH | EssilorLuxottica | L. Roberto | M. Vimercati | Operations | PM - Project Governance | 0 | 0 | CLOSED | 0 | 2024 | 10 |  |  |  | 1 | 5 | 3 | 2 | [5 empty] | 0 | 0 | 0 | 0.045455 | 0.25 | 0.15 | 0.086957 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-11-02 | 2025-12-31 | ABS24539 | ABS24539 | CRM/CS | Trenord | Trenord | L. Roberto | L. Roberto | Operations | PM - Project Governance | 58 | 7 | ON GOING | 0 | 2024 | 7 | [10 empty] | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.22727
PRE-SALES | PRJ |  | 2025 | 2025-02-01 | 2025-06-30 |  |  | LOGISTIC | Control tower AI - Preparazione proposta | EssilorLuxottica | M. Calabrese | F. Spacagna | Operations | Tech Lead | 15 | 11 | CLOSED | 1 | 2024 | 2 | [5 empty] | 2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
PRE-SALES | PRJ |  | 2025 | 2025-02-01 | 2025-06-30 |  |  | LOGISTIC | Control tower AI - Preparazione proposta | EssilorLuxottica | M. Calabrese | G. Sironi | Operations | Team Leadership | 15 | 11 | CLOSED | 1 | 2024 | 3 |  |  |  |  | 1 | 2 | [6 empty] | 0 | 0 | 0 | 0 | 0.05 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
PRE-SALES | PRJ |  | 2025 | 2025-02-01 | 2025-06-30 |  |  | LOGISTIC | Control tower AI - Preparazione proposta | EssilorLuxottica | M. Calabrese | M. Calabrese | Delivery Projects | PM - Project Governance | 15 | 11 | CLOSED | 1 | 2024 | 10 |  |  |  |  | 5 | 5 | [6 empty] | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
PRE-SALES | PRJ |  | 2025 | 2025-02-01 | 2025-06-30 |  |  | LOGISTIC | Control tower AI - Preparazione proposta | EssilorLuxottica | M. Calabrese | M. Gomitoni | Operations | Backend | 15 | 11 | CLOSED | 1 | 2024 | 2 | [5 empty] | 2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile |  | 2022-01-01 | 2024-06-01 | ABS23298 | ACTEF | LOGISTIC | ELECTRA FRANCE-AUGE CONTROL TOWER | EssilorLuxottica | M. Calabrese | A. Strada | Operations | DataManagement | 1326 | 1111 | CLOSED | 1 | 2024 | 8.25 | 0.9 | 1.5 | 1.5 | 0.95 | 1 | 4 | 1.15 | 0.6 | 1.5 |  |  |  | 0.05 | 0.075 | 0.071429 | 0.043182 | 0.05 | 0.2 | 0.05 | 0.05 | 0.071429 | 0 | 0 | 0
CONTRACT | PRJ | Agile |  | 2022-01-01 | 2024-06-01 | ABS23298 | ACTEF | LOGISTIC | ELECTRA FRANCE-AUGE CONTROL TOWER | EssilorLuxottica | M. Calabrese | M. Calabrese | Delivery Projects | PM - Project Governance | 1326 | 1111 | CLOSED | 1 | 2024 | 29 | 1 | 1 | 1 | 5 | 5 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 0.055556 | 0.05 | 0.047619 | 0.22727 | 0.25 | 0.3 | 0.13043 | 0.25 | 0.14286 | 0.13043 | 0.14286 | 0.13636
CONTRACT | PRJ | Agile |  | 2022-01-01 | 2024-06-01 | ABS23298 | ACTEF | LOGISTIC | ELECTRA FRANCE-AUGE CONTROL TOWER | EssilorLuxottica | M. Calabrese | M. Sabarese | SAP FIORI | FrontEnd | 1326 | 1111 | CLOSED | 1 | 2024 | 4 | [5 empty] | 4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile |  | 2022-01-01 | 2024-06-01 | ABS23298 | ACTEF | LOGISTIC | ELECTRA FRANCE-AUGE CONTROL TOWER | EssilorLuxottica | M. Calabrese | R. Nunziata | SAP ECC | Analysis | 1326 | 1111 | CLOSED | 1 | 2024 | 12 | 9 | 1.5 | 1.5 | 9.5 | 5 | 5 | 2 | [5 empty] | 0.5 | 0.075 | 0.071429 | 0.43182 | 0.25 | 0.25 | 0.086957 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrumban | 2024 | 2024-01-01 | 2024-04-01 | ABS24103 | AESCARW | BIP | ELIOT SUPPLY CHAIN - ARS RXO W2 | EssilorLuxottica | M. Calabrese | A. Cerrato | Operations | Analysis | 43 | 43 | CLOSED | 1 | 2024 | 0 | 0.9 | 2.1 | 2.1 | [9 empty] | 0.05 | 0.105 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrumban | 2024 | 2024-01-01 | 2024-04-01 | ABS24103 | AESCARW | BIP | ELIOT SUPPLY CHAIN - ARS RXO W2 | EssilorLuxottica | M. Calabrese | M. Calabrese | Delivery Projects | PM - Project Governance | 43 | 43 | CLOSED | 1 | 2024 | 0 | 1.8 | 2.1 | 2.1 | [9 empty] | 0.1 | 0.105 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrumban | 2024 | 2024-01-01 | 2024-04-01 | ABS24103 | AESCARW | BIP | ELIOT SUPPLY CHAIN - ARS RXO W2 | EssilorLuxottica | M. Calabrese | M. Vimercati | Operations | FrontEnd | 43 | 43 | CLOSED | 1 | 2024 | 0 | 0.9 | 1.5 | 1.5 | [9 empty] | 0.05 | 0.075 | 0.071429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrumban | 2024 | 2024-01-01 | 2024-04-01 | ABS24103 | AESCARW | BIP | ELIOT SUPPLY CHAIN - ARS RXO W2 | EssilorLuxottica | M. Calabrese | R. Alves | Operations | FrontEnd | 43 | 43 | CLOSED | 1 | 2024 | 0 |  | 1.5 | 1.5 | [9 empty] | 0 | 0.075 | 0.071429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrumban | 2024 | 2024-01-01 | 2024-04-01 | ABS24103 | AESCARW | BIP | ELIOT SUPPLY CHAIN - ARS RXO W2 | EssilorLuxottica | M. Calabrese | R. Grienti | Operations | DataManagement | 43 | 43 | CLOSED | 1 | 2024 | 0 | 4.5 | 1.5 | 1.5 | [9 empty] | 0.25 | 0.075 | 0.071429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRESALES - DELIVERY | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24293 | ACTU | LOGISTIC | POC - CONTROL TOWER UNIFICATA | EssilorLuxottica | M. Calabrese | M. Calabrese | Delivery Projects | PM - Project Governance | 10 | 8 | CLOSED | 1 | 2024 | 3 |  |  | 2 |  | 1 | 2 | [6 empty] | 0 | 0 | 0.095238 | 0 | 0.05 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRESALES - DELIVERY | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24293 | ACTU | LOGISTIC | POC - CONTROL TOWER UNIFICATA | EssilorLuxottica | M. Calabrese | M. Piazza | SAP ECC | ECC Analyst | 10 | 8 | CLOSED | 1 | 2024 | 2 |  | 1 |  |  | 1 | 1 | [6 empty] | 0 | 0.05 | 0 | 0 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRESALES - DELIVERY | Waterfall | 2024 | 2024-06-01 | 2024-12-31 | ABS24293 | ACTU | LOGISTIC | POC - CONTROL TOWER UNIFICATA | EssilorLuxottica | M. Calabrese | R. Nunziata | SAP ECC | ECC Analyst | 10 | 8 | CLOSED | 1 | 2024 | 1 |  | 1 |  |  |  | 1 | [6 empty] | 0 | 0.05 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
PRE-SALES | PRESALES - GO TO MARKET |  | 2024 | 2024-01-01 | 2024-12-31 |  | ABS0007 | EPM | Attività di Pre-Sales |  | M. COCCHI | A. Albanese | Delivery Projects | Analysis | 0 | 0 | ON GOING | 0 | 2024 | 10 |  | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1 |  |  | 0 | 0.05 | 0.047619 | 0.045455 | 0.15 | 0.15 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0 | 0
PRE-SALES | PRESALES - GO TO MARKET |  | 2024 | 2024-01-01 | 2024-12-31 |  | ABS0007 | OTHER | Attività di Pre-Sales |  | M. COCCHI | F. Lombardini | Consolidated & Tax | Analysis | 0 | 0 | ON GOING | 0 | 2024 | 23 | 2 | 1 | 2 | 1 | 2 | 1 | 2 |  |  |  | 9 | 9 | 0.11111 | 0.05 | 0.095238 | 0.045455 | 0.1 | 0.05 | 0.086957 | 0 | 0 | 0 | 0.42857 | 0.40909
PRE-SALES | PRESALES - GO TO MARKET |  | 2024 | 2024-01-01 | 2024-12-31 |  | ABS0007 | FINANCE | Attività di Pre-Sales |  | M. COCCHI | M. Cocchi | Consolidated & Tax | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2024 | 46 | 9 | 11 | 11 | 1 | 1 | 9 | 11 | 5 | 1 | 11 | 1 | 7 | 0.5 | 0.55 | 0.52381 | 0.045455 | 0.05 | 0.45 | 0.47826 | 0.41667 | 0.047619 | 0.47826 | 0.047619 | 0.31818
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Carrier Manager Activities | Abstract | M. COCCHI | F. Lombardini | Consolidated & Tax | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2024 | 7 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Carrier Manager Activities | Abstract | M. COCCHI | M. Cocchi | Consolidated & Tax | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2024 | 7 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Carrier Manager Activities | Abstract | M. COCCHI | S. Preziosa | Delivery Projects | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2024 | 6 | [5 empty] | 1 | 1 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.043478 | 0 | 0.047619 | 0.043478 | 0.047619 | 0.045455
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-03-31 |  | EPM | OTHER | Corporate Performance Platform | Abstract | M. COCCHI | C. Tiberti | Operations | Analysis | 0 | 0 | ON GOING | 0 | 2024 | 8 | 8 | 8 | 8 | 8 | 8 | [7 empty] | 0.44444 | 0.4 | 0.38095 | 0.36364 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-03-31 |  | EPM | OTHER | Corporate Performance Platform | Abstract | M. COCCHI | F. Lombardini | Consolidated & Tax | Analysis | 0 | 0 | ON GOING | 0 | 2024 | 11 | 5 | 1 | 1 | 1 | 5 | 6 | [6 empty] | 0.27778 | 0.05 | 0.047619 | 0.045455 | 0.25 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-06-05 |  | EPM | CPP | Corporate Performance Platform | Abstract | M. COCCHI | G. Picerno | Consolidated & Tax | Analysis | 0 | 0 | ON GOING | 0 | 2024 | 10 | 7 | 14 | 14 | 12 | 5 | 5 | [6 empty] | 0.38889 | 0.7 | 0.66667 | 0.54545 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRESALES - GO TO MARKET |  | 2024 |  |  |  |  | CPP | CPP - ML forecasting | EssilorLuxottica | M. COCCHI | G. Sironi | Operations | Team Leadership | 0 | 0 | PROPOSAL | 0 | 2024 | 0 |  | 1 | 1 | 1 | [8 empty] | 0 | 0.05 | 0.047619 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRESALES - GO TO MARKET |  | 2024 |  |  |  |  | CPP | CPP - ML forecasting | EssilorLuxottica | M. COCCHI | M. Gomitoni | Operations | Tech Lead | 0 | 0 | PROPOSAL | 0 | 2024 | 0 |  | 1 | 2 | 2 | [8 empty] | 0 | 0.05 | 0.095238 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ |  | 2024 |  |  |  |  | EPM | EPM - Time series forecasting | EssilorLuxottica | M. COCCHI | A. Imbimbo | Operations | Data Scientist | 0 | 0 | CLOSED | 0 | 2024 | 0 | 2 | 4 | 2 | [9 empty] | 0.11111 | 0.2 | 0.095238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ |  | 2024 |  |  |  |  | EPM | EPM - Time series forecasting | EssilorLuxottica | M. COCCHI | F. Malvezzi | Operations | Data Scientist | 0 | 0 | CLOSED | 0 | 2024 | 0 | 4 | 7 | 4 | [9 empty] | 0.22222 | 0.35 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ |  | 2024 |  |  |  |  | EPM | EPM - Time series forecasting | EssilorLuxottica | M. COCCHI | G. Sabbatini | Operations | Data Engineering | 0 | 0 | CLOSED | 0 | 2024 | 0 | 2 | 3 | 2 | [9 empty] | 0.11111 | 0.15 | 0.095238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ |  | 2024 |  |  |  |  | EPM | EPM - Time series forecasting | EssilorLuxottica | M. COCCHI | G. Sironi | Operations | Team Leadership | 0 | 0 | CLOSED | 0 | 2024 | 0 | 2 | 3 | 2 | [9 empty] | 0.11111 | 0.15 | 0.095238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ |  | 2024 |  |  |  |  | EPM | EPM - Time series forecasting | EssilorLuxottica | M. COCCHI | M. Gomitoni | Operations | Tech Lead | 0 | 0 | CLOSED | 0 | 2024 | 0 | 5 | 1 | 5 | [9 empty] | 0.27778 | 0.05 | 0.2381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ |  | 2024 |  |  |  |  | EPM | EPM - Time series forecasting | EssilorLuxottica | M. COCCHI | V. Echarry | Operations | Data Scientist | 0 | 0 | CLOSED | 0 | 2024 | 0 | 4 | 7 | 4 | [9 empty] | 0.22222 | 0.35 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Formazione | Abstract | M. COCCHI | C. Di Lorenzo | Delivery Projects | Training | 19 | 0 | ON GOING | 0 | 2024 | 18 | [5 empty] | 2 | 5 |  | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.21739 | 0 | 0.14286 | 0.13043 | 0.14286 | 0.090909
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Formazione | Abstract | M. COCCHI | E. Storti | Delivery Projects | Training | 14 | 0 | ON GOING | 0 | 2024 | 13 | [5 empty] | 1 | 2 |  | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.086957 | 0 | 0.19048 | 0.086957 | 0.095238 | 0.090909
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Formazione | Abstract | M. COCCHI | F. Lombardini | Consolidated & Tax | Training | 3 | 0 | ON GOING | 0 | 2024 | 3 | [5 empty] | 1 |  |  |  | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0.043478 | 0.047619 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Formazione | Abstract | M. COCCHI | M. Salcini | Consolidated & Tax | Training | 3 | 0 | ON GOING | 0 | 2024 | 3 | [9 empty] | 2 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.047619 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Formazione nuovo assunto | Abstract | M. COCCHI | P. Galvagni | Consolidated & Tax | Training | 1 | 0 | CLOSED | 0 | 2024 | 1.5 | [8 empty] | 0.5 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02381 | 0.043478 | 0 | 0
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2024 | 2024-01-01 | 2024-12-31 |  | IAA | FINANCE | Gestione Consulting | ABSTRACT | M. COCCHI | M. Cocchi | Consolidated & Tax | PM - Project Governance | 0 | 0 | ON GOING | 1 | 2024 | 34 | 9 | 1 | 1 | 9 | 6 | 5 | 5 |  | 5 | 5 | 4 | 4 | 0.5 | 0.05 | 0.047619 | 0.40909 | 0.3 | 0.25 | 0.21739 | 0 | 0.2381 | 0.21739 | 0.19048 | 0.18182
CONTRACT | PRJ |  | 2024-2025 | 2024-11-01 | 2024-06-30 | ABS24604 |  | EPM | KPMG - Ferrero - Supporto + CR | FERRERO | M. COCCHI | A. Albanese | Delivery Projects | PM - Project Governance | 110 | 40 | ON GOING | 0 | 2024 | 1 | [9 empty] | 0.5 | 0.5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021739 | 0.02381 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-11-01 | 2024-06-30 | ABS24604 |  | EPM | KPMG - Ferrero - Supporto + CR | FERRERO | M. COCCHI | A. Albanese | Delivery Projects | PM - Project Governance | 110 | 40 | ON GOING | 0 | 2024 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | [7 empty] | 5 | 0.027778 | 0.025 | 0.02381 | 0.022727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22727
CONTRACT | PRJ |  | 2024-2025 | 2024-11-01 | 2024-06-30 | ABS24604 |  | EPM | KPMG - Ferrero - Supporto + CR | FERRERO | M. COCCHI | A. Di Pietro | Operations | BackEnd | 110 | 40 | ON GOING | 0 | 2024 | 24 | [9 empty] | 13 | 11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.56522 | 0.52381 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-11-01 | 2024-06-30 | ABS24604 |  | EPM | KPMG - Ferrero - Supporto + CR | FERRERO | M. COCCHI | I. Bressan | Operations | BackEnd | 110 | 40 | ON GOING | 0 | 2024 | 17 | [10 empty] | 17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.80952 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-11-01 | 2024-06-30 | ABS24604 |  | EPM | KPMG - Ferrero - Supporto + CR | FERRERO | M. COCCHI | M. Favalli | Operations | BackEnd | 110 | 40 | ON GOING | 0 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - Tax Control Framework | FERRERO | M. COCCHI | A. Albanese | Delivery Projects | PM - Project Governance | 305 | 300 | ON GOING | 0 | 2024 | 19 |  |  |  | 2 | 2 | 3 | 3 |  | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0.090909 | 0.1 | 0.15 | 0.13043 | 0 | 0.14286 | 0.13043 | 0.14286 | 0.090909
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - Tax Control Framework | FERRERO | M. COCCHI | F. Atanasio | Operations | BackEnd | 305 | 300 | ON GOING | 0 | 2024 | 24 |  |  |  |  | 3 | 2 | 16 | 0.5 | 1.5 |  | 1 |  | 0 | 0 | 0 | 0 | 0.15 | 0.1 | 0.69565 | 0.041667 | 0.071429 | 0 | 0.047619 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - Tax Control Framework | FERRERO | M. COCCHI | F. Lombardini | Consolidated & Tax | Analysis | 305 | 300 | ON GOING | 0 | 2024 | 15 |  |  |  |  | 1 | 7 | 4 | 3 |  |  |  |  | 0 | 0 | 0 | 0 | 0.05 | 0.35 | 0.17391 | 0.25 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - Tax Control Framework | FERRERO | M. COCCHI | I. Bressan | Operations | Tech Lead | 305 | 300 | ON GOING | 0 | 2024 | 27 |  |  |  |  | 1 | 16 | 7 |  | 1.5 | 1 | 0.5 |  | 0 | 0 | 0 | 0 | 0.05 | 0.8 | 0.30435 | 0 | 0.071429 | 0.043478 | 0.02381 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - Tax Control Framework | FERRERO | M. COCCHI | P. Galvagni | Consolidated & Tax | Analysis | 305 | 300 | ON GOING | 0 | 2024 | 68 |  |  |  |  | 22 | 2 | 23 |  | 21 |  |  |  | 0 | 0 | 0 | 0 | 1.1 | 0.1 | 1 | 0 | 1 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - Value Chain | FERRERO | M. COCCHI | A. Di Pietro | Operations | BackEnd | 305 | 300 | ON GOING | 0 | 2024 | 36 |  |  |  |  | 2 | 1 | 7 | 5.5 | 6 | 1.5 | 8 | 5 | 0 | 0 | 0 | 0 | 0.1 | 0.05 | 0.30435 | 0.45833 | 0.28571 | 0.065217 | 0.38095 | 0.22727
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - Value Chain | FERRERO | M. COCCHI | L. Mangili | Operations | BackEnd | 305 | 300 | ON GOING | 0 | 2024 | 10 |  |  |  |  | 2 | 1 | 7 | [5 empty] | 0 | 0 | 0 | 0 | 0.1 | 0.05 | 0.30435 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - VBA Support | FERRERO | M. COCCHI | F. De Pedis | Operations | BackEnd | 305 | 300 | CLOSED | 1 | 2024 | 0 |  |  | 3 | 2 | [8 empty] | 0 | 0 | 0.14286 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - VBA Support | FERRERO | M. COCCHI | P. Pieroni | Operations | BackEnd | 305 | 300 | CLOSED | 1 | 2024 | 0 |  |  | 2 | 1.5 | [8 empty] | 0 | 0 | 0.095238 | 0.068182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - Weekly Sales | FERRERO | M. COCCHI | F. Atanasio | Operations | BackEnd | 305 | 300 | ON GOING | 0 | 2024 | 19 |  |  |  | 16 | 19 | [7 empty] | 0 | 0 | 0 | 0.72727 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - Weekly Sales | FERRERO | M. COCCHI | L. Mangili | Operations | BackEnd | 305 | 300 | ON GOING | 0 | 2024 | 41.5 |  |  |  | 14.5 | 18 | 1 | 11 | 2 | 8 | 1.5 |  |  | 0 | 0 | 0 | 0.65909 | 0.9 | 0.05 | 0.47826 | 0.16667 | 0.38095 | 0.065217 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - Weekly Sales (CR Plus) | FERRERO | M. COCCHI | L. Mangili | Operations | BackEnd | 305 | 300 | ON GOING | 0 | 2024 | 35 | [9 empty] | 15 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.65217 | 0.71429 | 0.22727
INTERNAL PRJ | PRJ |  | 2024 |  |  |  | DSL | EPM | Laboratorio AI per Lux | EssilorLuxottica | M. COCCHI | L. Franco | Operations | Analysis | 0 | 0 | CLOSED | 1 | 2024 | 0 | 5 | 5 | [10 empty] | 0.27778 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Skill Acceleration Ed. 2 | Abstract | M. COCCHI | G. Picerno | Consolidated & Tax | Training | 5 | 0 | ON GOING | 0 | 2024 | 5 | [5 empty] | 1 | 1 |  | 1 | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.043478 | 0 | 0.047619 | 0.043478 | 0.047619 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-09-01 | 2024-11-30 |  | ATD | OTHER | Training on the Job FCCS - Pro Vision Group (xView) | Abstract | M. COCCHI | M. Salcini | Consolidated & Tax | BackEnd | 10 | 0 | ON GOING | 0 | 2024 | 10 | [8 empty] | 3 | 5 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.21739 | 0.095238 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-10-15 | 2024-05-30 | ABS24025 | ABS24025 | EPM | Webuild - Migrazione HFM | WeBuild | M. COCCHI | A. Albanese | Delivery Projects | PM - Project Governance | 115 | 15 | ON GOING | 0 | 2024 | 1.5 | [9 empty] | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021739 | 0.02381 | 0.022727
CONTRACT | PRJ |  | 2024-2025 | 2024-10-15 | 2024-05-30 | ABS24025 | ABS24025 | EPM | Webuild - Migrazione HFM | WeBuild | M. COCCHI | Esterno Oracle |  | PM - Project Governance | 115 | 15 | ON GOING | 0 | 2024 | 1 | [11 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.045455
CONTRACT | PRJ |  | 2024-2025 | 2024-10-15 | 2024-05-30 | ABS24025 | ABS24025 | EPM | Webuild - Migrazione HFM | WeBuild | M. COCCHI | F. De Pedis | Operations | BackEnd | 115 | 15 | ON GOING | 0 | 2024 | 2 | [11 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.090909
CONTRACT | PRJ |  | 2024-2025 | 2024-10-15 | 2024-05-30 | ABS24025 | ABS24025 | EPM | Webuild - Migrazione HFM | WeBuild | M. COCCHI | I. Bressan | Operations | Technical Leader | 115 | 15 | ON GOING | 0 | 2024 | 3 | [11 empty] | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13636
CONTRACT | PRJ |  | 2024-2025 | 2024-10-15 | 2024-05-30 | ABS24025 | ABS24025 | EPM | Webuild - Migrazione HFM | WeBuild | M. COCCHI | M. Salcini | Consolidated & Tax | Analysis | 115 | 15 | ON GOING | 0 | 2024 | 2 | [10 empty] | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0
INTERNAL PRJ | PRJ |  | 2024 | 2024-04-01 | 2024-12-31 |  | ABS0008 | ECC | ELETTRA JIRA |  | M. Pallotti | A. Torone | Delivery AMS | PM - Project Governance | 24 | 11 | ON GOING | 0 | 2024 | 17 |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 1 | 2 | 0 | 0 | 0 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0.16667 | 0.095238 | 0.17391 | 0.047619 | 0.090909
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 |  | ABS0008 | ECC | ELETTRA JIRA |  | M. Pallotti | A. Torone | Delivery AMS | PM - Project Governance | 24 | 0 | ON GOING | 0 | 2024 | 8 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.11111 | 0.1 | 0.095238 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 |  | ABS0008 | ECC | ELETTRA JIRA |  | M. Pallotti | C. Paz | Delivery Projects | PMO | 24 | 0 | ON GOING | 0 | 2024 | 15 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0.083333 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | AMS |  | 2024 | 2024-01-01 | 2024-06-30 | ABS24009 | AEAA1 | EPM | HFM Ariston AMS 2024 1 Semestre | ARISTON | M. Salcini | G. Galati | Delivery AMS | BackEnd | 60 | 0 | CLOSED | 1 | 2024 | 8 | 3.6 | 4.2 | 4.2 | 3.8 | 4 | 4 | [6 empty] | 0.2 | 0.21 | 0.2 | 0.17273 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2024-01-01 | 2024-06-30 | ABS24009 | AEAA1 | EPM | HFM Ariston AMS 2024 1 Semestre | ARISTON | M. Salcini | M. Salcini | Consolidated & Tax | PM - Project Governance | 60 | 0 | CLOSED | 1 | 2024 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | [6 empty] | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2024-01-01 | 2024-06-30 | ABS24009 | AEAA1 | EPM | HFM Ariston AMS 2024 1 Semestre | ARISTON | M. Salcini | M. Sorrentino | Consolidated & Tax | Analysis | 60 | 0 | CLOSED | 1 | 2024 | 6 | 1.8 | 2.1 | 2.1 | 1.9 | 2 | 4 | [6 empty] | 0.1 | 0.105 | 0.1 | 0.086364 | 0.1 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2024-01-01 | 2024-06-30 | ABS24009 | AEAA1 | EPM | HFM Ariston AMS 2024 1 Semestre | ARISTON | M. Salcini | R. Freddi | Operations | BackEnd | 60 | 0 | CLOSED | 1 | 2024 | 0 | 1.8 | 2.1 | 2.1 | 1.9 | [8 empty] | 0.1 | 0.105 | 0.1 | 0.086364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2024-01-01 | 2024-06-30 | ABS23317 | AETHA | EPM | Transmec AMS HFM 2023/2024 | Transmec | M. Salcini | G. Galati | Delivery AMS | BackEnd | 30 | 0 | CLOSED | 0 | 2024 | 14 | 1.8 | 2.1 | 2.1 | 1.9 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 0.1 | 0.105 | 0.1 | 0.086364 | 0.1 | 0.1 | 0.086957 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | AMS |  | 2024 | 2024-01-01 | 2024-06-30 | ABS23317 | AETHA | EPM | Transmec AMS HFM 2023/2024 | Transmec | M. Salcini | M. Salcini | Consolidated & Tax | PM - Project Governance | 30 | 0 | CLOSED | 0 | 2024 | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS |  | 2024 | 2024-01-01 | 2024-06-30 | ABS23317 | AETHA | EPM | Transmec AMS HFM 2023/2024 | Transmec | M. Salcini | M. Sorrentino | Consolidated & Tax | Analysis | 30 | 0 | CLOSED | 0 | 2024 | 6 | 1.8 | 2.1 | 2.1 | 1.9 | 3 | 3 | [6 empty] | 0.1 | 0.105 | 0.1 | 0.086364 | 0.15 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-09-01 | 2024-11-30 |  | ATD | OTHER | Corsi OneStream - Essentials | Abstract | M. SORRENTINO | C. Tiberti | Operations | Solution Architect | 4 | 0 | ON GOING | 0 | 2024 | 10 | [9 empty] | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17391 | 0.19048 | 0.090909
INTERNAL TRAINING | FORMAZIONE |  | 2024 |  |  |  | ATD | Formazione | Formazione HFM Consolidato | EssilorLuxottica | M. SORRENTINO | C. Tiberti | Operations | BackEnd | 0 | 0 | PROPOSAL | 0 | 2024 | 12 | [5 empty] | 9 | 3 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.45 | 0.13043 | 0 | 0 | 0 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Formazione Oracle FCCS | Abstract | M. SORRENTINO | C. Esposito | Consolidated & Tax | BackEnd | 3 | 0 | ON GOING | 0 | 2024 | 5 | [6 empty] | 3 |  |  | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0 | 0 | 0.086957 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Formazione Oracle FCCS | Abstract | M. SORRENTINO | C. Tiberti | Operations | BackEnd | 3 | 0 | ON GOING | 0 | 2024 | 5 | [6 empty] | 3 |  |  | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0 | 0 | 0.086957 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Formazione Oracle FCCS | Abstract | M. SORRENTINO | E. Tosetto | Consolidated & Tax | BackEnd | 3 | 0 | ON GOING | 0 | 2024 | 5 | [6 empty] | 3 |  |  | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0 | 0 | 0.086957 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Formazione Oracle FCCS | Abstract | M. SORRENTINO | L. Pigazzini | Consolidated & Tax | BackEnd | 3 | 0 | ON GOING | 0 | 2024 | 5 | [6 empty] | 3 |  |  | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0 | 0 | 0.086957 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Formazione Oracle FCCS | Abstract | M. SORRENTINO | M. Sorrentino | Consolidated & Tax | BackEnd | 3 | 0 | ON GOING | 0 | 2024 | 5 | [6 empty] | 3 |  |  | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0 | 0 | 0.086957 | 0 | 0
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-6 | HR | AMS - HR - Web App -2024 | EssilorLuxottica | N. GUERRERO | L. Carloni | Operations | Data Engineering | 112 | 59 | ON GOING | 0 | 2024 | 0 |  | 2 | 2 | [9 empty] | 0 | 0.1 | 0.095238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-6 | HR | AMS - HR - Web App -2024 | EssilorLuxottica | N. GUERRERO | M. Mannarino | Operations | Data Engineering | 112 | 59 | ON GOING | 0 | 2024 | 19 |  |  |  | 3 | 3 | 3 | 3 |  | 1 | 1 | 4 | 4 | 0 | 0 | 0 | 0.13636 | 0.15 | 0.15 | 0.13043 | 0 | 0.047619 | 0.043478 | 0.19048 | 0.18182
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-6 | HR | AMS - HR - Web App -2024 | EssilorLuxottica | N. GUERRERO | M. Porcu | Operations | Technical Leader | 112 | 59 | ON GOING | 0 | 2024 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 2 | 5 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0 | 0.047619 | 0.043478 | 0.095238 | 0.22727
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-6 | HR | AMS - HR - Web App -2024 | EssilorLuxottica | N. GUERRERO | M. Toci | Operations | BackEnd | 112 | 59 | ON GOING | 0 | 2024 | 14 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-6 | HR | AMS - HR - Web App -2024 | EssilorLuxottica | N. GUERRERO | N. GUERRERO | Delivery AMS | PM - Project Governance | 112 | 59 | ON GOING | 0 | 2024 | 7.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.041667 | 0.047619 | 0.043478 | 0.047619 | 0.045455
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-6 | HR | AMS - HR - Web App -2024 | EssilorLuxottica | N. GUERRERO | R. Marasca | Delivery Projects | Analysis | 112 | 59 | ON GOING | 0 | 2024 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0 | 0.047619 | 0.043478 | 0.047619 | 0
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-6 | HR | AMS - HR - Web App -2024 | EssilorLuxottica | N. GUERRERO | S. Beltrami | Operations | FrontEnd | 112 | 59 | ON GOING | 0 | 2024 | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0 | 0.047619 | 0.043478 | 0.047619 | 0.045455
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-31 | HR | CR - HR - Web App - 2024 | EssilorLuxottica | N. GUERRERO | A. Nastasi | Operations | DataManagement | 35 | 59 | ON GOING | 1 | 2024 | 3 | [5 empty] | 0.5 | 0.5 |  | 1 | 0.5 | 0.5 |  | 0 | 0 | 0 | 0 | 0 | 0.025 | 0.021739 | 0 | 0.047619 | 0.021739 | 0.02381 | 0
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-31 | HR | CR - HR - Web App - 2024 | EssilorLuxottica | N. GUERRERO | L. Carloni | Operations | Data Engineering | 35 | 59 | ON GOING | 1 | 2024 | 0 |  | 0.5 | 0.5 | [9 empty] | 0 | 0.025 | 0.02381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-31 | HR | CR - HR - Web App - 2024 | EssilorLuxottica | N. GUERRERO | M. Mannarino | Operations | Data Engineering | 35 | 59 | ON GOING | 1 | 2024 | 3 |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 |  | 0 | 0 | 0 | 0.022727 | 0.025 | 0.025 | 0.021739 | 0 | 0.02381 | 0.021739 | 0.02381 | 0
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-31 | HR | CR - HR - Web App - 2024 | EssilorLuxottica | N. GUERRERO | M. Porcu | Operations | Technical Leader | 35 | 59 | ON GOING | 1 | 2024 | 8.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 3 | 3 | 0 | 0.025 | 0.02381 | 0.022727 | 0.025 | 0.025 | 0.021739 | 0 | 0.02381 | 0.021739 | 0.14286 | 0.13636
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-31 | HR | CR - HR - Web App - 2024 | EssilorLuxottica | N. GUERRERO | M. Toci | Operations | BackEnd | 35 | 59 | ON GOING | 1 | 2024 | 14 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 8 | 0.027778 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0 | 0.047619 | 0.043478 | 0.047619 | 0.36364
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-31 | HR | CR - HR - Web App - 2024 | EssilorLuxottica | N. GUERRERO | N. GUERRERO | Delivery AMS | PM - Project Governance | 35 | 59 | ON GOING | 1 | 2024 | 1.4 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.011111 | 0.01 | 0.0095238 | 0.0090909 | 0.01 | 0.01 | 0.0086957 | 0 | 0.0095238 | 0.0086957 | 0.0095238 | 0.0090909
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-31 | HR | CR - HR - Web App - 2024 | EssilorLuxottica | N. GUERRERO | R. Marasca | Delivery Projects | Analysis | 35 | 59 | ON GOING | 1 | 2024 | 3.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.027778 | 0.025 | 0.02381 | 0.022727 | 0.025 | 0.025 | 0.021739 | 0 | 0.02381 | 0.021739 | 0.02381 | 0.022727
A CONSUMO | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24011 | ALDAAH2-31 | HR | CR - HR - Web App - 2024 | EssilorLuxottica | N. GUERRERO | S. Beltrami | Operations | FrontEnd | 35 | 59 | ON GOING | 1 | 2024 | 26.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 12 | 12 | 0.055556 | 0.025 | 0.02381 | 0.022727 | 0.025 | 0.025 | 0.021739 | 0 | 0.02381 | 0.021739 | 0.57143 | 0.54545
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | A. De Sanctis | Operations | DataManagement | 0 | 0 | CLOSED | 1 | 2024 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | A. Nastasi | Operations | DataManagement | 0 | 0 | CLOSED | 1 | 2024 | 34 |  |  | 5 | 16 | 17 | 17 | [6 empty] | 0 | 0 | 0.2381 | 0.72727 | 0.85 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | A. Torone | Delivery AMS | FrontEnd | 0 | 0 | CLOSED | 1 | 2024 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | F. D'Alberto | Operations | DataManagement | 0 | 0 | CLOSED | 1 | 2024 | 5 | 1 | 1 | 1 | 1 | 5 | [7 empty] | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | F. Plebani | Operations | DataManagement | 0 | 0 | CLOSED | 1 | 2024 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | G. Cataldo | Operations | DataManagement | 0 | 0 | CLOSED | 1 | 2024 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | I. Bressan | Operations | BackEnd | 0 | 0 | CLOSED | 1 | 2024 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | [6 empty] | 0.27778 | 0.25 | 0.2381 | 0.22727 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | M. Migliorati | Operations | FrontEnd | 0 | 0 | CLOSED | 1 | 2024 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | N. GUERRERO | Delivery AMS | PM - Project Governance | 0 | 0 | CLOSED | 1 | 2024 | 36 | 18 | 18 | 18 | 18 | 18 | 18 | [6 empty] | 1 | 0.9 | 0.85714 | 0.81818 | 0.9 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | R. Alves | Operations | BackEnd | 0 | 0 | CLOSED | 1 | 2024 | 2 |  | 1 | 1 | 1 | 1 | 1 | [6 empty] | 0 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | R. Marasca | Delivery Projects | Data Integrator | 0 | 0 | CLOSED | 1 | 2024 | 1 | [5 empty] | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24048 | ABS24048 | HR | HR Reporting AMS H1 2024 | EssilorLuxottica | N. GUERRERO | W. Morandelli | Operations | FrontEnd | 0 | 0 | CLOSED | 1 | 2024 | 32 | 16 | 16 | 16 | 16 | 16 | 16 | [6 empty] | 0.88889 | 0.8 | 0.7619 | 0.72727 | 0.8 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | A. De Sanctis | Operations | DataManagement | 0 | 0 | ON GOING | 0 | 2024 | 65 | [6 empty] | 1 |  | 21 | 23 | 2 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0 | 1 | 1 | 0.095238 | 0.81818
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | A. Nastasi | Operations | DataManagement | 0 | 0 | ON GOING | 0 | 2024 | 57 | [6 empty] | 2 |  | 14 | 15 | 14 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0 | 0.66667 | 0.65217 | 0.66667 | 0.54545
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | A. Torone | Delivery AMS | FrontEnd | 0 | 0 | ON GOING | 0 | 2024 | 2.5 | [6 empty] | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021739 | 0 | 0.02381 | 0.021739 | 0.02381 | 0.022727
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | F. Plebani | Operations | DataManagement | 0 | 0 | ON GOING | 0 | 2024 | 8 | [6 empty] | 4 |  | 4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.17391 | 0 | 0.19048 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | G. Cataldo | Operations | DataManagement | 0 | 0 | ON GOING | 0 | 2024 | 16 | [6 empty] | 5 |  | 5 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0 | 0.2381 | 0.086957 | 0.095238 | 0.090909
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | G. Fiorentini | Operations | DataManagement | 0 | 0 | ON GOING | 0 | 2024 | 2 | [6 empty] | 1 |  | 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0 | 0.047619 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | G. Galati | Delivery AMS | DataManagement | 0 | 0 | ON GOING | 0 | 2024 | 20 | [8 empty] | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2381 | 0.21739 | 0.2381 | 0.22727
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | G. Mordà | Operations | Data Management | 0 | 0 | ON GOING | 0 | 2024 | 42 | [8 empty] | 6 | 6 | 14 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28571 | 0.26087 | 0.66667 | 0.72727
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | I. Bressan | Operations | BackEnd | 0 | 0 | ON GOING | 0 | 2024 | 7 | [6 empty] | 5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0 | 0.02381 | 0.021739 | 0.02381 | 0.022727
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | L. Cariglia | Operations | DataManagement | 0 | 0 | ON GOING | 0 | 2024 | 30 | [6 empty] | 6 |  | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26087 | 0 | 0.28571 | 0.26087 | 0.28571 | 0.27273
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | M. Migliorati | Operations | FrontEnd | 0 | 0 | ON GOING | 0 | 2024 | 66 | [6 empty] | 2 |  | 21 | 23 | 2 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0 | 1 | 1 | 0.095238 | 0.81818
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | M. Vimercati | Operations | Data Management | 0 | 0 | ON GOING | 0 | 2024 | 6 | [9 empty] | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.095238 | 0.090909
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | N. GUERRERO | Delivery AMS | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2024 | 90 | [6 empty] | 18 |  | 18 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0.78261 | 0 | 0.85714 | 0.78261 | 0.85714 | 0.81818
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | R. Marasca | Delivery Projects | Data Integrator | 0 | 0 | ON GOING | 0 | 2024 | 9 | [6 empty] | 1 |  | 1 | 1 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0 | 0.047619 | 0.043478 | 0.047619 | 0.22727
CONTRACT | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-01 | ABS24080 | ABS24080 | HR | HR Reporting AMS H2 2024 | EssilorLuxottica | N. GUERRERO | W. Morandelli | Operations | FrontEnd | 0 | 0 | ON GOING | 0 | 2024 | 37 | [6 empty] | 16 |  | 21 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.69565 | 0 | 1 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-12-31 |  | IAA | OTHER | CC - Attività |  | O. Sagazio | A. Strada | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2024 | 62.4 |  |  | 8.4 | 7.6 | 8 | 8 | 9.2 | 4.8 | 8.4 | 9.2 | 8 | 6.8 | 0 | 0 | 0.4 | 0.34545 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.38095 | 0.30909
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-12-31 |  | IAA | OTHER | CC - Attività |  | O. Sagazio | G. Sironi | Operations | Team Management | 0 | 0 | ON GOING | 0 | 2024 | 34 |  |  |  |  | 8 | 6 | 3 | 2 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0.4 | 0.3 | 0.13043 | 0.16667 | 0.19048 | 0.17391 | 0.19048 | 0.13636
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-12-31 |  | IAA | OTHER | CC - Attività |  | O. Sagazio | L. Roberto | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2024 | 51 |  |  | 5 | 2 | 2 | 4 | 7 | 7 | 7 | 8 | 8 | 8 | 0 | 0 | 0.2381 | 0.090909 | 0.1 | 0.2 | 0.30435 | 0.58333 | 0.33333 | 0.34783 | 0.38095 | 0.36364
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-12-31 |  | IAA | OTHER | CC - Attività |  | O. Sagazio | M. Porcu | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2024 | 62.4 |  |  | 8.4 | 7.6 | 8 | 8 | 9.2 | 4.8 | 8.4 | 9.2 | 8 | 6.8 | 0 | 0 | 0.4 | 0.34545 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.38095 | 0.30909
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-12-31 |  | IAA | OTHER | CC - supporto CC Leader come Deputy |  | O. Sagazio | P. Anzellotti | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2024 | 37 |  |  | 5.25 | 4.75 | 5 | 5 | 5 | 3 | 5 | 5 | 5 | 4 | 0 | 0 | 0.25 | 0.21591 | 0.25 | 0.25 | 0.21739 | 0.25 | 0.2381 | 0.21739 | 0.2381 | 0.18182
PROSPECT | PRJ |  | 2024 |  |  |  |  | OTHER | DASHBOARDING FOR SAPWIN | EssilorLuxottica | O. Sagazio | t.b.d. | t.b.d. | FrontEnd | 0 | 0 |  | 0 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-08-31 |  | ATD | OTHER | Formazione | Abstract | O. Sagazio | G. Tartaglia | Operations | BackEnd | 0 | 0 | ON GOING | 0 | 2024 | 27 |  |  | 21 | 19 | 2 | 2 | 23 | [5 empty] | 0 | 0 | 1 | 0.86364 | 0.1 | 0.1 | 1 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-01-30 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | A. Nastasi | Operations | DataManagement | 110 | 0 | CLOSED | 1 | 2024 | 1 |  |  | 1.5 | 0.95 | 1 | [7 empty] | 0 | 0 | 0.071429 | 0.043182 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-04-01 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | D. Scalia | Operations | BackEnd | 110 | 0 | CLOSED | 1 | 2024 | 0 | 1.8 | 12.6 | 12.6 | [9 empty] | 0.1 | 0.63 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-04-01 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | D. Scarci | Operations | FrontEnd | 110 | 0 | CLOSED | 1 | 2024 | 0 | 18 | 21 | 21 | [9 empty] | 1 | 1.05 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-04-01 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | E. Soldoni | Operations | Graphic Interface | 110 | 0 | CLOSED | 1 | 2024 | 0 | 9 | 1.5 | 1.5 | [9 empty] | 0.5 | 0.075 | 0.071429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-04-01 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | E. Uliu | Operations | FrontEnd | 110 | 0 | CLOSED | 1 | 2024 | 0 | 9 | 1.5 | 1.5 | [9 empty] | 0.5 | 0.075 | 0.071429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-01-30 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | F. D'Alberto | Operations | DataManagement | 110 | 0 | CLOSED | 1 | 2024 | 1 |  |  | 1.5 | 0.95 | 1 | [7 empty] | 0 | 0 | 0.071429 | 0.043182 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-04-01 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | G. De Feo | Delivery Projects | PMO - Project Management Officer | 110 | 0 | CLOSED | 1 | 2024 | 2 |  |  | 4.2 | 3.8 | 2 | [7 empty] | 0 | 0 | 0.2 | 0.17273 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-04-01 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | L. Carloni | Operations | Data Engineering | 110 | 0 | CLOSED | 1 | 2024 | 0 | 18 | 21 | 1.5 | [9 empty] | 1 | 1.05 | 0.071429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-04-01 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | L. Tironese | Operations | Architecture Analysis | 110 | 0 | CLOSED | 1 | 2024 | 0 | 18 | 21 | 21 | [9 empty] | 1 | 1.05 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-01-30 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | M. Porcu | Operations | Architecture Analysis | 110 | 0 | CLOSED | 1 | 2024 | 1 |  |  | 9.45 | 8.55 | 1 | [7 empty] | 0 | 0 | 0.45 | 0.38864 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-01-30 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | M. Toci | Operations | BackEnd | 110 | 0 | CLOSED | 1 | 2024 | 2 |  |  | 4.2 | 3.8 | 2 | [7 empty] | 0 | 0 | 0.2 | 0.17273 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-04-01 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | O. Sagazio | Operations | PM - Project Governance | 110 | 0 | CLOSED | 1 | 2024 | 0 | 7.2 | 8.4 | 8.4 | [9 empty] | 0.4 | 0.42 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-04-01 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | P. Anzellotti | Operations | PM - Project Governance | 110 | 0 | CLOSED | 1 | 2024 | 1 |  |  | 1.5 | 0.95 | 1 | [7 empty] | 0 | 0 | 0.071429 | 0.043182 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-03-01 | 2024-04-01 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | R. Marasca | Delivery Projects | Analysis | 110 | 0 | CLOSED | 1 | 2024 | 3 |  | 4 | 4 | 3 | 3 | [7 empty] | 0 | 0.2 | 0.19048 | 0.13636 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  |  | 2024-03-01 | 2024-01-30 | ABS23221 | HW6WAS | HR | HR - SPLITTING W6 | EssilorLuxottica | O. Sagazio | S. Beltrami | Operations | FrontEnd | 110 | 0 | CLOSED | 1 | 2024 | 4 |  |  | 8.4 | 7.6 | 4 | [7 empty] | 0 | 0 | 0.4 | 0.34545 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ | Scrum | 2024 | 2024-11-15 | 2025-01-14 |  |  | RETAIL | HR - BUONI SCONTO - LSA | EssilorLuxottica | P. Anzellotti | A. Lorena | Operations | FrontEnd | 22 | 0 | ON GOING | 0 | 2024 | 5 | [10 empty] | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.090909
LEAD | PRJ | Scrum | 2024 | 2024-11-15 | 2025-01-14 |  |  | RETAIL | HR - BUONI SCONTO - LSA | EssilorLuxottica | P. Anzellotti | G. TARTAGLIA | Operations | BackEnd | 22 | 0 | ON GOING | 0 | 2024 | 5 | [10 empty] | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.090909
LEAD | PRJ | Scrum | 2024 | 2024-11-15 | 2025-01-14 |  |  | RETAIL | HR - BUONI SCONTO - LSA | EssilorLuxottica | P. Anzellotti | P. Anzellotti | Operations | Techincal Leader | 22 | 0 | ON GOING | 0 | 2024 | 7 | [10 empty] | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19048 | 0.13636
CONTRACT | PRJ | Scrum | 2024 | 2024-02-15 | 2024-07-01 | ABS24138 | AHBSDW | HR | HR - BUONI SCONTO - W2 | EssilorLuxottica | P. Anzellotti | N. Pescione | Operations | BackEnd | 156 | 0 | CLOSED | 1 | 2024 | 4 |  |  | 1.5 | 9.5 | 1 | 3 | [6 empty] | 0 | 0 | 0.071429 | 0.43182 | 0.05 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-02-15 | 2024-07-01 | ABS24138 | AHBSDW | HR | HR - BUONI SCONTO - W2 | EssilorLuxottica | P. Anzellotti | P. Anzellotti | Operations | PM - Project Governance | 156 | 0 | CLOSED | 1 | 2024 | 18 |  |  | 12.6 | 11.4 | 12 | 6 | [6 empty] | 0 | 0 | 0.6 | 0.51818 | 0.6 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-02-15 | 2024-07-01 | ABS24138 | AHBSDW | HR | HR - BUONI SCONTO - W2 | EssilorLuxottica | P. Anzellotti | R. Marasca | Delivery Projects | Analysis | 156 | 0 | CLOSED | 1 | 2024 | 0 | 5 | 4 | 4 | 4 | [8 empty] | 0.27778 | 0.2 | 0.19048 | 0.18182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-02-15 | 2024-07-01 | ABS24138 | AHBSDW | HR | HR - BUONI SCONTO - W2 | EssilorLuxottica | P. Anzellotti | S. Delle Fave | Operations | FrontEnd | 156 | 0 | CLOSED | 1 | 2024 | 9 |  |  | 7.35 | 6.65 | 7 | 2 | [6 empty] | 0 | 0 | 0.35 | 0.30227 | 0.35 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-01-01 | 2024-12-01 | ABS24138 | AHBSDW | HR | HR - BUONI SCONTO - W2 - CR | EssilorLuxottica | P. Anzellotti | M. Toci | Operations | BackEnd | 17 | 0 | CLOSED | 1 | 2024 | 2 | [6 empty] | 2 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-01-01 | 2024-12-01 | ABS24138 | AHBSDW | HR | HR - BUONI SCONTO - W2 - CR | EssilorLuxottica | P. Anzellotti | P. Anzellotti | Operations | Techincal Leader | 17 | 0 | CLOSED | 1 | 2024 | 4 | [6 empty] | 4 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0.17391 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2024 | 2024-01-01 | 2024-12-01 | ABS24138 | AHBSDW | HR | HR - BUONI SCONTO - W2 - CR | EssilorLuxottica | P. Anzellotti | S. Delle Fave | Operations | BackEnd | 17 | 0 | CLOSED | 1 | 2024 | 2 | [6 empty] | 2 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ | Scrum | 2024 | 2024-01-01 | 2024-12-01 | ABS24344 | ABS0008 | RETAIL | HR - BUONI SCONTO - W3 | EssilorLuxottica | P. Anzellotti | N. Pescione | Operations | BackEnd | 42 | 0 | CLOSED | 0 | 2024 | 4 | [8 empty] | 1 | 2 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0.086957 | 0.047619 | 0
LEAD | PRJ | Scrum | 2024 | 2024-01-01 | 2024-12-01 | ABS24344 | ABS0008 | RETAIL | HR - BUONI SCONTO - W3 | EssilorLuxottica | P. Anzellotti | P. Anzellotti | Operations | Techincal Leader | 42 | 0 | CLOSED | 0 | 2024 | 14 | [8 empty] | 3 | 8 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.34783 | 0.14286 | 0
LEAD | PRJ | Scrum | 2024 | 2024-01-01 | 2024-12-01 | ABS24344 | ABS0008 | RETAIL | HR - BUONI SCONTO - W3 | EssilorLuxottica | P. Anzellotti | S. Delle Fave | Operations | BackEnd | 42 | 0 | CLOSED | 0 | 2024 | 10 | [8 empty] | 2 | 6 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.26087 | 0.095238 | 0
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Carrier Manager Activities | Abstract | P. Pieroni | A. Di Pietro | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2024 | 7 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Carrier Manager Activities | Abstract | P. Pieroni | I. Bressan | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2024 | 7 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Carrier Manager Activities | Abstract | P. Pieroni | N. Fragale | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2024 | 7 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | EPM | Carrier Manager Activities | Abstract | P. Pieroni | P. Pieroni | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2024 | 6 | [5 empty] | 1 | 1 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.043478 | 0 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ABS0007 | PRACTICE DI | CDC/AREA MANAGEMENT | ABSTRACT | P. Pieroni | P. Pieroni | Operations | PM - Project Governance | 30 | 20 | ON GOING | 1 | 2024 | 30 | [5 empty] | 5 | 5 |  | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.21739 | 0 | 0.2381 | 0.21739 | 0.2381 | 0.22727
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-09-01 | 2024-12-31 |  | ATD | OTHER | Coaching | Abstract | P. Pieroni | F. De Pedis | Operations | BackEnd | 15 | 0 | ON GOING | 0 | 2024 | 15 | [8 empty] | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19048 | 0.17391 | 0.19048 | 0.13636
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-09-01 | 2024-12-31 |  | ATD | OTHER | Coaching | Abstract | P. Pieroni | I. Bressan | Operations | BackEnd | 15 | 0 | ON GOING | 0 | 2024 | 15 | [8 empty] | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19048 | 0.17391 | 0.19048 | 0.13636
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-09-01 | 2024-12-31 |  | ATD | OTHER | Coaching | Abstract | P. Pieroni | L. Franco | Operations | BackEnd | 15 | 0 | ON GOING | 0 | 2024 | 15 | [8 empty] | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19048 | 0.17391 | 0.19048 | 0.13636
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-09-01 | 2024-11-30 |  | ATD | OTHER | Corsi OneStream - Essentials | Abstract | P. Pieroni | I. Bressan | Operations | Solution Architect | 4 | 0 | ON GOING | 0 | 2024 | 10 | [9 empty] | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17391 | 0.19048 | 0.090909
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-09-01 | 2024-11-30 |  | ATD | OTHER | Corsi OneStream - Essentials | Abstract | P. Pieroni | P. Pieroni | Operations | BackEnd | 4 | 0 | ON GOING | 0 | 2024 | 11 | [8 empty] | 1 | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0.21739 | 0.14286 | 0.090909
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Formazione Oracle FCCS | Abstract | P. Pieroni | F. Atanasio | Operations | BackEnd | 3 | 0 | ON GOING | 0 | 2024 | 5 | [6 empty] | 3 |  |  | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0 | 0 | 0.086957 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Formazione Oracle FCCS | Abstract | P. Pieroni | F. De Pedis | Operations | BackEnd | 3 | 0 | ON GOING | 0 | 2024 | 5 | [6 empty] | 3 |  |  | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0 | 0 | 0.086957 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-01-01 | 2024-12-31 |  | ATD | OTHER | Formazione Oracle FCCS | Abstract | P. Pieroni | L. Franco | Operations | BackEnd | 3 | 0 | ON GOING | 0 | 2024 | 5 | [6 empty] | 3 |  |  | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0 | 0 | 0.086957 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 |  |  |  | DSL | FINANCE | Laboratorio per Lux |  | P. Pieroni | C. Paz | Delivery Projects | Analysis | 0 | 0 | CLOSED | 1 | 2024 | 14 | 14.4 | 16.8 | 16.8 | 5.7 | 6 | 8 | [6 empty] | 0.8 | 0.84 | 0.8 | 0.25909 | 0.3 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 |  |  |  | DSL | FINANCE | Laboratorio per Lux |  | P. Pieroni | F. Atanasio | Operations | BackEnd | 0 | 0 | ON GOING | 0 | 2024 | 0 |  | 4.2 | 7.35 | [9 empty] | 0 | 0.21 | 0.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 |  |  |  | DSL | FINANCE | Laboratorio per Lux |  | P. Pieroni | L. Mangili | Operations | BackEnd | 0 | 0 | ON GOING | 0 | 2024 | 0 | 1.8 | 21 | 21 | [9 empty] | 0.1 | 1.05 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 |  |  |  | DSL | FINANCE | Laboratorio per Lux |  | P. Pieroni | M. Favalli | Operations | BackEnd | 0 | 0 | ON GOING | 0 | 2024 | 0 | 9 | 14.7 | 18.9 | 11.4 | [8 empty] | 0.5 | 0.735 | 0.9 | 0.51818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 |  |  |  | DSL | FINANCE | Laboratorio per Lux |  | P. Pieroni | P. Buonasorte | Operations | BackEnd | 0 | 0 | ON GOING | 0 | 2024 | 0 | 9 | 14.7 | 18.9 | [9 empty] | 0.5 | 0.735 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-05-31 |  | ABS0007 | FINANCE | POC per Lux | EssilorLuxottica | P. Pieroni | C. Paz | Delivery Projects | Analysis | 0 | 0 | ON GOING | 0 | 2024 | 0 | 9 | 1.5 | 1.5 | 5.7 | [8 empty] | 0.5 | 0.075 | 0.071429 | 0.25909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-05-31 |  | ABS0007 | FINANCE | POC per Lux | EssilorLuxottica | P. Pieroni | F. Atanasio | Operations | BackEnd | 0 | 0 | ON GOING | 0 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-05-31 |  | ABS0007 | FINANCE | POC per Lux | EssilorLuxottica | P. Pieroni | L. Mangili | Operations | BackEnd | 0 | 0 | ON GOING | 0 | 2024 | 0 | 1.8 | 1.5 | 1.5 | [9 empty] | 0.1 | 0.075 | 0.071429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-05-31 |  | ABS0007 | FINANCE | POC per Lux | EssilorLuxottica | P. Pieroni | M. Favalli | Operations | BackEnd | 0 | 0 | ON GOING | 0 | 2024 | 0 | 9 | 1.5 | 1.5 | 9.5 | [8 empty] | 0.5 | 0.075 | 0.071429 | 0.43182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2024 | 2024-01-01 | 2024-05-31 |  | ABS0007 | FINANCE | POC per Lux | EssilorLuxottica | P. Pieroni | P. Buonasorte | Operations | BackEnd | 0 | 0 | ON GOING | 0 | 2024 | 0 | 9 | 1.5 | 1.5 | [9 empty] | 0.5 | 0.075 | 0.071429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Time&Materials | 2024 | 2024-04-01 | 2024-12-31 | ABS24342 | ABS24342 | EPM | RTT_Supporto_Piattaforma_Oracle_EPM | RTT | P. Pieroni | M. Favalli | Operations | BackEnd | 10 | 10 | CLOSED | 1 | 2024 | 5 | [6 empty] | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Time&Materials | 2024 | 2024-04-01 | 2024-12-31 | ABS24342 | ABS24342 | EPM | RTT_Supporto_Piattaforma_Oracle_EPM | RTT | P. Pieroni | P. Pieroni | Operations | BackEnd | 10 | 10 | CLOSED | 1 | 2024 | 5.5 |  |  |  | 2 | 1 | 4 | 0.5 | [5 empty] | 0 | 0 | 0 | 0.090909 | 0.05 | 0.2 | 0.021739 | 0 | 0 | 0 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-09-01 | 2024-11-30 |  | ATD | OTHER | Training on the Job FCCS - Pro Vision Group (xView) | Abstract | P. Pieroni | F. Atanasio | Operations | BackEnd | 10 | 0 | ON GOING | 0 | 2024 | 10 | [8 empty] | 3 | 5 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.21739 | 0.095238 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-09-01 | 2024-11-30 |  | ATD | OTHER | Training on the Job FCCS - Pro Vision Group (xView) | Abstract | P. Pieroni | F. De Pedis | Operations | BackEnd | 10 | 0 | ON GOING | 0 | 2024 | 10 | [8 empty] | 3 | 5 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.21739 | 0.095238 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2024 | 2024-09-01 | 2024-11-30 |  | ATD | OTHER | Training on the Job FCCS - Pro Vision Group (xView) | Abstract | P. Pieroni | M. Sorrentino | Consolidated & Tax | BackEnd | 10 | 0 | ON GOING | 0 | 2024 | 10 | [8 empty] | 3 | 5 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14286 | 0.21739 | 0.095238 | 0
CONTRACT | AMS |  | 2024 | 2024-01-01 | 2024-12-31 |  | EURMP | EPM | URMET - AMS Essbase | URMET | P. Pieroni | A. Di Pietro | Operations | BackEnd | 30 | 0 | ON GOING | 0 | 2024 | 1 | 0.9 | 1.5 | 2.1 | 0.95 | 1 | [7 empty] | 0.05 | 0.075 | 0.1 | 0.043182 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2024-01-01 | 2024-12-31 |  | EURMP | EPM | URMET - AMS Essbase | URMET | P. Pieroni | P. Pieroni | Operations | Analysis | 30 | 0 | ON GOING | 0 | 2024 | 1 | 0.9 | 1.5 | 2.1 | 0.95 | 1 | [7 empty] | 0.05 | 0.075 | 0.1 | 0.043182 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ |  | 2024 |  |  |  |  | R&D | R&D Lucy Control Tower con Generative AI | EssilorLuxottica | R. RUGGERI | A. Imbimbo | Operations | Data Scientist | 35 | 27 | CLOSED | 1 | 2024 | 22 |  |  |  | 5 | 7 | 7 | 7 |  | 1 |  |  |  | 0 | 0 | 0 | 0.22727 | 0.35 | 0.35 | 0.30435 | 0 | 0.047619 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-07-15 | 2024-10-15 |  |  | EPM | Essilor Wave1 - Upload Statutory Data From FDW | EssilorLuxottica | S. Preziosa | A. Albanese | Delivery Projects | Analysis | 20 | 0 | ON HOLD | 0 | 2024 | 7 | [6 empty] | 2 | 1 | 2 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.083333 | 0.095238 | 0.086957 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-10-15 |  |  | EPM | Essilor Wave1 - Upload Statutory Data From FDW | EssilorLuxottica | S. Preziosa | P. Singh | AREA TECH | BackEnd | 20 | 0 | ON HOLD | 0 | 2024 | 10 | [6 empty] | 5 | 1 | 2 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.083333 | 0.095238 | 0.086957 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-10-15 |  |  | EPM | Essilor Wave1 - Upload Statutory Data From FDW | EssilorLuxottica | S. Preziosa | S. Preziosa | Delivery Projects | Analysis | 20 | 0 | ON HOLD | 0 | 2024 | 10 | [6 empty] | 5 | 1 | 2 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.083333 | 0.095238 | 0.086957 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24044 | ABA2W | RETAIL | BULLSEYE AMS 2024 | EssilorLuxottica | T. Porzio | A. Ferrari | Operations | DataManagement | 200 | 78 | CLOSED | 0 | 2024 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0 | 0.047619 | 0.043478 | 0.047619 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24044 | ABA2W | RETAIL | BULLSEYE AMS 2024 | EssilorLuxottica | T. Porzio | A. Lorena | Operations | FrontEnd | 200 | 78 | CLOSED | 0 | 2024 | 14 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0.083333 | 0.095238 | 0.086957 | 0.095238 | 0.045455
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24044 | ABA2W | RETAIL | BULLSEYE AMS 2024 | EssilorLuxottica | T. Porzio | A. PIROLA | Operations | FrontEnd | 200 | 78 | CLOSED | 0 | 2024 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24044 | ABA2W | RETAIL | BULLSEYE AMS 2024 | EssilorLuxottica | T. Porzio | A. Vladi | Operations | DataManagement | 200 | 78 | CLOSED | 0 | 2024 | 16 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0.16667 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24044 | ABA2W | RETAIL | BULLSEYE AMS 2024 | EssilorLuxottica | T. Porzio | F. D'Alberto | Operations | DataManagement/SQL | 200 | 78 | CLOSED | 0 | 2024 | 45 |  | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 6 | 6 | 6 | 5 | 0 | 0.3 | 0.28571 | 0.27273 | 0.3 | 0.3 | 0.26087 | 0.33333 | 0.28571 | 0.26087 | 0.28571 | 0.22727
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24044 | ABA2W | RETAIL | BULLSEYE AMS 2024 | EssilorLuxottica | T. Porzio | F. Origlia | Operations | Architecture Analysis | 200 | 78 | CLOSED | 0 | 2024 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [7 empty] | 0.027778 | 0.025 | 0.02381 | 0.022727 | 0.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24044 | ABA2W | RETAIL | BULLSEYE AMS 2024 | EssilorLuxottica | T. Porzio | F. Origlia | Operations | BackEnd | 200 | 78 | CLOSED | 0 | 2024 | 1 | 1 | 1 | 1 | 1 | 1 | [7 empty] | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24044 | ABA2W | RETAIL | BULLSEYE AMS 2024 | EssilorLuxottica | T. Porzio | F. Spacagna | Operations | BackEnd | 200 | 78 | CLOSED | 0 | 2024 | 7 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.090909
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24044 | ABA2W | RETAIL | BULLSEYE AMS 2024 | EssilorLuxottica | T. Porzio | L. Franceschini | Delivery Projects | PM - Project Governance | 200 | 78 | CLOSED | 0 | 2024 | 2 | 1 | 2 | 2 | 2 | 2 | [7 empty] | 0.055556 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24044 | ABA2W | RETAIL | BULLSEYE AMS 2024 | EssilorLuxottica | T. Porzio | M. Vianelli | Delivery Projects | Analysis | 200 | 78 | CLOSED | 0 | 2024 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 |  | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0 | 0.095238 | 0.086957 | 0.095238 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24044 | ABA2W | RETAIL | BULLSEYE AMS 2024 | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 200 | 78 | CLOSED | 0 | 2024 | 21.5 | [5 empty] | 3 | 3 | 0.5 | 2 | 3 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.13043 | 0.041667 | 0.095238 | 0.13043 | 0.2381 | 0.22727
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24353 | ABS24353 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 1H | EssilorLuxottica | T. Porzio | A. Ferrari | Operations | BackEnd | 100 | 70 | CLOSED | 1 | 2024 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24353 | ABS24353 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 1H | EssilorLuxottica | T. Porzio | A. Lorena | Operations | FrontEnd | 100 | 70 | CLOSED | 1 | 2024 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | [6 empty] | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24353 | ABS24353 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 1H | EssilorLuxottica | T. Porzio | A. Nastasi | Operations | DataManagement | 100 | 70 | CLOSED | 1 | 2024 | 0 | 2 | 2 | 2 | [9 empty] | 0.11111 | 0.1 | 0.095238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24353 | ABS24353 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 1H | EssilorLuxottica | T. Porzio | A. PIROLA | Operations | FrontEnd | 100 | 70 | CLOSED | 1 | 2024 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24353 | ABS24353 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 1H | EssilorLuxottica | T. Porzio | A. Vladi | Operations | Team Leadership | 100 | 70 | CLOSED | 1 | 2024 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24353 | ABS24353 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 1H | EssilorLuxottica | T. Porzio | F. D'Alberto | Operations | BackEnd | 100 | 70 | CLOSED | 1 | 2024 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | [6 empty] | 0.27778 | 0.25 | 0.2381 | 0.22727 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24353 | ABS24353 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 1H | EssilorLuxottica | T. Porzio | L. Franceschini | Delivery Projects | PM - Project Governance | 100 | 70 | CLOSED | 1 | 2024 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-06-30 | ABS24353 | ABS24353 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 1H | EssilorLuxottica | T. Porzio | M. Vianelli | Delivery Projects | Analysis | 100 | 70 | CLOSED | 1 | 2024 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24354 | ABS24354 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 2H | EssilorLuxottica | T. Porzio | A. Ferrari | Operations | BackEnd | 100 | 30 | CLOSED | 0 | 2024 | 13 | [9 empty] | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.2381 | 0.13636
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24354 | ABS24354 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 2H | EssilorLuxottica | T. Porzio | A. Lorena | Operations | FrontEnd | 100 | 30 | CLOSED | 0 | 2024 | 9 | [9 empty] | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0.14286 | 0.13636
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24354 | ABS24354 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 2H | EssilorLuxottica | T. Porzio | A. Nastasi | Operations | DataManagement | 100 | 30 | CLOSED | 0 | 2024 | 6 | [9 empty] | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.095238 | 0.090909
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24354 | ABS24354 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 2H | EssilorLuxottica | T. Porzio | A. PIROLA | Operations | FrontEnd | 100 | 30 | CLOSED | 0 | 2024 | 1.5 | [9 empty] | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021739 | 0.02381 | 0.022727
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24354 | ABS24354 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 2H | EssilorLuxottica | T. Porzio | A. Vladi | Operations | Team Leadership | 100 | 30 | CLOSED | 0 | 2024 | 3 | [9 empty] | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.047619 | 0.045455
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24354 | ABS24354 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 2H | EssilorLuxottica | T. Porzio | F. D'Alberto | Operations | BackEnd | 100 | 30 | CLOSED | 0 | 2024 | 18 | [9 empty] | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26087 | 0.28571 | 0.27273
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24354 | ABS24354 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 2H | EssilorLuxottica | T. Porzio | M. Vianelli | Delivery Projects | Analysis | 100 | 30 | CLOSED | 0 | 2024 | 6 | [9 empty] | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.095238 | 0.090909
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24354 | ABS24354 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2024 2H | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 100 | 30 | CLOSED | 0 | 2024 | 9 | [9 empty] | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0.14286 | 0.13636
CONTRACT | AMS | Waterfall | 2024 | 2023-07-01 | 2024-06-30 | ABS24042 | AEEQ2 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | A. Di Pietro | Operations | BackEnd | 134 | 64 | CLOSED | 0 | 2024 | 5 |  | 3.15 | 2.1 | 2.85 | 3 | 2 | [6 empty] | 0 | 0.1575 | 0.1 | 0.12955 | 0.15 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2023-07-01 | 2024-06-30 | ABS24042 | AEEQ2 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | G. Minervini | Operations | BackEnd - Junior | 134 | 64 | CLOSED | 0 | 2024 | 8 | 3.6 | 4.2 | 4.2 | 3.8 | 4 | 4 | [6 empty] | 0.2 | 0.21 | 0.2 | 0.17273 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2023-07-01 | 2024-06-30 | ABS24042 | AEEQ2 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | N. Fragale | Operations | Analysis | 134 | 64 | CLOSED | 0 | 2024 | 8 |  | 2 | 4.2 | 3.8 | 4 | 4 | [6 empty] | 0 | 0.1 | 0.2 | 0.17273 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2023-07-01 | 2024-06-30 | ABS24042 | AEEQ2 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | O. BEN OTHMANE | Operations | BackEnd | 134 | 64 | CLOSED | 0 | 2024 | 8 | 3.6 | 4.2 | 4.2 | 3.8 | 4 | 4 | [6 empty] | 0.2 | 0.21 | 0.2 | 0.17273 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2023-07-01 | 2024-06-30 | ABS24042 | AEEQ2 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | P. Pieroni | Operations | BackEnd | 134 | 64 | CLOSED | 0 | 2024 | 9 | 2.7 | 3.15 |  | 2.85 | 3 | 2 | 2 | 2 |  |  |  |  | 0.15 | 0.1575 | 0 | 0.12955 | 0.15 | 0.1 | 0.086957 | 0.16667 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2023-07-01 | 2024-06-30 | ABS24042 | AEEQ2 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | S. Preziosa | Delivery Projects | PM - Project Governance | 134 | 64 | CLOSED | 0 | 2024 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2023-07-01 | 2024-06-30 | ABS24042 | AEEQ2 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | V. Raso | Operations | BackEnd | 134 | 64 | CLOSED | 0 | 2024 | 8 | 3.6 | 4.2 | 4.2 | 3.8 | 4 | 4 | [6 empty] | 0.2 | 0.21 | 0.2 | 0.17273 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS25063 | ABS25063 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2024 | EssilorLuxottica | T. Porzio | A. Di Pietro | Operations | BackEnd | 150 | 36 | CLOSED | 0 | 2024 | 14 | [6 empty] | 5 | 1 | 5 | 1 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.083333 | 0.2381 | 0.043478 | 0 | 0.090909
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS25063 | ABS25063 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2024 | EssilorLuxottica | T. Porzio | E. Storti | Delivery Projects | BackEnd | 150 | 36 | CLOSED | 0 | 2024 | 11.5 | [6 empty] | 0.5 |  | 1 | 1 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021739 | 0 | 0.047619 | 0.043478 | 0.19048 | 0.22727
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS25063 | ABS25063 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2024 | EssilorLuxottica | T. Porzio | L. Franco | Operations | BackEnd | 150 | 36 | CLOSED | 0 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS25063 | ABS25063 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2024 | EssilorLuxottica | T. Porzio | L. Mangili | Operations | BackEnd | 150 | 36 | CLOSED | 0 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS25063 | ABS25063 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2024 | EssilorLuxottica | T. Porzio | M. Favalli | Operations | BackEnd - Junior | 150 | 36 | CLOSED | 0 | 2024 | 5 | [11 empty] | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22727
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS25063 | ABS25063 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2024 | EssilorLuxottica | T. Porzio | N. Fragale | Operations | BackEnd | 150 | 36 | CLOSED | 0 | 2024 | 16 | [6 empty] | 2 |  | 2 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0 | 0.095238 | 0.21739 | 0.19048 | 0.13636
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS25063 | ABS25063 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2024 | EssilorLuxottica | T. Porzio | O. BEN OTHMANE | Operations | BackEnd - Junior | 150 | 36 | CLOSED | 0 | 2024 | 29 | [6 empty] | 9 | 2 | 9 | 4 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3913 | 0.16667 | 0.42857 | 0.17391 | 0.095238 | 0.13636
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS25063 | ABS25063 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2024 | EssilorLuxottica | T. Porzio | P. Pieroni | Operations | BackEnd | 150 | 36 | CLOSED | 0 | 2024 | 15.05 | [6 empty] | 3.45 | 0.5 | 2.1 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.041667 | 0.1 | 0.17391 | 0.14286 | 0.090909
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS25063 | ABS25063 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2024 | EssilorLuxottica | T. Porzio | S. Preziosa | Delivery Projects | Analysis | 150 | 36 | CLOSED | 0 | 2024 | 14 | [6 empty] | 2 |  | 2 | 2 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0 | 0.095238 | 0.086957 | 0.14286 | 0.22727
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS25063 | ABS25063 | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2024 | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 150 | 36 | CLOSED | 0 | 2024 | 5 | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0 | 0.047619 | 0.043478 | 0.047619 | 0.045455
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 |  |  | EPM | Emerald - CR PLUS 2025 H1 | EssilorLuxottica | T. Porzio | C. Esposito | Consolidated & Tax | BackEnd | 40 | 0 | TO START | 0 | 2024 | 2 | [11 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.090909
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 |  |  | EPM | Emerald - CR PLUS 2025 H1 | EssilorLuxottica | T. Porzio | E. Tosetto | Consolidated & Tax | BackEnd | 40 | 0 | TO START | 0 | 2024 | 2 | [11 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.090909
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 |  |  | EPM | Emerald - CR PLUS 2025 H1 | EssilorLuxottica | T. Porzio | L. Pigazzini | Consolidated & Tax | BackEnd - Junior | 40 | 0 | TO START | 0 | 2024 | 2 | [11 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.090909
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 |  |  | EPM | Emerald - CR PLUS 2025 H1 | EssilorLuxottica | T. Porzio | M. Salcini | Consolidated & Tax | Analysis | 40 | 0 | TO START | 0 | 2024 | 2 | [11 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.090909
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 |  |  | EPM | Emerald - CR PLUS 2025 H1 | EssilorLuxottica | T. Porzio | M. Sorrentino | Consolidated & Tax | BackEnd | 40 | 0 | TO START | 0 | 2024 | 2 | [11 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.090909
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 |  |  | EPM | Emerald - CR PLUS 2025 H1 | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 40 | 0 | TO START | 0 | 2024 | 2 | [11 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.090909
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24333 | ABS24333 | EPM | HFM Ariston AMS 2024 2 Semestre | ARISTON | T. Porzio | G. Galati | Delivery AMS | BackEnd | 45 | 8 | ON GOING | 0 | 2024 | 6 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24333 | ABS24333 | EPM | HFM Ariston AMS 2024 2 Semestre | ARISTON | T. Porzio | M. Salcini | Consolidated & Tax | Analysis | 45 | 8 | ON GOING | 0 | 2024 | 4.5 | [6 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021739 | 0.041667 | 0.02381 | 0.021739 | 0.02381 | 0.090909
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24333 | ABS24333 | EPM | HFM Ariston AMS 2024 2 Semestre | ARISTON | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 45 | 8 | ON GOING | 0 | 2024 | 1 | [6 empty] | 0.2 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0086957 | 0 | 0.0095238 | 0.0086957 | 0.0095238 | 0.0090909
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | A. Di Pietro | Operations | BackEnd | 1812 | 1872 | CLOSED | 0 | 2024 | 60 | 14 | 17 | 17 | 15 | 16 | 8 | 8 | 6 | 5 | 5 | 5 | 7 | 0.77778 | 0.85 | 0.80952 | 0.68182 | 0.8 | 0.4 | 0.34783 | 0.5 | 0.2381 | 0.21739 | 0.2381 | 0.31818
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | C. Esposito | Consolidated & Tax | BackEnd | 1812 | 1872 | CLOSED | 0 | 2024 | 84 | 14 | 17 | 17 | 1 | 1 | 1 | 15 | 4 | 17 | 16 | 15 | 15 | 0.77778 | 0.85 | 0.80952 | 0.045455 | 0.05 | 0.05 | 0.65217 | 0.33333 | 0.80952 | 0.69565 | 0.71429 | 0.68182
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | E. Storti | Delivery Projects | Analysis | 1812 | 1872 | CLOSED | 0 | 2024 | 8 | 14 | 16 | 16 | 14 | 5 | 3 | [6 empty] | 0.77778 | 0.8 | 0.7619 | 0.63636 | 0.25 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | E. Tosetto | Consolidated & Tax | BackEnd | 1812 | 1872 | CLOSED | 0 | 2024 | 116 | 14 | 17 | 17 | 15 | 16 | 5 | 18 | 1 | 14 | 23 | 22 | 17 | 0.77778 | 0.85 | 0.80952 | 0.68182 | 0.8 | 0.25 | 0.78261 | 0.083333 | 0.66667 | 1 | 1.0476 | 0.77273
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | F. De Pedis | Operations | BackEnd | 1812 | 1872 | CLOSED | 0 | 2024 | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | F. Lombardini | Consolidated & Tax | Analysis | 1812 | 1872 | CLOSED | 0 | 2024 | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | G. Galati | Delivery AMS | BackEnd | 1812 | 1872 | CLOSED | 0 | 2024 | 7 | 3 | 3 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 0.16667 | 0.15 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | G. Minervini | Operations | BackEnd - Junior | 1812 | 1872 | CLOSED | 0 | 2024 | 115 | 14 | 17 | 17 | 15 | 16 | 16 | 18 | 6 | 17 | 23 | 2 | 17 | 0.77778 | 0.85 | 0.80952 | 0.68182 | 0.8 | 0.8 | 0.78261 | 0.5 | 0.80952 | 1 | 0.095238 | 0.77273
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | L. Franco | Operations | BackEnd | 1812 | 1872 | CLOSED | 0 | 2024 | 10 | [5 empty] | 5 | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.21739 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | L. Pigazzini | Consolidated & Tax | BackEnd - Junior | 1812 | 1872 | CLOSED | 0 | 2024 | 61 | [8 empty] | 19 | 23 | 2 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90476 | 1 | 0.095238 | 0.77273
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | M. Salcini | Consolidated & Tax | Analysis | 1812 | 1872 | CLOSED | 0 | 2024 | 41 | 12 | 15 | 15 | 13 | 12 | 8 | 2 | 5 | 3 | 5 | 5 | 1 | 0.66667 | 0.75 | 0.71429 | 0.59091 | 0.6 | 0.4 | 0.086957 | 0.41667 | 0.14286 | 0.21739 | 0.2381 | 0.045455
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | M. Sorrentino | Consolidated & Tax | Backend | 1812 | 1872 | CLOSED | 0 | 2024 | 39 | 12 | 15 | 15 | 13 | 12 | 8 | 2 | 6 | 3 | 1 | 6 | 1 | 0.66667 | 0.75 | 0.71429 | 0.59091 | 0.6 | 0.4 | 0.086957 | 0.5 | 0.14286 | 0.043478 | 0.28571 | 0.045455
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | N. Fragale | Operations | BackEnd | 1812 | 1872 | CLOSED | 0 | 2024 | 121 | 14 | 17 | 17 | 15 | 16 | 16 | 18 | 6 | 17 | 18 | 16 | 14 | 0.77778 | 0.85 | 0.80952 | 0.68182 | 0.8 | 0.8 | 0.78261 | 0.5 | 0.80952 | 0.78261 | 0.7619 | 0.63636
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | O. BEN OTHMANE | Operations | BackEnd - Junior | 1812 | 1872 | CLOSED | 0 | 2024 | 108 | 14 | 17 | 17 | 15 | 16 | 16 | 18 | 6 | 17 | 19 | 2 | 14 | 0.77778 | 0.85 | 0.80952 | 0.68182 | 0.8 | 0.8 | 0.78261 | 0.5 | 0.80952 | 0.82609 | 0.095238 | 0.63636
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | P. Buonasorte | Operations | BackEnd - Junior | 1812 | 1872 | CLOSED | 0 | 2024 | 33 | [5 empty] | 1 | 1 | 5 | 1 | 13 | 11 | 1 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.043478 | 0.41667 | 0.047619 | 0.56522 | 0.52381 | 0.045455
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | P. Pieroni | Operations | BackEnd | 1812 | 1872 | CLOSED | 0 | 2024 | 13 | 14 | 17 | 17 | 15 | 1 | 1 | 1 | 6 | 1 | 1 | 1 | 1 | 0.77778 | 0.85 | 0.80952 | 0.68182 | 0.05 | 0.05 | 0.043478 | 0.5 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | R. Freddi | Operations | BackEnd | 1812 | 1872 | CLOSED | 0 | 2024 | 0 | 2 | 2 | 2 | 2 | [8 empty] | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | S. Preziosa | Delivery Projects | Analysis | 1812 | 1872 | CLOSED | 0 | 2024 | 64 | 13 | 16 | 16 | 14 | 9 | 8 | 9 | 6 | 7 | 7 | 9 | 9 | 0.72222 | 0.8 | 0.7619 | 0.63636 | 0.45 | 0.4 | 0.3913 | 0.5 | 0.33333 | 0.30435 | 0.42857 | 0.40909
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 1812 | 1872 | CLOSED | 0 | 2024 | 30 | [6 empty] | 5 | 2 | 1 | 8 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.16667 | 0.047619 | 0.34783 | 0.38095 | 0.27273
CONTRACT | AMS | Waterfall | 2024 | 2024-01-01 | 2024-12-31 | ABS24041 | ALDEAE2 | EPM | LUX-DI-EPM-AMS EssilorLuxottica EPM 2024 | EssilorLuxottica | T. Porzio | V. Raso | Operations | BackEnd | 1812 | 1872 | CLOSED | 0 | 2024 | 115 | 14 | 17 | 17 | 15 | 16 | 16 | 18 | 6 | 17 | 23 | 2 | 17 | 0.77778 | 0.85 | 0.80952 | 0.68182 | 0.8 | 0.8 | 0.78261 | 0.5 | 0.80952 | 1 | 0.095238 | 0.77273
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24359 | ABS24359 | EPM | LUX–DI-EPM–enhancements plus 10 HFM Q3Q4 2024 | EssilorLuxottica | T. Porzio | C. Esposito | Consolidated & Tax | BackEnd | 40 | 18 | CLOSED | 0 | 2024 | 7 | [6 empty] | 3 |  |  | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0 | 0 | 0.043478 | 0.047619 | 0.090909
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24359 | ABS24359 | EPM | LUX–DI-EPM–enhancements plus 10 HFM Q3Q4 2024 | EssilorLuxottica | T. Porzio | M. Salcini | Consolidated & Tax | Analysis | 40 | 18 | CLOSED | 0 | 2024 | 9 | [6 empty] | 3 | 1 |  | 1 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0.083333 | 0 | 0.043478 | 0.047619 | 0.13636
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24359 | ABS24359 | EPM | LUX–DI-EPM–enhancements plus 10 HFM Q3Q4 2024 | EssilorLuxottica | T. Porzio | M. Sorrentino | Consolidated & Tax | Backend | 40 | 18 | CLOSED | 0 | 2024 | 10 | [6 empty] | 3 |  |  | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0 | 0 | 0.086957 | 0.095238 | 0.13636
A CONSUMO | AMS | Waterfall | 2024 | 2024-07-01 | 2024-12-31 | ABS24359 | ABS24359 | EPM | LUX–DI-EPM–enhancements plus 10 HFM Q3Q4 2024 | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 40 | 18 | CLOSED | 0 | 2024 | 1.5 | [9 empty] | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021739 | 0.02381 | 0.022727
CONTRACT | AMS |  | 2024 | 2024-07-01 | 2024-12-31 | ABS24332 | ABS24332 | EPM | Transmec AMS HFM 2024/2025 | Transmec | T. Porzio | C. Esposito | Consolidated & Tax | BackEnd | 15 | 3 | ON GOING | 0 | 2024 | 9 | [6 empty] | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.065217 | 0.125 | 0.071429 | 0.065217 | 0.071429 | 0.068182
CONTRACT | AMS |  | 2024 | 2024-07-01 | 2024-12-31 | ABS24332 | ABS24332 | EPM | Transmec AMS HFM 2024/2025 | Transmec | T. Porzio | M. Sorrentino | Consolidated & Tax | Analysis | 15 | 3 | ON GOING | 0 | 2024 | 4.5 | [6 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021739 | 0.041667 | 0.02381 | 0.021739 | 0.02381 | 0.090909
CONTRACT | AMS |  | 2024 | 2024-07-01 | 2024-12-31 | ABS24332 | ABS24332 | EPM | Transmec AMS HFM 2024/2025 | Transmec | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 15 | 3 | ON GOING | 0 | 2024 | 1.2 | [6 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0086957 | 0.016667 | 0.0095238 | 0.0086957 | 0.0095238 | 0.0090909
CONTRACT | AMS |  | 2023-2024 | 2023-10-01 | 2024-09-24 | ABS24024 | BS23402 | EPM | WEBUILD AMS HFM 10/23 - 09/24 | WeBuild | T. Porzio | C. Esposito | Consolidated & Tax | BackEnd | 60 | 47 | CLOSED | 0 | 2024 | 14 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 |  |  |  | 0.16667 | 0.15 | 0.14286 | 0.13636 | 0.15 | 0.15 | 0.13043 | 0.16667 | 0.14286 | 0 | 0 | 0
CONTRACT | AMS |  | 2023-2024 | 2023-10-01 | 2024-09-24 | ABS24024 | BS23402 | EPM | WEBUILD AMS HFM 10/23 - 09/24 | WeBuild | T. Porzio | M. Salcini | Consolidated & Tax | Analysis | 60 | 47 | CLOSED | 0 | 2024 | 5 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 |  |  |  | 0.16667 | 0.15 | 0.14286 | 0.13636 | 0.05 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0 | 0 | 0
CONTRACT | AMS |  | 2023-2024 | 2023-10-01 | 2024-09-24 | ABS24024 | BS23402 | EPM | WEBUILD AMS HFM 10/23 - 09/24 | WeBuild | T. Porzio | M. Sorrentino | Consolidated & Tax | Technical Leader | 60 | 47 | CLOSED | 0 | 2024 | 8 | 2 | 2 | 2 | 2 | 2 | 3 | 1 | 1 | 1 |  |  |  | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.15 | 0.043478 | 0.083333 | 0.047619 | 0 | 0 | 0
CONTRACT | AMS |  | 2024-2025 | 2024-10-01 | 2025-09-30 | ABS24404 | ABS24404 | EPM | WEBUILD AMS HFM 10/24 - 09/25 | WeBuild | T. Porzio | C. Esposito | Consolidated & Tax | BackEnd | 15 | 0 | ON GOING | 0 | 2024 | 9 | [9 empty] | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0.14286 | 0.13636
CONTRACT | AMS |  | 2024-2025 | 2024-10-01 | 2025-09-30 | ABS24404 | ABS24404 | EPM | WEBUILD AMS HFM 10/24 - 09/25 | WeBuild | T. Porzio | M. Salcini | Consolidated & Tax | Analysis | 15 | 0 | ON GOING | 0 | 2024 | 3 | [9 empty] | 0.5 | 0.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021739 | 0.02381 | 0.090909
CONTRACT | AMS |  | 2024-2025 | 2024-10-01 | 2025-09-30 | ABS24404 | ABS24404 | EPM | WEBUILD AMS HFM 10/24 - 09/25 | WeBuild | T. Porzio | M. Sorrentino | Consolidated & Tax | Technical Leader | 15 | 0 | ON GOING | 0 | 2024 | 3 | [9 empty] | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS |  | 2024-2025 | 2024-10-01 | 2025-09-30 | ABS24404 | ABS24404 | EPM | WEBUILD AMS HFM 10/24 - 09/25 | WeBuild | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 15 | 0 | ON GOING | 0 | 2024 | 0.6 | [9 empty] | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0086957 | 0.0095238 | 0.0090909
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-04-30 |  | ESE | OTHER | ESSILOR SEE4C FR | EssilorLuxottica | Xherahu Florida | R. Bondi | Operations | FrontEnd | 0 | 0 | CLOSED | 1 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-04-30 |  | ESE | OTHER | ESSILOR SEE4C US | EssilorLuxottica | Xherahu Florida | A. Strada | Operations | BackEnd | 0 | 0 | ON HOLD | 0 | 2024 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-04-01 | 2024-04-30 |  | ESE | OTHER | ESSILOR SEE4C US | EssilorLuxottica | Xherahu Florida | R. Bondi | Operations | FrontEnd | 0 | 0 | ON GOING | 0 | 2024 | 4 |  |  |  |  | 4 | [7 empty] | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS24401 | ABS24401 | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - EVOLUTIVA DI 2024 | AO FERRARA | A. Coletti | A. Elia | UI | Front End | 100 | 258 | ON GOING | 0 | 2025 | 0 |  |  | 15 | 15 | [8 empty] | 0 | 0 | 0.71429 | 0.68182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS24401 | ABS24401 | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - EVOLUTIVA DI 2024 | AO FERRARA | A. Coletti | L. Lazzari | SAP ECC | Account Manager | 100 | 258 | ON GOING | 0 | 2025 | 0 |  |  | 2 | 2 | [8 empty] | 0 | 0 | 0.095238 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS24401 | ABS24401 | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - EVOLUTIVA DI 2024 | AO FERRARA | A. Coletti | M. Calabrese | Delivery Projects | PM - Project Governance | 100 | 258 | ON GOING | 0 | 2025 | 2 | 5 | 5 | 5 | 5 | 2 | [7 empty] | 0.27778 | 0.25 | 0.2381 | 0.22727 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS24401 | ABS24401 | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - EVOLUTIVA DI 2024 | AO FERRARA | A. Coletti | R. Tortora | Operations | Front End | 100 | 258 | ON GOING | 0 | 2025 | 0 |  |  | 1 | 1 | [8 empty] | 0 | 0 | 0.047619 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-12-01 | 2024-12-24 | ABS24565 | ABS24565 | LOGISTIC | CONTROL TOWER - Grand Vision Italy and Poland plant integration | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | Data Engineering | 30 | 29 | CLOSED | 1 | 2025 | 0 | 8 | [11 empty] | 0.44444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-12-01 | 2024-12-24 | ABS24565 | ABS24565 | LOGISTIC | CONTROL TOWER - Grand Vision Italy and Poland plant integration | EssilorLuxottica | A. Cuomo | J. Daci | Operations | BackEnd | 30 | 29 | CLOSED | 1 | 2025 | 0 | 8 | [11 empty] | 0.44444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-12-01 | 2024-12-24 | ABS24565 | ABS24565 | LOGISTIC | CONTROL TOWER - Grand Vision Italy and Poland plant integration | EssilorLuxottica | A. Cuomo | T. Lazzari | SAP ECC | ECC Developer | 30 | 29 | CLOSED | 1 | 2025 | 0 | 4 | [11 empty] | 0.22222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-20 | 2025-03-08 | ABS25101 | ABS25101 | LOGISTIC | Control Tower (Mercury) - LensBest website integration | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | Data Engineering | 32 | 30 | CLOSED | 1 | 2025 | 0 | 3 | 15 | 1 | [9 empty] | 0.16667 | 0.75 | 0.047619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-20 | 2025-03-08 | ABS25101 | ABS25101 | LOGISTIC | Control Tower (Mercury) - LensBest website integration | EssilorLuxottica | A. Cuomo | T. Lazzari | SAP ECC | ECC Developer | 32 | 30 | CLOSED | 1 | 2025 | 0 | 5 | 15 | 3 | [9 empty] | 0.27778 | 0.75 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-07 | 2025-03-08 | ABS25102 | ABS25102 | LOGISTIC | Control Tower (Mercury) - Rollout + CRs | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | Data Engineering | 105 | 97 | CLOSED | 1 | 2025 | 0 | 16 | 5 | 5 | [9 empty] | 0.88889 | 0.25 | 0.2381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-07 | 2025-03-08 | ABS25102 | ABS25102 | LOGISTIC | Control Tower (Mercury) - Rollout + CRs | EssilorLuxottica | A. Cuomo | F. Tarquini | SAP ECC | ECC Analyst | 105 | 97 | CLOSED | 1 | 2025 | 0 | 2 | 15 | 5 | [9 empty] | 0.11111 | 0.75 | 0.2381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-07 | 2025-03-08 | ABS25102 | ABS25102 | LOGISTIC | Control Tower (Mercury) - Rollout + CRs | EssilorLuxottica | A. Cuomo | J. Daci | Operations | BackEnd | 105 | 97 | CLOSED | 1 | 2025 | 0 | 16 | 2 | 5 | [9 empty] | 0.88889 | 0.1 | 0.2381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-07 | 2025-03-08 | ABS25102 | ABS25102 | LOGISTIC | Control Tower (Mercury) - Rollout + CRs | EssilorLuxottica | A. Cuomo | T. Lazzari | SAP ECC | ECC Developer | 105 | 97 | CLOSED | 1 | 2025 | 0 | 11 | 5 | [10 empty] | 0.61111 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-03-10 | 2025-09-12 | ABS25287 | ABS25287 | LOGISTIC | CONTROL TOWER MERCURY - REPLENISHMENT BBP | EssilorLuxottica | A. Cuomo | A. Camara | SAP ECC | ECC Analyst | 475 | 111 | ON GOING | 0 | 2025 | 38 |  |  | 8 | 8 | 10 | 10 | 7 | 6 | 5 |  |  |  | 0 | 0 | 0.38095 | 0.36364 | 0.5 | 0.5 | 0.30435 | 0.5 | 0.2381 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-03-10 | 2025-09-12 | ABS25287 | ABS25287 | LOGISTIC | CONTROL TOWER MERCURY - REPLENISHMENT BBP | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | Data Engineering | 475 | 111 | ON GOING | 0 | 2025 | 79 |  |  | 15 | 17 | 19 | 21 | 18 | 11 | 10 |  |  |  | 0 | 0 | 0.71429 | 0.77273 | 0.95 | 1.05 | 0.78261 | 0.91667 | 0.47619 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-03-10 | 2025-09-12 | ABS25287 | ABS25287 | LOGISTIC | CONTROL TOWER MERCURY - REPLENISHMENT BBP | EssilorLuxottica | A. Cuomo | F. Ianni | SAP FIORI | Front End | 475 | 111 | ON GOING | 0 | 2025 | 19 |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.33333 | 0.47619 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-03-10 | 2025-09-12 | ABS25287 | ABS25287 | LOGISTIC | CONTROL TOWER MERCURY - REPLENISHMENT BBP | EssilorLuxottica | A. Cuomo | F. Taita | Delivery Projects | PM - Project Governance | 475 | 111 | ON GOING | 0 | 2025 | 15 |  |  | 0 | 0 | 0 | 0 | 5 | 5 | 5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.41667 | 0.2381 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-03-10 | 2025-09-12 | ABS25287 | ABS25287 | LOGISTIC | CONTROL TOWER MERCURY - REPLENISHMENT BBP | EssilorLuxottica | A. Cuomo | F. Tarquini | SAP ECC | ECC Analyst | 475 | 111 | ON GOING | 0 | 2025 | 38 |  |  | 3 | 8 | 10 | 10 | 7 | 6 | 5 |  |  |  | 0 | 0 | 0.14286 | 0.36364 | 0.5 | 0.5 | 0.30435 | 0.5 | 0.2381 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-03-10 | 2025-09-12 | ABS25287 | ABS25287 | LOGISTIC | CONTROL TOWER MERCURY - REPLENISHMENT BBP | EssilorLuxottica | A. Cuomo | J. Daci | Operations | Data Management | 475 | 111 | ON GOING | 0 | 2025 | 69 |  |  | 16 | 17 | 4 | 21 | 23 | 11 | 10 |  |  |  | 0 | 0 | 0.7619 | 0.77273 | 0.2 | 1.05 | 1 | 0.91667 | 0.47619 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-03-10 | 2025-09-12 | ABS25287 | ABS25287 | LOGISTIC | CONTROL TOWER MERCURY - REPLENISHMENT BBP | EssilorLuxottica | A. Cuomo | M. Sabarese | SAP FIORI | Front End | 475 | 111 | ON GOING | 0 | 2025 | 19 |  |  | 0 | 0 | 0 | 0 | 5 | 4 | 10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.33333 | 0.47619 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-03-10 | 2025-09-12 | ABS25287 | ABS25287 | LOGISTIC | CONTROL TOWER MERCURY - REPLENISHMENT BBP | EssilorLuxottica | A. Cuomo | P. Cielo | SAP ECC | ECC Project Manager | 475 | 111 | ON GOING | 0 | 2025 | 38 |  |  | 5 | 8 | 10 | 10 | 7 | 6 | 5 |  |  |  | 0 | 0 | 0.2381 | 0.36364 | 0.5 | 0.5 | 0.30435 | 0.5 | 0.2381 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-03-10 | 2025-09-12 | ABS25287 | ABS25287 | LOGISTIC | CONTROL TOWER MERCURY - REPLENISHMENT BBP | EssilorLuxottica | A. Cuomo | T. Lazzari | SAP ECC | ECC Developer | 475 | 111 | ON GOING | 0 | 2025 | 25 |  |  | 2 | 1 | 1 | 3 | 5 | 6 | 10 |  |  |  | 0 | 0 | 0.095238 | 0.045455 | 0.05 | 0.15 | 0.21739 | 0.5 | 0.47619 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-01-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | A. Cuomo | Operations | Data Engineering | 190 | 177 | CLOSED | 1 | 2025 | 0 | 3.5 | [11 empty] | 0.19444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-01-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | A. Strada | Operations | BackEnd | 190 | 177 | CLOSED | 1 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-01-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | A. Torone | Delivery AMS | Data Management | 190 | 177 | CLOSED | 1 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-01-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | C. Paz | Delivery Projects | PMO - Project Management Officer | 190 | 177 | CLOSED | 1 | 2025 | 0 | 0.5 | [11 empty] | 0.027778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-01-31 | ABS24061 | ALD | CRM/CS | DMV DIGITAL MEDIA VALUATION - Banner pubblicitari - Dismissione DWH - | EssilorLuxottica | A. Cuomo | F. Reale | Operations | FrontEnd | 190 | 177 | CLOSED | 1 | 2025 | 0 | 2 | [11 empty] | 0.11111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | Lucy | Lucy PTP AI: buyer 2025 | EssilorLuxottica | A. Graziani | A. Imbimbo | AI Operations | Data Scientist | 15 | 0 | PROPOSAL | 0 | 2025 | 0 | 1 | 1 | [10 empty] | 0.055556 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | Lucy | Lucy PTP AI: buyer 2025 | EssilorLuxottica | A. Graziani | F. Malvezzi | AI Operations | Data Scientist | 15 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | Lucy | Lucy PTP AI: buyer 2025 | EssilorLuxottica | A. Graziani | G. Sironi | AI Operations | PM - Project Governance | 15 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | Lucy | Lucy PTP AI: buyer 2025 | EssilorLuxottica | A. Graziani | M. Gomitoni | AI Operations | Technical Leader | 15 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | Lucy | Lucy PTP AI: buyer 2025 | EssilorLuxottica | A. Graziani | V. Echarry | AI Operations | Data Scientist | 15 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | LUCY | Lucy | Lucy PTP AI: coding 2025 | EssilorLuxottica | A. Graziani | A. Imbimbo | AI Operations | Data Scientist | 150 | 0 | PROPOSAL | 0 | 2025 | 15 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | [5 empty] | 0.27778 | 0.25 | 0.2381 | 0.22727 | 0.25 | 0.25 | 0.21739 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | LUCY | Lucy | Lucy PTP AI: coding 2025 | EssilorLuxottica | A. Graziani | F. Malvezzi | AI Operations | Data Scientist | 60 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | LUCY | Lucy | Lucy PTP AI: coding 2025 | EssilorLuxottica | A. Graziani | G. Sironi | AI Operations | PM - Project Governance | 60 | 0 | PROPOSAL | 0 | 2025 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | LUCY | Lucy | Lucy PTP AI: coding 2025 | EssilorLuxottica | A. Graziani | M. Gomitoni | AI Operations | Technical Leader | 60 | 0 | PROPOSAL | 0 | 2025 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | LUCY | Lucy | Lucy PTP AI: coding 2025 | EssilorLuxottica | A. Graziani | V. Echarry | AI Operations | Data Scientist | 60 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | LUCY | Lucy | Lucy PTP AI: vendor 2025 | EssilorLuxottica | A. Graziani | A. Imbimbo | AI Operations | Data Scientist | 30 | 0 | PROPOSAL | 0 | 2025 | 0 | 2 | 2 | 2 | [9 empty] | 0.11111 | 0.1 | 0.095238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | LUCY | Lucy | Lucy PTP AI: vendor 2025 | EssilorLuxottica | A. Graziani | F. Malvezzi | AI Operations | Data Scientist | 30 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | LUCY | Lucy | Lucy PTP AI: vendor 2025 | EssilorLuxottica | A. Graziani | G. Sironi | AI Operations | PM - Project Governance | 30 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | LUCY | Lucy | Lucy PTP AI: vendor 2025 | EssilorLuxottica | A. Graziani | M. Gomitoni | AI Operations | Technical Leader | 30 | 0 | PROPOSAL | 0 | 2025 | 0 | 1 | 1 | 1 | [9 empty] | 0.055556 | 0.05 | 0.047619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | LUCY | Lucy | Lucy PTP AI: vendor 2025 | EssilorLuxottica | A. Graziani | V. Echarry | AI Operations | Data Scientist | 30 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | OTHER | FDP AI 2025 - Fraud Detection Plathform Updates | EssilorLuxottica | A. Morterra | A. Imbimbo | AI Operations | Data Scientist | 200 | 0 | PROPOSAL | 0 | 2025 | 25 | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 5 |  |  |  | 0.27778 | 0.25 | 0.19048 | 0.22727 | 0.25 | 0.25 | 0.21739 | 0.41667 | 0.2381 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | OTHER | FDP AI 2025 - Fraud Detection Plathform Updates | EssilorLuxottica | A. Morterra | F. Malvezzi | AI Operations | Data Scientist | 200 | 0 | PROPOSAL | 0 | 2025 | 40 | 1 | 1 | 5 | 8 | 10 | 10 | 10 | 5 | 5 |  |  |  | 0.055556 | 0.05 | 0.2381 | 0.36364 | 0.5 | 0.5 | 0.43478 | 0.41667 | 0.2381 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | OTHER | FDP AI 2025 - Fraud Detection Plathform Updates | EssilorLuxottica | A. Morterra | G. Sironi | AI Operations | PM - Project Governance | 200 | 0 | PROPOSAL | 0 | 2025 | 12 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 0.16667 | 0.15 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0.16667 | 0.095238 | 0.086957 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | OTHER | FDP AI 2025 - Fraud Detection Plathform Updates | EssilorLuxottica | A. Morterra | L. Cariglia | AI Operations | Data Management | 200 | 0 | PROPOSAL | 0 | 2025 | 14 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0.083333 | 0.095238 | 0.086957 | 0.047619 | 0.090909
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | OTHER | FDP AI 2025 - Fraud Detection Plathform Updates | EssilorLuxottica | A. Morterra | M. Gomitoni | AI Operations | Technical Leader | 200 | 0 | PROPOSAL | 0 | 2025 | 19 | 4 | 4 | 4 | 5 | 5 | 5 | 3 | 3 | 3 |  |  |  | 0.22222 | 0.2 | 0.19048 | 0.22727 | 0.25 | 0.25 | 0.13043 | 0.25 | 0.14286 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | OTHER | FDP AI 2025 - Fraud Detection Plathform Updates | EssilorLuxottica | A. Morterra | V. Echarry | AI Operations | Data Scientist | 200 | 0 | PROPOSAL | 0 | 2025 | 17 | 5 | 5 | 5 | 1 | 1 | 1 | 5 | 5 | 5 |  |  |  | 0.27778 | 0.25 | 0.2381 | 0.045455 | 0.05 | 0.05 | 0.21739 | 0.41667 | 0.2381 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25020 | ABS25020 | RETAIL | DMV AMS 2025 | EssilorLuxottica | A. Torone | A. Torone | Delivery Project | PM - Project Governance | 75 | 0 | TO START | 0 | 2025 | 30 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 4 | 4 | 4 | 4 | 0.22222 | 0.2 | 0.19048 | 0.18182 | 0.2 | 0.2 | 0.17391 | 0.16667 | 0.19048 | 0.17391 | 0.19048 | 0.18182
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25020 | ABS25020 | RETAIL | DMV AMS 2025 | EssilorLuxottica | A. Torone | F. Reale | Operations | Data Management | 75 | 0 | TO START | 0 | 2025 | 38 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 5 | 5 | 5 | 5 | 0.27778 | 0.25 | 0.2381 | 0.22727 | 0.25 | 0.25 | 0.21739 | 0.25 | 0.2381 | 0.21739 | 0.2381 | 0.22727
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | HR | PAYROLL FRANCIA | EssilorLuxottica | A. Torone | F. Plebani | Operations | Data Management | 100 | 0 | ON GOING | 0 | 2025 | 30 |  | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 4 | 4 | 4 | 4 | 0 | 0.2 | 0.19048 | 0.18182 | 0.2 | 0.2 | 0.17391 | 0.16667 | 0.19048 | 0.17391 | 0.19048 | 0.18182
INTERNAL PRJ | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | BS000QA | QA | Quality Assurance nella DI | Abstract | A. Torone | A. Torone | Delivery Project | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2025 | 120 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 0.83333 | 0.75 | 0.71429 | 0.68182 | 0.75 | 0.75 | 0.65217 | 1.25 | 0.71429 | 0.65217 | 0.71429 | 0.68182
INTERNAL PRJ | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | BS000QA | QA | Quality Assurance nella DI | Abstract | A. Torone | L. STEFANELLI | Delivery AMS | Tester | 0 | 0 | ON GOING | 0 | 2025 | 16 | 18 | 22 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0.16667 | 0.095238 | 0.086957 | 0.095238 | 0.090909
INTERNAL PRJ | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | BS000QA | QA | Quality Assurance nella DI | Abstract | A. Torone | M. STRADA | Delivery AMS | Tester | 0 | 0 | ON GOING | 0 | 2025 | 16 | 18 | 22 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0.16667 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | AMS |  | 2024 | 2025-01-01 | 2025-06-30 | ABS24060 | ABS24060 | EPM | RDM - AMS Talentia | RDM | F. Lombardini | F. Lombardini | Consolidated & Tax | PM - Project Governance | 40 | 8 | ON GOING | 0 | 2025 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | [6 empty] | 0.16667 | 0.05 | 0.047619 | 0.090909 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024 | 2025-01-01 | 2025-06-30 | ABS24060 | ABS24060 | EPM | RDM - AMS Talentia | RDM | F. Lombardini | G. Picerno | Consolidated & Tax | Back End | 40 | 8 | ON GOING | 0 | 2025 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | [6 empty] | 0.16667 | 0.05 | 0.047619 | 0.090909 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024-2025 | 2024-07-01 | 2025-06-30 | ABS24334 | ABS24334 | EPM | Thom Browne | Thom Browne | F. Lombardini | F. Lombardini | Consolidated & Tax | Analyst | 20 | 0 | ON GOING | 0 | 2025 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | [6 empty] | 0.055556 | 0.05 | 0.02381 | 0.022727 | 0.025 | 0.025 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS |  | 2024-2025 | 2024-07-01 | 2025-06-30 | ABS24334 | ABS24334 | EPM | Thom Browne | Thom Browne | F. Lombardini | G. Picerno | Consolidated & Tax | Analyst | 20 | 0 | ON GOING | 0 | 2025 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2025-01-06 | 2025-05-31 | ABS24606 | ABS24606 | BIP | ARS - RXO enhacement 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Engineering | 34 | 30 | CLOSED | 1 | 2025 | 0 |  | 1 | 4 | [9 empty] | 0 | 0.05 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2025-01-06 | 2025-05-31 | ABS24606 | ABS24606 | BIP | ARS - RXO enhacement 2025 | EssilorLuxottica | F. Taita | M. Regini | Operations | BackEnd | 34 | 30 | CLOSED | 1 | 2025 | 0 | 2 | 5 | 7 | [9 empty] | 0.11111 | 0.25 | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2025-01-06 | 2025-05-31 | ABS24606 | ABS24606 | BIP | ARS - RXO enhacement 2025 | EssilorLuxottica | F. Taita | T. Baldi | Operations | BackEnd | 34 | 30 | CLOSED | 1 | 2025 | 0 | 3 | 3 | 5 | [9 empty] | 0.16667 | 0.15 | 0.2381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-04 | 2025-06-30 | ABS25192 | ABS25192 | BIP | ARS - RXO Enhancement 2 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Engineering | 70 | 14 | ON GOING | 0 | 2025 | 13 |  |  |  | 4 | 4 | 4 | 4 |  | 1 |  |  |  | 0 | 0 | 0 | 0.18182 | 0.2 | 0.2 | 0.17391 | 0 | 0.047619 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-04 | 2025-06-30 | ABS25192 | ABS25192 | BIP | ARS - RXO Enhancement 2 2025 | EssilorLuxottica | F. Taita | M. Regini | Operations | Back End | 70 | 14 | ON GOING | 0 | 2025 | 20 |  |  |  | 6 | 6 | 6 | 6 |  | 2 |  |  |  | 0 | 0 | 0 | 0.27273 | 0.3 | 0.3 | 0.26087 | 0 | 0.095238 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-04 | 2025-06-30 | ABS25192 | ABS25192 | BIP | ARS - RXO Enhancement 2 2025 | EssilorLuxottica | F. Taita | T. Baldi | Operations | Back End | 70 | 14 | ON GOING | 0 | 2025 | 21 |  |  |  | 6 | 6 | 6 | 6 |  | 3 |  |  |  | 0 | 0 | 0 | 0.27273 | 0.3 | 0.3 | 0.26087 | 0 | 0.14286 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-02-15 | 2025-12-31 | ABS25114 | ABS25114 | BIP | BIP rollout support 2 2025 | EssilorLuxottica | F. Taita | A. Seira | Operations | Backend | 60 | 58 | CLOSED | 0 | 2025 | 0 |  | 1 | 21 | 18 | [8 empty] | 0 | 0.05 | 1 | 0.81818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-02-15 | 2025-12-31 | ABS25114 | ABS25114 | BIP | BIP rollout support 2 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | DataManagement | 60 | 58 | CLOSED | 0 | 2025 | 0 |  | 6 | 6 | 3 | [8 empty] | 0 | 0.3 | 0.28571 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-02-15 | 2025-12-31 | ABS25114 | ABS25114 | BIP | BIP rollout support 2 2025 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | Backend | 60 | 58 | CLOSED | 0 | 2025 | 0 |  | 6 | 14 | 3 | [8 empty] | 0 | 0.3 | 0.66667 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-02-15 | 2025-12-31 | ABS25114 | ABS25114 | BIP | BIP rollout support 2 2025 | EssilorLuxottica | F. Taita | T. Baldi | Operations | Backend | 60 | 58 | CLOSED | 0 | 2025 | 0 |  | 6 | 12 | 4 | [8 empty] | 0 | 0.3 | 0.57143 | 0.18182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-04-01 | 2025-12-31 | ABS25231 | ABS25231 | BIP | BIP rollout support 3 2025 | EssilorLuxottica | F. Taita | A. Seira | Operations | Back End | 60 | 22 | ON GOING | 0 | 2025 | 31 |  |  |  |  | 11 | 11 | 9 | [5 empty] | 0 | 0 | 0 | 0 | 0.55 | 0.55 | 0.3913 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-04-01 | 2025-12-31 | ABS25231 | ABS25231 | BIP | BIP rollout support 3 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Management | 60 | 22 | ON GOING | 0 | 2025 | 6 |  |  |  |  | 2 | 2 | 2 | [5 empty] | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.086957 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-04-01 | 2025-12-31 | ABS25231 | ABS25231 | BIP | BIP rollout support 3 2025 | EssilorLuxottica | F. Taita | L. Altobelli | Operations | Back End | 60 | 22 | ON GOING | 0 | 2025 | 13 |  |  |  |  | 5 | 5 | 3 | [5 empty] | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0.13043 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-04-01 | 2025-12-31 | ABS25231 | ABS25231 | BIP | BIP rollout support 3 2025 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | Back End | 60 | 22 | ON GOING | 0 | 2025 | 21 |  |  |  |  | 7 | 7 | 7 | [5 empty] | 0 | 0 | 0 | 0 | 0.35 | 0.35 | 0.30435 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-04-01 | 2025-12-31 | ABS25231 | ABS25231 | BIP | BIP rollout support 3 2025 | EssilorLuxottica | F. Taita | T. Baldi | Operations | Back End | 60 | 22 | ON GOING | 0 | 2025 | 15 |  |  |  |  | 5 | 5 | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0.21739 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-10-15 | 2025-12-31 |  |  | BIP | BIP rollout support 6 2025 | EssilorLuxottica | F. Taita | A. Seira | Operations | Back End | 60 | 0 | TO START | 0 | 2025 | 20 | [10 empty] | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47619 | 0.45455
CONTRACT | AMS | Waterfall | 2025 | 2025-10-15 | 2025-12-31 |  |  | BIP | BIP rollout support 6 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Management | 60 | 0 | TO START | 0 | 2025 | 10 | [10 empty] | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2381 | 0.22727
CONTRACT | AMS | Waterfall | 2025 | 2025-10-15 | 2025-12-31 |  |  | BIP | BIP rollout support 6 2025 | EssilorLuxottica | F. Taita | L. altobelli | Operations | Back End | 60 | 0 | TO START | 0 | 2025 | 14 | [10 empty] | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33333 | 0.31818
CONTRACT | AMS | Waterfall | 2025 | 2025-10-15 | 2025-12-31 |  |  | BIP | BIP rollout support 6 2025 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | Back End | 60 | 0 | TO START | 0 | 2025 | 20 | [10 empty] | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47619 | 0.45455
CONTRACT | AMS | Waterfall | 2025 | 2025-10-15 | 2025-12-31 |  |  | BIP | BIP rollout support 6 2025 | EssilorLuxottica | F. Taita | T. Baldi | Operations | Back End | 60 | 0 | TO START | 0 | 2025 | 14 | [10 empty] | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33333 | 0.31818
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-10-31 | ABS25236 | ABS25236 | LOGISTIC | EL Complete Pair France LABEX ARS RXO | EssilorLuxottica | F. Taita | T. Baldi | Operations | Data Engineering | 45 | 9 | ON GOING | 0 | 2025 | 17 |  |  |  | 2 | 5 | 5 | 5 |  | 2 |  |  |  | 0 | 0 | 0 | 0.090909 | 0.25 | 0.25 | 0.21739 | 0 | 0.095238 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-10-31 | ABS25236 | ABS25236 | LOGISTIC | EL Complete Pair France LABEX ARS RXO | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Engineering | 45 | 9 | ON GOING | 0 | 2025 | 14 |  |  |  | 2 | 4 | 4 | 4 |  | 2 |  |  |  | 0 | 0 | 0 | 0.090909 | 0.2 | 0.2 | 0.17391 | 0 | 0.095238 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-10-31 | ABS25236 | ABS25236 | LOGISTIC | EL Complete Pair France LABEX ARS RXO | EssilorLuxottica | F. Taita | M. Regini | Operations | Data Engineering | 45 | 9 | ON GOING | 0 | 2025 | 10 |  |  |  |  | 3 | 3 | 3 |  | 1 |  |  |  | 0 | 0 | 0 | 0 | 0.15 | 0.15 | 0.13043 | 0 | 0.047619 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2025 | 2025-05-01 | 2025-10-31 | ABS25236 | ABS25236 | LOGISTIC | EL Complete Pair France LABEX PLANNING FILES | EssilorLuxottica | F. Taita | A. Seira | Operations | Back End | 100 | 12 | ON GOING | 0 | 2025 | 24 |  |  |  |  | 7 | 7 | 7 |  | 3 |  |  |  | 0 | 0 | 0 | 0 | 0.35 | 0.35 | 0.30435 | 0 | 0.14286 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-10-31 | ABS25236 | ABS25236 | LOGISTIC | EL Complete Pair France LABEX PLANNING FILES | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Engineering | 100 | 12 | ON GOING | 0 | 2025 | 18 |  |  |  | 3 | 5 | 5 | 5 |  | 3 |  |  |  | 0 | 0 | 0 | 0.13636 | 0.25 | 0.25 | 0.21739 | 0 | 0.14286 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2025 | 2025-05-01 | 2025-10-31 | ABS25236 | ABS25236 | LOGISTIC | EL Complete Pair France LABEX PLANNING FILES | EssilorLuxottica | F. Taita | L. Altobelli | Operations | Data Engineering | 100 | 12 | ON GOING | 0 | 2025 | 28 |  |  |  |  | 7 | 8 | 8 |  | 5 |  |  |  | 0 | 0 | 0 | 0 | 0.35 | 0.4 | 0.34783 | 0 | 0.2381 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-10-31 | ABS25236 | ABS25236 | LOGISTIC | EL Complete Pair France LABEX PLANNING FILES | EssilorLuxottica | F. Taita | L. Stroppa | Operations | Data Engineering | 100 | 12 | ON GOING | 0 | 2025 | 29 |  |  |  | 3 | 8 | 8 | 8 |  | 5 |  |  |  | 0 | 0 | 0 | 0.13636 | 0.4 | 0.4 | 0.34783 | 0 | 0.2381 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-10-31 | ABS25236 | ABS25236 | LOGISTIC | EL Complete Pair France LABEX SHORT TRIP | EssilorLuxottica | F. Taita | C. Piraccini | Operations | Data Engineering | 15 | 1 | ON GOING | 0 | 2025 | 11 |  |  |  | 2 | 4 | 3 | 3 |  | 1 |  |  |  | 0 | 0 | 0 | 0.090909 | 0.2 | 0.15 | 0.13043 | 0 | 0.047619 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-10-31 | ABS25236 | ABS25236 | LOGISTIC | EL Complete Pair France LABEX SHORT TRIP | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Engineering | 15 | 1 | ON GOING | 0 | 2025 | 4 |  |  |  | 2 | 1 | 1 | 1 |  | 1 |  |  |  | 0 | 0 | 0 | 0.090909 | 0.05 | 0.05 | 0.043478 | 0 | 0.047619 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | BIP | BIP rollot support 4 2025 | EssilorLuxottica | F. Taita | A. Seira | Operations | Back End | 60 | 0 | TO START | 0 | 2025 | 28 | [6 empty] | 10 | 8 | 10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.43478 | 0.66667 | 0.47619 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | BIP | BIP rollot support 4 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Management | 60 | 0 | TO START | 0 | 2025 | 15 | [6 empty] | 5 | 5 | 5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.41667 | 0.2381 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | BIP | BIP rollot support 4 2025 | EssilorLuxottica | F. Taita | L. altobelli | Operations | Back End | 60 | 0 | TO START | 0 | 2025 | 9 | [6 empty] | 3 | 3 | 3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0.25 | 0.14286 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | BIP | BIP rollot support 4 2025 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | Back End | 60 | 0 | TO START | 0 | 2025 | 18 | [6 empty] | 9 |  | 9 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.3913 | 0 | 0.42857 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | BIP | BIP rollot support 4 2025 | EssilorLuxottica | F. Taita | T. Baldi | Operations | Back End | 60 | 0 | TO START | 0 | 2025 | 8 | [6 empty] | 4 |  | 4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.17391 | 0 | 0.19048 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25037 | ABS25037 | BIP | First BIP rollout support 2025 | EssilorLuxottica | F. Taita | A. Seira | Operations | Backend | 58 | 58 | CLOSED | 1 | 2025 | 0 | 16 | 16 | [10 empty] | 0.88889 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25037 | ABS25037 | BIP | First BIP rollout support 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | DataManagement | 58 | 58 | CLOSED | 1 | 2025 | 0 | 3 | 6 | [10 empty] | 0.16667 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25037 | ABS25037 | BIP | First BIP rollout support 2025 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | Backend | 58 | 58 | CLOSED | 1 | 2025 | 0 | 16 | 9 | [10 empty] | 0.88889 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25037 | ABS25037 | BIP | First BIP rollout support 2025 | EssilorLuxottica | F. Taita | T. Baldi | Operations | Backend | 58 | 58 | CLOSED | 1 | 2025 | 0 | 15 | 6 | [10 empty] | 0.83333 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-05-15 | 2025-12-31 |  |  | BIP | BIP rollout support 5 2025 | EssilorLuxottica | F. Taita | A. Seira | Operations | Back End | 60 | 0 | TO START | 0 | 2025 | 18 | [8 empty] | 9 | 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42857 | 0.3913 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-05-15 | 2025-12-31 |  |  | BIP | BIP rollout support 5 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Management | 60 | 0 | TO START | 0 | 2025 | 10 | [8 empty] | 5 | 5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2381 | 0.21739 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-05-15 | 2025-12-31 |  |  | BIP | BIP rollout support 5 2025 | EssilorLuxottica | F. Taita | L. altobelli | Operations | Back End | 60 | 0 | TO START | 0 | 2025 | 8 | [8 empty] | 4 | 4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19048 | 0.17391 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-05-15 | 2025-12-31 |  |  | BIP | BIP rollout support 5 2025 | EssilorLuxottica | F. Taita | L. Stroppa | Operations | Back End | 60 | 0 | TO START | 0 | 2025 | 20 | [8 empty] | 10 | 10 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47619 | 0.43478 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-05-15 | 2025-12-31 |  |  | BIP | BIP rollout support 5 2025 | EssilorLuxottica | F. Taita | T. Baldi | Operations | Back End | 60 | 0 | TO START | 0 | 2025 | 4 | [8 empty] | 2 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095238 | 0.086957 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25086 | ABS25086 | LOGISTIC | LMS LIGHT 2025 | EssilorLuxottica | F. Taita | C. Piraccini | Operations | Data Engineering | 228 | 93 | ON GOING | 0 | 2025 | 71 | 5 | 6 | 8 | 8 | 8 | 10 | 10 | 5 | 10 | 10 | 10 | 8 | 0.27778 | 0.3 | 0.38095 | 0.36364 | 0.4 | 0.5 | 0.43478 | 0.41667 | 0.47619 | 0.43478 | 0.47619 | 0.36364
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25086 | ABS25086 | LOGISTIC | LMS LIGHT 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Engineering | 228 | 93 | ON GOING | 0 | 2025 | 22 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 1 | 3 | 3 | 3 | 3 | 0.055556 | 0.1 | 0.095238 | 0.090909 | 0.15 | 0.15 | 0.13043 | 0.083333 | 0.14286 | 0.13043 | 0.14286 | 0.13636
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25086 | ABS25086 | LOGISTIC | LMS LIGHT 2025 | EssilorLuxottica | F. Taita | M. Regini | Operations | Back End | 228 | 93 | ON GOING | 0 | 2025 | 66 | 5 | 5 | 5 | 6 | 6 | 10 | 10 | 5 | 9 | 9 | 9 | 8 | 0.27778 | 0.25 | 0.2381 | 0.27273 | 0.3 | 0.5 | 0.43478 | 0.41667 | 0.42857 | 0.3913 | 0.42857 | 0.36364
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25086 | ABS25086 | LOGISTIC | LMS LIGHT 2025 | EssilorLuxottica | F. Taita | R. Bondi | Operations | Data Engineering | 228 | 93 | ON GOING | 0 | 2025 | 2 |  |  |  | 1 | 2 | [7 empty] | 0 | 0 | 0 | 0.045455 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 2024-12-31 | ABS24164 | ALT | LOGISTIC | LMS TIJUANA | EssilorLuxottica | F. Taita | C. Piraccini | Operations | Data Engineering | 185 | 94 | ON GOING | 0 | 2025 | 12 | 3 | 6 | 6 | 6 | 6 | 6 | [6 empty] | 0.16667 | 0.3 | 0.28571 | 0.27273 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-04-01 | 2024-12-31 | ABS24164 | ALT | LOGISTIC | LMS TIJUANA | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Engineering | 185 | 94 | ON GOING | 0 | 2025 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | [6 empty] | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 | 2024-12-31 | ABS24164 | ALT | LOGISTIC | LMS TIJUANA | EssilorLuxottica | F. Taita | M. Regini | Operations | Back End | 185 | 94 | ON GOING | 0 | 2025 | 9 | 3 | 5 | 5 | 5 | 5 | 4 | [6 empty] | 0.16667 | 0.25 | 0.2381 | 0.22727 | 0.25 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-06-01 | 2025-12-31 |  |  | LOGISTIC | LMS Tijuana wave 2 2025 | EssilorLuxottica | F. Taita | C. Piraccini | Operations | Data Engineering | 30 | 0 | TO START | 0 | 2025 | 8 | [6 empty] | 3 | 2 | 3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0.16667 | 0.14286 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-06-01 | 2025-12-31 |  |  | LOGISTIC | LMS Tijuana wave 2 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Engineering | 30 | 0 | TO START | 0 | 2025 | 4 | [5 empty] | 1 | 1 | 1 | 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-06-01 | 2025-12-31 |  |  | LOGISTIC | LMS Tijuana wave 2 2025 | EssilorLuxottica | F. Taita | M. Regini | Operations | Back End | 30 | 0 | TO START | 0 | 2025 | 15 | [5 empty] | 4 | 4 | 3 | 4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.17391 | 0.25 | 0.19048 | 0 | 0 | 0
CONTRACT | TIME MATERIAL | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25031 | ABS25031 | LOGISTIC | LUX DM Supporto ELECTRA 2025 - Enhancement & Rollout | EssilorLuxottica | F. Taita | C. Piraccini | Operations | Back End | 70 | 27 | ON GOING | 0 | 2025 | 12 |  | 2 | 1 | 5 | 5 | 2 | 1 | 1 | 1 | 1 | 1 |  | 0 | 0.1 | 0.047619 | 0.22727 | 0.25 | 0.1 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0
CONTRACT | TIME MATERIAL | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25031 | ABS25031 | LOGISTIC | LUX DM Supporto ELECTRA 2025 - Enhancement & Rollout | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Management | 70 | 27 | ON GOING | 0 | 2025 | 3 |  | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 0 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | TIME MATERIAL | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25031 | ABS25031 | LOGISTIC | LUX DM Supporto ELECTRA 2025 - Enhancement & Rollout | EssilorLuxottica | F. Taita | M. Regini | Operations | Back End | 70 | 27 | ON GOING | 0 | 2025 | 29 |  | 5 | 5 | 5 | 5 | 5 | 5 |  | 5 | 5 | 4 |  | 0 | 0.25 | 0.2381 | 0.22727 | 0.25 | 0.25 | 0.21739 | 0 | 0.2381 | 0.21739 | 0.19048 | 0
CONTRACT | PRJ | Scrum | 2025 | 2025-01-01 | 2025-12-31 | ABS25083 | ABS25083 | LOGISTIC | OPTIMIZATION OF RTTF CHAINS | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | PM - Project Governance | 13 | 11 | CLOSED | 1 | 2025 | 0 | 1 | 2 | 1 | [9 empty] | 0.055556 | 0.1 | 0.047619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2025 | 2025-01-01 | 2025-12-31 | ABS25083 | ABS25083 | LOGISTIC | OPTIMIZATION OF RTTF CHAINS | EssilorLuxottica | F. Taita | M. Vimercati | Operations | FrontEnd | 13 | 11 | CLOSED | 1 | 2025 | 0 |  | 1 | [10 empty] | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2025 | 2025-01-01 | 2025-12-31 | ABS25083 | ABS25083 | LOGISTIC | OPTIMIZATION OF RTTF CHAINS | EssilorLuxottica | F. Taita | S. Ben Younes | Operations | BackEnd | 13 | 11 | CLOSED | 1 | 2025 | 0 |  | 7 | 1 | [9 empty] | 0 | 0.35 | 0.047619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2025 | 2025-01-01 | 2025-12-31 | ABS25120 | ABS25120 | LOGISTIC | RTTF SUPPORT 2025 | EssilorLuxottica | F. Taita | A. Seira | Operations | Back End | 60 | 30 | ON GOING | 0 | 2025 | 14 |  |  | 3 | 3 | 3 | 8 | 3 | [5 empty] | 0 | 0 | 0.14286 | 0.13636 | 0.15 | 0.4 | 0.13043 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2025 | 2025-01-01 | 2025-12-31 | ABS25120 | ABS25120 | LOGISTIC | RTTF SUPPORT 2025 | EssilorLuxottica | F. Taita | F. Reale | Operations | Front End | 60 | 30 | ON GOING | 0 | 2025 | 8 |  |  | 2 | 2 | 3 | 5 | [6 empty] | 0 | 0 | 0.095238 | 0.090909 | 0.15 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2025 | 2025-01-01 | 2025-12-31 | ABS25120 | ABS25120 | LOGISTIC | RTTF SUPPORT 2025 | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | PM - Project Governance | 60 | 30 | ON GOING | 0 | 2025 | 7 |  |  | 3 | 3 | 3 | 3 | 1 | [5 empty] | 0 | 0 | 0.14286 | 0.13636 | 0.15 | 0.15 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Scrum | 2025 | 2025-01-01 | 2025-12-31 | ABS25120 | ABS25120 | LOGISTIC | RTTF SUPPORT 2025 | EssilorLuxottica | F. Taita | S. Ben Younes | Operations | Back End | 60 | 30 | ON GOING | 0 | 2025 | 20 |  |  | 7 | 8 | 8 | 5 | 7 | [5 empty] | 0 | 0 | 0.33333 | 0.36364 | 0.4 | 0.25 | 0.30435 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | RETAIL | VAPP CR Plus Q3Q4 2025 | EssilorLuxottica | F. Vassallo | A. Pirola | Operations | Front End | 250 | 0 | PROPOSAL | 0 | 2025 | 1 | [8 empty] | 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | RETAIL | VAPP CR Plus Q3Q4 2025 | EssilorLuxottica | F. Vassallo | D. Heba | Operations | Back End | 250 | 0 | PROPOSAL | 0 | 2025 | 27 | [8 empty] | 11 | 8 | 1 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52381 | 0.34783 | 0.047619 | 0.31818
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | RETAIL | VAPP CR Plus Q3Q4 2025 | EssilorLuxottica | F. Vassallo | F. Vassallo | Delivery AMS | PM - Project Governance | 250 | 0 | PROPOSAL | 0 | 2025 | 38 | [6 empty] | 8 | 5 | 5 | 5 | 15 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.34783 | 0.41667 | 0.2381 | 0.21739 | 0.71429 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | RETAIL | VAPP CR Plus Q3Q4 2025 | EssilorLuxottica | F. Vassallo | M. Mannarino | Operations | Data Engineering | 250 | 0 | PROPOSAL | 0 | 2025 | 36 | [6 empty] | 1 | 5 | 9 | 11 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.41667 | 0.42857 | 0.47826 | 0.38095 | 0.090909
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | RETAIL | VAPP CR Plus Q3Q4 2025 | EssilorLuxottica | F. Vassallo | M. Vianelli | Delivery Projects | Analyst | 250 | 0 | PROPOSAL | 0 | 2025 | 19 | [8 empty] | 5 | 5 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2381 | 0.21739 | 0.2381 | 0.18182
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | RETAIL | VAPP CR Plus Q3Q4 2025 | EssilorLuxottica | F. Vassallo | R. Grandi | Operations | Data Management | 250 | 0 | PROPOSAL | 0 | 2025 | 6 | [8 empty] | 1 | 5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.047619 | 0.21739 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25002 | ABS25002 | RETAIL | VAPP AMS App 2025 | EssilorLuxottica | F. Vassallo | A. Pirola | Operations | Front End | 800 | 287 | ON GOING | 0 | 2025 | 16 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0.16667 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25002 | ABS25002 | RETAIL | VAPP AMS App 2025 | EssilorLuxottica | F. Vassallo | C. Piraccini | Operations | Data Management | 800 | 287 | ON GOING | 0 | 2025 | 44 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 7 | 7 | 0 | 0 | 0.2381 | 0.22727 | 0.25 | 0.25 | 0.21739 | 0.41667 | 0.2381 | 0.21739 | 0.33333 | 0.31818
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25002 | ABS25002 | RETAIL | VAPP AMS App 2025 | EssilorLuxottica | F. Vassallo | D. Heba | Operations | Back End | 800 | 287 | ON GOING | 0 | 2025 | 55 | 16 | 16 | 17 | 5 | 5 | 5 | 5 | 8 | 8 | 8 | 8 | 8 | 0.88889 | 0.8 | 0.80952 | 0.22727 | 0.25 | 0.25 | 0.21739 | 0.66667 | 0.38095 | 0.34783 | 0.38095 | 0.36364
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25002 | ABS25002 | RETAIL | VAPP AMS App 2025 | EssilorLuxottica | F. Vassallo | F. Vassallo | Delivery AMS | PM - Project Governance | 800 | 287 | ON GOING | 0 | 2025 | 127 | 18 | 18 | 2 | 15 | 18 | 15 | 15 | 10 | 18 | 18 | 18 | 15 | 1 | 0.9 | 0.095238 | 0.68182 | 0.9 | 0.75 | 0.65217 | 0.83333 | 0.85714 | 0.78261 | 0.85714 | 0.68182
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25002 | ABS25002 | RETAIL | VAPP AMS App 2025 | EssilorLuxottica | F. Vassallo | G. Mordà | Operations | Data Management | 800 | 287 | ON GOING | 0 | 2025 | 16 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0.16667 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25002 | ABS25002 | RETAIL | VAPP AMS App 2025 | EssilorLuxottica | F. Vassallo | M. Mannarino | Operations | Back End | 800 | 287 | ON GOING | 0 | 2025 | 40 | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0.33333 | 0.3 | 0.28571 | 0.27273 | 0.25 | 0.25 | 0.21739 | 0.41667 | 0.2381 | 0.21739 | 0.2381 | 0.22727
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25002 | ABS25002 | RETAIL | VAPP AMS App 2025 | EssilorLuxottica | F. Vassallo | M. Vianelli | Delivery Projects | Analyst | 800 | 287 | ON GOING | 0 | 2025 | 40 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0.16667 | 0.25 | 0.2381 | 0.22727 | 0.25 | 0.25 | 0.21739 | 0.41667 | 0.2381 | 0.21739 | 0.2381 | 0.22727
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25002 | ABS25002 | RETAIL | VAPP AMS App 2025 | EssilorLuxottica | F. Vassallo | P. Anzellotti | Operations | Technical Leader | 800 | 287 | ON GOING | 0 | 2025 | 0 | 2 | 2 | 2 | [9 empty] | 0.11111 | 0.1 | 0.095238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25002 | ABS25002 | RETAIL | VAPP AMS App 2025 | EssilorLuxottica | F. Vassallo | R. Grandi | Operations | Data Management | 800 | 287 | ON GOING | 0 | 2025 | 72 | 15 | 18 | 15 | 8 | 10 | 8 | 8 | 8 | 8 | 10 | 10 | 10 | 0.83333 | 0.9 | 0.71429 | 0.36364 | 0.5 | 0.4 | 0.34783 | 0.66667 | 0.38095 | 0.43478 | 0.47619 | 0.45455
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25032 | ABS25032 | RETAIL | VAPP CR Plus Q1Q2 2025 | EssilorLuxottica | F. Vassallo | A. Pirola | Operations | Front End | 190 | 56 | ON GOING | 0 | 2025 | 20 |  |  | 1 | 1 | 5 | 10 | 5 | [5 empty] | 0 | 0 | 0.047619 | 0.045455 | 0.25 | 0.5 | 0.21739 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25032 | ABS25032 | RETAIL | VAPP CR Plus Q1Q2 2025 | EssilorLuxottica | F. Vassallo | S. Beltrami | Operations | Front End | 190 | 56 | ON GOING | 0 | 2025 | 4 |  |  |  |  | 2 | 2 | [6 empty] | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25032 | ABS25032 | RETAIL | VAPP CR Plus Q1Q2 2025 | EssilorLuxottica | F. Vassallo | C. Piraccini | Operations | Data Management | 190 | 56 | ON GOING | 0 | 2025 | 10 |  |  | 1 | 7 | 2 | 5 | 3 | [5 empty] | 0 | 0 | 0.047619 | 0.31818 | 0.1 | 0.25 | 0.13043 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25032 | ABS25032 | RETAIL | VAPP CR Plus Q1Q2 2025 | EssilorLuxottica | F. Vassallo | D. Heba | Operations | Back End | 190 | 56 | ON GOING | 0 | 2025 | 18 | 2 | 1 | 3 | 7 | 10 | 5 | 3 | [5 empty] | 0.11111 | 0.05 | 0.14286 | 0.31818 | 0.5 | 0.25 | 0.13043 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25032 | ABS25032 | RETAIL | VAPP CR Plus Q1Q2 2025 | EssilorLuxottica | F. Vassallo | F. Vassallo | Delivery AMS | PM - Project Governance | 190 | 56 | ON GOING | 0 | 2025 | 7 | 2 |  | 1 | 2 | 3 | 2 | 2 | [5 empty] | 0.11111 | 0 | 0.047619 | 0.090909 | 0.15 | 0.1 | 0.086957 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25032 | ABS25032 | RETAIL | VAPP CR Plus Q1Q2 2025 | EssilorLuxottica | F. Vassallo | M. Mannarino | Operations | Data Engineering | 190 | 56 | ON GOING | 0 | 2025 | 21 | 6 | 4 | 3 | 5 | 10 | 6 | 5 | [5 empty] | 0.33333 | 0.2 | 0.14286 | 0.22727 | 0.5 | 0.3 | 0.21739 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25032 | ABS25032 | RETAIL | VAPP CR Plus Q1Q2 2025 | EssilorLuxottica | F. Vassallo | M. Vianelli | Delivery Projects | Analyst | 190 | 56 | ON GOING | 0 | 2025 | 9 |  |  | 3 | 4 | 3 | 2 | 4 | [5 empty] | 0 | 0 | 0.14286 | 0.18182 | 0.15 | 0.1 | 0.17391 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25032 | ABS25032 | RETAIL | VAPP CR Plus Q1Q2 2025 | EssilorLuxottica | F. Vassallo | R. Grandi | Operations | Data Management | 190 | 56 | ON GOING | 0 | 2025 | 13 |  |  | 3 | 10 | 5 | 5 | 3 | [5 empty] | 0 | 0 | 0.14286 | 0.45455 | 0.25 | 0.25 | 0.13043 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | A. Pirola | Operations | Front End | 75 | 14 | ON GOING | 0 | 2025 | 0 | 2 | [11 empty] | 0.11111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | C. Piraccini | Operations | Data Management | 75 | 14 | ON GOING | 0 | 2025 | 0 | 6 | [11 empty] | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | D. Heba | Operations | Back End | 75 | 14 | ON GOING | 0 | 2025 | 0 | 3 | [11 empty] | 0.16667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | F. Vassallo | Delivery AMS | PM - Project Governance | 75 | 14 | ON GOING | 0 | 2025 | 0 | 3 | [11 empty] | 0.16667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | M. Mannarino | Operations | Data Engineering | 75 | 14 | ON GOING | 0 | 2025 | 0 | 3 | [11 empty] | 0.16667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | M. Vianelli | Consulting | Analyst | 75 | 14 | ON GOING | 0 | 2025 | 0 | 2 | [11 empty] | 0.11111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2024 | 2024-12-01 | 2025-01-31 | ABS24591 | ABS24591 | RETAIL | VAPP Integration FGX | EssilorLuxottica | F. Vassallo | R. Grandi | Operations | Data Management | 75 | 14 | ON GOING | 0 | 2025 | 0 | 1 | [11 empty] | 0.055556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Watefall | 2024-2025 | 2025-10-01 | 2025-09-30 | ABS24217 | ABS24217 | CRM | Global CS B2B AMS 2024-2025 | EssilorLuxottica | G. Galati | G. Galati | Delivery AMS | PM - Project Governance | 12 | 0 | ON GOING | 0 | 2025 | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  | 0.25 |  |  |  | 0.013889 | 0.0125 | 0.011905 | 0.011364 | 0.0125 | 0.0125 | 0.01087 | 0 | 0.011905 | 0 | 0 | 0
CONTRACT | AMS | Watefall | 2024-2025 | 2025-10-01 | 2025-09-30 | ABS24217 | ABS24217 | CRM | Global CS B2B AMS 2024-2025 | EssilorLuxottica | G. Galati | M. Toci | Operations | Back End | 12 | 0 | ON GOING | 0 | 2025 | 3 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 |  | 0.75 |  |  |  | 0.041667 | 0.0375 | 0.035714 | 0.034091 | 0.0375 | 0.0375 | 0.032609 | 0 | 0.035714 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | Logistic | CTRL-Tower Atlanta AMS 2025 | EssilorLuxottica | G. Luongo | A. Crescimone | Operations | Back End | 212 | 21 | ON GOING | 0 | 2025 | 16 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.1 | 0.1 | 0.086957 | 0.16667 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | Logistic | CTRL-Tower Atlanta AMS 2025 | EssilorLuxottica | G. Luongo | A. Saija | Operations | Back End | 212 | 21 | ON GOING | 0 | 2025 | 0 | 1 | 1 | 1 | 1 | [8 empty] | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | Logistic | CTRL-Tower Atlanta AMS 2025 | EssilorLuxottica | G. Luongo | G. Luongo | Delivery AMS | PM - Project Governance | 212 | 21 | ON GOING | 0 | 2025 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | Logistic | CTRL-Tower Atlanta AMS 2025 | EssilorLuxottica | G. Luongo | J. Daci | Operations | Data Management | 212 | 21 | ON GOING | 0 | 2025 | 16 | 0 | 0 | 0 | 2 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.090909 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | Logistic | CTRL-Tower Atlanta AMS 2025 | EssilorLuxottica | G. Luongo | L. Gullotto | Operations | Back End | 212 | 21 | ON GOING | 0 | 2025 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | Logistic | CTRL-Tower Atlanta AMS 2025 | EssilorLuxottica | G. Luongo | P. Assirelli | Operations | Technical Leader | 212 | 21 | ON GOING | 0 | 2025 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25023 | ABS25023 | RETAIL | OneLRA AMS 2025 | EssilorLuxottica | G. Luongo | A. Crescimone | Operations | Back End | 1610 | 320 | ON GOING | 0 | 2025 | 103 | 17 | 19 | 2 | 21 | 2 | 18 | 21 | 1 | 19 | 21 | 19 | 2 | 0.94444 | 0.95 | 0.095238 | 0.95455 | 0.1 | 0.9 | 0.91304 | 0.083333 | 0.90476 | 0.91304 | 0.90476 | 0.090909
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25023 | ABS25023 | RETAIL | OneLRA AMS 2025 | EssilorLuxottica | G. Luongo | A. Saija | Operations | Back End | 1610 | 320 | ON GOING | 0 | 2025 | 20 | 6 | 2 | 21 | 18 | 20 | [7 empty] | 0.33333 | 0.1 | 1 | 0.81818 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25023 | ABS25023 | RETAIL | OneLRA AMS 2025 | EssilorLuxottica | G. Luongo | B. Capotorto | Operations | Analyst | 1610 | 320 | ON GOING | 0 | 2025 | 109 | 14 | 18 | 19 | 15 | 15 | 13 | 16 | 6 | 14 | 16 | 14 | 15 | 0.77778 | 0.9 | 0.90476 | 0.68182 | 0.75 | 0.65 | 0.69565 | 0.5 | 0.66667 | 0.69565 | 0.66667 | 0.68182
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25023 | ABS25023 | RETAIL | OneLRA AMS 2025 | EssilorLuxottica | G. Luongo | G. Luongo | Delivery AMS | PM - Project Governance | 1610 | 320 | ON GOING | 0 | 2025 | 104 | 2 | 22 | 2 | 19 | 19 | 17 | 2 | 9 | 18 | 2 | 18 | 19 | 0.11111 | 1.1 | 0.095238 | 0.86364 | 0.95 | 0.85 | 0.086957 | 0.75 | 0.85714 | 0.086957 | 0.85714 | 0.86364
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25023 | ABS25023 | RETAIL | OneLRA AMS 2025 | EssilorLuxottica | G. Luongo | G. Mordà | Operations | Reperibilità | 1610 | 320 | ON GOING | 0 | 2025 | 14 | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0.16667 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25023 | ABS25023 | RETAIL | OneLRA AMS 2025 | EssilorLuxottica | G. Luongo | L. Altobelli | Operations | Back End | 1610 | 320 | ON GOING | 0 | 2025 | 78 |  |  |  | 11 | 8.5 | 9 | 10.5 | 6 | 11 | 11 | 11 | 11 | 0 | 0 | 0 | 0.5 | 0.425 | 0.45 | 0.45652 | 0.5 | 0.52381 | 0.47826 | 0.52381 | 0.5
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25023 | ABS25023 | RETAIL | OneLRA AMS 2025 | EssilorLuxottica | G. Luongo | L. Gullotto | Operations | Back End | 1610 | 320 | ON GOING | 0 | 2025 | 116 | 17 | 19 | 13 | 16 | 16 | 14 | 17 | 6 | 15 | 17 | 15 | 16 | 0.94444 | 0.95 | 0.61905 | 0.72727 | 0.8 | 0.7 | 0.73913 | 0.5 | 0.71429 | 0.73913 | 0.71429 | 0.72727
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25023 | ABS25023 | RETAIL | OneLRA AMS 2025 | EssilorLuxottica | G. Luongo | P. Assirelli | Operations | Analyst | 1610 | 320 | ON GOING | 0 | 2025 | 60 | 2 | 15 | 13 | 11 | 6 | 9 | 12 | 5 | 5 | 12 | 5 | 6 | 0.11111 | 0.75 | 0.61905 | 0.5 | 0.3 | 0.45 | 0.52174 | 0.41667 | 0.2381 | 0.52174 | 0.2381 | 0.27273
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25023 | ABS25023 | RETAIL | OneLRA AMS 2025 | EssilorLuxottica | G. Luongo | P. Gamboni | Operations | Back End | 1610 | 320 | ON GOING | 0 | 2025 | 118 |  |  |  | 22 | 22 | 2 | 18 | 9 | 16 | 18 | 16 | 17 | 0 | 0 | 0 | 1 | 1.1 | 0.1 | 0.78261 | 0.75 | 0.7619 | 0.78261 | 0.7619 | 0.77273
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-04-30 | ABS25030 | ABS25030 | RETAIL | ONELRA Enhancements plus5 2025 Q1 | EssilorLuxottica | G. Luongo | B. Capotorto | Operations | BackEnd | 78 | 75 | CLOSED | 1 | 2025 | 0 | 4 | 2 | 2 | [9 empty] | 0.22222 | 0.1 | 0.095238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-04-30 | ABS25030 | ABS25030 | RETAIL | ONELRA Enhancements plus5 2025 Q1 | EssilorLuxottica | G. Luongo | C. Piraccini | Operations | BackEnd | 78 | 75 | CLOSED | 1 | 2025 | 0 |  | 1 | [10 empty] | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-04-30 | ABS25030 | ABS25030 | RETAIL | ONELRA Enhancements plus5 2025 Q1 | EssilorLuxottica | G. Luongo | G. Luongo | Delivery AMS | PM - Project Governance | 78 | 75 | CLOSED | 1 | 2025 | 0 | 2 | 2 | 2 | [9 empty] | 0.11111 | 0.1 | 0.095238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-04-30 | ABS25030 | ABS25030 | RETAIL | ONELRA Enhancements plus5 2025 Q1 | EssilorLuxottica | G. Luongo | L. Gullotto | Operations | BackEnd | 78 | 75 | CLOSED | 1 | 2025 | 0 |  |  | 7 | [9 empty] | 0 | 0 | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-04-30 | ABS25030 | ABS25030 | RETAIL | ONELRA Enhancements plus5 2025 Q1 | EssilorLuxottica | G. Luongo | M. Regini | Operations | BackEnd | 78 | 75 | CLOSED | 1 | 2025 | 0 |  | 1 | [10 empty] | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-04-30 | ABS25030 | ABS25030 | RETAIL | ONELRA Enhancements plus5 2025 Q1 | EssilorLuxottica | G. Luongo | P. Assirelli | Operations | Technical Leader | 78 | 75 | CLOSED | 1 | 2025 | 0 | 15 | 4 | 7 | [9 empty] | 0.83333 | 0.2 | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-04-01 | 2025-06-30 |  |  | RETAIL | ONELRA Enhancements plus5 2025 Q2 | EssilorLuxottica | G. Luongo | B. Capotorto | Operations | Back End | 100 | 0 | ON GOING | 0 | 2025 | 14 |  |  |  | 7 | 7 | 7 | [6 empty] | 0 | 0 | 0 | 0.31818 | 0.35 | 0.35 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-04-01 | 2025-06-30 |  |  | RETAIL | ONELRA Enhancements plus5 2025 Q2 | EssilorLuxottica | G. Luongo | G. Luongo | Delivery AMS | PM - Project Governance | 100 | 0 | ON GOING | 0 | 2025 | 4 |  |  |  | 2 | 2 | 2 | [6 empty] | 0 | 0 | 0 | 0.090909 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-04-01 | 2025-06-30 |  |  | RETAIL | ONELRA Enhancements plus5 2025 Q2 | EssilorLuxottica | G. Luongo | L. Gullotto | Operations | Back End | 100 | 0 | ON GOING | 0 | 2025 | 10 |  |  |  | 5 | 5 | 5 | [6 empty] | 0 | 0 | 0 | 0.22727 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-04-01 | 2025-06-30 |  |  | RETAIL | ONELRA Enhancements plus5 2025 Q2 | EssilorLuxottica | G. Luongo | P. Assirelli | Operations | Technical Leader | 100 | 0 | ON GOING | 0 | 2025 | 16 |  |  |  | 1 | 15 | 1 | [6 empty] | 0 | 0 | 0 | 0.045455 | 0.75 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-09-30 |  |  | RETAIL | ONELRA Enhancements plus5 2025 Q3 | EssilorLuxottica | G. Luongo | B. Capotorto | Operations | Back End | 100 | 0 | TO START | 0 | 2025 | 20 | [6 empty] | 7 | 6 | 7 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.30435 | 0.5 | 0.33333 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-09-30 |  |  | RETAIL | ONELRA Enhancements plus5 2025 Q3 | EssilorLuxottica | G. Luongo | G. Luongo | Delivery AMS | PM - Project Governance | 100 | 0 | TO START | 0 | 2025 | 6 | [6 empty] | 2 | 2 | 2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.16667 | 0.095238 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-09-30 |  |  | RETAIL | ONELRA Enhancements plus5 2025 Q3 | EssilorLuxottica | G. Luongo | L. Gullotto | Operations | Back End | 100 | 0 | TO START | 0 | 2025 | 15 | [6 empty] | 5 | 5 | 5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.41667 | 0.2381 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-09-30 |  |  | RETAIL | ONELRA Enhancements plus5 2025 Q3 | EssilorLuxottica | G. Luongo | P. Assirelli | Operations | Technical Leader | 100 | 0 | TO START | 0 | 2025 | 22 | [6 empty] | 1 | 6 | 15 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.5 | 0.71429 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-09-30 |  |  | RETAIL | ONELRA Enhancements plus5 2025 Q3 | EssilorLuxottica | G. Luongo | P. Gamboni | Operations | Back End | 100 | 0 | TO START | 0 | 2025 | 13 | [6 empty] | 5 | 3 | 5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.25 | 0.2381 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-10-01 | 2025-12-31 |  |  | RETAIL | ONELRA Enhancements plus5 2025 Q4 | EssilorLuxottica | G. Luongo | B. Capotorto | Operations | Back End | 100 | 0 | TO START | 0 | 2025 | 21 | [9 empty] | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30435 | 0.33333 | 0.31818
A CONSUMO | AMS | Waterfall | 2025 | 2025-10-01 | 2025-12-31 |  |  | RETAIL | ONELRA Enhancements plus5 2025 Q4 | EssilorLuxottica | G. Luongo | G. Luongo | Delivery AMS | PM - Project Governance | 100 | 0 | TO START | 0 | 2025 | 6 | [9 empty] | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.095238 | 0.090909
A CONSUMO | AMS | Waterfall | 2025 | 2025-10-01 | 2025-12-31 |  |  | RETAIL | ONELRA Enhancements plus5 2025 Q4 | EssilorLuxottica | G. Luongo | L. Gullotto | Operations | Back End | 100 | 0 | TO START | 0 | 2025 | 15 | [9 empty] | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.2381 | 0.22727
A CONSUMO | AMS | Waterfall | 2025 | 2025-10-01 | 2025-12-31 |  |  | RETAIL | ONELRA Enhancements plus5 2025 Q4 | EssilorLuxottica | G. Luongo | P. Assirelli | Operations | Technical Leader | 100 | 0 | TO START | 0 | 2025 | 31 | [9 empty] | 1 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.71429 | 0.68182
A CONSUMO | AMS | Waterfall | 2025 | 2025-10-01 | 2025-12-31 |  |  | RETAIL | ONELRA Enhancements plus5 2025 Q4 | EssilorLuxottica | G. Luongo | P. Gamboni | Operations | Back End | 100 | 0 | TO START | 0 | 2025 | 15 | [9 empty] | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.2381 | 0.22727
INTERNAL TRAINING | FORMAZIONE |  | 2025 | 2025-01-01 | 2025-12-31 |  | ATD | OTHER | Training SAP BW/4HANA | Abstract | G. Luongo | G. Mordà | Operations | Back End - Junior | 0 | 0 | ON GOING | 0 | 2025 | 8 |  |  |  | 5 | 5 | 3 | [6 empty] | 0 | 0 | 0 | 0.22727 | 0.25 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | RETAIL | Edison Targeting & Churn | Edison | G. Sironi | A. Imbimbo | AI Operations | Data Scientist | 110 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | RETAIL | Edison Targeting & Churn | Edison | G. Sironi | F. Malvezzi | AI Operations | Data Scientist | 110 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | RETAIL | Edison Targeting & Churn | Edison | G. Sironi | G. Sironi | AI Operations | PM - Project Governance | 110 | 0 | PROPOSAL | 0 | 2025 | 6 |  |  |  | 2 | 2 | 2 | 1 | 1 |  |  |  |  | 0 | 0 | 0 | 0.090909 | 0.1 | 0.1 | 0.043478 | 0.083333 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | RETAIL | Edison Targeting & Churn | Edison | G. Sironi | M. Gomitoni | AI Operations | Technical Leader | 110 | 0 | PROPOSAL | 0 | 2025 | 10 |  |  |  | 5 | 4 | 3 | 3 | [5 empty] | 0 | 0 | 0 | 0.22727 | 0.2 | 0.15 | 0.13043 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | RETAIL | Edison Targeting & Churn | Edison | G. Sironi | V. Echarry | AI Operations | Data Scientist | 110 | 0 | PROPOSAL | 0 | 2025 | 20 |  |  |  | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 0 | 0 | 0 | 0.22727 | 0.25 | 0.25 | 0.21739 | 0.41667 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 |  | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 - Modelling CR | EssilorLuxottica | G. SIRONI | A. Imbimbo | Operations | Data Scientist | 105 | 0 | PROPOSAL | 0 | 2025 | 4 |  |  |  | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 0 | 0 | 0 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0 | 0.047619 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 |  | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 - Modelling CR | EssilorLuxottica | G. SIRONI | A. Pirola | Operations | Front End | 105 | 0 | PROPOSAL | 0 | 2025 | 8 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 2 | 1 |  |  |  | 0.055556 | 0.05 | 0.047619 | 0.090909 | 0.05 | 0.1 | 0.086957 | 0.16667 | 0.047619 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 |  | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 - Modelling CR | EssilorLuxottica | G. SIRONI | G. Lopez | Operations | Front End | 105 | 0 | PROPOSAL | 0 | 2025 | 0 | 1 | 1 | 5 | [9 empty] | 0.055556 | 0.05 | 0.2381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 |  | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 - Modelling CR | EssilorLuxottica | G. SIRONI | G. Mordà | Operations | Data Management | 105 | 0 | PROPOSAL | 0 | 2025 | 0 | 1 | 1 | 1 | [9 empty] | 0.055556 | 0.05 | 0.047619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 |  | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 - Modelling CR | EssilorLuxottica | G. SIRONI | G. Sironi | Operations | PM - Project Governance | 105 | 0 | PROPOSAL | 0 | 2025 | 0 | 1 | 1 | 1 | [9 empty] | 0.055556 | 0.05 | 0.047619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 |  | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 - Modelling CR | EssilorLuxottica | G. SIRONI | M. Vianelli | Delivery Projects | Analyst | 105 | 0 | PROPOSAL | 0 | 2025 | 6 | 1 |  |  | 1 | 3 | 1 | 1 |  | 1 |  |  |  | 0.055556 | 0 | 0 | 0.045455 | 0.15 | 0.05 | 0.043478 | 0 | 0.047619 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 |  | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 - Modelling CR | EssilorLuxottica | G. SIRONI | N. Pescione | Operations | Back End | 105 | 0 | PROPOSAL | 0 | 2025 | 0 | 1 | 1 | 5 | [9 empty] | 0.055556 | 0.05 | 0.2381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 |  | ALRTTW | RETAIL | ELRTT - RETAIL TESTING TOOL W3 - Modelling CR | EssilorLuxottica | G. SIRONI | P. Anzellotti | Operations | Team Leadership Support | 105 | 0 | PROPOSAL | 0 | 2025 | 0 | 3 | 3 | 3 | [9 empty] | 0.16667 | 0.15 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 |  |  | RETAIL | ELRTT - RETAIL TESTING TOOL W4 | EssilorLuxottica | G. SIRONI | A. Imbimbo | Operations | Data Scientist | 105 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 |  |  | RETAIL | ELRTT - RETAIL TESTING TOOL W4 | EssilorLuxottica | G. SIRONI | G. Lopez | Operations | Front End | 105 | 0 | PROPOSAL | 0 | 2025 | 22 |  |  |  |  | 5 | 5 | 5 | 2 | 5 |  |  |  | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0.21739 | 0.16667 | 0.2381 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 |  |  | RETAIL | ELRTT - RETAIL TESTING TOOL W4 | EssilorLuxottica | G. SIRONI | G. Mordà | Operations | Data Management | 105 | 0 | PROPOSAL | 0 | 2025 | 1 |  |  |  | 1 | 1 | [7 empty] | 0 | 0 | 0 | 0.045455 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 |  |  | RETAIL | ELRTT - RETAIL TESTING TOOL W4 | EssilorLuxottica | G. SIRONI | G. Sironi | Operations | PM - Project Governance | 105 | 0 | PROPOSAL | 0 | 2025 | 4 |  |  |  | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 0 | 0 | 0 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0 | 0.047619 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 |  |  | RETAIL | ELRTT - RETAIL TESTING TOOL W4 | EssilorLuxottica | G. SIRONI | N. Pescione | Operations | Back End | 105 | 0 | PROPOSAL | 0 | 2025 | 17 |  |  |  | 5 | 1 | 1 | 5 | 5 | 5 |  |  |  | 0 | 0 | 0 | 0.22727 | 0.05 | 0.05 | 0.21739 | 0.41667 | 0.2381 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 |  |  | RETAIL | ELRTT - RETAIL TESTING TOOL W4 | EssilorLuxottica | G. SIRONI | P. Anzellotti | Operations | Team Leadership Support | 105 | 0 | PROPOSAL | 0 | 2025 | 9 |  |  |  | 3 | 3 | 3 | 2 | 1 |  |  |  |  | 0 | 0 | 0 | 0.13636 | 0.15 | 0.15 | 0.086957 | 0.083333 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-06-01 |  |  | Lucy | Lucy Control Tower GenAI - Productionalization | EssilorLuxottica | G. SIRONI | A. Imbimbo | AI Operations | Data Scientist | 60 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-06-01 |  |  | Lucy | Lucy Control Tower GenAI - Productionalization | EssilorLuxottica | G. SIRONI | M. Gomitoni | AI Operations | Data Scientist | 60 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | LUCY | Lucy | Lucy4 Lease AI | EssilorLuxottica | G. Sironi | A. Imbimbo | AI Operations | Data Scientist | 100 | 0 | ON GOING | 0 | 2025 | 20 |  |  | 5 | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 0 | 0 | 0.2381 | 0.22727 | 0.25 | 0.25 | 0.21739 | 0.41667 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | LUCY | Lucy | Lucy4 Lease AI | EssilorLuxottica | G. Sironi | F. Malvezzi | AI Operations | Data Scientist | 100 | 0 | ON GOING | 0 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | LUCY | Lucy | Lucy4 Lease AI | EssilorLuxottica | G. Sironi | G. Sironi | AI Operations | PM - Project Governance | 100 | 0 | ON GOING | 0 | 2025 | 12 |  |  | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  |  | 0 | 0 | 0.14286 | 0.13636 | 0.15 | 0.15 | 0.13043 | 0.25 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | LUCY | Lucy | Lucy4 Lease AI | EssilorLuxottica | G. Sironi | M. Gomitoni | AI Operations | Technical Leader | 100 | 0 | ON GOING | 0 | 2025 | 20 |  |  | 5 | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 0 | 0 | 0.2381 | 0.22727 | 0.25 | 0.25 | 0.21739 | 0.41667 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | LUCY | Lucy | Lucy4 Lease AI | EssilorLuxottica | G. Sironi | V. Echarry | AI Operations | Data Scientist | 100 | 0 | ON GOING | 0 | 2025 | 20 |  |  | 5 | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 0 | 0 | 0.2381 | 0.22727 | 0.25 | 0.25 | 0.21739 | 0.41667 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | RETAIL | RC & Rec - Migration & New Features 2025 | EssilorLuxottica | G. SIRONI | A. Imbimbo | AI Operations | Data Scientist | 150 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | RETAIL | RC & Rec - Migration & New Features 2025 | EssilorLuxottica | G. SIRONI | F. Malvezzi | AI Operations | Data Scientist | 150 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | RETAIL | RC & Rec - Migration & New Features 2025 | EssilorLuxottica | G. SIRONI | G. Sabbatini | AI Operations | Data Engineering | 150 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | RETAIL | RC & Rec - Migration & New Features 2025 | EssilorLuxottica | G. SIRONI | G. Sironi | AI Operations | PM - Project Governance | 150 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | RETAIL | RC & Rec - Migration & New Features 2025 | EssilorLuxottica | G. SIRONI | M. Gomitoni | AI Operations | Technical Leader | 150 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  |  | RETAIL | RC & Rec - Migration & New Features 2025 | EssilorLuxottica | G. SIRONI | V. Echarry | AI Operations | Data Scientist | 150 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-04-01 | 2025-09-01 | ABS25208 | ABS25208 | LOGISTIC | CT Electra Complete Pair and LABEX | EssilorLuxottica | L. BARIANI | A. Strada | Operations | Back End | 30 | 0 | ON GOING | 0 | 2025 | 1 |  |  |  | 12 | 1 | [7 empty] | 0 | 0 | 0 | 0.54545 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-04-01 | 2025-09-01 | ABS25208 | ABS25208 | LOGISTIC | CT Electra Complete Pair and LABEX | EssilorLuxottica | L. BARIANI | L. BARIANI | Operations | PM - Project Governance | 30 | 0 | ON GOING | 0 | 2025 | 1 |  |  |  | 2 | 1 | [7 empty] | 0 | 0 | 0 | 0.090909 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-04-01 | 2025-09-01 | ABS25208 | ABS25208 | LOGISTIC | CT Electra Complete Pair and LABEX | EssilorLuxottica | L. BARIANI | M. Sabarese | Operations | Front End | 30 | 0 | ON GOING | 0 | 2025 | 2 |  |  |  | 3 | 2 | [7 empty] | 0 | 0 | 0 | 0.13636 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | A. BRANDIZZI | Operations | FrontEnd | 800 | 0 | CLOSED | 0 | 2025 | 0 | 17 | 2 | 22 | [9 empty] | 0.94444 | 0.1 | 1.0476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | A. TORONE | Delivery AMS | Analysis | 800 | 190 | CLOSED | 0 | 2025 | 0 | 6 | 6 | 6 | [9 empty] | 0.33333 | 0.3 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | C. DI LORENZO | Delivery Projects | Analysis | 800 | 190 | CLOSED | 0 | 2025 | 0 | 6 | 6 | 6 | [9 empty] | 0.33333 | 0.3 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | C. TIBERTI | Operations | Analysis | 800 | 190 | CLOSED | 0 | 2025 | 0 | 22 | 22 | 22 | [9 empty] | 1.2222 | 1.1 | 1.0476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | F. SCOGNAMIGLIO | Operations | Data Engineering | 800 | 0 | CLOSED | 0 | 2025 | 0 | 17 | 2 | 2 | [9 empty] | 0.94444 | 0.1 | 0.095238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | F. SPACAGNA | Operations | Data Engineering | 800 | 0 | CLOSED | 0 | 2025 | 0 | 6 | 6 | 6 | [9 empty] | 0.33333 | 0.3 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | G. TARTAGLIA | Operations | BackEnd | 800 | 0 | CLOSED | 0 | 2025 | 0 | 17 | 2 | 22 | [9 empty] | 0.94444 | 0.1 | 1.0476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | I. OSTYMCHUCK | Operations | Data Engineering | 800 | 0 | CLOSED | 0 | 2025 | 0 | 17 | 2 | 2 | [9 empty] | 0.94444 | 0.1 | 0.095238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | J. SORGATO |  | Analysis | 800 | 190 | CLOSED | 0 | 2025 | 0 | 4 | 4 | 4 | [9 empty] | 0.22222 | 0.2 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | L. BARIANI | Delivery Projects | PM - Project Governance | 800 | 190 | CLOSED | 0 | 2025 | 0 | 6 | 6 | 6 | [9 empty] | 0.33333 | 0.3 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | L. BARIANI | Delivery Projects | Analysis | 800 | 190 | CLOSED | 0 | 2025 | 0 | 12 | 15 | 15 | [9 empty] | 0.66667 | 0.75 | 0.71429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | L. CATTANEO |  | Analysis | 800 | 190 | CLOSED | 0 | 2025 | 0 | 4 | 4 | 4 | [9 empty] | 0.22222 | 0.2 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | M. Porcu | Operations | Technical Leader | 800 | 0 | CLOSED | 0 | 2025 | 0 | 15 | 15 | 15 | [9 empty] | 0.83333 | 0.75 | 0.71429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | M. TOCI | Operations | BackEnd | 800 | 0 | CLOSED | 0 | 2025 | 0 | 17 | 2 | 2 | [9 empty] | 0.94444 | 0.1 | 0.095238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | O. SAGAZIO | Operations | PM - Project Governance | 800 | 0 | CLOSED | 0 | 2025 | 0 | 6 | 6 | 6 | [9 empty] | 0.33333 | 0.3 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | S. Beltrami | Operations | BackEnd | 800 | 0 | CLOSED | 0 | 2025 | 0 | 6 | 6 | 6 | [9 empty] | 0.33333 | 0.3 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | S. BEN YOUNES | Operations | Analysis | 800 | 190 | CLOSED | 0 | 2025 | 0 | 6 | 6 | 6 | [9 empty] | 0.33333 | 0.3 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-03-31 | ABS24375 | ABS24375 | RETAIL | FFD - Field Force Dashboard - Wave 2 | EssilorLuxottica | L. BARIANI | S. DELLE FAVE | Operations | FrontEnd | 800 | 0 | CLOSED | 0 | 2025 | 0 | 17 | 2 | 22 | [9 empty] | 0.94444 | 0.1 | 1.0476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ | Waterfall | 2025 | 2025-02-02 | 2025-03-06 | ABS25041 |  | EPM | Nuance & Meta Integration | EssilorLuxottica | L. BARIANI | E. STORTI | Delivery Projects | Analyst | 20 | 0 | ON GOING | 0 | 2025 | 0 |  | 6 | [10 empty] | 0 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ | Waterfall | 2025 | 2025-02-02 | 2025-03-06 | ABS25041 |  | EPM | Nuance & Meta Integration | EssilorLuxottica | L. BARIANI | G. MINERVINI | Operations | Back End | 20 | 0 | ON GOING | 0 | 2025 | 0 |  | 5 | [10 empty] | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ | Waterfall | 2025 | 2025-02-02 | 2025-03-06 | ABS25041 |  | EPM | Nuance & Meta Integration | EssilorLuxottica | L. BARIANI | L. BARIANI | Delivery Projects | PM - Project Governance | 20 | 0 | ON GOING | 0 | 2025 | 0 |  | 2 | [10 empty] | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ | Waterfall | 2025 | 2025-02-02 | 2025-03-06 | ABS25041 |  | EPM | Nuance & Meta Integration | EssilorLuxottica | L. BARIANI | N. FRAGALE | Operations | Back End | 20 | 0 | ON GOING | 0 | 2025 | 0 |  | 5 | [10 empty] | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ | Waterfall | 2025 | 2025-02-02 | 2025-03-06 | ABS25041 |  | EPM | Nuance & Meta Integration | EssilorLuxottica | L. BARIANI | P. PIERONI | Operations | Solution Architect | 20 | 0 | ON GOING | 0 | 2025 | 0 |  | 2 | [10 empty] | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ | Waterfall | 2025 | 2025-02-02 | 2025-03-06 | ABS25041 |  | EPM | Nuance & Meta Integration | EssilorLuxottica | L. BARIANI | S. PREZIOSA | Delivery Projects | Analyst | 20 | 0 | ON GOING | 0 | 2025 | 0 |  | 2 | [10 empty] | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ |  | 2025 | 2025-05-18 | 2025-07-30 |  |  | EPM | One View - FDW | EssilorLuxottica | L. Bariani | L. Bariani | Delivery Projects | PM - Project Governance | 90 | 0 | PROPOSAL | 0 | 2025 | 16 |  |  |  |  | 5 | 6 | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0.25 | 0.3 | 0.21739 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ |  | 2025 | 2025-05-18 | 2025-07-30 |  |  | EPM | One View - FDW | EssilorLuxottica | L. Bariani | A. Strada | Operations | Back End | 90 | 0 | PROPOSAL | 0 | 2025 | 6 |  |  |  |  | 2 | 2 | 2 | [5 empty] | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.086957 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ |  | 2025 | 2025-05-18 | 2025-07-30 |  |  | EPM | One View - FDW | EssilorLuxottica | L. Bariani | C. Piraccini | Operations | Back End | 90 | 0 | PROPOSAL | 0 | 2025 | 21 |  |  |  |  | 5 | 8 | 8 | [5 empty] | 0 | 0 | 0 | 0 | 0.25 | 0.4 | 0.34783 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ |  | 2025 | 2025-05-18 | 2025-07-30 |  |  | EPM | One View - FDW | EssilorLuxottica | L. Bariani | M. Regini | Operations | Back End | 90 | 0 | PROPOSAL | 0 | 2025 | 21 |  |  |  |  | 5 | 8 | 8 | [5 empty] | 0 | 0 | 0 | 0 | 0.25 | 0.4 | 0.34783 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ |  | 2025 | 2025-05-18 | 2025-07-30 |  |  | EPM | One View - FDW | EssilorLuxottica | L. Bariani | S. BEN YOUNES | Delivery Projects | Back End | 90 | 0 | PROPOSAL | 0 | 2025 | 26 |  |  |  |  | 8 | 9 | 9 | [5 empty] | 0 | 0 | 0 | 0 | 0.4 | 0.45 | 0.3913 | 0 | 0 | 0 | 0 | 0
LEAD | PRESALES - DELIVERY |  | 2024-2025 | 2024-09-01 | 2025-01-31 | ABS24523 | ABS24523 | EPM | Tax Cube | EssilorLuxottica | L. Bariani | A. Di Pietro | Operations | Back End | 180 | 0 | ON HOLD | 0 | 2025 | 0 | 1 | [11 empty] | 0.055556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRESALES - DELIVERY |  | 2024-2025 | 2024-09-01 | 2025-01-31 | ABS24523 | ABS24523 | EPM | Tax Cube | EssilorLuxottica | L. Bariani | E. Storti | Delivery Projects | Analyst | 180 | 0 | ON HOLD | 0 | 2025 | 0 | 4 | [11 empty] | 0.22222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRESALES - DELIVERY |  | 2024-2025 | 2024-09-01 | 2025-01-31 | ABS24523 | ABS24523 | EPM | Tax Cube | EssilorLuxottica | L. Bariani | F. Atanasio | Operations | Back End | 180 | 0 | ON HOLD | 0 | 2025 | 0 | 1 | [11 empty] | 0.055556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25xxx | ABW2E | RETAIL | BULLSEYE ROLLOUT EMEA (IT-UK-DACH) | EssilorLuxottica | L. Franceschini | A. Vladi | Operations | Data Management - ETL | 100 | 13 | ON HOLD | 0 | 2025 | 15 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 5 | 5 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.2381 | 0.22727
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25xxx | ABW2E | RETAIL | BULLSEYE ROLLOUT EMEA (IT-UK-DACH) | EssilorLuxottica | L. Franceschini | F. D'Alberto | Operations | Data Analyst | 100 | 13 | ON HOLD | 0 | 2025 | 10 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.05 | 0.086957 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25xxx | ABW2E | RETAIL | BULLSEYE ROLLOUT EMEA (IT-UK-DACH) | EssilorLuxottica | L. Franceschini | F. Spacagna | Operations | Solution Architect | 100 | 13 | ON HOLD | 0 | 2025 | 16 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 3 | 0.055556 | 0.05 | 0.095238 | 0.090909 | 0.05 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.17391 | 0.19048 | 0.13636
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25xxx | ABW2E | RETAIL | BULLSEYE ROLLOUT EMEA (IT-UK-DACH) | EssilorLuxottica | L. Franceschini | G. Franchi | Operations | Back End - Java | 100 | 13 | ON HOLD | 0 | 2025 | 4 | 1 | 2 | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 0.055556 | 0.1 | 0.047619 | 0 | 0.05 | 0 | 0.043478 | 0 | 0.047619 | 0 | 0.047619 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25xxx | ABW2E | RETAIL | BULLSEYE ROLLOUT EMEA (IT-UK-DACH) | EssilorLuxottica | L. Franceschini | L. Franceschini | Delivery Projects | PM - Project Governance | 100 | 13 | ON HOLD | 0 | 2025 | 15 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 1 | 2 | 1 | 2 | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.15 | 0.1 | 0.086957 | 0.16667 | 0.047619 | 0.086957 | 0.047619 | 0.090909
CONTRACT | PRJ | Waterfall | 2025 | 2024-01-01 | 2025-06-30 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | A. Nastasi | Operations | Data Management | 780 | 735 | ON HOLD | 0 | 2025 | 0 | 1 | 1 | 5 | 5 | [8 empty] | 0.055556 | 0.05 | 0.2381 | 0.22727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-01-01 | 2025-06-30 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | A. Pirola | Operations | Front End | 780 | 735 | ON HOLD | 0 | 2025 | 0 | 1 | 1 | 2 | 2 | [8 empty] | 0.055556 | 0.05 | 0.095238 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-01-01 | 2025-06-30 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | A. Vladi | Operations | Technical Leader - Data Management | 780 | 735 | ON HOLD | 0 | 2025 | 0 | 15 | 18 | 18 | 19 | [8 empty] | 0.83333 | 0.9 | 0.85714 | 0.86364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-01-01 | 2025-06-30 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | C. Elia | Operations | Data Management | 780 | 735 | ON HOLD | 0 | 2025 | 14 | 7 | 8 | 8 | 8 | [5 empty] | 6 | 4 | 4 | 0.38889 | 0.4 | 0.38095 | 0.36364 | 0 | 0 | 0 | 0 | 0 | 0.26087 | 0.19048 | 0.18182
CONTRACT | PRJ | Waterfall | 2025 | 2024-01-01 | 2025-06-30 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | F. D'Alberto | Operations | Data Management | 780 | 735 | ON HOLD | 0 | 2025 | 0 | 1 | 15 | 15 | 15 | [8 empty] | 0.055556 | 0.75 | 0.71429 | 0.68182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-01-01 | 2025-06-30 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | F. Spacagna | Operations | Solution Architect | 780 | 735 | ON HOLD | 0 | 2025 | 0 | 13 | 12 | 12 | 12 | [8 empty] | 0.72222 | 0.6 | 0.57143 | 0.54545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-01-01 | 2025-06-30 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | G. Franchi | Operations | Back End | 780 | 735 | ON HOLD | 0 | 2025 | 0 | 15 | 15 | 15 | 15 | [8 empty] | 0.83333 | 0.75 | 0.71429 | 0.68182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-01-01 | 2025-06-30 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | L. Franceschini | Delivery Projects | PM - Project Governance | 780 | 735 | ON HOLD | 0 | 2025 | 64 | 2 | 2 | 2 | 2 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.4 | 0.4 | 0.34783 | 0.66667 | 0.38095 | 0.34783 | 0.38095 | 0.36364
CONTRACT | PRJ | Waterfall | 2025 | 2024-01-01 | 2025-06-30 | ABS24105 | ABROS2W | RETAIL | BULLSEYE W3 | EssilorLuxottica | L. Franceschini | M. Vianelli | Delivery Projects | Analyst | 780 | 735 | ON HOLD | 0 | 2025 | 0 | 3 | 4 | 4 | 4 | [8 empty] | 0.16667 | 0.2 | 0.19048 | 0.18182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-09-30 | ABS25191 |  | RETAIL | Bullseye Wave 3 - DTBRK Integration | EssilorLuxottica | L. Franceschini | A. Pirola | Operations | Front End | 70 | 0 | PROPOSAL | 0 | 2025 | 1 |  |  |  | 1 | 1 | [7 empty] | 0 | 0 | 0 | 0.045455 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-09-30 | ABS25191 |  | RETAIL | Bullseye Wave 3 - DTBRK Integration | EssilorLuxottica | L. Franceschini | A. Vladi | Operations | Technical Leader - Data Management | 70 | 0 | PROPOSAL | 0 | 2025 | 15 | 2 | 2 | 5 | 5 | 5 | 5 | 5 | [5 empty] | 0.11111 | 0.1 | 0.2381 | 0.22727 | 0.25 | 0.25 | 0.21739 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-09-30 | ABS25191 |  | RETAIL | Bullseye Wave 3 - DTBRK Integration | EssilorLuxottica | L. Franceschini | F. D'Alberto | Operations | Data Management | 70 | 0 | PROPOSAL | 0 | 2025 | 5 |  |  |  | 5 | 5 | [7 empty] | 0 | 0 | 0 | 0.22727 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-09-30 | ABS25191 |  | RETAIL | Bullseye Wave 3 - DTBRK Integration | EssilorLuxottica | L. Franceschini | F. Spacagna | Operations | Solution Architect | 70 | 0 | PROPOSAL | 0 | 2025 | 3 | [5 empty] | 1 | 1 |  | 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.043478 | 0 | 0.047619 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-09-30 | ABS25191 |  | RETAIL | Bullseye Wave 3 - DTBRK Integration | EssilorLuxottica | L. Franceschini | G. Franchi | Operations | Back End | 70 | 0 | PROPOSAL | 0 | 2025 | 15 |  |  |  | 5 | 5 | 5 | 5 | [5 empty] | 0 | 0 | 0 | 0.22727 | 0.25 | 0.25 | 0.21739 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-09-30 | ABS25191 |  | RETAIL | Bullseye Wave 3 - DTBRK Integration | EssilorLuxottica | L. Franceschini | L. Franceschini | Delivery Projects | PM - Project Governance | 70 | 0 | PROPOSAL | 0 | 2025 | 10 |  |  |  |  | 3 | 3 | 4 | [5 empty] | 0 | 0 | 0 | 0 | 0.15 | 0.15 | 0.17391 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-01 | 2025-09-30 | ABS25191 |  | RETAIL | Bullseye Wave 3 - DTBRK Integration | EssilorLuxottica | L. Franceschini | TBD | Operations | Data Management | 70 | 0 | PROPOSAL | 0 | 2025 | 5 |  |  |  | 5 | 5 | [7 empty] | 0 | 0 | 0 | 0.22727 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2024-02-28 | ABS25121 | ABS25121 | FINANCE | EDEN W2 - integrazione | EssilorLuxottica | L. Franceschini | A. Strada | Operations | Data Management | 49 | 2 | ON GOING | 0 | 2025 | 0 |  | 1 | 1 | [9 empty] | 0 | 0.05 | 0.047619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2024-02-28 | ABS25121 | ABS25121 | FINANCE | EDEN W2 - integrazione | EssilorLuxottica | L. Franceschini | D. De Pecol | Operations | Front End | 49 | 2 | ON GOING | 0 | 2025 | 5 |  |  | 8 | 8 | 5 | [7 empty] | 0 | 0 | 0.38095 | 0.36364 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2024-02-28 | ABS25121 | ABS25121 | FINANCE | EDEN W2 - integrazione | EssilorLuxottica | L. Franceschini | L. Franceschini | Delivery Projects | PM - Project Governance | 49 | 2 | ON GOING | 0 | 2025 | 8 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2024-02-28 | ABS25121 | ABS25121 | FINANCE | EDEN W2 - integrazione | EssilorLuxottica | L. Franceschini | R. Bondi | Operations | Front End | 49 | 2 | ON GOING | 0 | 2025 | 0 |  |  | 1 | 1 | [8 empty] | 0 | 0 | 0.047619 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-01 | 2024-02-28 | ABS25121 | ABS25121 | FINANCE | EDEN W2 - integrazione | EssilorLuxottica | L. Franceschini | S. Ben Younes | Operations | Data Management | 49 | 2 | ON GOING | 0 | 2025 | 5 |  | 2 | 7 | 7 | 5 | [7 empty] | 0 | 0.1 | 0.33333 | 0.31818 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | ABS0015 | RETAIL | Shield - POC Data Science | EssilorLuxottica | L. Franceschini | A. Imbimbo | Operations | Data Scientist | 160 | 14 | ON GOING | 0 | 2025 | 20 |  |  |  |  | 5 | 5 | 5 |  | 5 |  |  |  | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0.21739 | 0 | 0.2381 | 0 | 0 | 0
PROSPECT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | ABS0015 | RETAIL | Shield - POC Data Science | EssilorLuxottica | L. Franceschini | A. Pirola | Operations | Front End | 160 | 14 | ON GOING | 0 | 2025 | 6 |  |  |  |  | 2 | 2 | 1 |  | 1 |  |  |  | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.043478 | 0 | 0.047619 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | ABS0015 | RETAIL | Shield - POC Data Science | EssilorLuxottica | L. Franceschini | A. Vladi | Operations | Data Engineering | 160 | 14 | ON GOING | 0 | 2025 | 20 |  |  |  |  | 5 | 5 | 5 |  | 5 |  |  |  | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0.21739 | 0 | 0.2381 | 0 | 0 | 0
PROSPECT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | ABS0015 | RETAIL | Shield - POC Data Science | EssilorLuxottica | L. Franceschini | F. Spacagna | Operations | Solution Architect | 160 | 14 | ON GOING | 0 | 2025 | 12 |  |  |  |  | 3 | 3 | 3 |  | 3 |  |  |  | 0 | 0 | 0 | 0 | 0.15 | 0.15 | 0.13043 | 0 | 0.14286 | 0 | 0 | 0
PROSPECT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | ABS0015 | RETAIL | Shield - POC Data Science | EssilorLuxottica | L. Franceschini | G. Sironi | Operations | Team Leadership | 160 | 14 | ON GOING | 0 | 2025 | 20 |  |  |  |  | 5 | 5 | 5 |  | 5 |  |  |  | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0.21739 | 0 | 0.2381 | 0 | 0 | 0
PROSPECT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | ABS0015 | RETAIL | Shield - POC Data Science | EssilorLuxottica | L. Franceschini | L. Franceschini | Delivery Projects | PM - Project Governance | 160 | 14 | ON GOING | 0 | 2025 | 8 |  |  |  |  | 2 | 2 | 2 |  | 2 |  |  |  | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.086957 | 0 | 0.095238 | 0 | 0 | 0
PROSPECT | PRESALES - DELIVERY | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | ABS0015 | RETAIL | Shield - POC Data Science | EssilorLuxottica | L. Franceschini | TBD |  | Back End | 160 | 14 | ON GOING | 0 | 2025 | 20 |  |  |  |  | 5 | 5 | 5 |  | 5 |  |  |  | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0.21739 | 0 | 0.2381 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2025-01-01 | 2025-12-31 |  | U20R | ERP | UNIEURO | UNIEURO | L. Franceschini | L. Franceschini | Delivery Projects | PM - Project Governance | 100 | 55 | ON GOING | 0 | 2025 | 13 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 1 | 2 | 1 | 1 |  | 0.11111 | 0.1 | 0.095238 | 0.13636 | 0.15 | 0.15 | 0.086957 | 0.083333 | 0.095238 | 0.043478 | 0.047619 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-09 | 2025-04-30 |  | ABS0008-103 | HR | Dashboard CSR | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analyst | 82 | 0 | ON GOING | 0 | 2025 | 19 |  |  |  | 5 | 8 | 8 | 3 | [5 empty] | 0 | 0 | 0 | 0.22727 | 0.4 | 0.4 | 0.13043 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-09 | 2025-04-30 |  | ABS0008-103 | HR | Dashboard CSR | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 82 | 0 | ON GOING | 0 | 2025 | 10 |  |  |  | 3 | 4 | 3 | 1 | 1 | 1 |  |  |  | 0 | 0 | 0 | 0.13636 | 0.2 | 0.15 | 0.043478 | 0.083333 | 0.047619 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-03-09 | 2025-04-30 |  | ABS0008-103 | HR | Dashboard CSR | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 82 | 0 | ON GOING | 0 | 2025 | 4 |  |  |  | 1 | 2 | 1 | 1 | [5 empty] | 0 | 0 | 0 | 0.045455 | 0.1 | 0.05 | 0.043478 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-03-09 | 2025-04-30 |  | ABS0008-103 | HR | Dashboard CSR | EssilorLuxottica | L. Roberto | M. Vimercati | Operations | Data Management | 82 | 0 | ON GOING | 0 | 2025 | 27 |  |  |  | 6 | 12 | 15 | [6 empty] | 0 | 0 | 0 | 0.27273 | 0.6 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-03-09 | 2025-04-30 |  | ABS0008-103 | HR | Dashboard CSR | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Front End | 82 | 0 | ON GOING | 0 | 2025 | 20 |  |  |  | 1 | 6 | 10 | 4 | [5 empty] | 0 | 0 | 0 | 0.045455 | 0.3 | 0.5 | 0.17391 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ | Waterfall | 2025 | 2025-05-04 | 2025-07-31 |  | ABS0008-99 | HR | Dashboard data quality | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Business anlysis | 0 | 0 | PROPOSAL | 0 | 2025 | 9 | [5 empty] | 3 | 3 | 3 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.13043 | 0.25 | 0 | 0 | 0 | 0
LEAD | PRJ | Waterfall | 2025 | 2025-05-04 | 2025-07-31 |  | ABS0008-99 | HR | Dashboard data quality | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 0 | 0 | PROPOSAL | 0 | 2025 | 5 | [5 empty] | 1 |  |  | 2 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0.095238 | 0.086957 | 0 | 0
LEAD | PRJ | Waterfall | 2025 | 2025-05-04 | 2025-07-31 |  |  | HR | Dashboard Salary (dati vendite) | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Business anlysis | 0 | 0 | PROPOSAL | 0 | 2025 | 6 | [5 empty] | 2 | 2 | 2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0.16667 | 0 | 0 | 0 | 0
LEAD | PRJ | Waterfall | 2025 | 2025-05-04 | 2025-07-31 |  |  | HR | Dashboard Salary (dati vendite) | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 0 | 0 | PROPOSAL | 0 | 2025 | 8 | [5 empty] | 2 |  |  |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0.086957 | 0.095238 | 0.090909
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 |  |  | ABS0008-174 | HR | Evolutive Dashboard Aprile(post golive) | EssilorLuxottica | L. Roberto | D. DE PECOL |  | Data Management | 6 | 0 | ON GOING | 1 | 2025 | 0 |  |  |  | 2 | [8 empty] | 0 | 0 | 0 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 |  |  | ABS0008-174 | HR | Evolutive Dashboard Aprile(post golive) | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Business Analysis | 6 | 0 | ON GOING | 1 | 2025 | 0 |  |  |  | 1 | [8 empty] | 0 | 0 | 0 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 |  |  | ABS0008-174 | HR | Evolutive Dashboard Aprile(post golive) | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 6 | 0 | ON GOING | 0 | 2025 | 0 |  |  |  | 1 | [8 empty] | 0 | 0 | 0 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 |  |  | ABS0008-174 | HR | Evolutive Dashboard Aprile(post golive) | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 6 | 0 | ON GOING | 1 | 2025 | 0 |  |  |  | 1 | [8 empty] | 0 | 0 | 0 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 |  |  | ABS0008-174 | HR | Evolutive Dashboard Aprile(post golive) | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Data Management | 6 | 0 | ON GOING | 1 | 2025 | 0 |  |  |  | 2 | [8 empty] | 0 | 0 | 0 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 |  |  | ABS0008-202 | HR | Evolutive Dashboard Maggio(post golive) | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Business Analysis | 13 | 0 | ON GOING | 1 | 2025 | 1 |  |  |  | 1 | 1 | [7 empty] | 0 | 0 | 0 | 0.045455 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 |  |  | ABS0008-201 | HR | Evolutive Dashboard Maggio(post golive) | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 13 | 0 | ON GOING | 0 | 2025 | 5 |  |  |  | 1 | 3 | 2 | [6 empty] | 0 | 0 | 0 | 0.045455 | 0.15 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 |  |  | ABS0008-201 | HR | Evolutive Dashboard Maggio(post golive) | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 13 | 0 | ON GOING | 1 | 2025 | 1 |  |  |  | 1 | 1 | [7 empty] | 0 | 0 | 0 | 0.045455 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 |  |  | ABS0008-203 | HR | Evolutive Dashboard Maggio(post golive) | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Data Management | 13 | 0 | ON GOING | 1 | 2025 | 6 |  |  |  | 4 | 5 |  | 1 | [5 empty] | 0 | 0 | 0 | 0.18182 | 0.25 | 0 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 |  | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analyst | 100 | 0 | ON GOING | 0 | 2025 | 3 | 2 |  |  | 1 | 1 | 2 | [6 empty] | 0.11111 | 0 | 0 | 0.045455 | 0.05 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 |  | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Management | 100 | 0 | ON GOING | 0 | 2025 | 0 | 2 |  | 2 | [9 empty] | 0.11111 | 0 | 0.095238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 |  | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PM - Project Governance | 100 | 0 | ON GOING | 0 | 2025 | 7 | 1 |  | 1 | 2 | 3 | 4 | [6 empty] | 0.055556 | 0 | 0.047619 | 0.090909 | 0.15 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 |  | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 100 | 0 | ON GOING | 0 | 2025 | 17 |  |  |  | 8 | 15 | 2 | [6 empty] | 0 | 0 | 0 | 0.36364 | 0.75 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 |  | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | L. Carloni | Operations | Back End | 100 | 0 | ON GOING | 0 | 2025 | 1.5 |  |  |  |  | 1.5 | [7 empty] | 0 | 0 | 0 | 0 | 0.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 |  | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 100 | 0 | ON GOING | 0 | 2025 | 5 | 1 |  | 1 | 2 | 2 | 2 | 1 | [5 empty] | 0.055556 | 0 | 0.047619 | 0.090909 | 0.1 | 0.1 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 |  | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | M. Porcu | Operations | Technical Leader | 100 | 0 | ON GOING | 0 | 2025 | 1.5 |  |  |  |  | 1.5 | [7 empty] | 0 | 0 | 0 | 0 | 0.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 |  | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | M. Toci | Operations | Back End | 100 | 0 | ON GOING | 0 | 2025 | 1.5 |  |  |  |  | 1.5 | [7 empty] | 0 | 0 | 0 | 0 | 0.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 |  | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | M. Vimercati | Operations | Data Management | 100 | 0 | ON GOING | 0 | 2025 | 1 |  |  |  | 1 | 1 | [7 empty] | 0 | 0 | 0 | 0.045455 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 |  | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Front End | 100 | 0 | ON GOING | 0 | 2025 | 3 |  |  |  | 3 | 3 | [7 empty] | 0 | 0 | 0 | 0.13636 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 |  | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analyst | 100 | 0 | ON GOING | 0 | 2025 | 11 | 5 | 4 | 4 | 6 | 8 | 2 | 1 | [5 empty] | 0.27778 | 0.2 | 0.19048 | 0.27273 | 0.4 | 0.1 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-03-07 | 2025-03-28 |  | ABS0008-45 | HR | HR - File malloppo | EssilorLuxottica | L. Roberto | S. Beltrami | Operations | Front End | 100 | 0 | ON GOING | 0 | 2025 | 1.5 |  |  |  |  | 1.5 | [7 empty] | 0 | 0 | 0 | 0 | 0.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | A. Torone | Delivery Projects | Analyst | 100 | 0 | ON GOING | 0 | 2025 | 0 | 3.5 | 3.5 | [10 empty] | 0.19444 | 0.175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Management | 100 | 7 | ON GOING | 0 | 2025 | 1 | 1 | 1 |  | 1 | 1 | [7 empty] | 0.055556 | 0.05 | 0 | 0.045455 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 100 | 7 | ON GOING | 0 | 2025 | 3 | 2 | 2 |  | 2 | 2 | 1 | [6 empty] | 0.11111 | 0.1 | 0 | 0.090909 | 0.1 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 100 | 7 | ON GOING | 0 | 2025 | 5 | 1 | 1 |  | 5 | 3 | 2 | [6 empty] | 0.055556 | 0.05 | 0 | 0.22727 | 0.15 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 100 | 7 | ON GOING | 0 | 2025 | 3 | 2 | 2 |  | 2 | 2 | 1 | [6 empty] | 0.11111 | 0.1 | 0 | 0.090909 | 0.1 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | P. SINGH | Operations | Data Management | 100 | 7 | ON GOING | 0 | 2025 | 8 |  |  |  | 5 | 8 | [7 empty] | 0 | 0 | 0 | 0.22727 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analyst | 100 | 7 | ON GOING | 0 | 2025 | 4 | 1 | 1 | 1 | 4 | 3 | 1 | [6 empty] | 0.055556 | 0.05 | 0.047619 | 0.18182 | 0.15 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | R. Tortora | Operations | Data Management | 100 | 7 | ON GOING | 0 | 2025 | 1 |  |  |  | 2 | 1 | [7 empty] | 0 | 0 | 0 | 0.090909 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-10-21 | 2024-11-30 | ABS25085 | ABS25085 | HR | HR - LandingPage wave1 | EssilorLuxottica | L. Roberto | C. Elia | Operations | Back End | 65 | 36 | ON HOLD | 0 | 2025 | 0 | 2 | 1 | [10 empty] | 0.11111 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-10-21 | 2024-11-30 | ABS25085 | ABS25085 | HR | HR - LandingPage wave1 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 65 | 36 | ON HOLD | 0 | 2025 | 0 | 1 | 1 | [10 empty] | 0.055556 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-10-21 | 2024-11-30 | ABS25085 | ABS25085 | HR | HR - LandingPage wave1 | EssilorLuxottica | L. Roberto | M. Porcu | Operations | Back End | 65 | 36 | ON HOLD | 0 | 2025 | 0 | 2 | 1 | [10 empty] | 0.11111 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-10-21 | 2024-11-30 | ABS25085 | ABS25085 | HR | HR - LandingPage wave1 | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analyst | 65 | 36 | ON HOLD | 0 | 2025 | 0 | 1 | 1 | [10 empty] | 0.055556 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ | Agile | 2025 | 2025-03-02 | 2025-05-23 |  | ABS0008-194 | HR | HR - OrgView | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 0 | 0 | PROPOSAL | 0 | 2025 | 2 |  |  |  | 1 | 1 | 1 | [6 empty] | 0 | 0 | 0 | 0.045455 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ | Agile | 2025 | 2025-03-02 | 2025-05-23 |  | ABS0008-194 | HR | HR - OrgView | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analyst | 0 | 0 | PROPOSAL | 0 | 2025 | 6 |  |  |  | 2 | 3 | 3 | [6 empty] | 0 | 0 | 0 | 0.090909 | 0.15 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-12-02 | 2025-03-18 | ABS25085 | ABS25085 | HR | HR - Revisione DMGLOBAL | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Management | 109 | 91 | CLOSED | 1 | 2025 | 1 | 3 | 1 | 15 | 15 | 1 | [7 empty] | 0.16667 | 0.05 | 0.71429 | 0.68182 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-12-02 | 2025-03-18 | ABS25085 | ABS25085 | HR | HR - Revisione DMGLOBAL | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 109 | 91 | CLOSED | 1 | 2025 | 2 | 1 | 2 | 1 | 2 | 2 | [7 empty] | 0.055556 | 0.1 | 0.047619 | 0.090909 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-12-02 | 2025-03-18 | ABS25085 | ABS25085 | HR | HR - Revisione DMGLOBAL | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 109 | 91 | CLOSED | 1 | 2025 | 4 | 2 | 8 | 6 | 4 | 4 | [7 empty] | 0.11111 | 0.4 | 0.28571 | 0.18182 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-12-02 | 2025-03-18 | ABS25085 | ABS25085 | HR | HR - Revisione DMGLOBAL | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 109 | 91 | CLOSED | 1 | 2025 | 1 | 1 | 1 | 1 | 1 | 1 | [7 empty] | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-12-02 | 2025-03-18 | ABS25085 | ABS25085 | HR | HR - Revisione DMGLOBAL | EssilorLuxottica | L. Roberto | M. VIMERCATI | Operations | Data Management | 109 | 91 | CLOSED | 1 | 2025 | 0 | 2 | 3 | [10 empty] | 0.11111 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024-2025 | 2024-12-02 | 2025-03-18 | ABS25085 | ABS25085 | HR | HR - Revisione DMGLOBAL | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analyst | 109 | 91 | CLOSED | 1 | 2025 | 2 | 1 | 1 | 1 | 1 | 2 | [7 empty] | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 |  | ABS0008-16 | HR | HR - Revisione PA0002 | EssilorLuxottica | L. Roberto | G. Cataldo | Operations | Data Management | 29 | 19 | CLOSED | 1 | 2025 | 0 | 3 | [11 empty] | 0.16667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 |  | ABS0008-16 | HR | HR - Revisione PA0002 | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 29 | 19 | CLOSED | 1 | 2025 | 0 | 1 | 1 | [10 empty] | 0.055556 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 |  | ABS0008-16 | HR | HR - Revisione PA0002 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | Project Governance | 29 | 12 | CLOSED | 0 | 2025 | 0 | 1 | 1 | [10 empty] | 0.055556 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2024 | 2024-10-21 | 2024-11-30 |  | ABS0008-16 | HR | HR - Revisione PA0002 | EssilorLuxottica | L. Roberto | M. VIMERCATI | Operations | Data Management | 29 | 19 | CLOSED | 1 | 2025 | 0 | 3 | 2 | [10 empty] | 0.16667 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 |  | ABS24299 | ABS0008-138 | HR | Hypercare dismissione QLIK | EssilorLuxottica | L. Roberto | D. De Pecol |  | Data Management | 570 | 567 | On Going | 0 | 2025 | 0 |  |  | 1 | 1 | [8 empty] | 0 | 0 | 0.047619 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 |  | ABS24299 | ABS0008-138 | HR | Hypercare dismissione QLIK | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Business anlysis | 570 | 567 | On Going | 0 | 2025 | 0 |  |  | 4 | 5 | [8 empty] | 0 | 0 | 0.19048 | 0.22727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 |  | ABS24299 | ABS0008-138 | HR | Hypercare dismissione QLIK | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 570 | 567 | ON GOING | 0 | 2025 | 1 |  |  | 4 | 2 |  | 1 | [6 empty] | 0 | 0 | 0.19048 | 0.090909 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 |  | ABS24299 | ABS0008-138 | HR | Hypercare dismissione QLIK | EssilorLuxottica | L. Roberto | L. Roberto | Operations | Project Governance - PMO | 570 | 567 | On Going | 0 | 2025 | 1 |  |  | 2 | 1 | 1 | [7 empty] | 0 | 0 | 0.095238 | 0.045455 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 |  | ABS24299 | ABS0008-138 | HR | Hypercare dismissione QLIK | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Data Management | 570 | 567 | On Going | 0 | 2025 | 0 |  |  | 1 | 1 | [8 empty] | 0 | 0 | 0.047619 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  |  |  |  | ABS23222 | AIW3TRI | OTHER | Image Processing Tool - Wave 3 | EssilorLuxottica | L. Roberto | A. Ferrari | Operations | Data Engineering | 151 | 0 | TO START | 0 | 2025 | 20 | [5 empty] | 1 | 17.5 | 1.5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.76087 | 0.125 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  |  |  |  | ABS23222 | AIW3TRI | OTHER | Image Processing Tool - Wave 3 | EssilorLuxottica | L. Roberto | M. Porcu | Operations | Solution Architect | 151 | 0 | TO START | 0 | 2025 | 11.2 | [5 empty] | 2.4 | 4.6 | 4.2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.12 | 0.2 | 0.35 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  |  |  |  | ABS23222 | AIW3TRI | OTHER | Image Processing Tool - Wave 3 | EssilorLuxottica | L. Roberto | M. Toci | Operations | Back End | 151 | 0 | TO START | 0 | 2025 | 22.4 | [5 empty] | 9.2 | 4.8 | 8.4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.46 | 0.2087 | 0.7 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  |  |  |  | ABS23222 | AIW3TRI | OTHER | Image Processing Tool - Wave 3 | EssilorLuxottica | L. Roberto | S. Beltrami | Operations |  | 151 | 0 | TO START | 0 | 2025 | 22.4 | [5 empty] | 9.2 | 4.8 | 8.4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.46 | 0.2087 | 0.7 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-01-17 | 2025-04-03 |  | ABS0008-147 | HR | Migrazione autenticazione One Org su NAM | EssilorLuxottica | L. Roberto | C. Di Lorenzo | Delivery Projects | Analyst | 9 | 0 | ON HOLD | 0 | 2025 | 0 |  | 0.5 | 0.5 | [9 empty] | 0 | 0.025 | 0.02381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-01-17 | 2025-04-03 |  | ABS0008-147 | HR | Migrazione autenticazione One Org su NAM | EssilorLuxottica | L. Roberto | M. Porcu | Operations | Technical Leader | 9 | 0 | ON HOLD | 0 | 2025 | 0 |  | 1 | 1 | 1 | [8 empty] | 0 | 0.05 | 0.047619 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-01-17 | 2025-04-03 |  | ABS0008-147 | HR | Migrazione autenticazione One Org su NAM | EssilorLuxottica | L. Roberto | M. Toci | Operations | Back End | 9 | 0 | ON HOLD | 0 | 2025 | 0 |  |  | 3 | 3 | [8 empty] | 0 | 0 | 0.14286 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | A. BRANDIZZI | Operations | Front End | 450 | 244 | ON GOING | 0 | 2025 | 45 | 1 | 1 | 15 | 15 | 15 | 15 | 15 | [5 empty] | 0.055556 | 0.05 | 0.71429 | 0.68182 | 0.75 | 0.75 | 0.65217 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | A. Lorena | Operations | Front End | 450 | 244 | ON GOING | 0 | 2025 | 2 | 1 | 1 | 1 | 4 |  | 1 | 1 | [5 empty] | 0.055556 | 0.05 | 0.047619 | 0.18182 | 0 | 0.05 | 0.043478 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | A. Pirola | Operations | Back End | 450 | 244 | ON GOING | 0 | 2025 | 3 | 1 | 15 | 15 | 15 | 1 | 1 | 1 | [5 empty] | 0.055556 | 0.75 | 0.71429 | 0.68182 | 0.05 | 0.05 | 0.043478 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | C. Di Lorenzo | Delivery Projects | Analyst | 450 | 244 | ON GOING | 0 | 2025 | 12 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | [5 empty] | 0.16667 | 0.15 | 0.19048 | 0.18182 | 0.2 | 0.2 | 0.17391 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | F. Scognamiglio | Operations | Back End | 450 | 244 | ON GOING | 0 | 2025 | 57 |  |  |  | 15 | 15 | 20 | 22 | [5 empty] | 0 | 0 | 0 | 0.68182 | 0.75 | 1 | 0.95652 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | G. De Feo | Delivery Projects | PM - Project Governance | 450 | 244 | ON GOING | 0 | 2025 | 31 | 4 | 3 | 3 | 3 | 4 | 4 | 5 | 2 | 4 | 4 | 4 | 4 | 0.22222 | 0.15 | 0.14286 | 0.13636 | 0.2 | 0.2 | 0.21739 | 0.16667 | 0.19048 | 0.17391 | 0.19048 | 0.18182
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | G. Lopez | Operations | Front End | 450 | 244 | ON GOING | 0 | 2025 | 30 | 15 | 15 | 15 |  |  | 15 | 15 | [5 empty] | 0.83333 | 0.75 | 0.71429 | 0 | 0 | 0.75 | 0.65217 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | G. TARTAGLIA | Operations | Back End | 450 | 244 | ON GOING | 0 | 2025 | 42 | 15 | 15 | 15 |  |  | 20 | 22 | [5 empty] | 0.83333 | 0.75 | 0.71429 | 0 | 0 | 1 | 0.95652 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | M. TOCI | Operations | Back End | 450 | 244 | ON GOING | 0 | 2025 | 17 | 3 | 3 | 3 |  |  | 8 | 9 | [5 empty] | 0.16667 | 0.15 | 0.14286 | 0 | 0 | 0.4 | 0.3913 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | N. Pescione | Operations | Back End | 450 | 244 | ON GOING | 0 | 2025 | 0 | 15 | [11 empty] | 0.83333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | P. Anzellotti | Operations | Technical Leader | 450 | 244 | ON GOING | 0 | 2025 | 15 | 6 | 3 | 3 | 3 | 3 | 6 | 6 | [5 empty] | 0.33333 | 0.15 | 0.14286 | 0.13636 | 0.15 | 0.3 | 0.26087 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | S. Beltrami | Operations | Front End | 450 | 244 | ON GOING | 0 | 2025 | 0 | 3 | 3 | 3 | [9 empty] | 0.16667 | 0.15 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | S. Delle Fave | Operations | Front End | 450 | 244 | ON GOING | 0 | 2025 | 30 | 3 | 3 | 3 |  |  | 15 | 15 | [5 empty] | 0.16667 | 0.15 | 0.14286 | 0 | 0 | 0.75 | 0.65217 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-05-31 |  | IAA | HR | MY PLACE | Abstract | L. Roberto | C. Di Lorenzo | Delivery Projects | Business Analysis | 0 | 0 | ON GOING | 0 | 2025 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [5 empty] | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-05-31 |  | IAA | HR | MY PLACE | Abstract | L. Roberto | L. Roberto | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2025 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
INTERNAL PRJ | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-05-31 |  | IAA | HR | MY PLACE | Abstract | L. Roberto | M. Simeone | Operations | Front End | 0 | 0 | ON GOING | 0 | 2025 | 45 | 18 | 15 | 13 | 15 | 15 | 15 | 15 | [5 empty] | 1 | 0.75 | 0.61905 | 0.68182 | 0.75 | 0.75 | 0.65217 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-05-31 |  | IAA | HR | MY PLACE - MY CAREER | Abstract | L. Roberto | L. Roberto | Operations | PM - Project Governance | 450 | 244 | ON GOING | 0 | 2025 | 2 | 4 | 3 | 3 |  |  | 1 | 1 | [5 empty] | 0.22222 | 0.15 | 0.14286 | 0 | 0 | 0.05 | 0.043478 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ | Agile | 2025 | 2025-02-20 | 2025-05-10 |  |  | HR | One Org HR - desktop version | EssilorLuxottica | L. Roberto | A. Lorena | Operations | Front End | 185 | 0 | PROPOSAL | 0 | 2025 | 26 | [5 empty] | 6 | 12 | 1 | 1 | 6 |  |  | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.52174 | 0.083333 | 0.047619 | 0.26087 | 0 | 0
LEAD | PRJ | Agile | 2025 | 2025-02-20 | 2025-05-10 |  |  | HR | One Org HR - desktop version | EssilorLuxottica | L. Roberto | C. Di Lorenzo | Delivery Projects | Analyst | 185 | 0 | PROPOSAL | 0 | 2025 | 2 | 2 | 5 | 2 | 2 |  | 2 | [6 empty] | 0.11111 | 0.25 | 0.095238 | 0.090909 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ | Agile | 2025 | 2025-02-20 | 2025-05-10 |  |  | HR | One Org HR - desktop version | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PM - Project Governance | 185 | 0 | PROPOSAL | 0 | 2025 | 11 |  | 2 | 1 | 1 |  | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 0 | 0.1 | 0.047619 | 0.045455 | 0 | 0.1 | 0.086957 | 0.083333 | 0.095238 | 0.086957 | 0.047619 | 0.045455
LEAD | PRJ | Agile | 2025 | 2025-02-20 | 2025-05-10 |  |  | HR | One Org HR - desktop version | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 185 | 0 | PROPOSAL | 0 | 2025 | 6 | [5 empty] | 2 | 1 | 1 | 2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.043478 | 0.083333 | 0.095238 | 0 | 0 | 0
LEAD | PRJ | Agile | 2025 | 2025-02-20 | 2025-05-10 |  |  | HR | One Org HR - desktop version | EssilorLuxottica | L. Roberto | M. Porcu | Operations | Back End | 185 | 0 | PROPOSAL | 0 | 2025 | 10 | [5 empty] | 1.5 | 2 | 2 | 3 | 1.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0.075 | 0.086957 | 0.16667 | 0.14286 | 0.065217 | 0 | 0
LEAD | PRJ | Agile | 2025 | 2025-02-20 | 2025-05-10 |  |  | HR | One Org HR - desktop version | EssilorLuxottica | L. Roberto | M. TOCI | Operations | Back End | 185 | 0 | PROPOSAL | 0 | 2025 | 10 | [5 empty] | 2 | 2 | 2 | 2 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0.16667 | 0.095238 | 0.086957 | 0 | 0
LEAD | PRJ | Agile | 2025 | 2025-02-20 | 2025-05-10 |  |  | HR | One Org HR - desktop version | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analyst | 185 | 0 | PROPOSAL | 0 | 2025 | 10 |  |  |  | 2 |  | 4 | 2 | 2 | 2 |  |  |  | 0 | 0 | 0 | 0.090909 | 0 | 0.2 | 0.086957 | 0.16667 | 0.095238 | 0 | 0 | 0
LEAD | PRJ | Agile | 2025 | 2025-02-20 | 2025-05-10 |  |  | HR | One Org HR - desktop version | EssilorLuxottica | L. Roberto | S. Beltrami | Operations | Front End | 185 | 0 | PROPOSAL | 0 | 2025 | 26 | [5 empty] | 6 | 12 | 1 | 1 | 6 |  |  | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.52174 | 0.083333 | 0.047619 | 0.26087 | 0 | 0
LEAD | PRJ | Agile | 2025 | 2025-02-20 | 2025-05-10 |  |  | HR | One Org HR - desktop version | EssilorLuxottica | L. Roberto | TBD |  | UX/UI | 185 | 0 | PROPOSAL | 0 | 2025 | 15 |  |  |  | 15 | 5 |  | 5 | 5 |  |  |  |  | 0 | 0 | 0 | 0.68182 | 0.25 | 0 | 0.21739 | 0.41667 | 0 | 0 | 0 | 0
LEAD | PRJ | Agile | 2025 | 2025-03-01 | 2025-05-10 |  |  | HR | One Org HR - G+ | EssilorLuxottica | L. Roberto | C. Di Lorenzo | Delivery Projects | Analyst | 0 | 0 | PROPOSAL | 0 | 2025 | 6 |  |  | 5 |  |  | 3 | 3 | [5 empty] | 0 | 0 | 0.2381 | 0 | 0 | 0.15 | 0.13043 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ | Agile | 2025 | 2025-03-01 | 2025-05-10 |  |  | HR | One Org HR - G+ | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PM - Project Governance | 0 | 0 | PROPOSAL | 0 | 2025 | 4 |  |  | 2 |  |  | 2 | 2 | [5 empty] | 0 | 0 | 0.095238 | 0 | 0 | 0.1 | 0.086957 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ | Agile | 2025 | 2025-03-01 | 2025-05-10 |  |  | HR | One Org HR - G+ | EssilorLuxottica | L. Roberto | M. Porcu | Operations | Technical Leader | 0 | 0 | PROPOSAL | 0 | 2025 | 6 |  |  | 3 |  |  | 3 | 3 | [5 empty] | 0 | 0 | 0.14286 | 0 | 0 | 0.15 | 0.13043 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ | Agile | 2025 | 2025-03-01 | 2025-05-10 |  |  | HR | One Org HR - G+ | EssilorLuxottica | L. Roberto | M. TOCI | Operations | Back End | 0 | 0 | PROPOSAL | 0 | 2025 | 6 |  |  | 5 |  |  | 1 | 5 | [5 empty] | 0 | 0 | 0.2381 | 0 | 0 | 0.05 | 0.21739 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ | Agile | 2025 | 2025-03-01 | 2025-05-10 |  |  | HR | One Org HR - sort di tutte le linee | EssilorLuxottica | L. Roberto | C. Di Lorenzo | Delivery Projects | Analyst | 75 | 0 | PROPOSAL | 0 | 2025 | 7 |  | 2 |  |  |  | 3 | 2 | 2 |  |  |  |  | 0 | 0.1 | 0 | 0 | 0 | 0.15 | 0.086957 | 0.16667 | 0 | 0 | 0 | 0
LEAD | PRJ | Agile | 2025 | 2025-03-01 | 2025-05-10 |  |  | HR | One Org HR - sort di tutte le linee | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PM - Project Governance | 75 | 0 | PROPOSAL | 0 | 2025 | 4 |  | 1 |  |  |  | 1 | 1 | 2 |  |  |  |  | 0 | 0.05 | 0 | 0 | 0 | 0.05 | 0.043478 | 0.16667 | 0 | 0 | 0 | 0
LEAD | PRJ | Agile | 2025 | 2025-03-01 | 2025-05-10 |  |  | HR | One Org HR - sort di tutte le linee | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 75 | 0 | PROPOSAL | 0 | 2025 | 4 |  | 1 |  |  |  | 1 | 1 | 2 |  |  |  |  | 0 | 0.05 | 0 | 0 | 0 | 0.05 | 0.043478 | 0.16667 | 0 | 0 | 0 | 0
LEAD | PRJ | Agile | 2025 | 2025-03-01 | 2025-05-10 |  |  | HR | One Org HR - sort di tutte le linee | EssilorLuxottica | L. Roberto | M. Porcu | Operations | Back End | 75 | 0 | PROPOSAL | 0 | 2025 | 6 | [5 empty] | 2 | 2 | 2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0.16667 | 0 | 0 | 0 | 0
LEAD | PRJ | Agile | 2025 | 2025-03-01 | 2025-05-10 |  |  | HR | One Org HR - sort di tutte le linee | EssilorLuxottica | L. Roberto | M. TOCI | Operations | Back End | 75 | 0 | PROPOSAL | 0 | 2025 | 20 | [5 empty] | 12 | 5 | 3 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.6 | 0.21739 | 0.25 | 0 | 0 | 0 | 0
LEAD | PRJ | Agile | 2025 | 2025-03-01 | 2025-05-10 |  |  | HR | One Org HR - sort di tutte le linee | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analyst | 75 | 0 | PROPOSAL | 0 | 2025 | 4 |  | 1 |  |  |  | 2 | 1 | 1 |  |  |  |  | 0 | 0.05 | 0 | 0 | 0 | 0.1 | 0.043478 | 0.083333 | 0 | 0 | 0 | 0
LEAD | PRJ | Agile | 2025 | 2025-03-01 | 2025-05-10 |  |  | HR | One Org HR - sort di tutte le linee | EssilorLuxottica | L. Roberto | S. Beltrami | Operations | Front End | 75 | 0 | PROPOSAL | 0 | 2025 | 11 | [5 empty] | 8 | 1 | 2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.043478 | 0.16667 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-10-01 | 2024-12-31 | ABS25085 | ABS25085 | HR | Qlik - Project Dismissione - DE&I phase 1 | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analysis | 80 | 36 | CLOSED | 1 | 2025 | 0 | 4 | 1 | [10 empty] | 0.22222 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-10-01 | 2024-12-31 | ABS25085 | ABS25085 | HR | Qlik - Project Dismissione - DE&I phase 1 | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | Project Governance | 80 | 36 | CLOSED | 1 | 2025 | 0 | 2 | 1 | [10 empty] | 0.11111 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-10-01 | 2024-12-31 | ABS25085 | ABS25085 | HR | Qlik - Project Dismissione - DE&I phase 1 | EssilorLuxottica | L. Roberto | R. Bondi | Operations | FrontEnd | 80 | 36 | CLOSED | 1 | 2025 | 0 | 3 | 1 | [10 empty] | 0.16667 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ | Agile | 2025 | 2025-01-07 | 2025-02-28 |  |  | HR | Qlik - Project Dismissione - DE&I phase 2 | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analyst | 0 | 0 | PROPOSAL | 0 | 2025 | 12 | 2 | [6 empty] | 5 | 5 | 2 |  |  | 0.11111 | 0 | 0 | 0 | 0 | 0.25 | 0.21739 | 0.16667 |  | 0 |  | 0
LEAD | PRJ | Agile | 2025 | 2025-01-07 | 2025-02-28 |  |  | HR | Qlik - Project Dismissione - DE&I phase 2 | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PM - Project Governance | 0 | 0 | PROPOSAL | 0 | 2025 | 5 | [6 empty] | 2 | 2 | 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0.083333 | 0 | 0 |  | 0
LEAD | PRJ | Agile | 2025 | 2025-01-07 | 2025-02-28 |  |  | HR | Qlik - Project Dismissione - DE&I phase 2 | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 0 | 0 | PROPOSAL | 0 | 2025 | 8 | [6 empty] | 5 | 2 | 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.086957 | 0.083333 | 0 | 0 |  | 0
LEAD | PRJ | Agile | 2025 | 2025-01-07 | 2025-02-28 |  |  | HR | Qlik - Project Dismissione - DE&I phase 2 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 0 | 0 | PROPOSAL | 0 | 2025 | 4 | 1 | [5 empty] | 2 | 2 |  |  |  |  | 0.055556 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0 | 0 | 0 |  | 0
LEAD | PRJ | Agile | 2025 | 2025-01-07 | 2025-02-28 |  |  | HR | Qlik - Project Dismissione - DE&I phase 2 | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Front End | 0 | 0 | PROPOSAL | 0 | 2025 | 9 | [7 empty] | 6 | 1 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.043478 | 0.16667 |  | 0 |  | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - Training - support | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analysis | 570 | 567 | CLOSED | 1 | 2025 | 0 |  | 4 | [10 empty] | 0 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - Training - support | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | Project Governance - PMO | 570 | 567 | CLOSED | 1 | 2025 | 0 |  | 2 | [10 empty] | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - Training - support | EssilorLuxottica | L. Roberto | L. Roberto | Operations | Project Governance | 570 | 567 | CLOSED | 1 | 2025 | 0 |  | 2 | [10 empty] | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - Training - support | EssilorLuxottica | L. Roberto | R. Bondi | Operations | FrontEnd | 570 | 567 | CLOSED | 1 | 2025 | 0 |  | 4 | [10 empty] | 0 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
LEAD | PRJ | Agile | 2025 | 2025-03-07 | 2025-06-28 |  |  | HR | Qlik - Project Dismissione - WKF Country phase 2 | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analyst | 0 | 0 | PROPOSAL | 0 | 2025 | 21 | [7 empty] | 6 | 5 | 5 | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.26087 | 0.41667 | 0.2381 | 0.21739 |  | 0
LEAD | PRJ | Agile | 2025 | 2025-03-07 | 2025-06-28 |  |  | HR | Qlik - Project Dismissione - WKF Country phase 2 | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PM - Project Governance | 0 | 0 | PROPOSAL | 0 | 2025 | 12 | [7 empty] | 3 | 3 | 3 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0.25 | 0.14286 | 0.13043 |  | 0
LEAD | PRJ | Agile | 2025 | 2025-03-07 | 2025-06-28 |  |  | HR | Qlik - Project Dismissione - WKF Country phase 2 | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Engineering | 0 | 0 | PROPOSAL | 0 | 2025 | 19 | [7 empty] | 4 | 5 | 5 | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.17391 | 0.41667 | 0.2381 | 0.21739 |  | 0
LEAD | PRJ | Agile | 2025 | 2025-03-07 | 2025-06-28 |  |  | HR | Qlik - Project Dismissione - WKF Country phase 2 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 0 | 0 | PROPOSAL | 0 | 2025 | 6 | [7 empty] | 1 | 2 | 2 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.16667 | 0.095238 | 0.043478 |  | 0
LEAD | PRJ | Agile | 2025 | 2025-03-07 | 2025-06-28 |  |  | HR | Qlik - Project Dismissione - WKF Country phase 2 | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Front End | 0 | 0 | PROPOSAL | 0 | 2025 | 32 | [7 empty] | 8 | 8 | 8 | 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.34783 | 0.66667 | 0.38095 | 0.34783 |  | 0
LEAD | PRJ | Agile | 2025 | 2025-02-07 | 2025-03-28 |  |  | HR | Qlik - Project Dismissione - WKF Global phase 2 | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analyst | 0 | 0 | PROPOSAL | 0 | 2025 | 11 | [7 empty] | 6 | 5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.21739 |  | 0 | 0 |  | 0
LEAD | PRJ | Agile | 2025 | 2025-02-07 | 2025-03-28 |  |  | HR | Qlik - Project Dismissione - WKF Global phase 2 | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PM - Project Governance | 0 | 0 | PROPOSAL | 0 | 2025 | 6 | [7 empty] | 3 | 3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0.25 | 0 | 0 |  | 0
LEAD | PRJ | Agile | 2025 | 2025-02-07 | 2025-03-28 |  |  | HR | Qlik - Project Dismissione - WKF Global phase 2 | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Engineering | 0 | 0 | PROPOSAL | 0 | 2025 | 8 | [6 empty] | 3 | 3 | 2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.13043 | 0.16667 | 0 | 0 |  | 0
LEAD | PRJ | Agile | 2025 | 2025-02-07 | 2025-03-28 |  |  | HR | Qlik - Project Dismissione - WKF Global phase 2 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 0 | 0 | PROPOSAL | 0 | 2025 | 2 | [6 empty] | 1 | 1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.043478 | 0 | 0 | 0 |  | 0
LEAD | PRJ | Agile | 2025 | 2025-02-07 | 2025-03-28 |  |  | HR | Qlik - Project Dismissione - WKF Global phase 2 | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Front End | 0 | 0 | PROPOSAL | 0 | 2025 | 14 | [7 empty] | 8 | 6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.4 | 0.26087 |  | 0 | 0 |  | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Analysis | 570 | 567 | CLOSED | 1 | 2025 | 0 | 5 | 2 | [10 empty] | 0.27778 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye | EssilorLuxottica | L. Roberto | R. Bondi | Operations | FrontEnd | 570 | 567 | CLOSED | 1 | 2025 | 0 | 8 | 4 | [10 empty] | 0.44444 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - WKFEye & Eye - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 570 | 567 | CLOSED | 1 | 2025 | 0 | 4 | 2 | [10 empty] | 0.22222 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | C. Di Lorenzo | Delivery Projects | Analysis | 570 | 567 | CLOSED | 1 | 2025 | 0 | 2 | [11 empty] | 0.11111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | M. Porcu | Operations | Tech Lead | 570 | 567 | CLOSED | 1 | 2025 | 0 | 1 | [11 empty] | 0.055556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | M. Toci | Operations | BackEnd | 570 | 567 | CLOSED | 1 | 2025 | 0 | 4 | [11 empty] | 0.22222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 570 | 567 | CLOSED | 1 | 2025 | 0 | 2 | [11 empty] | 0.11111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-06-01 | 2024-12-31 | ABS24299 | ABS24299 | HR | Qlik - Project Dismissione - One Org, Data Enrichment | EssilorLuxottica | L. Roberto | S. Beltrami | Operations | FrontEnd | 570 | 567 | CLOSED | 1 | 2025 | 0 | 4 | [11 empty] | 0.22222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 |  | ABS0008-140 | HR | Regole automatizzate - file hr controlling | EssilorLuxottica | L. Roberto | A. Nastasi | Operations | Data Management | 18 | 0 | ON GOING | 0 | 2025 | 2 |  |  |  | 4 | 2 | [7 empty] | 0 | 0 | 0 | 0.18182 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 |  | ABS0008-140 | HR | Regole automatizzate - file hr controlling | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 18 | 0 | ON GOING | 0 | 2025 | 0 |  | 2 | 5 | 2 | [8 empty] | 0 | 0.1 | 0.2381 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 |  | ABS0008-140 | HR | Regole automatizzate - file hr controlling | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 18 | 0 | ON GOING | 0 | 2025 | 2 |  | 1 | 1 | 1 | 1 | 1 | [6 empty] | 0 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 |  | ABS0008-140 | HR | Regole automatizzate - file hr controlling | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Front End | 18 | 0 | ON GOING | 0 | 2025 | 0 |  |  | 1 | 1 | [8 empty] | 0 | 0 | 0.047619 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 |  | ABS0008-140 | HR | Regole automatizzate - file hr controlling | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analyst | 18 | 0 | ON GOING | 0 | 2025 | 4 |  | 2 | 1 | 1 | 1 | 2 | 1 | [5 empty] | 0 | 0.1 | 0.047619 | 0.045455 | 0.05 | 0.1 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-31 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 - AMS | EssilorLuxottica | L. Roberto | C. Di Lorenzo | Delivery Projects | Analyst | 65 | 0 | ON GOING | 0 | 2025 | 17 |  |  |  |  | 3 | 3 | 2 | 3 | 3 | 3 |  |  | 0 | 0 | 0 | 0 | 0.15 | 0.15 | 0.086957 | 0.25 | 0.14286 | 0.13043 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-31 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 - AMS | EssilorLuxottica | L. Roberto | C. Elia | Operations | Back End | 65 | 0 | ON GOING | 0 | 2025 | 17 |  |  |  |  | 3 | 3 | 3 | 2 | 3 | 3 |  |  | 0 | 0 | 0 | 0 | 0.15 | 0.15 | 0.13043 | 0.16667 | 0.14286 | 0.13043 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-31 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 - AMS | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 65 | 0 | ON GOING | 0 | 2025 | 12 |  |  |  |  | 3 | 3 | 3 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0.15 | 0.15 | 0.13043 | 0.083333 | 0.047619 | 0.043478 | 0 | 0
CONTRACT | PRJ |  | 2024 | 2024-07-01 | 2024-12-31 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 - AMS | EssilorLuxottica | L. Roberto | M. Simeone | Operations | Back End | 65 | 0 | ON GOING | 0 | 2025 | 12 |  |  |  |  | 3 | 3 | 3 | 2 | 1 |  |  |  | 0 | 0 | 0 | 0 | 0.15 | 0.15 | 0.13043 | 0.16667 | 0.047619 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-11-02 | 2025-01-31 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 w4 | EssilorLuxottica | L. Roberto | C. Di Lorenzo | Delivery Projects | Analysis | 58 | 66 | Closed | 1 | 2025 | 0 |  | 9 | 3 | 3 | [8 empty] | 0 | 0.45 | 0.14286 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-11-02 | 2025-01-31 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 w4 | EssilorLuxottica | L. Roberto | C. Elia | Operations | BackEnd | 58 | 66 | Closed | 1 | 2025 | 8 |  | 1 | 9 | 9 | 8 | [7 empty] | 0 | 0.05 | 0.42857 | 0.40909 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-11-02 | 2025-01-31 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 w4 | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 58 | 66 | Closed | 1 | 2025 | 0 |  | 3 | 3 | 3 | [8 empty] | 0 | 0.15 | 0.14286 | 0.13636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-11-02 | 2025-01-31 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 w4 | EssilorLuxottica | L. Roberto | S. Beltrami | Operations | FrontEnd | 58 | 66 | Closed | 1 | 2025 | 0 |  |  | 2 | 4 | [8 empty] | 0 | 0 | 0.095238 | 0.18182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-11-02 | 2025-12-31 | ABS24539 | ABS24539 | CRM/CS | Trenord | Trenord | L. Roberto | L. Roberto | Operations | PM - Project Governance | 186 | 21 | ON GOING | 0 | 2025 | 48 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0.33333 | 0.3 | 0.28571 | 0.27273 | 0.3 | 0.3 | 0.26087 | 0.5 | 0.28571 | 0.26087 | 0.28571 | 0.27273
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | A. Carmisciano | Not Available | Solution Architect | 2020 | 532 | PROPOSAL | 0 | 2025 | 47 | 5 | 1 | 1 | 12.5 | 5 | 5 | 12.5 | 5 | 5 | 12.5 | 1 | 1 | 0.27778 | 0.05 | 0.047619 | 0.56818 | 0.25 | 0.25 | 0.54348 | 0.41667 | 0.2381 | 0.54348 | 0.047619 | 0.045455
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | A. Mattucci | Not Available | Senior Consultant | 2020 | 532 | PROPOSAL | 0 | 2025 | 14.5 |  |  | 5 | 12.5 | 1 | 1 | 12.5 | [5 empty] | 0 | 0 | 0.2381 | 0.56818 | 0.05 | 0.05 | 0.54348 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | A. Torri | Not Available | Senior Consultant | 2020 | 532 | PROPOSAL | 0 | 2025 | 106 |  |  | 1.5 | 17.5 | 1 | 14 | 17.5 | 14 | 14 | 17.5 | 14 | 14 | 0 | 0 | 0.071429 | 0.79545 | 0.05 | 0.7 | 0.76087 | 1.1667 | 0.66667 | 0.76087 | 0.66667 | 0.63636
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | D. Reich | Not Available | Senior Consultant | 2020 | 532 | PROPOSAL | 0 | 2025 | 30 |  |  | 3 | 5 | 0 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 0 | 0 | 0.14286 | 0.22727 | 0 | 0.2 | 0.21739 | 0.33333 | 0.19048 | 0.21739 | 0.19048 | 0.18182
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | D. Scala | Not Available | Senior Consultant | 2020 | 532 | PROPOSAL | 0 | 2025 | 30 |  |  |  | 3 | 0 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 0 | 0 | 0 | 0.13636 | 0 | 0.2 | 0.21739 | 0.33333 | 0.19048 | 0.21739 | 0.19048 | 0.18182
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | F. Scognamiglio | Operations | Senior Consultant | 2020 | 532 | PROPOSAL | 0 | 2025 | 60 |  |  | 15 | 25 | 0 | 2 | 25 | 2 | 2 | 25 | 2 | 2 | 0 | 0 | 0.71429 | 1.1364 | 0 | 0.1 | 1.087 | 0.16667 | 0.095238 | 1.087 | 0.095238 | 0.090909
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | G. Izzo | Not Available | Senior Developer | 2020 | 532 | PROPOSAL | 0 | 2025 | 15 |  |  |  | 2 | 0 | 2 | 2.5 | 2 | 2 | 2.5 | 2 | 2 | 0 | 0 | 0 | 0.090909 | 0 | 0.1 | 0.1087 | 0.16667 | 0.095238 | 0.1087 | 0.095238 | 0.090909
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | G. Mandrioli | Not Available | Analyst | 2020 | 532 | PROPOSAL | 0 | 2025 | 34.5 |  | 1 | 1 | 12.5 | 1 | 1 | 12.5 | 10 | 10 |  |  |  | 0 | 0.05 | 0.047619 | 0.56818 | 0.05 | 0.05 | 0.54348 | 0.83333 | 0.47619 | 0 | 0 | 0
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | G. Tuninetti | Not Available | Consultant | 2020 | 532 | PROPOSAL | 0 | 2025 | 20 | 6 | 12 | 12 | 15 | 5 | 12 | 3 | [5 empty] | 0.33333 | 0.6 | 0.57143 | 0.68182 | 0.25 | 0.6 | 0.13043 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | I. Lopez | Not Available | Consultant | 2020 | 532 | PROPOSAL | 0 | 2025 | 10 |  | 8 | 8 | 1 | 0 | 8 | 2 | [5 empty] | 0 | 0.4 | 0.38095 | 0.045455 | 0 | 0.4 | 0.086957 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | L. Carloni | Operations | Senior Consultant | 2020 | 532 | PROPOSAL | 0 | 2025 | 60 |  |  | 15 | 25 | 0 | 2 | 25 | 2 | 2 | 25 | 2 | 2 | 0 | 0 | 0.71429 | 1.1364 | 0 | 0.1 | 1.087 | 0.16667 | 0.095238 | 1.087 | 0.095238 | 0.090909
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | M. Calabrese | Delivery Projects | Analyst | 2020 | 532 | PROPOSAL | 0 | 2025 | 40 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0.27778 | 0.25 | 0.2381 | 0.22727 | 0.25 | 0.25 | 0.21739 | 0.41667 | 0.2381 | 0.21739 | 0.2381 | 0.22727
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | P. Anzellotti | Operations | Solution Architect | 2020 | 532 | PROPOSAL | 0 | 2025 | 57 |  |  | 6 | 1 | 1 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0.28571 | 0.045455 | 0.05 | 0.4 | 0.34783 | 0.66667 | 0.38095 | 0.34783 | 0.38095 | 0.36364
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | P. Cimino | Not Available | Consultant | 2020 | 532 | PROPOSAL | 0 | 2025 | 60 |  |  |  | 2 | 0 | 2 | 25 | 2 | 2 | 25 | 2 | 2 | 0 | 0 | 0 | 0.090909 | 0 | 0.1 | 1.087 | 0.16667 | 0.095238 | 1.087 | 0.095238 | 0.090909
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | S. Ben Younes | Operations | Consultant | 2020 | 532 | PROPOSAL | 0 | 2025 | 90 |  |  | 9 | 15 | 0 | 12 | 15 | 12 | 12 | 15 | 12 | 12 | 0 | 0 | 0.42857 | 0.68182 | 0 | 0.6 | 0.65217 | 1 | 0.57143 | 0.65217 | 0.57143 | 0.54545
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | V. Carcaterra | Not Available | Developer | 2020 | 532 | PROPOSAL | 0 | 2025 | 60 |  |  | 15 | 25 | 0 | 2 | 25 | 2 | 2 | 25 | 2 | 2 | 0 | 0 | 0.71429 | 1.1364 | 0 | 0.1 | 1.087 | 0.16667 | 0.095238 | 1.087 | 0.095238 | 0.090909
LEAD | PRJ | AGILE | 2025 | 2025-01-26 | 2025-12-31 | ABS25024 | ABS25024 | real estate | ABS25024.LUXOTTICA GEOSTRATEGY | EssilorLuxottica | M. Calabrese | Y. Cherednychenko | Not Available | Developer | 2020 | 532 | PROPOSAL | 0 | 2025 | 15 |  |  |  | 2 | 0 | 2 | 2.5 | 2 | 2 | 2.5 | 2 | 2 | 0 | 0 | 0 | 0.090909 | 0 | 0.1 | 0.1087 | 0.16667 | 0.095238 | 0.1087 | 0.095238 | 0.090909
LEAD | PRJ | WATERFALL | 2025 | 2025-02-01 | 2025-06-30 |  |  | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - AI 2025 | AO FERRARA | M. Calabrese | F. Spacagna | Operations | Solution Architect | 150 | 0 | PROPOSAL | 0 | 2025 | 25 | [7 empty] | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41667 | 0.2381 | 0.21739 | 0.2381 | 0.22727
LEAD | PRJ | WATERFALL | 2025 | 2025-02-01 | 2025-06-30 |  |  | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - AI 2025 | AO FERRARA | M. Calabrese | G. Sironi | Operations | Data Scientist | 150 | 0 | PROPOSAL | 0 | 2025 | 25 | [7 empty] | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41667 | 0.2381 | 0.21739 | 0.2381 | 0.22727
LEAD | PRJ | WATERFALL | 2025 | 2025-02-01 | 2025-06-30 |  |  | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - AI 2025 | AO FERRARA | M. Calabrese | M. Calabrese | Delivery Projects | PM - Project Governance | 150 | 0 | PROPOSAL | 0 | 2025 | 25 | [7 empty] | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41667 | 0.2381 | 0.21739 | 0.2381 | 0.22727
LEAD | PRJ | WATERFALL | 2025 | 2025-02-01 | 2025-06-30 |  |  | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - AI 2025 | AO FERRARA | M. Calabrese | M. Gomitoni | Operations | Data Scientist | 150 | 0 | PROPOSAL | 0 | 2025 | 25 | [7 empty] | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41667 | 0.2381 | 0.21739 | 0.2381 | 0.22727
LEAD | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 |  |  | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - PLANNING 2025 | AO FERRARA | M. Calabrese | M. Calabrese | Delivery Projects | PM - Project Governance | 100 | 0 | PROPOSAL | 0 | 2025 | 15 | [6 empty] | 3 | 3 | 3 | 3 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0.25 | 0.14286 | 0.13043 | 0.14286 | 0
LEAD | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 |  |  | healthcare | AOFE - AZIENDA OSPEDALIERA FERRARA - PLANNING 2025 | AO FERRARA | M. Calabrese | R. Tortora | Operations | Technical Leader | 100 | 0 | PROPOSAL | 0 | 2025 | 25 | [6 empty] | 5 | 5 | 5 | 5 | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.41667 | 0.2381 | 0.21739 | 0.2381 | 0
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS25040 | ABS24401 | healthcare | AOFE DI FERRARA - OFFERTA AMS SAC ANNO 2025 | AO FERRARA | M. Calabrese | A. Elia | UI | Front End | 300 | 0 | TO START | 0 | 2025 | 15 |  |  |  |  | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.086957 | 0.083333 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS25040 | ABS24401 | healthcare | AOFE DI FERRARA - OFFERTA AMS SAC ANNO 2025 | AO FERRARA | M. Calabrese | L. Lazzari | SAP ECC | Account Manager | 300 | 0 | TO START | 0 | 2025 | 80 |  |  |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.43478 | 0.83333 | 0.47619 | 0.43478 | 0.47619 | 0.45455
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS25040 | ABS24401 | healthcare | AOFE DI FERRARA - OFFERTA AMS SAC ANNO 2025 | AO FERRARA | M. Calabrese | M. Calabrese | Delivery Projects | PM - Project Governance | 300 | 0 | TO START | 0 | 2025 | 40 |  |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0.21739 | 0.41667 | 0.2381 | 0.21739 | 0.2381 | 0.22727
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS25040 | ABS24401 | healthcare | AOFE DI FERRARA - OFFERTA AMS SAC ANNO 2025 | AO FERRARA | M. Calabrese | R. Tortora | Operations | Front End | 300 | 0 | TO START | 0 | 2025 | 80 |  |  |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.43478 | 0.83333 | 0.47619 | 0.43478 | 0.47619 | 0.45455
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS25039 | ABS24401 | healthcare | AUSL DI FERRARA - OFFERTA AMS SAC ANNO 2025 | AO FERRARA | M. Calabrese | A. Elia | UI | Front End | 300 | 0 | TO START | 0 | 2025 | 15 |  |  |  |  | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.086957 | 0.083333 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS25039 | ABS24401 | healthcare | AUSL DI FERRARA - OFFERTA AMS SAC ANNO 2025 | AO FERRARA | M. Calabrese | L. Lazzari | SAP ECC | Account Manager | 300 | 0 | TO START | 0 | 2025 | 80 |  |  |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.43478 | 0.83333 | 0.47619 | 0.43478 | 0.47619 | 0.45455
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS25039 | ABS24401 | healthcare | AUSL DI FERRARA - OFFERTA AMS SAC ANNO 2025 | AO FERRARA | M. Calabrese | M. Calabrese | Delivery Projects | PM - Project Governance | 300 | 0 | TO START | 0 | 2025 | 40 |  |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0.21739 | 0.41667 | 0.2381 | 0.21739 | 0.2381 | 0.22727
CONTRACT | PRJ | WATERFALL | 2025 | 2025-01-01 | 2025-12-31 | ABS25039 | ABS24401 | healthcare | AUSL DI FERRARA - OFFERTA AMS SAC ANNO 2025 | AO FERRARA | M. Calabrese | R. Tortora | Operations | Front End | 300 | 0 | TO START | 0 | 2025 | 80 |  |  |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.43478 | 0.83333 | 0.47619 | 0.43478 | 0.47619 | 0.45455
CONTRACT | PRJ |  | 2024-2025 | 2024-11-01 | 2024-06-30 | ABS24604 |  | EPM | KPMG - Ferrero - Supporto + CR | FERRERO | M. COCCHI | A. Di Pietro | Operations | Back End | 110 | 40 | ON GOING | 0 | 2025 | 2 | 19 | 15 | 1 | 1 | 1 | 1 | [6 empty] | 1.0556 | 0.75 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-11-01 | 2024-06-30 | ABS24604 |  | EPM | KPMG - Ferrero - Supporto + CR | FERRERO | M. COCCHI | F. Atanasio | Operations | Back End | 110 | 40 | ON GOING | 0 | 2025 | 0 | 4 | [11 empty] | 0.22222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-11-01 | 2024-06-30 | ABS24604 |  | EPM | KPMG - Ferrero - Supporto + CR | FERRERO | M. COCCHI | L. Mangili | Operations | Back End | 110 | 40 | ON GOING | 0 | 2025 | 2 | 2 | 5 | 2 | 5 | 1 | 1 | [6 empty] | 0.11111 | 0.25 | 0.095238 | 0.22727 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-11-01 | 2024-06-30 | ABS24604 |  | EPM | KPMG - Ferrero - Supporto + CR | FERRERO | M. COCCHI | M. Favalli | Operations | Back End | 110 | 40 | ON GOING | 0 | 2025 | 0 | 3 | [11 empty] | 0.16667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-03-01 | 2024-09-30 | ABS24207 | AKFWS | EPM | KPMG - Ferrero - Weekly Sales | FERRERO | M. COCCHI | L. Mangili | Operations | Back End | 305 | 300 | ON GOING | 0 | 2025 | 0 | 7 | [11 empty] | 0.38889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ |  | 2025 | 2025-05-01 | 2025-12-31 |  |  | EPM | KPMG - Vision Group - AMS | Vision Group | M. COCCHI | F. Atanasio | Operations | Back End | 60 | 0 | PROPOSAL | 0 | 2025 | 30 |  |  |  |  | 4 | 4 | 4 | 1 | 5 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.17391 | 0.083333 | 0.2381 | 0.17391 | 0.19048 | 0.18182
LEAD | PRJ |  | 2025 | 2025-05-01 | 2025-12-31 |  |  | EPM | KPMG - Vision Group - AMS | Vision Group | M. COCCHI | L. Franco | Operations | Back End | 60 | 0 | PROPOSAL | 0 | 2025 | 30 |  |  |  |  | 4 | 4 | 4 | 1 | 5 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.17391 | 0.083333 | 0.2381 | 0.17391 | 0.19048 | 0.18182
LEAD | PRJ |  | 2025 | 2025-01-01 | 2025-01-31 |  |  | EPM | KPMG - Vision Group - Consolidato Managerial / Store P&L - 2025 | Vision Group | M. COCCHI | A. Albanese | Delivery Projects | PM - Project Governance | 30 | 0 | PROPOSAL | 0 | 2025 | 0 | 0.5 | 0.5 | 0.5 | [9 empty] | 0.027778 | 0.025 | 0.02381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ |  | 2025 | 2025-01-01 | 2025-01-31 |  |  | EPM | KPMG - Vision Group - Consolidato Managerial / Store P&L - 2025 | Vision Group | M. COCCHI | F. Atanasio | Operations | Back End | 30 | 0 | PROPOSAL | 0 | 2025 | 0 | 2 | 6 | 5 | [9 empty] | 0.11111 | 0.3 | 0.2381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ |  | 2025 | 2025-01-01 | 2025-01-31 |  |  | EPM | KPMG - Vision Group - Consolidato Managerial / Store P&L - 2025 | Vision Group | M. COCCHI | L. Franco | Operations | Technical Leader | 30 | 0 | PROPOSAL | 0 | 2025 | 0 | 2 | 6 | 5 | [9 empty] | 0.11111 | 0.3 | 0.2381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ |  | 2025 | 2025-01-01 | 2025-01-31 |  |  | EPM | KPMG - Vision Group - Consolidato Managerial / Store P&L - 2025 | Vision Group | M. COCCHI | M. Favalli | Operations | Back End | 30 | 0 | PROPOSAL | 0 | 2025 | 0 | 1 | [11 empty] | 0.055556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ |  | 2025 | 2025-01-01 | 2025-01-31 |  |  | EPM | KPMG - Vision Group - Consolidato Managerial / Store P&L - 2025 | Vision Group | M. COCCHI | S. Preziosa | Delivery Projects | Analyst | 30 | 0 | PROPOSAL | 0 | 2025 | 0 | 1 | [11 empty] | 0.055556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ |  | 2025 | 2025-04-01 | 2025-09-30 |  |  | EPM | KPMG - Vision Group Pianificazione PBCS | Vision Group | M. COCCHI | A. Albanese | Delivery Projects | PM - Project Governance | 300 | 0 | PROPOSAL | 0 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ |  | 2025 | 2025-04-01 | 2025-09-30 |  |  | EPM | KPMG - Vision Group Pianificazione PBCS | Vision Group | M. COCCHI | F. Atanasio | Operations | Back End - Junior | 300 | 0 | PROPOSAL | 0 | 2025 | 80 |  |  |  | 1 | 15 | 15 | 15 | 5 | 15 | 15 |  |  | 0 | 0 | 0 | 0.045455 | 0.75 | 0.75 | 0.65217 | 0.41667 | 0.71429 | 0.65217 | 0 | 0
PROSPECT | PRJ |  | 2025 | 2025-04-01 | 2025-09-30 |  |  | EPM | KPMG - Vision Group Pianificazione PBCS | Vision Group | M. COCCHI | L. Franco | Operations | Solution Architect | 300 | 0 | PROPOSAL | 0 | 2025 | 42 |  |  |  | 7 | 7 | 6 | 8 | 6 | 7 | 8 |  |  | 0 | 0 | 0 | 0.31818 | 0.35 | 0.3 | 0.34783 | 0.5 | 0.33333 | 0.34783 | 0 | 0
PROSPECT | PRJ |  | 2025 | 2025-04-01 | 2025-09-30 |  |  | EPM | KPMG - Vision Group Pianificazione PBCS | Vision Group | M. COCCHI | L. Mangili | Operations | Back End | 300 | 0 | PROPOSAL | 0 | 2025 | 10 |  |  |  | 1 | 1 | 1 | 1 | 5 | 1 | 1 |  |  | 0 | 0 | 0 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.41667 | 0.047619 | 0.043478 | 0 | 0
PROSPECT | PRJ |  | 2025 | 2025-04-01 | 2025-09-30 |  |  | EPM | KPMG - Vision Group Pianificazione PBCS | Vision Group | M. COCCHI | S. Preziosa | Delivery Projects | Analyst | 300 | 0 | PROPOSAL | 0 | 2025 | 6 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-10-15 | 2024-05-30 | ABS24025 | ABS24025 | EPM | Webuild - Migrazione HFM | WeBuild | M. COCCHI | A. Albanese | Delivery Projects | PM - Project Governance | 115 | 15 | ON GOING | 0 | 2025 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | [8 empty] | 0.027778 | 0.025 | 0.02381 | 0.022727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-10-15 | 2024-05-30 | ABS24025 | ABS24025 | EPM | Webuild - Migrazione HFM | WeBuild | M. COCCHI | Esterno Oracle |  | PM - Project Governance | 115 | 15 | ON GOING | 0 | 2025 | 0 |  |  |  | 1 | [8 empty] | 0 | 0 | 0 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-10-15 | 2024-05-30 | ABS24025 | ABS24025 | EPM | Webuild - Migrazione HFM | WeBuild | M. COCCHI | F. De Pedis | Operations | Back End | 115 | 15 | ON GOING | 0 | 2025 | 1 | 18 | 15 | 15 | 2 | 1 | [7 empty] | 1 | 0.75 | 0.71429 | 0.090909 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2024-2025 | 2024-10-15 | 2024-05-30 | ABS24025 | ABS24025 | EPM | Webuild - Migrazione HFM | WeBuild | M. COCCHI | I. Bressan | Operations | Technical Leader | 115 | 15 | ON GOING | 0 | 2025 | 1 | 13 | 13 | 13 | 2 | 1 | [7 empty] | 0.72222 | 0.65 | 0.61905 | 0.090909 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 |  | ABS0008-2 | LOGISTIC | Supporto Area Logistica | Abstract | M. Pallotti | C. Paz | Delivery Projects | PMO - Project Management Officer | 0 | 0 | ON GOING | 0 | 2025 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25033 | ABS25033-18 | HR | AMS - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | A. Ferrari | Operations | Data Engineering | 112 | 0 | TO START | 0 | 2025 | 1 | 0.5 | 0.5 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.027778 | 0.025 | 0.047619 | 0.045455 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25033 | ABS25033-18 | HR | AMS - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | C. Di Lorenzo | Delivery Projects | Analyst | 112 | 0 | TO START | 0 | 2025 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.027778 | 0.025 | 0.02381 | 0.022727 | 0.025 | 0.025 | 0.021739 | 0.041667 | 0.02381 | 0.021739 | 0.02381 | 0.022727
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25033 | ABS25033-18 | HR | AMS - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | L. Carloni | Operations | Data Engineering | 112 | 0 | TO START | 0 | 2025 | 7 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 0.5 | 0.027778 | 0.025 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.041667 | 0.047619 | 0.043478 | 0.047619 | 0.022727
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25033 | ABS25033-18 | HR | AMS - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | M. Mannarino | Operations | Data Engineering | 112 | 0 | TO START | 0 | 2025 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25033 | ABS25033-18 | HR | AMS - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | M. Porcu | Operations | Technical Leader | 112 | 0 | TO START | 0 | 2025 | 14 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0.083333 | 0.095238 | 0.086957 | 0.095238 | 0.045455
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25033 | ABS25033-18 | HR | AMS - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | M. Toci | Operations | Back End | 112 | 0 | TO START | 0 | 2025 | 12.5 | 2 | 2 | 1.5 | 1.5 | 2 | 1.5 | 2 | 1 | 1 | 2 | 2 | 1 | 0.11111 | 0.1 | 0.071429 | 0.068182 | 0.1 | 0.075 | 0.086957 | 0.083333 | 0.047619 | 0.086957 | 0.095238 | 0.045455
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25033 | ABS25033-18 | HR | AMS - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | N. GUERRERO | Delivery AMS | PM - Project Governance | 112 | 0 | TO START | 0 | 2025 | 10.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 1.5 | 1.5 | 1 | 0.083333 | 0.075 | 0.071429 | 0.068182 | 0.075 | 0.075 | 0.065217 | 0.041667 | 0.071429 | 0.065217 | 0.071429 | 0.045455
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25033 | ABS25033-18 | HR | AMS - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | R. Marasca | Delivery Projects | Analyst | 112 | 0 | TO START | 0 | 2025 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.027778 | 0.025 | 0.02381 | 0.022727 | 0.025 | 0.025 | 0.021739 | 0.041667 | 0.02381 | 0.021739 | 0.02381 | 0.022727
LEAD | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25033 | ABS25033-18 | HR | AMS - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | S. Beltrami | Operations | Front End | 112 | 0 | TO START | 0 | 2025 | 11 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 2 | 1.5 | 0.5 | 1 | 1.5 | 1.5 | 1.5 | 0.055556 | 0.075 | 0.071429 | 0.068182 | 0.075 | 0.1 | 0.065217 | 0.041667 | 0.047619 | 0.065217 | 0.071429 | 0.068182
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | A. Ferrari | Operations | Data Engineering | 200 | 0 | TO START | 0 | 2025 | 1.5 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.068182 | 0.075 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | A. Nastasi | Operations | Data Management | 200 | 0 | TO START | 0 | 2025 | 8 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.055556 | 0.1 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | C. Di Lorenzo | Delivery Projects | Analyst | 200 | 0 | TO START | 0 | 2025 | 18.5 | 2 | 2 | 3 | 2.5 | 3 | 2.5 | 3 | 1 | 2.5 | 3 | 2.5 | 1 | 0.11111 | 0.1 | 0.14286 | 0.11364 | 0.15 | 0.125 | 0.13043 | 0.083333 | 0.11905 | 0.13043 | 0.11905 | 0.045455
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | L. Cariglia | Operations | Technical Leader | 200 | 0 | TO START | 0 | 2025 | 8 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.11111 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | L. Carloni | Operations | Data Engineering | 200 | 0 | TO START | 0 | 2025 | 14 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0.083333 | 0.095238 | 0.086957 | 0.095238 | 0.045455
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | M. Mannarino | Operations | Data Engineering | 200 | 0 | ON GOING | 0 | 2025 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.055556 | 0.05 | 0.047619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | M. Porcu | Operations | Technical Leader | 200 | 0 | TO START | 0 | 2025 | 14 | 2 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 0.11111 | 0.15 | 0.14286 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0.083333 | 0.095238 | 0.086957 | 0.095238 | 0.045455
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | M. Toci | Operations | Back End | 200 | 0 | TO START | 0 | 2025 | 22.5 | 3 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 0.5 | 3.5 | 3.5 | 3.5 | 1 | 0.16667 | 0.175 | 0.16667 | 0.15909 | 0.175 | 0.175 | 0.15217 | 0.041667 | 0.16667 | 0.15217 | 0.16667 | 0.045455
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | N. GUERRERO | Delivery AMS | PM - Project Governance | 200 | 0 | TO START | 0 | 2025 | 9.5 | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 1.5 | 1.5 | 1 | 0.5 | 0.055556 | 0.075 | 0.071429 | 0.068182 | 0.075 | 0.075 | 0.065217 | 0.041667 | 0.071429 | 0.065217 | 0.047619 | 0.022727
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | R. Marasca | Delivery Projects | Analyst | 200 | 0 | TO START | 0 | 2025 | 7 | 1 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 0.5 | 0.055556 | 0.025 | 0.02381 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.041667 | 0.047619 | 0.043478 | 0.047619 | 0.022727
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | T. Wu | Not Available | Analyst | 200 | 0 | TO START | 0 | 2025 | 0 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.055556 | 0.025 | 0.02381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 |  | ABS25033-9 | HR | CR - HR - Web App - 2025 | EssilorLuxottica | N. GUERRERO | S. Beltrami | Operations | Front End | 200 | 0 | TO START | 0 | 2025 | 18.5 | 1 | 3 | 3 | 3 | 3 | 2.5 | 3 | 0.5 | 3 | 3 | 2.5 | 1 | 0.055556 | 0.15 | 0.14286 | 0.13636 | 0.15 | 0.125 | 0.13043 | 0.041667 | 0.14286 | 0.13043 | 0.11905 | 0.045455
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | A. De Sanctis | Operations | Data Management | 0 | 0 | TO START | 0 | 2025 | 24 | 18 | 2 | 21 | 22 | 22 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.1 | 1 | 1 | 1.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | A. Nastasi | Operations | Data Management | 0 | 0 | TO START | 0 | 2025 | 17 | 12 | 13 | 9 | 9 | 9 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66667 | 0.65 | 0.42857 | 0.40909 | 0.45 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | D. De Pecol |  | Data Management | 0 | 0 | ON GOING | 0 | 2025 | 0 | 0 | 0 | 9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42857 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | G. Cataldo | Operations | Data Management | 0 | 0 | TO START | 0 | 2025 | 4 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.055556 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | G. Galati | Delivery AMS | Data Management | 0 | 0 | TO START | 0 | 2025 | 14 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38889 | 0.35 | 0.33333 | 0.31818 | 0.35 | 0.35 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | G. Mordà | Operations | Data Management | 0 | 0 | ON GOING | 0 | 2025 | 28 | 13 | 14 | 15 | 14 | 15 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72222 | 0.7 | 0.71429 | 0.63636 | 0.75 | 0.65 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | I. Bressan | Operations | Back End | 0 | 0 | TO START | 0 | 2025 | 0.5 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0.013889 | 0.0125 | 0.011905 | 0.011364 | 0.0125 | 0.0125 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | L. Cariglia | Operations | Data Management | 0 | 0 | TO START | 0 | 2025 | 12 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33333 | 0.3 | 0.28571 | 0.27273 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | M. Migliorati | Operations | Front End | 0 | 0 | TO START | 0 | 2025 | 34 | 19 | 2 | 0 | 0 | 18 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0556 | 0.1 | 0 | 0 | 0.9 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | M. Vimercati | Operations | Data Management | 0 | 0 | TO START | 0 | 2025 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | N. GUERRERO | Delivery AMS | PM - Project Governance | 0 | 0 | TO START | 0 | 2025 | 36 | 18 | 19 | 20 | 19 | 19 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.95 | 0.95238 | 0.86364 | 0.95 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | R. Bondi | Operations | Data Management | 0 | 0 | ON GOING | 0 | 2025 | 4 | 0 | 0 | 9 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42857 | 0.045455 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | R. Marasca | Delivery Projects | Data Integrator | 0 | 0 | TO START | 0 | 2025 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | T. Wu | Not Available | Analyst | 0 | 0 | TO START | 0 | 2025 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.095238 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | L. Colombo | Not Available | Analyst | 0 | 0 | TO START | 0 | 2025 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.2381 | 0.22727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25XXX | ABS25XXX | HR | HR Reporting AMS H1 2025 | EssilorLuxottica | N. GUERRERO | K. Dadaian | Delivery Projects | Analyst | 0 | 0 | TO START | 0 | 2025 | 38 | 0 | 0 | 0 | 0 | 18 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | A. De Sanctis | Operations | Data Management | 0 | 0 | TO START | 0 | 2025 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 8 | 21 | 23 | 21 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95652 | 0.66667 | 1 | 1 | 1 | 0.77273
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | A. Nastasi | Operations | Data Management | 0 | 0 | TO START | 0 | 2025 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 2 | 12 | 12 | 11 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52174 | 0.16667 | 0.57143 | 0.52174 | 0.52381 | 0.13636
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | D. De Pecol |  | Data Management | 0 | 0 | TO START | 0 | 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | G. Cataldo | Operations | Data Management | 0 | 0 | TO START | 0 | 2025 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.083333 | 0.095238 | 0.086957 | 0.095238 | 0.045455
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | G. Galati | Delivery AMS | Data Management | 0 | 0 | TO START | 0 | 2025 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 2 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30435 | 0.16667 | 0.33333 | 0.30435 | 0.33333 | 0.31818
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | G. Mordà | Operations | Data Management | 0 | 0 | TO START | 0 | 2025 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 3 | 16 | 17 | 14 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73913 | 0.25 | 0.7619 | 0.73913 | 0.66667 | 0.5
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | I. Bressan | Operations | Back End | 0 | 0 | TO START | 0 | 2025 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0.01087 | 0.020833 | 0.011905 | 0.01087 | 0.011905 | 0.011364
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | L. Cariglia | Operations | Data Management | 0 | 0 | TO START | 0 | 2025 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 | 6 | 6 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26087 | 0.16667 | 0.28571 | 0.26087 | 0.28571 | 0.22727
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | M. Migliorati | Operations | Front End | 0 | 0 | TO START | 0 | 2025 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 1 | 17 | 19 | 17 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82609 | 0.083333 | 0.80952 | 0.82609 | 0.80952 | 0.81818
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | M. Vimercati | Operations | Data Management | 0 | 0 | TO START | 0 | 2025 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | N. GUERRERO | Delivery AMS | PM - Project Governance | 0 | 0 | TO START | 0 | 2025 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 7 | 20 | 21 | 19 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86957 | 0.58333 | 0.95238 | 0.91304 | 0.90476 | 0.72727
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | R. Bondi | Operations | Data Management | 0 | 0 | TO START | 0 | 2025 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.083333 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | R. Marasca | Delivery Projects | Data Integrator | 0 | 0 | TO START | 0 | 2025 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 1.5 | 1.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.083333 | 0.095238 | 0.065217 | 0.071429 | 0.045455
CONTRACT | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | HR | HR Reporting AMS H2 2025 | EssilorLuxottica | N. GUERRERO | K. Dadaian | Delivery Projects | Analyst | 0 | 0 | TO START | 0 | 2025 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 10 | 22 | 22 | 21 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.83333 | 1.0476 | 0.95652 | 1 | 0.81818
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-01 | 2025-12-31 |  | IAA | OTHER | CC - supporto CC Leader come Deputy |  | O. Sagazio | P. Anzellotti | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2025 | 17 | 3 | 3 | 3 |  |  | 3 | 3 | 1 | 3 | 3 | 3 | 1 | 0.16667 | 0.15 | 0.14286 | 0 | 0 | 0.15 | 0.13043 | 0.083333 | 0.14286 | 0.13043 | 0.14286 | 0.045455
CONTRACT | AMS | Agile | 2025 | 2025-03-01 | 2025-04-11 |  |  | HR | A3198544L - BSD Integrazione gestione Buoni Nuance | EssilorLuxottica | P. Anzellotti | A. Lorena | Operations | Front End | 28 | 0 | To Start | 1 | 2025 | 0 |  |  | 5 | 1 | [8 empty] | 0 | 0 | 0.2381 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Agile | 2025 | 2025-03-01 | 2025-04-11 |  | ABS0008-169 | HR | A3198544L - BSD Integrazione gestione Buoni Nuance | EssilorLuxottica | P. Anzellotti | G. De Feo | Operations | PMO - Project Management Officer | 28 | 0 | CLOSED | 1 | 2025 | 0 |  |  | 2 | 1 | [8 empty] | 0 | 0 | 0.095238 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Agile | 2025 | 2025-03-01 | 2025-04-11 |  |  | HR | A3198544L - BSD Integrazione gestione Buoni Nuance | EssilorLuxottica | P. Anzellotti | G. TARTAGLIA | Operations | Back End | 28 | 0 | To Start | 1 | 2025 | 0 |  |  | 5 | 1 | [8 empty] | 0 | 0 | 0.2381 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-03-01 | 2025-04-11 |  |  | HR | A3198544L - BSD Integrazione gestione Buoni Nuance | EssilorLuxottica | P. Anzellotti | P. Anzellotti | Operations | Technical Leader | 28 | 0 | To Start | 1 | 2025 | 0 |  |  | 3 | 1 | [8 empty] | 0 | 0 | 0.14286 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Agile | 2025 | 2025-03-01 | 2025-04-11 |  |  | HR | A3198544L - BSD Integrazione gestione Buoni Nuance | EssilorLuxottica | P. Anzellotti | S. Delle Fave | Operations | Front End | 28 | 0 | To Start | 1 | 2025 | 2 |  |  |  | 1 | 2 | [7 empty] | 0 | 0 | 0 | 0.045455 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | AMS | Agile | 2025 | 2025-03-01 | 2025-04-11 |  |  | HR | BSD - Blocco utilizzo stesso N. Ordine + Codice LSA su stesso Buono Sconto | EssilorLuxottica | P. Anzellotti | A. Lorena | Operations | Front End | 10 | 0 | To Start | 1 | 2025 | 2 |  |  |  | 1 | 2 | [7 empty] | 0 | 0 | 0 | 0.045455 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | AMS | Agile | 2025 | 2025-03-01 | 2025-04-11 |  |  | HR | BSD - Blocco utilizzo stesso N. Ordine + Codice LSA su stesso Buono Sconto | EssilorLuxottica | P. Anzellotti | G. De Feo | Operations | PMO - Project Management Officer | 10 | 0 | To Start | 1 | 2025 | 1 | [5 empty] | 1 | 1 | [5 empty] | 0 | 0 | 0 | 0.045455 | 0.05 |  |  | 0 | 0 | 0 | 0 | 0
PROSPECT | AMS | Agile | 2025 | 2025-03-01 | 2025-04-11 |  |  | HR | BSD - Blocco utilizzo stesso N. Ordine + Codice LSA su stesso Buono Sconto | EssilorLuxottica | P. Anzellotti | G. TARTAGLIA | Operations | Back End | 10 | 0 | To Start | 1 | 2025 | 2 |  |  |  | 1 | 2 | [7 empty] | 0 | 0 | 0 | 0.045455 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | AMS | Agile | 2025 | 2025-03-01 | 2025-04-11 |  |  | HR | BSD - Blocco utilizzo stesso N. Ordine + Codice LSA su stesso Buono Sconto | EssilorLuxottica | P. Anzellotti | P. Anzellotti | Operations | Technical Leader | 10 | 0 | To Start | 1 | 2025 | 2 |  |  |  | 1 | 2 | [7 empty] | 0 | 0 | 0 | 0.045455 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-01-07 | 2025-02-15 |  |  | HR | Buoni Sconto Digitali - LSA CR | EssilorLuxottica | P. Anzellotti | A. Lorena | Operations | Front End | 20 | 0 | To Start | 1 | 2025 | 0 | 3 | 3 | 4 | [9 empty] | 0.16667 | 0.15 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-01-07 | 2025-02-15 |  | ABS0008-59 | HR | Buoni Sconto Digitali - LSA CR | EssilorLuxottica | P. Anzellotti | G. De Feo | Operations | PM - Project Governance | 20 | 0 | CLOSED | 1 | 2025 | 0 | 1 | 1 | [10 empty] | 0.055556 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-01-07 | 2025-02-15 |  |  | HR | Buoni Sconto Digitali - LSA CR | EssilorLuxottica | P. Anzellotti | G. TARTAGLIA | Operations | Back End | 20 | 0 | To Start | 1 | 2025 | 0 | 6 | 4 | 4 | [9 empty] | 0.33333 | 0.2 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-01-07 | 2025-02-15 |  |  | HR | Buoni Sconto Digitali - LSA CR | EssilorLuxottica | P. Anzellotti | P. Anzellotti | Operations | Technical Leader | 20 | 0 | To Start | 1 | 2025 | 0 | 3 | 3 | 3 | [9 empty] | 0.16667 | 0.15 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2025 | 2025-01-01 | 2025-12-31 |  | ATD | OTHER | Carrier Manager Activities | Abstract | P. Pieroni | A. Di Pietro | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2025 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.027778 | 0.025 | 0.02381 | 0.022727 | 0.025 | 0.025 | 0.021739 | 0.041667 | 0.02381 | 0.021739 | 0.02381 | 0.022727
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2025 | 2025-01-01 | 2025-12-31 |  | ATD | OTHER | Carrier Manager Activities | Abstract | P. Pieroni | I. Bressan | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2025 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.027778 | 0.025 | 0.02381 | 0.022727 | 0.025 | 0.025 | 0.021739 | 0.041667 | 0.02381 | 0.021739 | 0.02381 | 0.022727
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2025 | 2025-01-01 | 2025-12-31 |  | ATD | OTHER | Carrier Manager Activities | Abstract | P. Pieroni | L. Franco | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2025 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.027778 | 0.025 | 0.02381 | 0.022727 | 0.025 | 0.025 | 0.021739 | 0.041667 | 0.02381 | 0.021739 | 0.02381 | 0.022727
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2025 | 2025-01-01 | 2025-12-31 |  | ATD | OTHER | Carrier Manager Activities | Abstract | P. Pieroni | N. Fragale | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2025 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.027778 | 0.025 | 0.02381 | 0.022727 | 0.025 | 0.025 | 0.021739 | 0.041667 | 0.02381 | 0.021739 | 0.02381 | 0.022727
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2025 | 2025-01-01 | 2025-12-31 |  | ATD | EPM | Carrier Manager Activities | Abstract | P. Pieroni | P. Pieroni | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2025 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CDC/AREA MANAGEMENT | CDC GOVERNANCE |  | 2025 | 2025-01-01 | 2025-12-31 |  | ABS0007 | PRACTICE DI | CDC/AREA MANAGEMENT | Abstract | P. Pieroni | P. Pieroni | Operations | PM - Project Governance | 55 | 0 | ON GOING | 1 | 2025 | 35 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  | 5 | 5 | 5 | 5 | 0.27778 | 0.25 | 0.2381 | 0.22727 | 0.25 | 0.25 | 0.21739 | 0 | 0.2381 | 0.21739 | 0.2381 | 0.22727
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25018 | ABS25018 | RETAIL | BULLSEYE AMS 2025 | EssilorLuxottica | T. Porzio | A. Nastasi | Operations | Data Management - SQL | 200 | 64 | ON GOING | 0 | 2025 | 27 | 0.5 | 0.5 | 1 | 4 | 4 | 4 | 4 | 1 | 4 | 4 | 4 | 2 | 0.027778 | 0.025 | 0.047619 | 0.18182 | 0.2 | 0.2 | 0.17391 | 0.083333 | 0.19048 | 0.17391 | 0.19048 | 0.090909
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25018 | ABS25018 | RETAIL | BULLSEYE AMS 2025 | EssilorLuxottica | T. Porzio | A. PIROLA | Operations | Front End | 200 | 64 | ON GOING | 0 | 2025 | 8 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.027778 | 0.025 | 0.02381 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25018 | ABS25018 | RETAIL | BULLSEYE AMS 2025 | EssilorLuxottica | T. Porzio | A. Vladi | Operations | Data Management | 200 | 64 | ON GOING | 0 | 2025 | 27 | 3 | 4 | 5 | 5 | 4 | 4 | 4 | 1 | 4 | 4 | 4 | 2 | 0.16667 | 0.2 | 0.2381 | 0.22727 | 0.2 | 0.2 | 0.17391 | 0.083333 | 0.19048 | 0.17391 | 0.19048 | 0.090909
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25018 | ABS25018 | RETAIL | BULLSEYE AMS 2025 | EssilorLuxottica | T. Porzio | F. D'Alberto | Operations | Data Management - SQL | 200 | 64 | ON GOING | 0 | 2025 | 13 | 3 | 4 | 4 | 0 | 0 | 1 | 1 | 3 | 1 | 1 | 1 | 5 | 0.16667 | 0.2 | 0.19048 | 0 | 0 | 0.05 | 0.043478 | 0.25 | 0.047619 | 0.043478 | 0.047619 | 0.22727
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25018 | ABS25018 | RETAIL | BULLSEYE AMS 2025 | EssilorLuxottica | T. Porzio | F. Spacagna | Operations | Back End | 200 | 64 | ON GOING | 0 | 2025 | 7 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 0.5 | 0.027778 | 0.025 | 0.02381 | 0.022727 | 0.05 | 0.05 | 0.043478 | 0.041667 | 0.047619 | 0.043478 | 0.047619 | 0.022727
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25018 | ABS25018 | RETAIL | BULLSEYE AMS 2025 | EssilorLuxottica | T. Porzio | M. Vianelli | Delivery Projects | Analyst | 200 | 64 | ON GOING | 0 | 2025 | 17 | 1 | 2 | 2 | 2 | 4 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 0.055556 | 0.1 | 0.095238 | 0.090909 | 0.2 | 0.1 | 0.086957 | 0.083333 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25018 | ABS25018 | RETAIL | BULLSEYE AMS 2025 | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 200 | 64 | ON GOING | 0 | 2025 | 15 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 2 | 2 | 0.16667 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0.086957 | 0.083333 | 0.095238 | 0.086957 | 0.095238 | 0.090909
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25019 | ABS25019 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 1H | EssilorLuxottica | T. Porzio | A. Ferrari | Operations | Back End | 100 | 0 | ON GOING | 0 | 2025 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25019 | ABS25019 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 1H | EssilorLuxottica | T. Porzio | A. Lorena | Operations | Front End | 100 | 0 | ON GOING | 0 | 2025 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | [6 empty] | 0.055556 | 0.05 | 0.047619 | 0.090909 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25019 | ABS25019 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 1H | EssilorLuxottica | T. Porzio | A. PIROLA | Operations | Front End | 100 | 0 | ON GOING | 0 | 2025 | 4 | 1 | 1 | 1 | 2 | 2 | 2 | [6 empty] | 0.055556 | 0.05 | 0.047619 | 0.090909 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25019 | ABS25019 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 1H | EssilorLuxottica | T. Porzio | A. Vladi | Operations | Team Leadership | 100 | 0 | ON GOING | 0 | 2025 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25019 | ABS25019 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 1H | EssilorLuxottica | T. Porzio | F. D'Alberto | Operations | Back End | 100 | 0 | ON GOING | 0 | 2025 | 10 | 5 | 7 | 5 |  | 5 | 5 | [6 empty] | 0.27778 | 0.35 | 0.2381 | 0 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25019 | ABS25019 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 1H | EssilorLuxottica | T. Porzio | F. Spacagna | Operations | Back End | 100 | 0 | ON GOING | 0 | 2025 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25019 | ABS25019 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 1H | EssilorLuxottica | T. Porzio | M. Vianelli | Delivery Projects | Analyst | 100 | 0 | ON GOING | 0 | 2025 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 0.11111 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25019 | ABS25019 | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 1H | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 100 | 0 | ON GOING | 0 | 2025 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | [6 empty] | 0.055556 | 0.05 | 0.047619 | 0.090909 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 2H | EssilorLuxottica | T. Porzio | A. Ferrari | Operations | Back End | 100 | 0 | TO START | 0 | 2025 | 13 | [9 empty] | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21739 | 0.2381 | 0.13636
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 2H | EssilorLuxottica | T. Porzio | A. Lorena | Operations | Front End | 100 | 0 | TO START | 0 | 2025 | 9 | [9 empty] | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0.14286 | 0.13636
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 2H | EssilorLuxottica | T. Porzio | A. PIROLA | Operations | Front End | 100 | 0 | TO START | 0 | 2025 | 1.5 | [9 empty] | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.021739 | 0.02381 | 0.022727
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 2H | EssilorLuxottica | T. Porzio | A. Vladi | Operations | Team Leadership | 100 | 0 | TO START | 0 | 2025 | 6 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 2H | EssilorLuxottica | T. Porzio | F. D'Alberto | Operations | Back End | 100 | 0 | TO START | 0 | 2025 | 41 | [6 empty] | 8 | 4 | 8 | 8 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.34783 | 0.33333 | 0.38095 | 0.34783 | 0.38095 | 0.22727
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 2H | EssilorLuxottica | T. Porzio | F. Spacagna | Operations | Back End | 100 | 0 | TO START | 0 | 2025 | 12 | [6 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.16667 | 0.095238 | 0.086957 | 0.095238 | 0.090909
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 2H | EssilorLuxottica | T. Porzio | M. Vianelli | Delivery Projects | Analyst | 100 | 0 | TO START | 0 | 2025 | 12 | [6 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.16667 | 0.095238 | 0.086957 | 0.095238 | 0.090909
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | RETAIL | BULLSEYE ENHANCEMENTS PLUS 5 2025 2H | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 100 | 0 | TO START | 0 | 2025 | 14 | [6 empty] | 2 | 2 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0.16667 | 0.14286 | 0.13043 | 0.095238 | 0.090909
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2025 | EssilorLuxottica | T. Porzio | E. Storti | Delivery Projects | Back End | 100 | 0 | TO START | 0 | 2025 | 10 | [6 empty] | 2 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2025 | EssilorLuxottica | T. Porzio | N. Fragale | Operations | Back End | 100 | 0 | TO START | 0 | 2025 | 15 | [6 empty] | 3 |  | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0 | 0.14286 | 0.13043 | 0.14286 | 0.13636
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2025 | EssilorLuxottica | T. Porzio | O. BEN OTHMANE | Operations | Back End - Junior | 100 | 0 | TO START | 0 | 2025 | 14 | [6 empty] | 2 |  | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0 | 0.14286 | 0.13043 | 0.14286 | 0.13636
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2025 | EssilorLuxottica | T. Porzio | P. Pieroni | Operations | Back End | 100 | 0 | TO START | 0 | 2025 | 12 | [6 empty] | 2 |  | 2 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0 | 0.095238 | 0.13043 | 0.14286 | 0.090909
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2025 | EssilorLuxottica | T. Porzio | S. Preziosa | Delivery Projects | Analyst | 100 | 0 | TO START | 0 | 2025 | 18 | [6 empty] | 2 |  | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0 | 0.19048 | 0.17391 | 0.19048 | 0.18182
A CONSUMO | AMS | Waterfall | 2025 | 2025-07-01 | 2025-12-31 |  |  | EPM | CR - LUX-DI-EPM-AMS EssilorLuxottica EPM PLN Q3Q4.2025 | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 100 | 0 | TO START | 0 | 2025 | 11 | [6 empty] | 3 |  | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.13043 | 0 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-01 | 2025-12-31 |  |  |  | Gara Leonardo | Regione Veneto | T. Porzio | A. Cuomo | Operations | Data Management | 2000 | 0 | TO START | 0 | 2025 | 120 | [7 empty] | 24 | 24 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1.1429 | 1.0435 | 1.1429 | 1.0909
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-01 | 2025-12-31 |  |  |  | Gara Leonardo | Regione Veneto | T. Porzio | A. Strada | Operations | Data Management | 2000 | 0 | TO START | 0 | 2025 | 120 | [7 empty] | 24 | 24 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1.1429 | 1.0435 | 1.1429 | 1.0909
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-01 | 2025-12-31 |  |  |  | Gara Leonardo | Regione Veneto | T. Porzio | C. Elia | Operations | Solution Architect | 2000 | 0 | TO START | 0 | 2025 | 10 | [7 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16667 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-01 | 2025-12-31 |  |  |  | Gara Leonardo | Regione Veneto | T. Porzio | F. SPACAGNA | Operations | Data Engineering | 2000 | 0 | TO START | 0 | 2025 | 90 | [7 empty] | 18 | 18 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0.85714 | 0.78261 | 0.85714 | 0.81818
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-01 | 2025-12-31 |  |  |  | Gara Leonardo | Regione Veneto | T. Porzio | M. Aristide | Operations | PM - Project Governance | 2000 | 0 | TO START | 0 | 2025 | 25 | [7 empty] | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41667 | 0.2381 | 0.21739 | 0.2381 | 0.22727
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-01 | 2025-12-31 |  |  |  | Gara Leonardo | Regione Veneto | T. Porzio | M. Gomitoni | Operations | Data Scientist | 2000 | 0 | TO START | 0 | 2025 | 40 | [7 empty] | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66667 | 0.38095 | 0.34783 | 0.38095 | 0.36364
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-01 | 2025-12-31 |  |  |  | Gara Leonardo | Regione Veneto | T. Porzio | M. Porcu | Operations | Solution Architect | 2000 | 0 | TO START | 0 | 2025 | 10 | [7 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16667 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-01 | 2025-12-31 |  |  |  | Gara Leonardo | Regione Veneto | T. Porzio | M. TOCI | Operations | Back End | 2000 | 0 | TO START | 0 | 2025 | 65 | [7 empty] | 13 | 13 | 13 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0833 | 0.61905 | 0.56522 | 0.61905 | 0.59091
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-01 | 2025-12-31 |  |  |  | Gara Leonardo | Regione Veneto | T. Porzio | P. Anzellotti | Operations | Solution Architect | 2000 | 0 | TO START | 0 | 2025 | 80 | [7 empty] | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3333 | 0.7619 | 0.69565 | 0.7619 | 0.72727
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-01 | 2025-12-31 |  |  |  | Gara Leonardo | Regione Veneto | T. Porzio | S. DELLE FAVE | Operations | Front End | 2000 | 0 | TO START | 0 | 2025 | 65 | [7 empty] | 13 | 13 | 13 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0833 | 0.61905 | 0.56522 | 0.61905 | 0.59091
CONTRACT | PRJ | Waterfall | 2025 | 2025-03-01 | 2025-12-31 |  |  |  | Gara Leonardo | Regione Veneto | T. Porzio | T. Porzio | Operations | PM - Project Governance | 2000 | 0 | TO START | 0 | 2025 | 35 | [7 empty] | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58333 | 0.33333 | 0.30435 | 0.33333 | 0.31818
A CONSUMO | PRJ | Waterfall | 2024-2025 | 2025-01-01 | 2025-02-28 |  |  | EPM | Lux - Job Type - Wave2 | EssilorLuxottica | T. Porzio | A. Albanese | Delivery Projects | Back End | 24 | 0 | ON HOLD | 0 | 2025 | 0 | 1 | [11 empty] | 0.055556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | PRJ | Waterfall | 2024-2025 | 2025-01-01 | 2025-02-28 |  |  | EPM | Lux - Job Type - Wave2 | EssilorLuxottica | T. Porzio | L. Mangili | Operations | Back End | 24 | 0 | ON HOLD | 0 | 2025 | 0 | 2 | [11 empty] | 0.11111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | PRJ | Waterfall | 2024-2025 | 2025-01-01 | 2025-02-28 |  |  | EPM | Lux - Job Type - Wave2 | EssilorLuxottica | T. Porzio | P. Pieroni | Operations | Back End | 24 | 0 | ON HOLD | 0 | 2025 | 0 | 2 | [11 empty] | 0.11111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | PRJ | Waterfall | 2024-2025 | 2025-01-01 | 2025-02-28 |  |  | EPM | Lux - Job Type - Wave2 | EssilorLuxottica | T. Porzio | T. Baldi | Operations | Back End | 24 | 0 | ON HOLD | 0 | 2025 | 0 | 1 | [11 empty] | 0.055556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25063 | ABS25063 | EPM | LUX–DI-EPM–enhancements plus 10 Planning 2025_dismissioneWHSP | EssilorLuxottica | T. Porzio | G. Minervini | Operations | Analyst | 24 | 0 | TO START | 0 | 2025 | 0 |  |  | 5 | 5 | [8 empty] | 0 | 0 | 0.2381 | 0.22727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25063 | ABS25063 | EPM | LUX–DI-EPM–enhancements plus 10 Planning 2025_dismissioneWHSP | EssilorLuxottica | T. Porzio | N. Fragale | Operations | Back End | 24 | 0 | TO START | 0 | 2025 | 0 |  |  | 5 | 5 | [8 empty] | 0 | 0 | 0.2381 | 0.22727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25063 | ABS25063 | EPM | LUX–DI-EPM–enhancements plus 10 Planning 2025_dismissioneWHSP | EssilorLuxottica | T. Porzio | P. Pieroni | Operations | Analyst | 24 | 0 | TO START | 0 | 2025 | 0 |  |  | 1 | 1 | [8 empty] | 0 | 0 | 0.047619 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25063 | ABS25063 | EPM | LUX–DI-EPM–enhancements plus 10 Planning 2025_dismissioneWHSP | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 24 | 0 | TO START | 0 | 2025 | 0 |  |  | 1 | 1 | [8 empty] | 0 | 0 | 0.047619 | 0.045455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25013 | ABS25013 | EPM | Luxottica - DI - AMS EPM PLN 2025 | EssilorLuxottica | T. Porzio | A. Di Pietro | Operations | Back End | 1161 | 430 | ON GOING | 0 | 2025 | 0 | 2 | 2 | [10 empty] | 0.11111 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25013 | ABS25013 | EPM | Luxottica - DI - AMS EPM PLN 2025 | EssilorLuxottica | T. Porzio | G. Minervini | Operations | Back End - Junior | 1161 | 430 | ON GOING | 0 | 2025 | 164 | 18 | 2 | 21 | 19 | 22 | 20 | 23 | 12 | 21 | 23 | 21 | 22 | 1 | 0.1 | 1 | 0.86364 | 1.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25013 | ABS25013 | EPM | Luxottica - DI - AMS EPM PLN 2025 | EssilorLuxottica | T. Porzio | M. Favalli | Operations | Back End - Junior | 1161 | 430 | ON GOING | 0 | 2025 | 153 |  |  | 13 | 13 | 13 | 20 | 23 | 12 | 21 | 23 | 21 | 20 | 0 | 0 | 0.61905 | 0.59091 | 0.65 | 1 | 1 | 1 | 1 | 1 | 1 | 0.90909
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25013 | ABS25013 | EPM | Luxottica - DI - AMS EPM PLN 2025 | EssilorLuxottica | T. Porzio | N. Fragale | Operations | Back End | 1161 | 430 | ON GOING | 0 | 2025 | 147 | 18 | 18 | 2 | 22 | 22 | 16 | 20 | 12 | 21 | 23 | 18 | 15 | 1 | 0.9 | 0.095238 | 1 | 1.1 | 0.8 | 0.86957 | 1 | 1 | 1 | 0.85714 | 0.68182
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25013 | ABS25013 | EPM | Luxottica - DI - AMS EPM PLN 2025 | EssilorLuxottica | T. Porzio | O. BEN OTHMANE | Operations | Back End - Junior | 1161 | 430 | ON GOING | 0 | 2025 | 155 | 17 | 17 | 18 | 17 | 18 | 20 | 23 | 12 | 21 | 23 | 21 | 17 | 0.94444 | 0.85 | 0.85714 | 0.77273 | 0.9 | 1 | 1 | 1 | 1 | 1 | 1 | 0.77273
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25013 | ABS25013 | EPM | Luxottica - DI - AMS EPM PLN 2025 | EssilorLuxottica | T. Porzio | P. Pieroni | Operations | Back End | 1161 | 430 | ON GOING | 0 | 2025 | 22 | 5 | 8 | 8 | 8 | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0.27778 | 0.4 | 0.38095 | 0.36364 | 0.4 | 0.1 | 0.086957 | 0.16667 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25013 | ABS25013 | EPM | Luxottica - DI - AMS EPM PLN 2025 | EssilorLuxottica | T. Porzio | S. Preziosa | Delivery Projects | Analyst | 1161 | 430 | ON GOING | 0 | 2025 | 13 | 1 | 13 | 13 | 9 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.055556 | 0.65 | 0.61905 | 0.40909 | 0.3 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25013 | ABS25013 | EPM | Luxottica - DI - AMS EPM PLN 2025 | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 1161 | 430 | ON GOING | 0 | 2025 | 61 | 7 | 7 | 7 | 7 | 8 | 8 | 9 | 5 | 8 | 8 | 8 | 7 | 0.38889 | 0.35 | 0.33333 | 0.31818 | 0.4 | 0.4 | 0.3913 | 0.41667 | 0.38095 | 0.34783 | 0.38095 | 0.31818
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25013 | ABS25013 | EPM | Luxottica - DI - AMS EPM PLN 2025 | EssilorLuxottica | T. Porzio | V. Raso | Operations | Back End | 1161 | 430 | ON GOING | 0 | 2025 | 0 | 18 | 18 | [10 empty] | 1 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25013 | ABS25013 | EPM | Luxottica - DI - AMS EPM PLN 2025 | EssilorLuxottica | T. Porzio | A. Di Pietro | Operations | Back End | 1161 | 430 | ON GOING | 0 | 2025 | 39 |  |  |  |  | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0.2 | 0.25 | 0.21739 | 0.41667 | 0.2381 | 0.21739 | 0.2381 | 0.22727
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25016 | ABS25016 | EPM | Luxottica - DI - Enhancements plus 10 EPM PLN Q1 Q2 2025 | EssilorLuxottica | T. Porzio | A. Albanese | Delivery Projects | Back End | 150 | 0 | ON GOING | 0 | 2025 | 0 |  | 1 | [10 empty] | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25016 | ABS25016 | EPM | Luxottica - DI - Enhancements plus 10 EPM PLN Q1 Q2 2025 | EssilorLuxottica | T. Porzio | A. Di Pietro | Operations | Back End | 150 | 0 | ON GOING | 0 | 2025 | 2 | 3 | 3 | 3 | 2 | 1 | 1 | [6 empty] | 0.16667 | 0.15 | 0.14286 | 0.090909 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25016 | ABS25016 | EPM | Luxottica - DI - Enhancements plus 10 EPM PLN Q1 Q2 2025 | EssilorLuxottica | T. Porzio | E. Storti | Delivery Projects | Back End | 150 | 0 | ON GOING | 0 | 2025 | 4 | 1 | 5 | 3 | 2 | 2 | 2 | [6 empty] | 0.055556 | 0.25 | 0.14286 | 0.090909 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25016 | ABS25016 | EPM | Luxottica - DI - Enhancements plus 10 EPM PLN Q1 Q2 2025 | EssilorLuxottica | T. Porzio | L. Franco | Operations | Back End | 150 | 0 | ON GOING | 0 | 2025 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25016 | ABS25016 | EPM | Luxottica - DI - Enhancements plus 10 EPM PLN Q1 Q2 2025 | EssilorLuxottica | T. Porzio | L. Mangili | Operations | Back End | 150 | 0 | ON GOING | 0 | 2025 | 0 |  | 4 | 4 | [9 empty] | 0 | 0.2 | 0.19048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25016 | ABS25016 | EPM | Luxottica - DI - Enhancements plus 10 EPM PLN Q1 Q2 2025 | EssilorLuxottica | T. Porzio | M. Favalli | Operations | Back End - Junior | 150 | 0 | ON GOING | 0 | 2025 | 0 |  |  | 3 | [9 empty] | 0 | 0 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25016 | ABS25016 | EPM | Luxottica - DI - Enhancements plus 10 EPM PLN Q1 Q2 2025 | EssilorLuxottica | T. Porzio | N. Fragale | Operations | Back End | 150 | 0 | ON GOING | 0 | 2025 | 0 |  | 2 | 2 | 2 | [8 empty] | 0 | 0.1 | 0.095238 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25016 | ABS25016 | EPM | Luxottica - DI - Enhancements plus 10 EPM PLN Q1 Q2 2025 | EssilorLuxottica | T. Porzio | O. BEN OTHMANE | Operations | Back End - Junior | 150 | 0 | ON GOING | 0 | 2025 | 4 | 1 | 3 | 4 | 5 | 4 | 0 | [6 empty] | 0.055556 | 0.15 | 0.19048 | 0.22727 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25016 | ABS25016 | EPM | Luxottica - DI - Enhancements plus 10 EPM PLN Q1 Q2 2025 | EssilorLuxottica | T. Porzio | P. Pieroni | Operations | Back End | 150 | 0 | ON GOING | 0 | 2025 | 5 | 2 | 6 | 2 | 3 | 3 | 2 | [6 empty] | 0.11111 | 0.3 | 0.095238 | 0.13636 | 0.15 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25016 | ABS25016 | EPM | Luxottica - DI - Enhancements plus 10 EPM PLN Q1 Q2 2025 | EssilorLuxottica | T. Porzio | S. Preziosa | Delivery Projects | Analyst | 150 | 0 | ON GOING | 0 | 2025 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | [6 empty] | 0.22222 | 0.2 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
A CONSUMO | AMS | Waterfall | 2025 | 2025-01-01 | 2025-06-30 | ABS25016 | ABS25016 | EPM | Luxottica - DI - Enhancements plus 10 EPM PLN Q1 Q2 2025 | EssilorLuxottica | T. Porzio | T. Porzio | Delivery AMS | PM - Project Governance | 150 | 0 | ON GOING | 0 | 2025 | 4 | 3 | 2 | 2 | 2 | 2 | 2 | [6 empty] | 0.16667 | 0.1 | 0.095238 | 0.090909 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL TRAINING | FORMAZIONE |  | 2025 | 2025-01-01 | 2025-12-31 |  | ATD | OTHER | Training Luxottica - DI - AMS EPM PLN 2025 | Abstract | T. Porzio | M. Favalli | Operations | Back End - Junior | 0 | 0 | ON GOING | 0 | 2025 | 0 | 1 | 15 | [10 empty] | 0.055556 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ | Waterfall | 2025 | 2025-05-04 | 2025-07-31 |  | ABS0008-99 | HR | Dashboard data quality | EssilorLuxottica | L. Roberto | R. Bondi | Delivery Projects | Front End | 0 | 0 | PROPOSAL | 0 | 2025 | 3 | [5 empty] | 1 | 1 | 1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.043478 | 0.083333 | 0 | 0 | 0 | 0
LEAD | PRESALES - DELIVERY |  | 2025 |  |  |  | ABS0008-159 |  | GEOX - Retail Community - Sales Assistant | GEOX | L. Roberto | L. Roberto | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2025 | 8 |  |  |  |  | 4 | 4 | [6 empty] | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRESALES - DELIVERY |  | 2025 |  |  |  | ABS0008-159 |  | GEOX - Retail Community - Sales Assistant | GEOX | L. Roberto | F. Spacagna | Operations | Technical Leader | 0 | 0 | ON GOING | 0 | 2025 | 5 |  |  |  |  | 5 | [7 empty] | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRESALES - DELIVERY |  | 2025 |  |  |  | ABS0008-159 |  | GEOX - Retail Community - Sales Assistant | GEOX | L. Roberto | G. Sironi | Operations | Data Scientist | 0 | 0 | ON GOING | 0 | 2025 | 5 |  |  |  |  | 5 | [7 empty] | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRESALES - DELIVERY |  | 2025 |  |  |  | ABS0008-159 |  | GEOX - Retail Community - Sales Assistant | GEOX | L. Roberto | A. Imbimbo | Operations | Data Scientist | 0 | 0 | ON GOING | 0 | 2025 | 5 |  |  |  |  | 5 | [7 empty] | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRESALES - DELIVERY |  | 2025 |  |  |  | ABS0008-159 |  | GEOX - Retail Community - Sales Assistant | GEOX | L. Roberto | M. GOMITONI | Operations | Data Scientist | 0 | 0 | ON GOING | 0 | 2025 | 5 |  |  |  |  | 5 | [7 empty] | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 |  |  | ABS0008-248 ABS0008-227 ABS0008-219 | HR | Evolutive Dashboard Maggio(post golive) | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 0 | 0 | ON GOING | 0 | 2025 | 2 |  |  |  |  | 2 | [7 empty] | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 |  |  | ABS0008-248 ABS0008-227 ABS0008-219 | HR | Evolutive Dashboard Maggio(post golive) | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Front End | 0 | 0 | ON GOING | 0 | 2025 | 4 |  |  |  |  | 2 | 1 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0.1 | 0.05 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 |  |  | ABS0008-248 ABS0008-227 ABS0008-219 | HR | Evolutive Dashboard Maggio(post golive) | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Business Analyst | 0 | 0 | ON GOING | 0 | 2025 | 3 |  |  |  |  | 3 | [7 empty] | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-05-31 |  | IAA | HR | MY PLACE | Abstract | L. Roberto | G. De Feo | Operations | PMO - Project Management Officer | 0 | 0 | ON GOING | 0 | 2025 | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.086957 | 0.16667 | 0.095238 | 0.086957 | 0.095238 | 0.090909
LEAD | PRJ | Waterfall | 2025 | 2025-05-04 | 2025-07-31 |  | ABS0008-99 | HR | Dashboard data quality | EssilorLuxottica | L. Roberto | L. Roberto | Delivery Projects | PM - Project Governance | 0 | 0 | PROPOSAL | 0 | 2025 | 2 | [6 empty] | 1 | 1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.043478 | 0.083333 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 |  | ABS0008-140 | HR | Regole automatizzate - file hr controlling | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 18 | 0 | ON GOING | 0 | 2025 | 3 |  |  |  |  | 1 | 2 | [6 empty] | 0 | 0 | 0 | 0 | 0.05 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 |  | ABS0008-154 | HR | Talent Card BO | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 0 | 0 | ON GOING | 0 | 2025 | 3 |  |  |  |  | 1 | 1 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0.05 | 0.05 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 |  | ABS0008-154 | HR | Talent Card BO | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2025 | 3 |  |  |  |  | 1 | 1 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0.05 | 0.05 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 |  | ABS0008-154 | HR | Talent Card BO | EssilorLuxottica | L. Roberto | E. Storti | Delivery Projects | Business Analyst | 0 | 0 | ON GOING | 0 | 2025 | 9 |  |  |  |  | 3 | 3 | 3 | [5 empty] | 0 | 0 | 0 | 0 | 0.15 | 0.15 | 0.13043 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 |  | ABS0008-154 | HR | Talent Card BO | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Front End | 0 | 0 | ON GOING | 0 | 2025 | 13 |  |  |  |  | 3 | 5 | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0.15 | 0.25 | 0.21739 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 |  | ABS0008-154 | HR | Talent Card BO | EssilorLuxottica | L. Roberto | M. Porcu | Operations | Tech Lead | 0 | 0 | ON GOING | 0 | 2025 | 3 |  |  |  |  | 1 | 1 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0.05 | 0.05 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Agile | 2025 | 2025-02-18 | 2025-03-27 |  | ABS0008-154 | HR | Talent Card BO | EssilorLuxottica | L. Roberto | M. Toci | Operations | Backend | 0 | 0 | ON GOING | 0 | 2025 | 4 |  |  |  |  | 2 | 1 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0.1 | 0.05 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 |  | ABS24299 | ABS0008-138 | HR | Hypercare dismissione QLIK | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 570 | 567 | On Going | 0 | 2025 | 2 |  |  | 1 | 1 | 2 | [7 empty] | 0 | 0 | 0.047619 | 0.045455 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-257 | HR | HR - Banding | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 0 | 0 | ON GOING | 0 | 2025 | [5 empty] | 1 | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-257 | HR | HR - Banding | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Front End | 0 | 0 | ON GOING | 0 | 2025 | [5 empty] | 1 | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-257 | HR | HR - Banding | EssilorLuxottica | L. Roberto | S. Beltrami | Operations | Front End | 0 | 0 | ON GOING | 0 | 2025 | [5 empty] | 1 | [7 empty] | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-257 | HR | HR - Banding | EssilorLuxottica | L. Roberto | S. Toci | Operations | Back End | 0 | 0 | ON GOING | 0 | 2025 | [5 empty] | 1 | [7 empty] | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-257 | HR | HR - Banding | EssilorLuxottica | L. Roberto | L. Carloni | Operations | Back End | 0 | 0 | ON GOING | 0 | 2025 | [5 empty] | 1 | [7 empty] | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-257 | HR | HR - Banding | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 0 | 0 | ON GOING | 0 | 2025 | [5 empty] | 1 | [7 empty] | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-262 | HR | HR - Grade US | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 0 | 0 | ON GOING | 0 | 2025 | [5 empty] | 1 | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-262 | HR | HR - Grade US | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 0 | 0 | ON GOING | 0 | 2025 | [5 empty] | 1 | 8 | [6 empty] | 0 | 0 | 0 | 0 | 0.05 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-263 | HR | HR - HR Controlling - New Segment | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 0 | 0 | ON GOING | 0 | 2025 | [5 empty] | 2 | 3 | [6 empty] | 0 | 0 | 0 | 0 | 0.1 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-263 | HR | HR - HR Controlling - New Segment | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Business Analyst | 0 | 0 | ON GOING | 0 | 2025 | 6 |  |  |  |  | 2 | 3 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0.1 | 0.15 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-263 | HR | HR - HR Controlling - New Segment | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 0 | 0 | ON GOING | 0 | 2025 | [5 empty] | 1 | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-263 | HR | HR - HR Controlling - New Segment | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Front - End | 0 | 0 | ON GOING | 0 | 2025 | [6 empty] | 2 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-263 | HR | HR - HR Controlling - New Segment | EssilorLuxottica | L. Roberto | M. Toci | Operations | Back end | 0 | 0 | ON GOING | 0 | 2025 | [6 empty] | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-263 | HR | HR - HR Controlling - New Segment | EssilorLuxottica | L. Roberto | M. Porcu | Operations | Tech Lead | 0 | 0 | ON GOING | 0 | 2025 | [6 empty] | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-257 | HR | HR - Banding | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Business Analyst | 0 | 0 | ON GOING | 0 | 2025 | 4 |  |  |  |  | 1 | 2 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0.05 | 0.1 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 |  |  | ABS0008-248 ABS0008-227 ABS0008-219 | HR | Evolutive Dashboard Maggio(post golive) | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Business Analyst | 0 | 0 | ON GOING | 0 | 2025 | 3 |  |  |  |  | 3 | [7 empty] | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-05-07 | 2025-06-28 |  | ABS0008-262 | HR | HR - Grade US | EssilorLuxottica | L. Roberto | R. Marasca | Operations | Business Analyst | 0 | 0 | ON GOING | 0 | 2025 | 4 |  |  |  |  | 1 | 2 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0.05 | 0.1 | 0.043478 | 0 | 0 | 0 | 0 | 0
INTERNAL PRJ | PRJ |  | 2025 | 2025-01-07 | 2024-05-31 |  | IAA | HR | MY CAREER | Abstract | L. Roberto | D. Heba | Operations | Back end | 450 | 244 | ON GOING | 0 | 2025 | [5 empty] | 3 | 10 | 12 | [5 empty] | 0 | 0 | 0 | 0 | 0.15 | 0.5 | 0.52174 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25089 | ABS25089 | FINANCE | AMS FDP - Fraud Detection Platform 2025 | EssilorLuxottica | A. Morterra | A. Crescimone | Operations |  | 0 | 0 | ONGOING | 0 | 2025 | 24 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.15 | 0.15 | 0.13043 | 0.25 | 0.14286 | 0.13043 | 0.14286 | 0.13636
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25089 | ABS25089 | FINANCE | AMS FDP - Fraud Detection Platform 2025 | EssilorLuxottica | A. Morterra | A. Saija | Operations |  | 0 | 0 | ONGOING | 0 | 2025 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25089 | ABS25089 | FINANCE | AMS FDP - Fraud Detection Platform 2025 | EssilorLuxottica | A. Morterra | G. Luongo | Delivery AMS |  | 0 | 0 | ONGOING | 0 | 2025 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.055556 | 0.05 | 0.047619 | 0.045455 | 0.05 | 0.05 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | AMS | Waterfall | 2025 | 2025-01-01 | 2025-12-31 | ABS25089 | ABS25089 | FINANCE | AMS FDP - Fraud Detection Platform 2025 | EssilorLuxottica | A. Morterra | L. Gullotto | Operations |  | 0 | 0 | ONGOING | 0 | 2025 | 4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.027778 | 0.025 | 0.02381 | 0.022727 | 0.025 | 0.025 | 0.021739 | 0.041667 | 0.02381 | 0.021739 | 0.02381 | 0.022727
INTERNAL PRJ | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-05-31 |  | IAA | HR | MY PLACE | Abstract | L. Roberto | C. Elia | Operations | Backend | 0 | 0 | ON GOING | 0 | 2025 | [5 empty] | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.043478 | 0.083333 | 0.047619 | 0.043478 | 0.047619 | 0.045455
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | C. Elia | Operations | Data Management | 100 | 7 | ON GOING | 0 | 2025 | [5 empty] | 2 | 5 | [6 empty] | 0 | 0 | 0 | 0 | 0.1 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | M. Porcu | Operations | Tech Lead | 100 | 7 | ON GOING | 0 | 2025 | [5 empty] | 1 | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | M. Toci | Operations | Backend | 100 | 7 | ON GOING | 0 | 2025 | [5 empty] | 2 | [7 empty] | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LEAD | PRJ | Waterfall | 2025 | 2025-05-04 | 2025-07-31 |  |  | HR | Dashboard Salary (dati vendite) | EssilorLuxottica | L. Roberto | R. Bondi | Operations | Front End | 0 | 0 | PROPOSAL | 0 | 2025 | 3 | [5 empty] | 1 | 1 | 1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.043478 | 0.083333 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo revisione | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analyst | 0 | 0 | PROPOSAL | 0 | 2025 | 4 | [5 empty] | 2 | 2 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.086957 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo revisione | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 0 | 0 | PROPOSAL | 0 | 2025 | 4 | [5 empty] | 2 | 1 | 1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.043478 | 0.083333 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo revisione | EssilorLuxottica | L. Roberto | P. Flora | Delivery AMS | PM - Project Governance | 0 | 0 | PROPOSAL | 0 | 2025 | 2 | [5 empty] | 2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo revisione | EssilorLuxottica | L. Roberto | A. De Sanctis | Operations | DataManagement | 0 | 0 | PROPOSAL | 0 | 2025 | 10 | [5 empty] | 5 | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.21739 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo revisione | EssilorLuxottica | L. Roberto | P. SINGH |  | DataManagement | 0 | 0 | PROPOSAL | 0 | 2025 | 10 | [5 empty] | 6 | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.21739 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo revisione | EssilorLuxottica | L. Roberto | L. Roberto | Delivery Projects | PM - Project Governance | 0 | 0 | PROPOSAL | 0 | 2025 | 1 | [5 empty] | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo revisione | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | DataManagement | 0 | 0 | PROPOSAL | 0 | 2025 | 10 | [5 empty] | 4 | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.21739 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo revisione | EssilorLuxottica | L. Roberto | K. Dadaian | Consulting | Analisys | 0 | 0 | PROPOSAL | 0 | 2025 | 2 | [6 empty] | 2 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo revisione | EssilorLuxottica | L. Roberto | M. Migliorati | Operations | DataManagement | 0 | 0 | PROPOSAL | 0 | 2025 | 8 | [6 empty] | 8 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0.34783 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo AI | EssilorLuxottica | L. Roberto | G. Sironi | Operations |  | 0 | 0 | PROPOSAL | 0 | 2025 | 5 | [5 empty] | 5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo AI | EssilorLuxottica | L. Roberto | M. Gomitoni | Operations |  | 0 | 0 | PROPOSAL | 0 | 2025 | 5 | [5 empty] | 5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo AI | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | DataManagement | 0 | 0 | PROPOSAL | 0 | 2025 | 3 | [5 empty] | 3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo AI | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analyst | 0 | 0 | PROPOSAL | 0 | 2025 | 5 | [5 empty] | 3 | 2 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.086957 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo AI | EssilorLuxottica | L. Roberto | L. Roberto | Delivery Projects | PM - Project Governance | 0 | 0 | PROPOSAL | 0 | 2025 | 1 | [5 empty] | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-01-07 | 2025-02-28 | ABS24518 | ABS0008-29 | HR | HR - Job Architecture - Grade | EssilorLuxottica | L. Roberto | R. Bondi | Operations | FrontEnd | 100 | 7 | ON GOING | 0 | 2025 | [5 empty] | 2 | [7 empty] | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2024-04-01 |  |  | ABS0008-221 | HR | Evolutive Dashboard Maggio (post golive) | EssilorLuxottica | L. Roberto | M.Vimercati | Operations | Data Management | 6 | 0 | ON GOING | 0 | 2025 | 1 |  |  |  | 1 | 1 | [7 empty] | 0 | 0 | 0 | 0.045455 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-06-23 | 2025-09-15 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 w4 - myEL integration | EssilorLuxottica | L. Roberto | C. Di Lorenzo | Delivery Projects | Analysis | 65 | 0 | To Be Start | 0 | 2025 | 3 | [5 empty] | 4 | 3 | 3 | 3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.13043 | 0.25 | 0.14286 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-06-23 | 2025-09-15 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 w4 - myEL integration | EssilorLuxottica | L. Roberto | C. Elia | Operations | BackEnd | 65 | 0 | To Be Start | 0 | 2025 | 3 | [5 empty] | 5 | 4 | 3 | 3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.17391 | 0.25 | 0.14286 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-06-23 | 2025-09-15 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 w4 - myEL integration | EssilorLuxottica | L. Roberto | L. Roberto | Operations | PM - Project Governance | 65 | 0 | To Be Start | 0 | 2025 | 1 | [5 empty] | 3 | 3 | 2 | 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.13043 | 0.16667 | 0.047619 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-06-23 | 2025-09-15 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 w4 - myEL integration | EssilorLuxottica | L. Roberto | S. Beltrami | Operations | FrontEnd | 65 | 0 | To Be Start | 0 | 2025 | 3 | [5 empty] | 5 | 9 | 9 | 3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.3913 | 0.75 | 0.14286 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-06-23 | 2025-09-15 | ABS24567 | ABS24567 | CRM/CS | REWARD HUB 4.0 w4 - myEL integration | EssilorLuxottica | L. Roberto | S. Delle Fave | Operations | FrontEnd | 65 | 0 | To Be Start | 0 | 2025 | 0 | [5 empty] | 1 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.043478 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 | 2025-05-15 |  |  | ABS0008-278 | HR | HR - Assenteismo AI | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 0 | 0 | PROPOSAL | 0 | 2025 | 11 | [5 empty] | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.043478 | 0.083333 | 0.095238 | 0.086957 | 0.095238 | 0.090909
CONTRACT | PRJ | Waterfall | 2025 | 2025-06-23 | 2025-06-21 |  |  | HR | Flusso Automatico Utenze | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 7 | 0 | PROPOSAL | 0 | 2025 | 1 | [5 empty] | 0.5 | 0.5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.025 | 0.021739 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 |  |  |  |  | HR | Tracking HR Tools | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 0 | 0 | PROPOSAL | 0 | 2025 | [6 empty] | 1 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.043478 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ | Waterfall | 2025 |  |  |  | ABS0008-67 | HR | One Org HR - geolocalizzazione puntuale in cartina | EssilorLuxottica | L. Roberto | G. De Feo | Delivery Projects | PMO - Project Management Officer | 0 | 0 | PROPOSAL | 0 | 2025 | [6 empty] | 0.5 |  |  | 2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.025 | 0 | 0 | 0.095238 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Statutory | EssilorLuxottica | M. Cocchi | M. Cocchi | Consolidated & Tax | PM - Project Governance | 510 | 0 | ONGOING | 0 | 2025 | [6 empty] | 4 | 2.625 | 1.375 | 4 | 4.5 | 2.75 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.11413 | 0.11458 | 0.19048 | 0.19565 | 0.13095 | 0.034091
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Statutory | EssilorLuxottica | M. Cocchi | G. Campri | Operations | PM - Project Governance | 510 | 0 | ONGOING | 0 | 2025 | [6 empty] | 2.25 | 3.875 | 1.75 | 4.75 | 4.375 | 2.25 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0.1125 | 0.16848 | 0.14583 | 0.22619 | 0.19022 | 0.10714 | 0.034091
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Statutory | EssilorLuxottica | M. Cocchi | TBD | Operations | PM - Project Governance | 510 | 0 | ONGOING | 0 | 2025 | [6 empty] | 2.75 | 5.75 | 2.25 | 7.25 | 6.25 | 3.75 | 2 | 0 | 0 | 0 | 0 | 0 | 0.1375 | 0.25 | 0.1875 | 0.34524 | 0.27174 | 0.17857 | 0.090909
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Statutory | EssilorLuxottica | M. Cocchi | M. Salcini | Consolidated & Tax | Analisys | 510 | 0 | ONGOING | 0 | 2025 | [6 empty] | 19.5 | 11.125 | 5.5 | 14.5 | 13 | 4.375 | 2 | 0 | 0 | 0 | 0 | 0 | 0.975 | 0.4837 | 0.45833 | 0.69048 | 0.56522 | 0.20833 | 0.090909
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Statutory | EssilorLuxottica | M. Cocchi | G. Natili | Operations | Principal Consultant | 510 | 0 | ONGOING | 0 | 2025 | [6 empty] | 9 | 11.5 | 4.5 | 11 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0.5 | 0.375 | 0.52381 | 0.17391 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Statutory | EssilorLuxottica | M. Cocchi | TBD | Operations | Senior Consultant | 510 | 0 | ONGOING | 0 | 2025 | [6 empty] | 11 | 23 | 7 | 22 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55 | 1 | 0.58333 | 1.0476 | 0.73913 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Statutory | EssilorLuxottica | M. Cocchi | TBD | Operations | Consultant | 510 | 0 | ONGOING | 0 | 2025 | [6 empty] | 11 | 23 | 8 | 22 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55 | 1 | 0.66667 | 1.0476 | 0.69565 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Statutory | EssilorLuxottica | M. Cocchi | P. Vernieri | Operations | Consultant | 510 | 0 | ONGOING | 0 | 2025 | [6 empty] | 0 | 19 | 16 | 22 | 23 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82609 | 1.3333 | 1.0476 | 1 | 0.2381 | 0.22727
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Statutory | EssilorLuxottica | M. Cocchi | A. Parisella | Operations | Consultant | 510 | 0 | ONGOING | 0 | 2025 | [6 empty] | 16 | 23 | 11 | 22 | 3 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0.8 | 1 | 0.91667 | 1.0476 | 0.13043 | 0 | 0.22727
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Managerial | EssilorLuxottica | M. Cocchi | M. Cocchi | Consolidated & Tax | PM - Project Governance | 277 | 0 | ONGOING | 0 | 2025 | [6 empty] | 2.25 | 1.625 | 0.75 | 1.75 | 1.75 | 1.5 | 0.375 | 0 | 0 | 0 | 0 | 0 | 0.1125 | 0.070652 | 0.0625 | 0.083333 | 0.076087 | 0.071429 | 0.017045
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Managerial | EssilorLuxottica | M. Cocchi | G. Campri | Operations | PM - Project Governance | 277 | 0 | ONGOING | 0 | 2025 | [6 empty] | 1.625 | 2.875 | 1 | 3 | 3.5 | 2.25 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0.08125 | 0.125 | 0.083333 | 0.14286 | 0.15217 | 0.10714 | 0.034091
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Managerial | EssilorLuxottica | M. Cocchi | S. Preziosa | Consolidated & Tax | Team Leader | 277 | 0 | ONGOING | 0 | 2025 | [6 empty] | 10 | 10 | 4 | 9 | 9 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.43478 | 0.33333 | 0.42857 | 0.3913 | 0.33333 | 0.090909
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Managerial | EssilorLuxottica | M. Cocchi | P. Pieroni | Operations | Solution Architect | 277 | 0 | ONGOING | 0 | 2025 | [6 empty] | 10 | 9.5 | 4.5 | 8.5 | 9 | 7.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.41304 | 0.375 | 0.40476 | 0.3913 | 0.35714 | 0.090909
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Managerial | EssilorLuxottica | M. Cocchi | TBD | Operations | Senior Consultant | 277 | 0 | ONGOING | 0 | 2025 | [6 empty] | 3 | 11.5 | 5.5 | 11.5 | 9 | 9.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.5 | 0.45833 | 0.54762 | 0.3913 | 0.45238 | 0
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - Managerial | EssilorLuxottica | M. Cocchi | L. Mangilli | Operations | Consultant | 277 | 0 | ONGOING | 0 | 2025 | [6 empty] | 11 | 23 | 11 | 22 | 23 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55 | 1 | 0.91667 | 1.0476 | 1 | 0.47619 | 0
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - FDMEE | EssilorLuxottica | M. Cocchi | I. Bressan | Operations | TeamLeader | 90 | 0 | ONGOING | 0 | 2025 | [6 empty] | 7 | 6 | 5 | 11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.35 | 0.26087 | 0.41667 | 0.52381 | 0.26087 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - FDMEE | EssilorLuxottica | M. Cocchi | E. Storti | Operations | Senior Consultant | 90 | 0 | ONGOING | 0 | 2025 | [6 empty] | 4 | 6 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.26087 | 0 | 0.2381 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - FDMEE | EssilorLuxottica | M. Cocchi | F. Atanasio | Operations | Senior Consultant | 90 | 0 | ONGOING | 0 | 2025 | [6 empty] | 6 | 18.5 | 3 | 11 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.80435 | 0.25 | 0.52381 | 0.065217 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - APEX | EssilorLuxottica | M. Cocchi | F. De Pedis | Operations | TeamLeader | 90 | 0 | ONGOING | 0 | 2025 | [6 empty] | 5.5 | 10.5 | 4 | 11 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.275 | 0.45652 | 0.33333 | 0.52381 | 0.17391 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - APEX | EssilorLuxottica | M. Cocchi | F. Lombardini | Consolidated & Tax | Senior Consultant | 90 | 0 | ONGOING | 0 | 2025 | [6 empty] | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2381 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - APEX | EssilorLuxottica | M. Cocchi | TBD | Operations | Consultant | 90 | 0 | ONGOING | 0 | 2025 | [6 empty] | 1 | 23 | 6 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 1 | 0.5 | 0.95238 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - CMFA STAT | EssilorLuxottica | M. Cocchi | F. De Pedis | Operations | Team Leader | 90 | 0 | ONGOING | 0 | 2025 | [6 empty] | 5 | 11 | 4 | 11 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.47826 | 0.33333 | 0.52381 | 0.17391 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - CMFA STAT | EssilorLuxottica | M. Cocchi | F. Lombardini | Consolidated & Tax | Senior Consultant | 90 | 0 | ONGOING | 0 | 2025 | [6 empty] | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2381 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - CMFA STAT | EssilorLuxottica | M. Cocchi | TBD | Operations | Consultant | 90 | 0 | ONGOING | 0 | 2025 | [6 empty] | 0 | 0 | 0 | 8.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.40476 | 0.065217 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - CMFA STAT | EssilorLuxottica | M. Cocchi | I. Bressan | Operations | Solution Architect | 90 | 0 | ONGOING | 0 | 2025 | [6 empty] | 3 | 9.5 | 5 | 11 | 11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.41304 | 0.41667 | 0.52381 | 0.5 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - PMO | EssilorLuxottica | M. Cocchi | C. Paz | Delivery Projects | PMO - Project Management Officer | 0 | 0 | ONGOING | 0 | 2025 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ |  | 2025 | 2025-06-03 | 2025-12-12 |  | ABS25293 | EPM | One View - PMO | EssilorLuxottica | M. Cocchi | M. Vianelli | Delivery Projects | PMO - Project Management Officer | 0 | 0 | ONGOING | 0 | 2025 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-06-23 | 2025-06-21 |  |  | HR | Flusso Automatico Utenze | EssilorLuxottica | L. Roberto | L. Cariglia | Operations | Data Management | 7 | 0 | PROPOSAL | 0 | 2025 | 2 | [5 empty] | 1 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.05 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-06-23 | 2025-06-21 |  |  | HR | Flusso Automatico Utenze | EssilorLuxottica | L. Roberto | R. Marasca | Delivery Projects | Analysis | 7 | 0 | PROPOSAL | 0 | 2025 | 1.5 | [5 empty] | 0.5 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0.025 | 0.043478 | 0 | 0 | 0 | 0 | 0
CONTRACT | PRJ | Waterfall | 2025 | 2025-06-23 | 2025-06-21 |  |  | HR | Flusso Automatico Utenze | EssilorLuxottica | L. Roberto | M. Toci | Operations | Back End | 7 | 0 | PROPOSAL | 0 | 2025 | 2 | [6 empty] | 2 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0.086957 | 0 | 0 | 0 | 0 | 0
[8 empty] | LOGISTIC | BIP - Caratteri speciali | EssilorLuxottica | F. Taita | F. Taita | Delivery Projects | Data Engineering | 200 | 0 | TO START | 0 | 2025 | 40 |  |  |  | 0 | 0 | 7 | 7 | 5 | 7 | 7 | 7 |  | 0 | 0 | 0 | 0 | 0 | 0.35 | 0.30435 | 0.41667 | 0.33333 | 0.30435 | 0.33333 | 0
[8 empty] | LOGISTIC | BIP - Caratteri speciali | EssilorLuxottica | F. Taita | L. Altobelli | Operations | Data Engineering | 200 | 0 | TO START | 0 | 2025 | 75 |  |  |  |  | 0 | 10 | 15 | 5 | 15 | 15 | 15 |  | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.65217 | 0.41667 | 0.71429 | 0.65217 | 0.71429 | 0
[8 empty] | LOGISTIC | BIP - Caratteri speciali | EssilorLuxottica | F. Taita | T. Baldi | Operations | Data Engineering | 200 | 0 | TO START | 0 | 2025 | 75 |  |  |  | 0 | 0 | 10 | 15 | 5 | 15 | 15 | 15 |  | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.65217 | 0.41667 | 0.71429 | 0.65 | 0.71429 | 0
CONTRACT | PRJ |  |  | 2025-06-22 | 2025-06-22 | [9 empty] | 0 | 0 |  | 0 | 2025 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROSPECT | PRJ |  |  | 2025-01-01 | 2025-12-31 |  |  |  | Red Carpet Events 2025 | EssilorLuxottica |  | A. Imbimbo |  |  | 0 | 0 |  | 0 | 2025 |  | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0
PROSPECT | PRJ |  |  | 2025-01-01 | 2025-12-31 |  |  |  | Red Carpet Events 2025 | EssilorLuxottica |  | F. Malvezzi |  |  | 0 | 0 |  | 0 | 2025 |  | 2 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 5 | 2
PROSPECT | PRJ |  |  | 2025-01-01 | 2025-12-31 |  |  |  | Red Carpet Events 2025 | EssilorLuxottica |  | G. Sabbatini |  |  | 0 | 0 |  | 0 | 2025 |  | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 1
PROSPECT | PRJ |  |  | 2025-01-01 | 2025-12-31 |  |  |  | Red Carpet Events 2025 | EssilorLuxottica |  | G. Sironi |  |  | 0 | 0 |  | 0 | 2025 |  | 1 | 2 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 2 | 1
PROSPECT | PRJ |  |  | 2025-01-01 | 2025-12-31 |  |  |  | Red Carpet Events 2025 | EssilorLuxottica |  | M. Gomitoni |  |  | 0 | 0 |  | 0 | 2025 |  | 1 | 2 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 1 | 2 | 1
PROSPECT | PRJ |  |  | 2025-01-01 | 2025-12-31 |  |  |  | Red Carpet Events 2025 | EssilorLuxottica |  | V. Echarry |  |  | 0 | 0 |  | 0 | 2025 |  | 0 | 6 | 0 | 0 | 3 | 3 | 3 | 3 | 2 | 3 | 5 | 2

## LoVs
ITEM_TYPE | DELIVERY_TYPE | WORKSTREAM | PROJECT_STREAM | JOB | STATUS | USER
CONTRACT | PRJ | Agile | HR | BackEnd | PROPOSAL | A. VLADI
LEAD | AMS | Waterfall | RETAIL | FrontEnd | TO START | M. VIMERCATI
PROSPECT | PreSales - GO TO MARKET | Scrum | WHOLESALE | DataManagement | STARTED | M. VIANELLI
INTERNAL PRJ | PreSales - GARE | Kanban | LOGISTIC | Analisys | ON GOING | F. VASSALLO
INTERNAL TRAINING | PreSales - DELIVERY | Scrumban | BIP | Data Engineering | ON HOLD | E. TOSETTO
PRE-SALES | TRAINING | PRINCE2 | FINANCE | Graphic Interface | CLOSED | A. TORONE
SALES |  | Six Sigma | CRM/CS | PM - Project Governance | POST-GO LIVE | M. TOCI
INTERNAL ACTIVITES |  | CPM | ALTRO | Architecture Analysis |  | C. TIBERTI
|  | CCPM | EPM | PMO - Project Management Officer |  | G. TARTAGLIA
|  | Lean management | CS | ECC Developer |  | F. TAITA
|  | PMBOK | CONSOLIDATO | ECC Analyst |  | A. STRADA
|  | XP |  | SM - Service Manager |  | E. STORTI
|  | Time&Materials |  | Tech Lead |  | F. SPACAGNA
M. SORRENTINO
G. SIRONI
P. SINGH
H. SINGH
A. SIMONE
A. SANTORO
M. SALCINI
A. SAIJA
O. SAGAZIO
L. ROBERTO
F. REALE
V. RASO
S. PREZIOSA
T. PORZIO
M. PORCU
A. PIROLA
F. PINNELLI
L. PIGAZZINI
P. PIERONI
G. PICERNO
N. PESCIONE
C. PAZ
G. PAOLO
F. ORIGLIA
A. NASTASI
G. MINERVINI
D. MILANI
M. MIGLIORATI
A. MICALI
M. SIMEONE
M. ATTANASIO
R. MARASCA
L. MANGILI
F. MALVEZZI
G. LUONGO
A. LORENA
F. LOMBARDINI
A. IMBIMBO
A. IEMBO
L. GULLOTTO
N. GUERRERO
R. GRANDI
M. GOMITONI
G. GALATI
R. FREDDI
L. FRANCO
L. FRANCESCHINI
N. FRAGALE
A. FERRARI
M. FAVALLI
G. ESPOSITO
C. ESPOSITO
C. ELIA
A. ELIA
V. ECHARRY
A. DI PIETRO
C. DI LORENZO
S. DELLE FAVE
A. DE SANCTIS
F. DE PEDIS
G. DE FEO
G. D'AMANTI
F. D'ALBERTO
J. DACI
A. CUOMO
A. CRESCIMONE
M. COCCHI
L. CARIGLIA
G. LOPEZ
M. CALABRESE
P. BUONASORTE
I. BRESSAN
A. BRANDIZZI
R. BONDI
Y. BEN
O. BEN OTHMANE
S. BELTRAMI
L. BARIANI
F. ATANASIO
P. ANZELLOTTI
R. ALVES
A. ALBANESE
S. LUCA
S. MATTEO
P. GALVAGNI
L. TIRONESE
D. SCALIA
L. CARLONI
E. ULIU
D. SCARCI
E. SOLDONI
M. VERGANI
G. LA FRANCA
A. CERRATO
R. GRIENTI
R. NUNZIATA
L. STROPPA
T. BALDI
G. SABBATINI
F. ORIGLIA
S. BORIASHOV
G. CATALDO
F. PLEBANI
C. PIRACCINI
M. REGINI
M. BARAGIOLI
M. MANNARINO
O. BEN OTHMANE
G.F. Fiorentini
O. BEN OTHMANE
A. Caldana
B. Capotorto
G.F. Fiorentini
A. Caldana
B. Capotorto
G.F. Fiorentini